## Cover & Control
Alder Ridge Mechanical ¦ WIP Schedule
May 2026 close - controller final ¦ Amounts in USD unless noted
Legal entity | Alder Ridge Mechanical, Inc.
Reporting period | 2026-05-31
Version | FINAL - posted 2026-06-04 16:42 PT
Prepared by | Kara Singh, Senior Project Accountant
Reviewed by | Natalie Brooks, Controller
Revenue method | Cost-to-cost percentage of completion
System cutoff | Posted GL, job cost, and billings through 2026-05-31
June refresh note | May WIP journal automatically reverses on 2026-06-01
Close-control summary
Contract value |  | Schedule-to-system cost check
Cost to date |  | Schedule-to-system billing check
Earned revenue |  | Projects requiring controller review
Billings to date |  | Workbook status
Contract asset
Contract liability

## WIP Detail
May 2026 WIP Detail
Blue font = hardcoded estimate/input ¦ green font = internal workbook link ¦ black = formula
Project ID | Project / Customer | Branch | PM | Status | Contract Type | Current Contract | Cost to Date | Forecast ETC | EAC | % Complete | Earned Revenue | Billings to Date | Contract Asset | Contract Liability | Est. Margin | Margin % | Review Flag
ARM-2318 | Columbia Biologics Clean Utilities ¦ C-1039 | Portland | Maya Chen | Substantially Complete | GMP | 9392500 | 6926546.05 | 356653.95 |  |  |  | 8512152.76
ARM-2403 | Riverton Civic Center HVAC Renewal ¦ C-1007 | Portland | Elliot Marks | Active | Lump Sum | 6868000 | 4192134.95 | 1046565.05 |  |  |  | 5734064.25
ARM-2409 | Northline Cold Storage Expansion ¦ C-1021 | Portland | Priya Raman | Active | GMP | 5526000 | 3569607.87 | 745892.13 |  |  |  | 4296079.58
ARM-2412 | OSU Kelley Engineering Lab Ventilation ¦ C-1051 | Portland | Elliot Marks | Active | Lump Sum | 5411000 | 2994198.07 | 1109001.93 |  |  |  | 3876983.92
ARM-2417 | Cascade Health Ambulatory Pavilion ¦ C-1013 | Portland | Maya Chen | Active | GMP | 10487000 | 4891292 | 3366508 |  |  |  | 5930347.24
ARM-2421 | Juniper Hotel Boiler Plant Replacement ¦ C-1044 | Bend | Lucas Bennett | Warranty | Lump Sum | 2309000 | 1738600 | 31000 |  |  |  | 2305000
ARM-2501 | PDX Concourse E Controls Retrofit ¦ C-1032 | Portland | Sofia Alvarez | Active | Time & Material NTE | 3688000 | 1777329.63 | 1082970.37 |  |  |  | 2280372.34
ARM-2506 | Eastbank Data Hall Cooling Expansion ¦ C-1048 | Portland | Priya Raman | Active | GMP | 11580000 | 3885358.45 | 5129541.55 |  |  |  | 4964633.06
ARM-2510 | Hawthorne Yard Mixed-Use Mechanical ¦ C-1062 | Portland | Maya Chen | Active | GMP | 7836000 | 2555851.51 | 3567348.49 |  |  |  | 3389902.39
ARM-2514 | Redmond Unified Schools Phase 2 ¦ C-1028 | Bend | Lucas Bennett | Active | Lump Sum | 7284000 | 3452548.44 | 1962151.56 |  |  |  | 5486464.09
ARM-2518 | Deschutes Fleet Services Maintenance Facility ¦ C-1067 | Bend | Lucas Bennett | Active | Lump Sum | 3348000 | 1102005.11 | 1482494.89 |  |  |  | 1542733.47
ARM-2522 | Summit Surgical Center Central Plant ¦ C-1071 | Portland | Elliot Marks | Active | GMP | 4585000 | 1255495.15 | 2215604.85 |  |  |  | 1837762.48
ARM-2526 | Willamette Food Co-op Refrigeration Upgrade ¦ C-1058 | Portland | Sofia Alvarez | Active | Lump Sum | 1852500 | 860224.18 | 543575.82 |  |  |  | 1420426.99
ARM-2602 | Pacific NW Distribution Center Heat Recovery ¦ C-1076 | Portland | Priya Raman | Active | Design-Build | 5920000 | 716508 | 3846092 |  |  |  | 1111267.63
ARM-2605 | Rose Quarter Event Level Ventilation ¦ C-1080 | Portland | Elliot Marks | Active | GMP | 6360000 | 526126.43 | 4302073.57 |  |  |  | 843953.68
ARM-2608 | Cascade Health Imaging Suite Controls ¦ C-1013 | Portland | Sofia Alvarez | Active | Time & Material NTE | 1982000 | 372230.13 | 1041569.87 |  |  |  | 680198.95
TOTAL

## Prior Month Bridge
Project Margin Bridge
April final to May final - used for exception review
Project ID | Project | April EAC | April Margin % | May EAC | May Margin % | Margin Change (bps) | Driver / reviewer note
ARM-2318 | Columbia Biologics Clean Utilities | 7195802 |  |  |  |  | Buyout savings partly offset by field overtime
ARM-2403 | Riverton Civic Center HVAC Renewal | 5207268 |  |  |  |  | Change-order cost budget aligned to executed scope
ARM-2409 | Northline Cold Storage Expansion | 4315500 |  |  |  |  | No material movement; ordinary production update
ARM-2412 | OSU Kelley Engineering Lab Ventilation | 4127819 |  |  |  |  | Late design coordination added remaining labor
ARM-2417 | Cascade Health Ambulatory Pavilion | 8356894 |  |  |  |  | Close-out reserve updated from superintendent punchlist
ARM-2421 | Juniper Hotel Boiler Plant Replacement | 1748365 |  |  |  |  | Buyout savings partly offset by field overtime
ARM-2501 | PDX Concourse E Controls Retrofit | 2843138 |  |  |  |  | Change-order cost budget aligned to executed scope
ARM-2506 | Eastbank Data Hall Cooling Expansion | 9014900 |  |  |  |  | No material movement; ordinary production update
ARM-2510 | Hawthorne Yard Mixed-Use Mechanical | 6159939 |  |  |  |  | Late design coordination added remaining labor
ARM-2514 | Redmond Unified Schools Phase 2 | 5479676 |  |  |  |  | Close-out reserve updated from superintendent punchlist
ARM-2518 | Deschutes Fleet Services Maintenance Facility | 2553486 |  |  |  |  | Buyout savings partly offset by field overtime
ARM-2522 | Summit Surgical Center Central Plant | 3450273 |  |  |  |  | Change-order cost budget aligned to executed scope
ARM-2526 | Willamette Food Co-op Refrigeration Upgrade | 1403800 |  |  |  |  | No material movement; ordinary production update
ARM-2602 | Pacific NW Distribution Center Heat Recovery | 4589976 |  |  |  |  | Late design coordination added remaining labor
ARM-2605 | Rose Quarter Event Level Ventilation | 4886138 |  |  |  |  | Close-out reserve updated from superintendent punchlist
ARM-2608 | Cascade Health Imaging Suite Controls | 1396834 |  |  |  |  | Buyout savings partly offset by field overtime

## Checks
WIP Control Checks
All required checks must read PASS before posting
Check | Expected | Actual / Delta | Status | Where to fix
MODEL STATUS | All checks PASS |  |  | Review failed checks below
Cost detail ties to accounting-system extract | 40816055.97 |  |  | WIP Detail column H / current job cost extract
Billings tie to accounting-system extract | 54212342.83 |  |  | WIP Detail column M / current billing extract
Contract asset and liability do not net by project | 0 |  |  | WIP Detail columns N and O
EAC is not below cost to date | 0 |  |  | WIP Detail columns H and J
Percent complete does not exceed 100% | 0 |  |  | WIP Detail column K

## JC dump 5.31
PASTE FROM JC-220 6/1/26 06:42 - values only - DO NOT USE FOR JUNE (there are 3 late AP batches in June)
Posting date | Document | Source | Job | Cost code | Cost code desc | Vendor | Employee | Units | Amount | Description
2025-01-03 | AP-0003735 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2241 |  | 80.46 | 14481.95 | Controls Panels and Devices - released equipment package
2025-01-03 | AP-0003744 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2358 |  | 8037.85 | 8037.85 | Temporary Facilities and Protection - rental and logistics
2025-01-06 | AP-0003732 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2021 |  | 64.4 | 11592.54 | Sheet Metal and Ductwork - valves and piping lot
2025-01-06 | AP-0003739 | AP | ARM-2318 | 04-200 | Electrical and Controls Subcontract | V-2293 |  | 25268.27 | 25268.27 | Electrical and Controls Subcontract - testing and balancing services
2025-01-06 | AP-0003741 | AP | ARM-2318 | 05-100 | Equipment Rental and Rigging | V-2317 |  | 6720.99 | 6720.99 | Equipment Rental and Rigging - permit and inspection fees
2025-01-07 | PRJ-PAY-ARM-2318-20250107 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1026 | 39.45 | 2801 | Rework and Quality Correction - field installation time
2025-01-07 | PRJ-PAY-ARM-2318-20250107 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1033 | 41.13 | 3516.35 | Project Management and Supervision - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2318-20250107 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 47.15 | 3960.54 | Engineering, BIM and Coordination - supervision and planning
2025-01-07 | PRJ-PAY-ARM-2318-20250107 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1047 | 33.69 | 3049.19 | Field Installation Labor - startup and checkout
2025-01-07 | PRJ-PAY-ARM-2318-20250107 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1080 | 30.76 | 2984.2 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-10 | AP-0003736 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2258 |  | 70.97 | 12774.87 | Sheet Metal and Ductwork - fabricated material delivery
2025-01-13 | AP-0003733 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2094 |  | 55.58 | 10003.58 | Controls Panels and Devices - ductwork release
2025-01-13 | AP-0003740 | AP | ARM-2318 | 04-100 | Insulation Subcontract | V-2307 |  | 34653.52 | 34653.52 | Insulation Subcontract - electrical coordination scope
2025-01-13 | AP-0003742 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2331 |  | 3909.01 | 3909.01 | Small Tools and Consumables - freight and expediting
2025-01-14 | PRJ-PAY-ARM-2318-20250114 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1031 | 44.63 | 3525.43 | Project Management and Supervision - coordination and layout
2025-01-14 | PRJ-PAY-ARM-2318-20250114 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1038 | 38.1 | 2952.7 | Engineering, BIM and Coordination - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2318-20250114 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1045 | 44.02 | 3697.53 | Field Installation Labor - startup and checkout
2025-01-14 | PRJ-PAY-ARM-2318-20250114 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1052 | 37.29 | 3374.96 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-14 | PRJ-PAY-ARM-2318-20250114 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1085 | 33.26 | 3226.22 | Sheet Metal Fabrication Labor - field installation time
2025-01-17 | AP-0003737 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2277 |  | 101.85 | 18332.21 | Controls Panels and Devices - valves and piping lot
2025-01-20 | AP-0003734 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2220 |  | 89.97 | 16194.75 | Sheet Metal and Ductwork - jobsite material replenishment
2025-01-20 | AP-0003743 | AP | ARM-2318 | 05-200 | Permits, Fees and Bonds | V-2345 |  | 5845.6 | 5845.6 | Permits, Fees and Bonds - small tools and field consumables
2025-01-21 | PRJ-PAY-ARM-2318-20250121 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1036 | 67.82 | 4815.21 | Engineering, BIM and Coordination - supervision and planning
2025-01-21 | PRJ-PAY-ARM-2318-20250121 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1043 | 43.54 | 3374.48 | Field Installation Labor - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2318-20250121 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1050 | 40.44 | 3397.12 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-21 | PRJ-PAY-ARM-2318-20250121 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1083 | 37.27 | 3373.07 | Sheet Metal Fabrication Labor - field installation time
2025-01-21 | PRJ-PAY-ARM-2318-20250121 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1090 | 39.28 | 3810.23 | Controls Programming and Checkout - coordination and layout
2025-01-24 | AP-0003738 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2291 |  | 51.26 | 9226.5 | Sheet Metal and Ductwork - ductwork release
2025-01-28 | PRJ-PAY-ARM-2318-20250128 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1041 | 53.95 | 3830.7 | Field Installation Labor - startup and checkout
2025-01-28 | PRJ-PAY-ARM-2318-20250128 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 44.51 | 3449.24 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2318-20250128 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1081 | 37.57 | 3155.9 | Sheet Metal Fabrication Labor - field installation time
2025-01-28 | PRJ-PAY-ARM-2318-20250128 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1088 | 45.79 | 4144.11 | Controls Programming and Checkout - coordination and layout
2025-01-28 | PRJ-PAY-ARM-2318-20250128 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1095 | 33.37 | 3237.25 | Warranty and Punchlist - supervision and planning
2025-01-28 | PRJ-PAY-ARM-2318-20250128 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1008 | 25.52 | 2641.29 | Closeout and O&M Documentation - startup and checkout
2025-01-31 | PRJ-PAY-ARM-2318-20250131 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 44.3 | 3145.57 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-31 | PRJ-PAY-ARM-2318-20250131 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1053 | 41.41 | 3209.17 | Sheet Metal Fabrication Labor - field installation time
2025-01-31 | PRJ-PAY-ARM-2318-20250131 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1086 | 44.73 | 3757.02 | Controls Programming and Checkout - coordination and layout
2025-01-31 | PRJ-PAY-ARM-2318-20250131 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1093 | 28.39 | 2569.24 | Warranty and Punchlist - supervision and planning
2025-01-31 | PRJ-PAY-ARM-2318-20250131 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1100 | 40.71 | 3948.88 | Closeout and O&M Documentation - startup and checkout
2025-01-31 | PRJ-PAY-ARM-2318-20250131 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1014 | 35.36 | 3659.8 | Rework and Quality Correction - punchlist and closeout labor
2025-02-03 | AP-0003751 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2448 |  | 83.98 | 15115.62 | Hydronic Piping and Valves - jobsite material replenishment
2025-02-06 | AP-0003748 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2408 |  | 42.03 | 7565.15 | Insulation and Specialty Material - fabricated material delivery
2025-02-07 | PRJ-PAY-ARM-2318-20250207 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1027 | 44.72 | 3533.02 | Project Management and Supervision - field installation time
2025-02-07 | PRJ-PAY-ARM-2318-20250207 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1034 | 47.62 | 3690.25 | Engineering, BIM and Coordination - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2318-20250207 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1041 | 39.42 | 3310.97 | Field Installation Labor - supervision and planning
2025-02-07 | PRJ-PAY-ARM-2318-20250207 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 50.23 | 4545.4 | Startup, Testing and Commissioning - startup and checkout
2025-02-07 | PRJ-PAY-ARM-2318-20250207 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1081 | 33.38 | 3237.56 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-09 | AP-0003745 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2367 |  | 74.15 | 13347.18 | Hydronic Piping and Valves - ductwork release
2025-02-09 | AP-0003752 | AP | ARM-2318 | 04-300 | Testing and Balancing Subcontract | V-2450 |  | 28716.81 | 28716.81 | Testing and Balancing Subcontract - electrical coordination scope
2025-02-09 | AP-0003754 | AP | ARM-2318 | 05-200 | Permits, Fees and Bonds | V-2474 |  | 6049.53 | 6049.53 | Permits, Fees and Bonds - freight and expediting
2025-02-13 | AP-0003749 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2422 |  | 57.67 | 10380.76 | Hydronic Piping and Valves - valves and piping lot
2025-02-14 | PRJ-PAY-ARM-2318-20250214 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1032 | 57.69 | 4095.72 | Engineering, BIM and Coordination - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2318-20250214 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1039 | 41.42 | 3209.8 | Field Installation Labor - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2318-20250214 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 43.76 | 3675.67 | Startup, Testing and Commissioning - startup and checkout
2025-02-14 | PRJ-PAY-ARM-2318-20250214 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1053 | 34.34 | 3107.38 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-14 | PRJ-PAY-ARM-2318-20250214 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1086 | 26.6 | 2580.06 | Controls Programming and Checkout - field installation time
2025-02-14 | PRJ-PAY-ARM-2318-20250214 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1093 | 36.96 | 3824.85 | Warranty and Punchlist - coordination and layout
2025-02-16 | AP-0003746 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2381 |  | 86.82 | 15627.27 | Insulation and Specialty Material - jobsite material replenishment
2025-02-16 | AP-0003753 | AP | ARM-2318 | 04-200 | Electrical and Controls Subcontract | V-2464 |  | 27633.28 | 27633.28 | Electrical and Controls Subcontract - rigging and specialty support
2025-02-16 | AP-0003755 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2488 |  | 6930.1 | 6930.1 | Temporary Facilities and Protection - small tools and field consumables
2025-02-20 | AP-0003750 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2436 |  | 52.59 | 9466.11 | Insulation and Specialty Material - ductwork release
2025-02-21 | PRJ-PAY-ARM-2318-20250221 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1037 | 47.27 | 3356.44 | Field Installation Labor - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2318-20250221 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1044 | 44.69 | 3463.58 | Startup, Testing and Commissioning - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2318-20250221 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1051 | 37.57 | 3155.69 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-21 | PRJ-PAY-ARM-2318-20250221 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1084 | 50.12 | 4535.95 | Controls Programming and Checkout - field installation time
2025-02-21 | PRJ-PAY-ARM-2318-20250221 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1091 | 44.44 | 4310.69 | Warranty and Punchlist - coordination and layout
2025-02-21 | PRJ-PAY-ARM-2318-20250221 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1098 | 33.96 | 3514.53 | Closeout and O&M Documentation - supervision and planning
2025-02-23 | AP-0003747 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2395 |  | 92.77 | 16698.05 | Hydronic Piping and Valves - released equipment package
2025-02-23 | AP-0003756 | AP | ARM-2318 | 05-300 | Freight and Expediting | V-2502 |  | 6620.39 | 6620.39 | Freight and Expediting - rental and logistics
2025-02-28 | PRJ-PAY-ARM-2318-20250228 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 43.44 | 3084.53 | Startup, Testing and Commissioning - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2318-20250228 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 39.38 | 3052.26 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2318-20250228 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1082 | 40.86 | 3432.41 | Controls Programming and Checkout - field installation time
2025-02-28 | PRJ-PAY-ARM-2318-20250228 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1089 | 44.3 | 4008.84 | Warranty and Punchlist - coordination and layout
2025-02-28 | PRJ-PAY-ARM-2318-20250228 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1096 | 47.57 | 4614.59 | Closeout and O&M Documentation - supervision and planning
2025-02-28 | PRJ-PAY-ARM-2318-20250228 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1009 | 38.26 | 3959.94 | Rework and Quality Correction - startup and checkout
2025-03-06 | AP-0003763 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2255 |  | 86.15 | 15507.7 | Plumbing Fixtures and Piping - released equipment package
2025-03-07 | PRJ-PAY-ARM-2318-20250307 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1028 | 61.51 | 4367.43 | Engineering, BIM and Coordination - field installation time
2025-03-07 | PRJ-PAY-ARM-2318-20250307 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1035 | 43 | 3332.28 | Field Installation Labor - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2318-20250307 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 43.34 | 3640.71 | Startup, Testing and Commissioning - supervision and planning
2025-03-07 | PRJ-PAY-ARM-2318-20250307 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 31.2 | 2823.6 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-07 | PRJ-PAY-ARM-2318-20250307 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1082 | 29.34 | 2845.95 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-09 | AP-0003760 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2056 |  | 49.14 | 8845.6 | Major HVAC Equipment - valves and piping lot
2025-03-12 | AP-0003757 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2512 |  | 80.03 | 14404.82 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-03-12 | AP-0003765 | AP | ARM-2318 | 04-400 | Crane, Rigging and Specialty Trade | V-2274 |  | 29251.99 | 29251.99 | Crane, Rigging and Specialty Trade - rigging and specialty support
2025-03-12 | AP-0003767 | AP | ARM-2318 | 05-300 | Freight and Expediting | V-2298 |  | 5748.93 | 5748.93 | Freight and Expediting - small tools and field consumables
2025-03-13 | AP-0003764 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2274 |  | 86.13 | 15504.04 | Major HVAC Equipment - fabricated material delivery
2025-03-14 | PRJ-PAY-ARM-2318-20250314 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1033 | 42.5 | 3017.22 | Field Installation Labor - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2318-20250314 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1040 | 40.52 | 3140.07 | Startup, Testing and Commissioning - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2318-20250314 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 37.76 | 3171.78 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-14 | PRJ-PAY-ARM-2318-20250314 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1080 | 54.2 | 4904.92 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-14 | PRJ-PAY-ARM-2318-20250314 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1087 | 44.39 | 4306.04 | Warranty and Punchlist - field installation time
2025-03-16 | AP-0003761 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2213 |  | 67.52 | 12154.36 | Plumbing Fixtures and Piping - ductwork release
2025-03-19 | AP-0003758 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2526 |  | 50.7 | 9125.7 | Major HVAC Equipment - released equipment package
2025-03-19 | AP-0003766 | AP | ARM-2318 | 04-300 | Testing and Balancing Subcontract | V-2288 |  | 26163.05 | 26163.05 | Testing and Balancing Subcontract - trade partner progress billing
2025-03-19 | AP-0003768 | AP | ARM-2318 | 05-100 | Equipment Rental and Rigging | V-2312 |  | 7636.47 | 7636.47 | Equipment Rental and Rigging - rental and logistics
2025-03-21 | PRJ-PAY-ARM-2318-20250321 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1038 | 42.37 | 3008.18 | Startup, Testing and Commissioning - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2318-20250321 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1045 | 40.73 | 3156.2 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2318-20250321 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1052 | 45.73 | 3841.44 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-21 | PRJ-PAY-ARM-2318-20250321 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1085 | 45.05 | 4077.42 | Warranty and Punchlist - field installation time
2025-03-21 | PRJ-PAY-ARM-2318-20250321 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1092 | 44.37 | 4303.82 | Closeout and O&M Documentation - coordination and layout
2025-03-23 | AP-0003762 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2234 |  | 74.76 | 13456.97 | Major HVAC Equipment - jobsite material replenishment
2025-03-25 | AP-0003759 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2014 |  | 37.32 | 6717.7 | Plumbing Fixtures and Piping - fabricated material delivery
2025-03-25 | AP-0003769 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2326 |  | 4246.66 | 4246.66 | Small Tools and Consumables - permit and inspection fees
2025-03-28 | PRJ-PAY-ARM-2318-20250328 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 52.79 | 3748.29 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2318-20250328 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1050 | 37.54 | 2909.17 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2318-20250328 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1083 | 44.14 | 3707.92 | Warranty and Punchlist - field installation time
2025-03-28 | PRJ-PAY-ARM-2318-20250328 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1090 | 27.01 | 2444.13 | Closeout and O&M Documentation - coordination and layout
2025-03-28 | PRJ-PAY-ARM-2318-20250328 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1097 | 40.02 | 3882.19 | Rework and Quality Correction - supervision and planning
2025-03-31 | PRJ-PAY-ARM-2318-20250331 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1048 | 52.81 | 3749.48 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2318-20250331 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1081 | 39.43 | 3055.59 | Warranty and Punchlist - field installation time
2025-03-31 | PRJ-PAY-ARM-2318-20250331 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1088 | 51.17 | 4298.6 | Closeout and O&M Documentation - coordination and layout
2025-03-31 | PRJ-PAY-ARM-2318-20250331 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1095 | 43.19 | 3909 | Rework and Quality Correction - supervision and planning
2025-04-05 | AP-0003772 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2364 |  | 79.06 | 14230.87 | Controls Panels and Devices - valves and piping lot
2025-04-05 | AP-0003780 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2458 |  | 6949.85 | 6949.85 | Temporary Facilities and Protection - freight and expediting
2025-04-07 | PRJ-PAY-ARM-2318-20250407 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1029 | 38.08 | 2703.48 | Field Installation Labor - field installation time
2025-04-07 | PRJ-PAY-ARM-2318-20250407 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1036 | 45.41 | 3519.11 | Startup, Testing and Commissioning - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2318-20250407 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 37.28 | 3131.19 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-07 | PRJ-PAY-ARM-2318-20250407 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1050 | 46.07 | 4169.12 | Controls Programming and Checkout - startup and checkout
2025-04-07 | PRJ-PAY-ARM-2318-20250407 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1083 | 36.86 | 3574.96 | Warranty and Punchlist - punchlist and closeout labor
2025-04-12 | AP-0003773 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2377 |  | 92.97 | 16734.61 | Sheet Metal and Ductwork - ductwork release
2025-04-14 | PRJ-PAY-ARM-2318-20250414 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1034 | 40.37 | 2866.44 | Startup, Testing and Commissioning - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2318-20250414 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1041 | 48.07 | 3725.23 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2318-20250414 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1048 | 33.85 | 2843.73 | Controls Programming and Checkout - startup and checkout
2025-04-14 | PRJ-PAY-ARM-2318-20250414 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1081 | 44.69 | 4044.84 | Warranty and Punchlist - punchlist and closeout labor
2025-04-14 | PRJ-PAY-ARM-2318-20250414 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1088 | 35.84 | 3476.55 | Closeout and O&M Documentation - field installation time
2025-04-15 | AP-0003770 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2336 |  | 48.36 | 8705.32 | Controls Panels and Devices - released equipment package
2025-04-15 | AP-0003776 | AP | ARM-2318 | 04-100 | Insulation Subcontract | V-2408 |  | 18469.27 | 18469.27 | Insulation Subcontract - trade partner progress billing
2025-04-15 | AP-0003778 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2433 |  | 8308.96 | 8308.96 | Small Tools and Consumables - rental and logistics
2025-04-19 | AP-0003774 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2391 |  | 63.3 | 11394.27 | Controls Panels and Devices - jobsite material replenishment
2025-04-21 | PRJ-PAY-ARM-2318-20250421 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1039 | 54.41 | 3863.1 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2318-20250421 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1046 | 61.46 | 4763.02 | Controls Programming and Checkout - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2318-20250421 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1053 | 37.49 | 3149.06 | Warranty and Punchlist - punchlist and closeout labor
2025-04-21 | PRJ-PAY-ARM-2318-20250421 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1086 | 39.98 | 3618.13 | Closeout and O&M Documentation - field installation time
2025-04-22 | AP-0003771 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2350 |  | 48.5 | 8730.13 | Sheet Metal and Ductwork - fabricated material delivery
2025-04-22 | AP-0003777 | AP | ARM-2318 | 04-400 | Crane, Rigging and Specialty Trade | V-2422 |  | 33637.88 | 33637.88 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-04-22 | AP-0003779 | AP | ARM-2318 | 05-200 | Permits, Fees and Bonds | V-2445 |  | 5130.94 | 5130.94 | Permits, Fees and Bonds - permit and inspection fees
2025-04-25 | AP-0003775 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2405 |  | 95.74 | 17232.77 | Sheet Metal and Ductwork - released equipment package
2025-04-28 | PRJ-PAY-ARM-2318-20250428 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1044 | 64.34 | 4568.09 | Controls Programming and Checkout - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2318-20250428 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1051 | 46.81 | 3627.59 | Warranty and Punchlist - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2318-20250428 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1084 | 33.92 | 2848.98 | Closeout and O&M Documentation - field installation time
2025-04-28 | PRJ-PAY-ARM-2318-20250428 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1091 | 30.94 | 2800.22 | Rework and Quality Correction - coordination and layout
2025-04-30 | PRJ-PAY-ARM-2318-20250430 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1049 | 39.39 | 2796.84 | Warranty and Punchlist - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2318-20250430 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1082 | 51.11 | 3961.35 | Closeout and O&M Documentation - field installation time
2025-04-30 | PRJ-PAY-ARM-2318-20250430 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1089 | 50.86 | 4272.61 | Rework and Quality Correction - coordination and layout
2025-04-30 | PRJ-PAY-ARM-2318-20250430 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1096 | 27.46 | 2704.33 | Project Management and Supervision - supervision and planning
2025-05-05 | AP-0003786 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2010 |  | 42.21 | 7596.95 | Hydronic Piping and Valves - fabricated material delivery
2025-05-07 | PRJ-PAY-ARM-2318-20250507 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1030 | 50.66 | 3597.19 | Startup, Testing and Commissioning - field installation time
2025-05-07 | PRJ-PAY-ARM-2318-20250507 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1037 | 40.1 | 3107.66 | Sheet Metal Fabrication Labor - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2318-20250507 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1044 | 44.85 | 3767.62 | Controls Programming and Checkout - supervision and planning
2025-05-07 | PRJ-PAY-ARM-2318-20250507 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1051 | 42.1 | 3809.66 | Warranty and Punchlist - startup and checkout
2025-05-07 | PRJ-PAY-ARM-2318-20250507 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1084 | 33.38 | 3237.46 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-08 | AP-0003783 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2496 |  | 90.71 | 16328.05 | Insulation and Specialty Material - ductwork release
2025-05-08 | AP-0003792 | AP | ARM-2318 | 05-100 | Equipment Rental and Rigging | V-2270 |  | 9300.9 | 9300.9 | Equipment Rental and Rigging - small tools and field consumables
2025-05-12 | AP-0003787 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2047 |  | 60.51 | 10891.64 | Insulation and Specialty Material - valves and piping lot
2025-05-14 | PRJ-PAY-ARM-2318-20250514 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1035 | 49.02 | 3480.51 | Sheet Metal Fabrication Labor - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2318-20250514 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1042 | 65.21 | 5053.91 | Controls Programming and Checkout - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2318-20250514 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1049 | 51.42 | 4319.36 | Warranty and Punchlist - startup and checkout
2025-05-14 | PRJ-PAY-ARM-2318-20250514 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1082 | 33.71 | 3050.43 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-15 | AP-0003784 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2510 |  | 72.8 | 13104.77 | Hydronic Piping and Valves - jobsite material replenishment
2025-05-18 | AP-0003781 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2469 |  | 60.13 | 10823.26 | Insulation and Specialty Material - fabricated material delivery
2025-05-18 | AP-0003788 | AP | ARM-2318 | 04-200 | Electrical and Controls Subcontract | V-2056 |  | 27173.14 | 27173.14 | Electrical and Controls Subcontract - insulation progress invoice
2025-05-18 | AP-0003790 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2231 |  | 4594.34 | 4594.34 | Temporary Facilities and Protection - permit and inspection fees
2025-05-21 | PRJ-PAY-ARM-2318-20250521 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1040 | 51.82 | 3679.04 | Controls Programming and Checkout - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2318-20250521 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1047 | 44.3 | 3433.42 | Warranty and Punchlist - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2318-20250521 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1080 | 42.49 | 3569.39 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-21 | PRJ-PAY-ARM-2318-20250521 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1087 | 40.03 | 3622.54 | Rework and Quality Correction - field installation time
2025-05-22 | AP-0003785 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2524 |  | 58.45 | 10521.15 | Insulation and Specialty Material - released equipment package
2025-05-25 | AP-0003782 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2483 |  | 71.59 | 12885.59 | Hydronic Piping and Valves - valves and piping lot
2025-05-25 | AP-0003789 | AP | ARM-2318 | 04-100 | Insulation Subcontract | V-2213 |  | 23030.5 | 23030.5 | Insulation Subcontract - testing and balancing services
2025-05-25 | AP-0003791 | AP | ARM-2318 | 05-300 | Freight and Expediting | V-2250 |  | 4360.62 | 4360.62 | Freight and Expediting - freight and expediting
2025-05-28 | PRJ-PAY-ARM-2318-20250528 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1045 | 44.43 | 3154.57 | Warranty and Punchlist - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2318-20250528 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1052 | 41.71 | 3232.31 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2318-20250528 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1085 | 44.8 | 3763.28 | Rework and Quality Correction - field installation time
2025-05-28 | PRJ-PAY-ARM-2318-20250528 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1092 | 41.02 | 4040.83 | Project Management and Supervision - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2318-20250531 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1050 | 56.98 | 4045.26 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2318-20250531 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1083 | 56.26 | 4360.15 | Rework and Quality Correction - field installation time
2025-05-31 | PRJ-PAY-ARM-2318-20250531 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1090 | 42.7 | 3928.34 | Project Management and Supervision - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2318-20250531 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1097 | 36.85 | 3334.51 | Engineering, BIM and Coordination - supervision and planning
2025-06-04 | AP-0003794 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2294 |  | 57.47 | 10343.72 | Plumbing Fixtures and Piping - ductwork release
2025-06-04 | AP-0003801 | AP | ARM-2318 | 04-200 | Electrical and Controls Subcontract | V-2379 |  | 25007.73 | 25007.73 | Electrical and Controls Subcontract - electrical coordination scope
2025-06-04 | AP-0003803 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2403 |  | 6694.88 | 6694.88 | Small Tools and Consumables - small tools and field consumables
2025-06-07 | PRJ-PAY-ARM-2318-20250607 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 58.85 | 4178.11 | Sheet Metal Fabrication Labor - field installation time
2025-06-07 | PRJ-PAY-ARM-2318-20250607 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1038 | 43.42 | 3365.14 | Controls Programming and Checkout - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2318-20250607 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1045 | 47.13 | 3959.06 | Warranty and Punchlist - supervision and planning
2025-06-07 | PRJ-PAY-ARM-2318-20250607 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1052 | 45.03 | 4074.87 | Closeout and O&M Documentation - startup and checkout
2025-06-08 | AP-0003798 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2350 |  | 63.29 | 11391.34 | Plumbing Fixtures and Piping - valves and piping lot
2025-06-11 | AP-0003795 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2308 |  | 66.73 | 12011.26 | Major HVAC Equipment - jobsite material replenishment
2025-06-14 | PRJ-PAY-ARM-2318-20250614 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1036 | 50.72 | 3601.29 | Controls Programming and Checkout - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2318-20250614 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1043 | 54.65 | 4235.42 | Warranty and Punchlist - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2318-20250614 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1050 | 40.4 | 3393.19 | Closeout and O&M Documentation - startup and checkout
2025-06-14 | PRJ-PAY-ARM-2318-20250614 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1083 | 30.72 | 2780.35 | Rework and Quality Correction - punchlist and closeout labor
2025-06-15 | AP-0003799 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2364 |  | 77.24 | 13902.47 | Major HVAC Equipment - ductwork release
2025-06-18 | AP-0003796 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2322 |  | 98.81 | 17785.31 | Plumbing Fixtures and Piping - released equipment package
2025-06-21 | AP-0003793 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2281 |  | 49.41 | 8894.1 | Major HVAC Equipment - valves and piping lot
2025-06-21 | AP-0003800 | AP | ARM-2318 | 04-300 | Testing and Balancing Subcontract | V-2365 |  | 26304.84 | 26304.84 | Testing and Balancing Subcontract - testing and balancing services
2025-06-21 | AP-0003802 | AP | ARM-2318 | 05-100 | Equipment Rental and Rigging | V-2389 |  | 8921.99 | 8921.99 | Equipment Rental and Rigging - freight and expediting
2025-06-21 | PRJ-PAY-ARM-2318-20250621 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1041 | 54.33 | 3857.33 | Warranty and Punchlist - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2318-20250621 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1048 | 37.83 | 2931.61 | Closeout and O&M Documentation - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2318-20250621 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1081 | 39.2 | 3292.44 | Rework and Quality Correction - punchlist and closeout labor
2025-06-21 | PRJ-PAY-ARM-2318-20250621 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1088 | 38.76 | 3817.8 | Project Management and Supervision - field installation time
2025-06-25 | AP-0003797 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2336 |  | 58.05 | 10449.09 | Major HVAC Equipment - fabricated material delivery
2025-06-28 | PRJ-PAY-ARM-2318-20250628 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1046 | 52.7 | 3741.97 | Closeout and O&M Documentation - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2318-20250628 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1053 | 52.43 | 4063.56 | Rework and Quality Correction - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2318-20250628 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1086 | 42.43 | 3903.94 | Project Management and Supervision - field installation time
2025-06-28 | PRJ-PAY-ARM-2318-20250628 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1093 | 40.18 | 3636.61 | Engineering, BIM and Coordination - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2318-20250630 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1051 | 49.61 | 3522.58 | Rework and Quality Correction - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2318-20250630 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1084 | 51.72 | 4421.76 | Project Management and Supervision - field installation time
2025-06-30 | PRJ-PAY-ARM-2318-20250630 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1091 | 39.98 | 3358.55 | Engineering, BIM and Coordination - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2318-20250630 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1098 | 31.12 | 2816.12 | Field Installation Labor - supervision and planning
2025-06-30 | PRJ-PAY-ARM-2318-20250630 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1012 | 29.91 | 2901.67 | Startup, Testing and Commissioning - startup and checkout
2025-07-04 | AP-0003808 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2469 |  | 66.88 | 12037.77 | Sheet Metal and Ductwork - valves and piping lot
2025-07-07 | AP-0003805 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2429 |  | 80.28 | 14450.16 | Controls Panels and Devices - jobsite material replenishment
2025-07-07 | AP-0003810 | AP | ARM-2318 | 04-300 | Testing and Balancing Subcontract | V-2488 |  | 21237.37 | 21237.37 | Testing and Balancing Subcontract - rigging and specialty support
2025-07-07 | AP-0003812 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2512 |  | 5017.2 | 5017.2 | Temporary Facilities and Protection - rental and logistics
2025-07-07 | PRJ-PAY-ARM-2318-20250707 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1032 | 50.65 | 3596.1 | Controls Programming and Checkout - field installation time
2025-07-07 | PRJ-PAY-ARM-2318-20250707 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1039 | 51.92 | 4023.94 | Warranty and Punchlist - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2318-20250707 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1046 | 51.58 | 4332.41 | Closeout and O&M Documentation - supervision and planning
2025-07-14 | AP-0003806 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2441 |  | 79.16 | 14248.25 | Sheet Metal and Ductwork - released equipment package
2025-07-14 | AP-0003813 | AP | ARM-2318 | 05-300 | Freight and Expediting | V-2526 |  | 6604.33 | 6604.33 | Freight and Expediting - permit and inspection fees
2025-07-14 | PRJ-PAY-ARM-2318-20250714 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1037 | 60.35 | 4284.9 | Warranty and Punchlist - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2318-20250714 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 47.8 | 3704.56 | Closeout and O&M Documentation - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2318-20250714 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1051 | 46.05 | 3868.23 | Rework and Quality Correction - startup and checkout
2025-07-21 | AP-0003807 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2455 |  | 65.88 | 11858.74 | Controls Panels and Devices - fabricated material delivery
2025-07-21 | PRJ-PAY-ARM-2318-20250721 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1042 | 36.66 | 2602.6 | Closeout and O&M Documentation - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2318-20250721 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1049 | 51.45 | 3987.11 | Rework and Quality Correction - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2318-20250721 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1082 | 28.7 | 2640.42 | Project Management and Supervision - punchlist and closeout labor
2025-07-21 | PRJ-PAY-ARM-2318-20250721 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1089 | 42.67 | 3861.94 | Engineering, BIM and Coordination - field installation time
2025-07-24 | AP-0003804 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2415 |  | 75.88 | 13658.13 | Sheet Metal and Ductwork - ductwork release
2025-07-24 | AP-0003809 | AP | ARM-2318 | 04-400 | Crane, Rigging and Specialty Trade | V-2474 |  | 21632.25 | 21632.25 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-07-24 | AP-0003811 | AP | ARM-2318 | 05-200 | Permits, Fees and Bonds | V-2498 |  | 5916.05 | 5916.05 | Permits, Fees and Bonds - small tools and field consumables
2025-07-28 | PRJ-PAY-ARM-2318-20250728 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1047 | 47.06 | 3341.48 | Rework and Quality Correction - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2318-20250728 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1080 | 49.61 | 4241.24 | Project Management and Supervision - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2318-20250728 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1087 | 44.96 | 3776.24 | Engineering, BIM and Coordination - field installation time
2025-07-28 | PRJ-PAY-ARM-2318-20250728 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1094 | 34.94 | 3161.75 | Field Installation Labor - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2318-20250731 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1052 | 51.36 | 4057.19 | Project Management and Supervision - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2318-20250731 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1085 | 44.69 | 3463.42 | Engineering, BIM and Coordination - field installation time
2025-07-31 | PRJ-PAY-ARM-2318-20250731 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1092 | 42.38 | 3559.58 | Field Installation Labor - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2318-20250731 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1099 | 41.44 | 3749.94 | Startup, Testing and Commissioning - supervision and planning
2025-08-03 | AP-0003814 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2001 |  | 48.22 | 8680.26 | Hydronic Piping and Valves - jobsite material replenishment
2025-08-03 | AP-0003819 | AP | ARM-2318 | 04-100 | Insulation Subcontract | V-2256 |  | 25713.52 | 25713.52 | Insulation Subcontract - rigging and specialty support
2025-08-03 | AP-0003821 | AP | ARM-2318 | 05-300 | Freight and Expediting | V-2286 |  | 5667.93 | 5667.93 | Freight and Expediting - rental and logistics
2025-08-07 | AP-0003818 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2250 |  | 64.62 | 11631.03 | Hydronic Piping and Valves - ductwork release
2025-08-07 | PRJ-PAY-ARM-2318-20250807 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1033 | 58.86 | 4178.9 | Warranty and Punchlist - field installation time
2025-08-07 | PRJ-PAY-ARM-2318-20250807 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 45.68 | 3539.91 | Closeout and O&M Documentation - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2318-20250807 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1047 | 39.93 | 3354.21 | Rework and Quality Correction - supervision and planning
2025-08-10 | AP-0003815 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2037 |  | 82.62 | 14870.99 | Insulation and Specialty Material - released equipment package
2025-08-10 | AP-0003820 | AP | ARM-2318 | 04-400 | Crane, Rigging and Specialty Trade | V-2275 |  | 17265.47 | 17265.47 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-08-10 | AP-0003822 | AP | ARM-2318 | 05-100 | Equipment Rental and Rigging | V-2300 |  | 9281.29 | 9281.29 | Equipment Rental and Rigging - permit and inspection fees
2025-08-14 | PRJ-PAY-ARM-2318-20250814 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 48.69 | 3457.19 | Closeout and O&M Documentation - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2318-20250814 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1045 | 50.33 | 3900.59 | Rework and Quality Correction - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2318-20250814 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1052 | 52.91 | 4867.93 | Project Management and Supervision - startup and checkout
2025-08-17 | AP-0003816 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2208 |  | 90.97 | 16373.85 | Hydronic Piping and Valves - fabricated material delivery
2025-08-21 | PRJ-PAY-ARM-2318-20250821 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1043 | 46.17 | 3278.2 | Rework and Quality Correction - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2318-20250821 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1050 | 41.89 | 3581.19 | Project Management and Supervision - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2318-20250821 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1083 | 39.46 | 3314.29 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-21 | PRJ-PAY-ARM-2318-20250821 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1090 | 37.42 | 3386.13 | Field Installation Labor - field installation time
2025-08-24 | AP-0003817 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2231 |  | 87.31 | 15715.34 | Insulation and Specialty Material - valves and piping lot
2025-08-28 | PRJ-PAY-ARM-2318-20250828 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1048 | 46.03 | 3636.19 | Project Management and Supervision - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2318-20250828 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1081 | 49.97 | 3872.73 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2318-20250828 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1088 | 39.7 | 3334.47 | Field Installation Labor - field installation time
2025-08-28 | PRJ-PAY-ARM-2318-20250828 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1095 | 33.21 | 3005.36 | Startup, Testing and Commissioning - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2318-20250831 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1053 | 39.7 | 2818.82 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2318-20250831 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1086 | 39.64 | 3071.86 | Field Installation Labor - field installation time
2025-08-31 | PRJ-PAY-ARM-2318-20250831 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1093 | 43.57 | 3659.49 | Startup, Testing and Commissioning - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2318-20250831 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1100 | 36.21 | 3276.7 | Sheet Metal Fabrication Labor - supervision and planning
2025-09-03 | AP-0003826 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2353 |  | 54.87 | 9877.11 | Major HVAC Equipment - ductwork release
2025-09-06 | AP-0003823 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2312 |  | 82.53 | 14854.89 | Plumbing Fixtures and Piping - released equipment package
2025-09-06 | AP-0003828 | AP | ARM-2318 | 04-200 | Electrical and Controls Subcontract | V-2372 |  | 32965.55 | 32965.55 | Electrical and Controls Subcontract - trade partner progress billing
2025-09-06 | AP-0003829 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2384 |  | 10489.05 | 10489.05 | Small Tools and Consumables - permit and inspection fees
2025-09-07 | PRJ-PAY-ARM-2318-20250907 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 38.42 | 2727.65 | Closeout and O&M Documentation - field installation time
2025-09-07 | PRJ-PAY-ARM-2318-20250907 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1041 | 50.44 | 3908.9 | Rework and Quality Correction - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2318-20250907 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1048 | 33.82 | 3111.66 | Project Management and Supervision - supervision and planning
2025-09-10 | AP-0003827 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2367 |  | 55.67 | 10021.2 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-09-13 | AP-0003824 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2326 |  | 70.73 | 12732.01 | Major HVAC Equipment - fabricated material delivery
2025-09-14 | PRJ-PAY-ARM-2318-20250914 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1039 | 51.8 | 3677.6 | Rework and Quality Correction - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2318-20250914 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1046 | 41.71 | 3565.86 | Project Management and Supervision - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2318-20250914 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1053 | 42.48 | 3568.5 | Engineering, BIM and Coordination - startup and checkout
2025-09-20 | AP-0003825 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2339 |  | 52.53 | 9455.29 | Plumbing Fixtures and Piping - valves and piping lot
2025-09-21 | PRJ-PAY-ARM-2318-20250921 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1044 | 51.37 | 4058.49 | Project Management and Supervision - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2318-20250921 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1051 | 44.87 | 3477.35 | Engineering, BIM and Coordination - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2318-20250921 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1084 | 41.74 | 3506.5 | Field Installation Labor - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2318-20250928 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 45.75 | 3248 | Engineering, BIM and Coordination - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2318-20250928 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1082 | 44.17 | 3423.37 | Field Installation Labor - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2318-20250928 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1089 | 42.34 | 3556.18 | Startup, Testing and Commissioning - field installation time
2025-09-30 | PRJ-PAY-ARM-2318-20250930 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1080 | 40.66 | 2886.55 | Field Installation Labor - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2318-20250930 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1087 | 45.05 | 3491.63 | Startup, Testing and Commissioning - field installation time
2025-09-30 | PRJ-PAY-ARM-2318-20250930 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1094 | 32.6 | 2738.52 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-06 | AP-0003833 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2439 |  | 84.41 | 15193.39 | Sheet Metal and Ductwork - jobsite material replenishment
2025-10-07 | PRJ-PAY-ARM-2318-20251007 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1035 | 51.09 | 3627.26 | Rework and Quality Correction - field installation time
2025-10-07 | PRJ-PAY-ARM-2318-20251007 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1042 | 43.33 | 3704.74 | Project Management and Supervision - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2318-20251007 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 40.06 | 3365.25 | Engineering, BIM and Coordination - supervision and planning
2025-10-09 | AP-0003830 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2398 |  | 64.56 | 11620.48 | Controls Panels and Devices - fabricated material delivery
2025-10-09 | AP-0003834 | AP | ARM-2318 | 04-300 | Testing and Balancing Subcontract | V-2445 |  | 33417.58 | 33417.58 | Testing and Balancing Subcontract - insulation progress invoice
2025-10-09 | AP-0003835 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2457 |  | 7415.17 | 7415.17 | Temporary Facilities and Protection - freight and expediting
2025-10-14 | PRJ-PAY-ARM-2318-20251014 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1040 | 51.9 | 4099.72 | Project Management and Supervision - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2318-20251014 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 53.79 | 4168.45 | Engineering, BIM and Coordination - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2318-20251014 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1080 | 31.63 | 2657.02 | Field Installation Labor - startup and checkout
2025-10-16 | AP-0003831 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2412 |  | 45.91 | 8263.3 | Sheet Metal and Ductwork - valves and piping lot
2025-10-16 | AP-0003836 | AP | ARM-2318 | 05-300 | Freight and Expediting | V-2471 |  | 5661.27 | 5661.27 | Freight and Expediting - small tools and field consumables
2025-10-21 | PRJ-PAY-ARM-2318-20251021 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1045 | 45.39 | 3222.86 | Engineering, BIM and Coordination - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2318-20251021 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1052 | 49.4 | 3828.41 | Field Installation Labor - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2318-20251021 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1085 | 36.52 | 3067.77 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-23 | AP-0003832 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2426 |  | 79.57 | 14322.74 | Controls Panels and Devices - ductwork release
2025-10-28 | PRJ-PAY-ARM-2318-20251028 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1050 | 37.19 | 2640.45 | Field Installation Labor - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2318-20251028 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1083 | 38.76 | 3003.75 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2318-20251028 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1090 | 40.19 | 3375.77 | Sheet Metal Fabrication Labor - field installation time
2025-10-31 | PRJ-PAY-ARM-2318-20251031 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 42.43 | 3012.34 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2318-20251031 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1088 | 35.21 | 2728.49 | Sheet Metal Fabrication Labor - field installation time
2025-10-31 | PRJ-PAY-ARM-2318-20251031 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1095 | 34.5 | 2897.63 | Controls Programming and Checkout - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2318-20251107 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1036 | 46.8 | 3697.57 | Project Management and Supervision - field installation time
2025-11-07 | PRJ-PAY-ARM-2318-20251107 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 39.48 | 3060.03 | Engineering, BIM and Coordination - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2318-20251107 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1050 | 47.56 | 3994.9 | Field Installation Labor - supervision and planning
2025-11-09 | AP-0003840 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2524 |  | 70.92 | 12766.5 | Hydronic Piping and Valves - released equipment package
2025-11-12 | AP-0003837 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2483 |  | 50.68 | 9122.57 | Insulation and Specialty Material - valves and piping lot
2025-11-12 | AP-0003841 | AP | ARM-2318 | 04-400 | Crane, Rigging and Specialty Trade | V-2531 |  | 30585.68 | 30585.68 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-11-12 | AP-0003842 | AP | ARM-2318 | 05-100 | Equipment Rental and Rigging | V-2021 |  | 4876.43 | 4876.43 | Equipment Rental and Rigging - small tools and field consumables
2025-11-14 | PRJ-PAY-ARM-2318-20251114 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 46.16 | 3277.61 | Engineering, BIM and Coordination - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2318-20251114 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1048 | 45.76 | 3546.52 | Field Installation Labor - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2318-20251114 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 37.32 | 3134.96 | Startup, Testing and Commissioning - startup and checkout
2025-11-19 | AP-0003838 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2496 |  | 63.16 | 11367.91 | Hydronic Piping and Valves - ductwork release
2025-11-19 | AP-0003843 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2094 |  | 6245.63 | 6245.63 | Small Tools and Consumables - rental and logistics
2025-11-21 | PRJ-PAY-ARM-2318-20251121 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1046 | 45.79 | 3251.12 | Field Installation Labor - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2318-20251121 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1053 | 40.1 | 3107.93 | Startup, Testing and Commissioning - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2318-20251121 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1086 | 29.98 | 2518.35 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-25 | AP-0003839 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2510 |  | 93.29 | 16792.31 | Insulation and Specialty Material - jobsite material replenishment
2025-11-28 | PRJ-PAY-ARM-2318-20251128 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 49.95 | 3546.24 | Startup, Testing and Commissioning - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2318-20251128 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1084 | 30.86 | 2391.66 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2318-20251128 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1091 | 30.52 | 2564.02 | Controls Programming and Checkout - field installation time
2025-11-30 | PRJ-PAY-ARM-2318-20251130 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 46.31 | 3287.95 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2318-20251130 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1089 | 42.35 | 3282.35 | Controls Programming and Checkout - field installation time
2025-11-30 | PRJ-PAY-ARM-2318-20251130 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1096 | 31.04 | 2607.56 | Warranty and Punchlist - coordination and layout
2025-12-05 | AP-0003846 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2256 |  | 59.58 | 10724.59 | Major HVAC Equipment - released equipment package
2025-12-07 | PRJ-PAY-ARM-2318-20251207 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 37.17 | 2639.17 | Engineering, BIM and Coordination - field installation time
2025-12-07 | PRJ-PAY-ARM-2318-20251207 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1044 | 30.04 | 2328.37 | Field Installation Labor - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2318-20251207 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 26.15 | 2196.5 | Startup, Testing and Commissioning - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2318-20251214 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1042 | 32.73 | 2324.02 | Field Installation Labor - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2318-20251214 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 27.18 | 2106.58 | Startup, Testing and Commissioning - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2318-20251214 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 23.28 | 1955.33 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-15 | AP-0003844 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2217 |  | 71.36 | 12845.36 | Major HVAC Equipment - ductwork release
2025-12-15 | AP-0003847 | AP | ARM-2318 | 04-100 | Insulation Subcontract | V-2270 |  | 22773.7 | 22773.7 | Insulation Subcontract - electrical coordination scope
2025-12-15 | AP-0003848 | AP | ARM-2318 | 05-200 | Permits, Fees and Bonds | V-2282 |  | 6931.13 | 6931.13 | Permits, Fees and Bonds - rental and logistics
2025-12-21 | PRJ-PAY-ARM-2318-20251221 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1047 | 36.57 | 2596.82 | Startup, Testing and Commissioning - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2318-20251221 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1080 | 22.4 | 1736.31 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2318-20251221 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1087 | 21.22 | 1782.7 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-22 | AP-0003845 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2237 |  | 78.09 | 14056.16 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-12-28 | PRJ-PAY-ARM-2318-20251228 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 26.2 | 1860.44 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2318-20251228 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1085 | 35.43 | 2745.93 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2318-20251228 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1092 | 23.76 | 1995.7 | Warranty and Punchlist - field installation time
2025-12-31 | PRJ-PAY-ARM-2318-20251231 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1083 | 35.69 | 2533.76 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2318-20251231 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1090 | 35.79 | 2774.11 | Warranty and Punchlist - field installation time
2025-12-31 | PRJ-PAY-ARM-2318-20251231 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1097 | 24.88 | 2089.73 | Closeout and O&M Documentation - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2318-20260107 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1038 | 35.01 | 2485.68 | Field Installation Labor - field installation time
2026-01-07 | PRJ-PAY-ARM-2318-20260107 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 24.03 | 1862.36 | Startup, Testing and Commissioning - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2318-20260107 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 30.55 | 2566.25 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-08 | AP-0003851 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2324 |  | 70.43 | 12676.75 | Sheet Metal and Ductwork - fabricated material delivery
2026-01-14 | PRJ-PAY-ARM-2318-20260114 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 29.86 | 2120.17 | Startup, Testing and Commissioning - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2318-20260114 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 29.82 | 2311.32 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2318-20260114 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1083 | 26.08 | 2190.35 | Controls Programming and Checkout - startup and checkout
2026-01-18 | AP-0003849 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2296 |  | 84.05 | 15128.65 | Sheet Metal and Ductwork - jobsite material replenishment
2026-01-18 | AP-0003852 | AP | ARM-2318 | 04-200 | Electrical and Controls Subcontract | V-2332 |  | 24011.12 | 24011.12 | Electrical and Controls Subcontract - rigging and specialty support
2026-01-18 | AP-0003853 | AP | ARM-2318 | 05-300 | Freight and Expediting | V-2345 |  | 9822.74 | 9822.74 | Freight and Expediting - permit and inspection fees
2026-01-21 | PRJ-PAY-ARM-2318-20260121 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1048 | 35.04 | 2487.49 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2318-20260121 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1081 | 32.58 | 2525.2 | Controls Programming and Checkout - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2318-20260121 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1088 | 25.42 | 2135.62 | Warranty and Punchlist - punchlist and closeout labor
2026-01-25 | AP-0003850 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2310 |  | 51.68 | 9302.7 | Controls Panels and Devices - released equipment package
2026-01-28 | PRJ-PAY-ARM-2318-20260128 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1053 | 28.75 | 2041 | Controls Programming and Checkout - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2318-20260128 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1086 | 40.7 | 3154.39 | Warranty and Punchlist - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2318-20260128 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1093 | 33.5 | 2814.28 | Closeout and O&M Documentation - field installation time
2026-01-31 | PRJ-PAY-ARM-2318-20260131 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1084 | 41.44 | 2942.04 | Warranty and Punchlist - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2318-20260131 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1091 | 36.69 | 2843.25 | Closeout and O&M Documentation - field installation time
2026-01-31 | PRJ-PAY-ARM-2318-20260131 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1098 | 31.29 | 2628.7 | Rework and Quality Correction - coordination and layout
2026-02-04 | AP-0003855 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2372 |  | 83.47 | 15024.9 | Insulation and Specialty Material - fabricated material delivery
2026-02-07 | PRJ-PAY-ARM-2318-20260207 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 44.8 | 3180.84 | Startup, Testing and Commissioning - field installation time
2026-02-07 | PRJ-PAY-ARM-2318-20260207 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 27.62 | 2140.67 | Sheet Metal Fabrication Labor - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2318-20260207 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1053 | 38.92 | 3269.18 | Controls Programming and Checkout - supervision and planning
2026-02-11 | AP-0003856 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2386 |  | 78.58 | 14144.16 | Hydronic Piping and Valves - valves and piping lot
2026-02-14 | PRJ-PAY-ARM-2318-20260214 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 41.51 | 2947.03 | Sheet Metal Fabrication Labor - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2318-20260214 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1051 | 48.25 | 3739.41 | Controls Programming and Checkout - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2318-20260214 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1084 | 30.8 | 2587.26 | Warranty and Punchlist - startup and checkout
2026-02-21 | AP-0003854 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2358 |  | 68.37 | 12306.36 | Hydronic Piping and Valves - released equipment package
2026-02-21 | AP-0003857 | AP | ARM-2318 | 04-300 | Testing and Balancing Subcontract | V-2395 |  | 26498.19 | 26498.19 | Testing and Balancing Subcontract - trade partner progress billing
2026-02-21 | AP-0003858 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2407 |  | 9216.76 | 9216.76 | Small Tools and Consumables - freight and expediting
2026-02-21 | PRJ-PAY-ARM-2318-20260221 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1049 | 57.18 | 4059.88 | Controls Programming and Checkout - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2318-20260221 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1082 | 38.2 | 2960.84 | Warranty and Punchlist - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2318-20260221 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1089 | 40.12 | 3370.44 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2318-20260228 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1080 | 52.09 | 3698.43 | Warranty and Punchlist - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2318-20260228 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1087 | 55.67 | 4314.4 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2318-20260228 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1094 | 34.56 | 2902.85 | Rework and Quality Correction - field installation time
2026-03-07 | AP-0003860 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2434 |  | 62.93 | 11327.7 | Major HVAC Equipment - valves and piping lot
2026-03-07 | PRJ-PAY-ARM-2318-20260307 | PAY | ARM-2318 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 38.51 | 2734.48 | Sheet Metal Fabrication Labor - field installation time
2026-03-07 | PRJ-PAY-ARM-2318-20260307 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1047 | 26.18 | 2029.17 | Controls Programming and Checkout - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2318-20260307 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1080 | 35.61 | 2990.91 | Warranty and Punchlist - supervision and planning
2026-03-14 | AP-0003861 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2446 |  | 77.57 | 13963.38 | Plumbing Fixtures and Piping - ductwork release
2026-03-14 | PRJ-PAY-ARM-2318-20260314 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1045 | 34.79 | 2470.05 | Controls Programming and Checkout - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2318-20260314 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1052 | 35.37 | 2741.09 | Warranty and Punchlist - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2318-20260314 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1085 | 41.4 | 3477.83 | Closeout and O&M Documentation - startup and checkout
2026-03-21 | AP-0003862 | AP | ARM-2318 | 02-110 | Major HVAC Equipment | V-2460 |  | 47.26 | 8506.88 | Major HVAC Equipment - jobsite material replenishment
2026-03-21 | PRJ-PAY-ARM-2318-20260321 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1050 | 41.76 | 2964.78 | Warranty and Punchlist - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2318-20260321 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1083 | 40.53 | 3140.69 | Closeout and O&M Documentation - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2318-20260321 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1090 | 35.98 | 3022.1 | Rework and Quality Correction - punchlist and closeout labor
2026-03-24 | AP-0003859 | AP | ARM-2318 | 02-410 | Plumbing Fixtures and Piping | V-2421 |  | 72.83 | 13108.77 | Plumbing Fixtures and Piping - fabricated material delivery
2026-03-24 | AP-0003863 | AP | ARM-2318 | 04-400 | Crane, Rigging and Specialty Trade | V-2467 |  | 27156.53 | 27156.53 | Crane, Rigging and Specialty Trade - insulation progress invoice
2026-03-24 | AP-0003864 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2479 |  | 8640.7 | 8640.7 | Temporary Facilities and Protection - small tools and field consumables
2026-03-28 | PRJ-PAY-ARM-2318-20260328 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1081 | 36.79 | 2612.36 | Closeout and O&M Documentation - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2318-20260328 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1088 | 48.98 | 3795.58 | Rework and Quality Correction - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2318-20260328 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1095 | 24.56 | 2259.18 | Project Management and Supervision - field installation time
2026-03-31 | PRJ-PAY-ARM-2318-20260331 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1086 | 35.58 | 2526.28 | Rework and Quality Correction - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2318-20260331 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1093 | 30.77 | 2630.93 | Project Management and Supervision - field installation time
2026-03-31 | PRJ-PAY-ARM-2318-20260331 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1100 | 30.64 | 2573.75 | Engineering, BIM and Coordination - coordination and layout
2026-04-03 | AP-0003865 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2493 |  | 92.64 | 16674.58 | Controls Panels and Devices - valves and piping lot
2026-04-03 | AP-0003869 | AP | ARM-2318 | 04-100 | Insulation Subcontract | V-2018 |  | 32498.13 | 32498.13 | Insulation Subcontract - testing and balancing services
2026-04-03 | AP-0003870 | AP | ARM-2318 | 05-100 | Equipment Rental and Rigging | V-2056 |  | 6362.44 | 6362.44 | Equipment Rental and Rigging - rental and logistics
2026-04-07 | PRJ-PAY-ARM-2318-20260407 | PAY | ARM-2318 | 03-400 | Controls Programming and Checkout |  | E-1041 | 48.77 | 3462.91 | Controls Programming and Checkout - field installation time
2026-04-07 | PRJ-PAY-ARM-2318-20260407 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1048 | 40.62 | 3147.96 | Warranty and Punchlist - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2318-20260407 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1081 | 41.35 | 3473.21 | Closeout and O&M Documentation - supervision and planning
2026-04-10 | AP-0003866 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2507 |  | 49.94 | 8989.59 | Sheet Metal and Ductwork - ductwork release
2026-04-10 | AP-0003871 | AP | ARM-2318 | 05-400 | Small Tools and Consumables | V-2213 |  | 6354.22 | 6354.22 | Small Tools and Consumables - permit and inspection fees
2026-04-14 | PRJ-PAY-ARM-2318-20260414 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1046 | 47.72 | 3387.98 | Warranty and Punchlist - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2318-20260414 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 48.44 | 3753.77 | Closeout and O&M Documentation - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2318-20260414 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1086 | 41.09 | 3451.36 | Rework and Quality Correction - startup and checkout
2026-04-17 | AP-0003867 | AP | ARM-2318 | 02-510 | Controls Panels and Devices | V-2521 |  | 76.77 | 13818.45 | Controls Panels and Devices - jobsite material replenishment
2026-04-21 | PRJ-PAY-ARM-2318-20260421 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 42.7 | 3031.93 | Closeout and O&M Documentation - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2318-20260421 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1084 | 41 | 3177.45 | Rework and Quality Correction - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2318-20260421 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1091 | 41.84 | 3849.34 | Project Management and Supervision - punchlist and closeout labor
2026-04-24 | AP-0003868 | AP | ARM-2318 | 02-210 | Sheet Metal and Ductwork | V-2534 |  | 47.55 | 8558.1 | Sheet Metal and Ductwork - released equipment package
2026-04-28 | PRJ-PAY-ARM-2318-20260428 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1082 | 42.01 | 2982.92 | Rework and Quality Correction - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2318-20260428 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1089 | 30.8 | 2633.3 | Project Management and Supervision - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2318-20260428 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1096 | 39.95 | 3356.02 | Engineering, BIM and Coordination - field installation time
2026-04-30 | PRJ-PAY-ARM-2318-20260430 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1087 | 25.64 | 2025.94 | Project Management and Supervision - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2318-20260430 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1094 | 39.7 | 3076.52 | Engineering, BIM and Coordination - field installation time
2026-04-30 | PRJ-PAY-ARM-2318-20260430 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1007 | 38.45 | 3230.11 | Field Installation Labor - coordination and layout
2026-05-03 | AP-0003875 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2286 |  | 40.45 | 7281.86 | Hydronic Piping and Valves - fabricated material delivery
2026-05-06 | AP-0003872 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2232 |  | 79.23 | 14260.93 | Insulation and Specialty Material - ductwork release
2026-05-06 | AP-0003877 | AP | ARM-2318 | 04-200 | Electrical and Controls Subcontract | V-2305 |  | 34742.25 | 34742.25 | Electrical and Controls Subcontract - electrical coordination scope
2026-05-06 | AP-0003878 | AP | ARM-2318 | 05-200 | Permits, Fees and Bonds | V-2317 |  | 6932.8 | 6932.8 | Permits, Fees and Bonds - permit and inspection fees
2026-05-07 | PRJ-PAY-ARM-2318-20260507 | PAY | ARM-2318 | 06-100 | Warranty and Punchlist |  | E-1042 | 59.42 | 4218.65 | Warranty and Punchlist - field installation time
2026-05-07 | PRJ-PAY-ARM-2318-20260507 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 57.73 | 4474.07 | Closeout and O&M Documentation - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2318-20260507 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1082 | 41.55 | 3490.59 | Rework and Quality Correction - supervision and planning
2026-05-10 | AP-0003876 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2300 |  | 78.47 | 14123.79 | Insulation and Specialty Material - valves and piping lot
2026-05-13 | AP-0003873 | AP | ARM-2318 | 02-310 | Hydronic Piping and Valves | V-2253 |  | 61.54 | 11077.29 | Hydronic Piping and Valves - jobsite material replenishment
2026-05-13 | AP-0003879 | AP | ARM-2318 | 06-400 | Temporary Facilities and Protection | V-2331 |  | 5700.74 | 5700.74 | Temporary Facilities and Protection - freight and expediting
2026-05-14 | PRJ-PAY-ARM-2318-20260514 | PAY | ARM-2318 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 48.54 | 3446.36 | Closeout and O&M Documentation - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2318-20260514 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1080 | 50.05 | 3879.02 | Rework and Quality Correction - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2318-20260514 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1087 | 46.12 | 4243.33 | Project Management and Supervision - startup and checkout
2026-05-20 | AP-0003874 | AP | ARM-2318 | 02-610 | Insulation and Specialty Material | V-2272 |  | 56.15 | 10107.09 | Insulation and Specialty Material - released equipment package
2026-05-21 | PRJ-PAY-ARM-2318-20260521 | PAY | ARM-2318 | 06-300 | Rework and Quality Correction |  | E-1052 | 50.58 | 3590.94 | Rework and Quality Correction - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2318-20260521 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1085 | 42.7 | 3650.51 | Project Management and Supervision - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2318-20260521 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1092 | 36.64 | 3077.67 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2318-20260528 | PAY | ARM-2318 | 01-100 | Project Management and Supervision |  | E-1083 | 36.99 | 2922.19 | Project Management and Supervision - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2318-20260528 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1090 | 53.32 | 4132.65 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2318-20260528 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1097 | 30.1 | 2528.58 | Field Installation Labor - field installation time
2026-05-31 | PRJ-PAY-ARM-2318-20260531 | PAY | ARM-2318 | 01-200 | Engineering, BIM and Coordination |  | E-1088 | 50.23 | 3566 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2318-20260531 | PAY | ARM-2318 | 03-100 | Field Installation Labor |  | E-1095 | 38.21 | 2961.01 | Field Installation Labor - field installation time
2026-05-31 | PRJ-PAY-ARM-2318-20260531 | PAY | ARM-2318 | 03-200 | Startup, Testing and Commissioning |  | E-1008 | 41.8 | 3511 | Startup, Testing and Commissioning - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2403-20250107 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1020 | 52.72 | 3743.08 | Field Installation Labor - field installation time
2025-01-07 | PRJ-PAY-ARM-2403-20250107 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 46.63 | 3613.45 | Startup, Testing and Commissioning - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2403-20250107 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 45.5 | 3821.98 | Sheet Metal Fabrication Labor - supervision and planning
2025-01-09 | AP-0003974 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2434 |  | 68.05 | 12249.05 | Controls Panels and Devices - jobsite material replenishment
2025-01-12 | AP-0003971 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2393 |  | 84.28 | 15170.44 | Sheet Metal and Ductwork - fabricated material delivery
2025-01-12 | AP-0003976 | AP | ARM-2403 | 04-400 | Crane, Rigging and Specialty Trade | V-2452 |  | 19477.86 | 19477.86 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-01-12 | AP-0003978 | AP | ARM-2403 | 06-400 | Temporary Facilities and Protection | V-2476 |  | 5860.83 | 5860.83 | Temporary Facilities and Protection - small tools and field consumables
2025-01-14 | PRJ-PAY-ARM-2403-20250114 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 58.9 | 4182.22 | Startup, Testing and Commissioning - coordination and layout
2025-01-14 | PRJ-PAY-ARM-2403-20250114 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 52.24 | 4048.59 | Sheet Metal Fabrication Labor - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2403-20250114 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1039 | 43.5 | 3654.1 | Controls Programming and Checkout - startup and checkout
2025-01-16 | AP-0003975 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2446 |  | 52.45 | 9440.78 | Sheet Metal and Ductwork - released equipment package
2025-01-19 | AP-0003972 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2407 |  | 58.55 | 10538.54 | Controls Panels and Devices - valves and piping lot
2025-01-19 | AP-0003977 | AP | ARM-2403 | 04-300 | Testing and Balancing Subcontract | V-2465 |  | 22136.87 | 22136.87 | Testing and Balancing Subcontract - testing and balancing services
2025-01-19 | AP-0003979 | AP | ARM-2403 | 05-300 | Freight and Expediting | V-2490 |  | 11163.37 | 11163.37 | Freight and Expediting - rental and logistics
2025-01-21 | PRJ-PAY-ARM-2403-20250121 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 49.29 | 3499.9 | Sheet Metal Fabrication Labor - supervision and planning
2025-01-21 | PRJ-PAY-ARM-2403-20250121 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1037 | 42.51 | 3294.2 | Controls Programming and Checkout - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2403-20250121 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1044 | 34.72 | 2916.6 | Warranty and Punchlist - punchlist and closeout labor
2025-01-21 | PRJ-PAY-ARM-2403-20250121 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 40.14 | 3632.61 | Closeout and O&M Documentation - field installation time
2025-01-25 | AP-0003973 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2421 |  | 93.97 | 16914.87 | Sheet Metal and Ductwork - ductwork release
2025-01-28 | PRJ-PAY-ARM-2403-20250128 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1035 | 51.39 | 3648.45 | Controls Programming and Checkout - startup and checkout
2025-01-28 | PRJ-PAY-ARM-2403-20250128 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1042 | 47.29 | 3665.36 | Warranty and Punchlist - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2403-20250128 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 40.57 | 3407.86 | Closeout and O&M Documentation - field installation time
2025-01-28 | PRJ-PAY-ARM-2403-20250128 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1082 | 38.58 | 3491.19 | Rework and Quality Correction - coordination and layout
2025-01-31 | PRJ-PAY-ARM-2403-20250131 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1040 | 50.42 | 3579.69 | Warranty and Punchlist - punchlist and closeout labor
2025-01-31 | PRJ-PAY-ARM-2403-20250131 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 45.63 | 3536.47 | Closeout and O&M Documentation - field installation time
2025-01-31 | PRJ-PAY-ARM-2403-20250131 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1080 | 40.54 | 3405.03 | Rework and Quality Correction - coordination and layout
2025-01-31 | PRJ-PAY-ARM-2403-20250131 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1087 | 32.21 | 3172.9 | Project Management and Supervision - supervision and planning
2025-02-05 | AP-0003982 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2529 |  | 88.46 | 15922.84 | Hydronic Piping and Valves - jobsite material replenishment
2025-02-07 | PRJ-PAY-ARM-2403-20250207 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 55.1 | 3912.17 | Startup, Testing and Commissioning - field installation time
2025-02-07 | PRJ-PAY-ARM-2403-20250207 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 53.07 | 4112.88 | Sheet Metal Fabrication Labor - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2403-20250207 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1035 | 47.39 | 3980.9 | Controls Programming and Checkout - supervision and planning
2025-02-07 | PRJ-PAY-ARM-2403-20250207 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1042 | 36.75 | 3325.81 | Warranty and Punchlist - startup and checkout
2025-02-12 | AP-0003983 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2021 |  | 64.39 | 11590.79 | Insulation and Specialty Material - released equipment package
2025-02-14 | PRJ-PAY-ARM-2403-20250214 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 52.78 | 3747.14 | Sheet Metal Fabrication Labor - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2403-20250214 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1033 | 48.91 | 3790.7 | Controls Programming and Checkout - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2403-20250214 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1040 | 36.81 | 3091.68 | Warranty and Punchlist - startup and checkout
2025-02-14 | PRJ-PAY-ARM-2403-20250214 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 38.2 | 3457.12 | Closeout and O&M Documentation - punchlist and closeout labor
2025-02-14 | PRJ-PAY-ARM-2403-20250214 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1080 | 32.23 | 3126.48 | Rework and Quality Correction - field installation time
2025-02-15 | AP-0003980 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2502 |  | 74.1 | 13338.19 | Hydronic Piping and Valves - valves and piping lot
2025-02-15 | AP-0003986 | AP | ARM-2403 | 04-100 | Insulation Subcontract | V-2225 |  | 28500.7 | 28500.7 | Insulation Subcontract - testing and balancing services
2025-02-15 | AP-0003988 | AP | ARM-2403 | 05-100 | Equipment Rental and Rigging | V-2258 |  | 7635.22 | 7635.22 | Equipment Rental and Rigging - rental and logistics
2025-02-19 | AP-0003984 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2094 |  | 65.59 | 11805.54 | Hydronic Piping and Valves - fabricated material delivery
2025-02-21 | PRJ-PAY-ARM-2403-20250221 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1031 | 46.29 | 3286.26 | Controls Programming and Checkout - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2403-20250221 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1038 | 50.99 | 3952.06 | Warranty and Punchlist - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2403-20250221 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 44.06 | 3701.37 | Closeout and O&M Documentation - punchlist and closeout labor
2025-02-21 | PRJ-PAY-ARM-2403-20250221 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1052 | 34.28 | 3101.97 | Rework and Quality Correction - field installation time
2025-02-21 | PRJ-PAY-ARM-2403-20250221 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1085 | 40.89 | 4293.19 | Project Management and Supervision - coordination and layout
2025-02-22 | AP-0003981 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2515 |  | 59.36 | 10683.98 | Insulation and Specialty Material - ductwork release
2025-02-22 | AP-0003987 | AP | ARM-2403 | 04-400 | Crane, Rigging and Specialty Trade | V-2244 |  | 17868.23 | 17868.23 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-02-22 | AP-0003989 | AP | ARM-2403 | 05-400 | Small Tools and Consumables | V-2277 |  | 8493.11 | 8493.11 | Small Tools and Consumables - permit and inspection fees
2025-02-25 | AP-0003985 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2220 |  | 51.31 | 9236.11 | Insulation and Specialty Material - valves and piping lot
2025-02-28 | PRJ-PAY-ARM-2403-20250228 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1036 | 55.87 | 3967.06 | Warranty and Punchlist - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2403-20250228 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 40.6 | 3146.44 | Closeout and O&M Documentation - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2403-20250228 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1050 | 37.86 | 3180.23 | Rework and Quality Correction - field installation time
2025-02-28 | PRJ-PAY-ARM-2403-20250228 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1083 | 39.26 | 3867.57 | Project Management and Supervision - coordination and layout
2025-02-28 | PRJ-PAY-ARM-2403-20250228 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1090 | 36.13 | 3504.34 | Engineering, BIM and Coordination - supervision and planning
2025-03-05 | AP-0003995 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2358 |  | 66.07 | 11892.54 | Major HVAC Equipment - ductwork release
2025-03-07 | PRJ-PAY-ARM-2403-20250307 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1022 | 64.61 | 4587.22 | Sheet Metal Fabrication Labor - field installation time
2025-03-07 | PRJ-PAY-ARM-2403-20250307 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1029 | 41.2 | 3193.02 | Controls Programming and Checkout - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2403-20250307 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1036 | 33.86 | 2844.66 | Warranty and Punchlist - supervision and planning
2025-03-07 | PRJ-PAY-ARM-2403-20250307 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 29.9 | 2705.58 | Closeout and O&M Documentation - startup and checkout
2025-03-08 | AP-0003992 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2317 |  | 74.02 | 13323.1 | Plumbing Fixtures and Piping - released equipment package
2025-03-14 | PRJ-PAY-ARM-2403-20250314 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1027 | 39.51 | 2805.36 | Controls Programming and Checkout - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2403-20250314 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1034 | 52.82 | 4093.63 | Warranty and Punchlist - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2403-20250314 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 50.22 | 4218.33 | Closeout and O&M Documentation - startup and checkout
2025-03-14 | PRJ-PAY-ARM-2403-20250314 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1048 | 34.05 | 3081.87 | Rework and Quality Correction - punchlist and closeout labor
2025-03-15 | AP-0003993 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2331 |  | 64.26 | 11567.32 | Major HVAC Equipment - fabricated material delivery
2025-03-18 | AP-0003990 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2289 |  | 61.27 | 11028.94 | Plumbing Fixtures and Piping - ductwork release
2025-03-18 | AP-0003996 | AP | ARM-2403 | 04-200 | Electrical and Controls Subcontract | V-2362 |  | 22312.3 | 22312.3 | Electrical and Controls Subcontract - electrical coordination scope
2025-03-18 | AP-0003998 | AP | ARM-2403 | 05-200 | Permits, Fees and Bonds | V-2386 |  | 7259.98 | 7259.98 | Permits, Fees and Bonds - permit and inspection fees
2025-03-21 | PRJ-PAY-ARM-2403-20250321 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1032 | 39.8 | 2825.81 | Warranty and Punchlist - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2403-20250321 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 52.65 | 4080.66 | Closeout and O&M Documentation - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2403-20250321 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1046 | 34.71 | 2915.83 | Rework and Quality Correction - punchlist and closeout labor
2025-03-21 | PRJ-PAY-ARM-2403-20250321 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1053 | 39.17 | 3858.63 | Project Management and Supervision - field installation time
2025-03-22 | AP-0003994 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2345 |  | 61.69 | 11103.8 | Plumbing Fixtures and Piping - valves and piping lot
2025-03-25 | AP-0003991 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2303 |  | 74.36 | 13384.13 | Major HVAC Equipment - jobsite material replenishment
2025-03-25 | AP-0003997 | AP | ARM-2403 | 04-100 | Insulation Subcontract | V-2376 |  | 19545.49 | 19545.49 | Insulation Subcontract - rigging and specialty support
2025-03-25 | AP-0003999 | AP | ARM-2403 | 06-400 | Temporary Facilities and Protection | V-2400 |  | 6058.41 | 6058.41 | Temporary Facilities and Protection - freight and expediting
2025-03-28 | PRJ-PAY-ARM-2403-20250328 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 60.1 | 4267.36 | Closeout and O&M Documentation - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2403-20250328 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1044 | 50.26 | 3895.44 | Rework and Quality Correction - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2403-20250328 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1051 | 44.45 | 4089.38 | Project Management and Supervision - field installation time
2025-03-31 | PRJ-PAY-ARM-2403-20250331 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1042 | 60.31 | 4281.8 | Rework and Quality Correction - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2403-20250331 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1049 | 38.91 | 3327.01 | Project Management and Supervision - field installation time
2025-03-31 | PRJ-PAY-ARM-2403-20250331 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 43.07 | 3617.73 | Engineering, BIM and Coordination - coordination and layout
2025-04-04 | AP-0004001 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2426 |  | 69.17 | 12450.95 | Sheet Metal and Ductwork - released equipment package
2025-04-04 | AP-0004006 | AP | ARM-2403 | 04-200 | Electrical and Controls Subcontract | V-2484 |  | 28022.59 | 28022.59 | Electrical and Controls Subcontract - trade partner progress billing
2025-04-04 | AP-0004008 | AP | ARM-2403 | 05-100 | Equipment Rental and Rigging | V-2509 |  | 7166.59 | 7166.59 | Equipment Rental and Rigging - small tools and field consumables
2025-04-07 | PRJ-PAY-ARM-2403-20250407 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1023 | 52.17 | 3704.08 | Controls Programming and Checkout - field installation time
2025-04-07 | PRJ-PAY-ARM-2403-20250407 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1030 | 55.8 | 4324.64 | Warranty and Punchlist - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2403-20250407 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 41.47 | 3483.77 | Closeout and O&M Documentation - supervision and planning
2025-04-07 | PRJ-PAY-ARM-2403-20250407 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1044 | 44.1 | 3990.82 | Rework and Quality Correction - startup and checkout
2025-04-11 | AP-0004002 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2439 |  | 57.09 | 10276.8 | Controls Panels and Devices - fabricated material delivery
2025-04-11 | AP-0004009 | AP | ARM-2403 | 05-400 | Small Tools and Consumables | V-2522 |  | 7286.35 | 7286.35 | Small Tools and Consumables - rental and logistics
2025-04-14 | PRJ-PAY-ARM-2403-20250414 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1028 | 48.69 | 3457.03 | Warranty and Punchlist - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2403-20250414 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 51.44 | 3986.3 | Closeout and O&M Documentation - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2403-20250414 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1042 | 46.79 | 3930.6 | Rework and Quality Correction - startup and checkout
2025-04-14 | PRJ-PAY-ARM-2403-20250414 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1049 | 36.18 | 3563.51 | Project Management and Supervision - punchlist and closeout labor
2025-04-18 | AP-0004003 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2452 |  | 65.85 | 11853.79 | Sheet Metal and Ductwork - valves and piping lot
2025-04-21 | AP-0004000 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2412 |  | 92.63 | 16673.94 | Controls Panels and Devices - jobsite material replenishment
2025-04-21 | AP-0004005 | AP | ARM-2403 | 04-300 | Testing and Balancing Subcontract | V-2471 |  | 18439.66 | 18439.66 | Testing and Balancing Subcontract - rigging and specialty support
2025-04-21 | AP-0004007 | AP | ARM-2403 | 05-300 | Freight and Expediting | V-2495 |  | 3727.93 | 3727.93 | Freight and Expediting - freight and expediting
2025-04-21 | PRJ-PAY-ARM-2403-20250421 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 42.87 | 3043.8 | Closeout and O&M Documentation - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2403-20250421 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1040 | 43.93 | 3404.49 | Rework and Quality Correction - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2403-20250421 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1047 | 30.06 | 2765.55 | Project Management and Supervision - punchlist and closeout labor
2025-04-21 | PRJ-PAY-ARM-2403-20250421 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1080 | 46.01 | 4163.63 | Engineering, BIM and Coordination - field installation time
2025-04-25 | AP-0004004 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2465 |  | 96.82 | 17427.85 | Controls Panels and Devices - ductwork release
2025-04-28 | PRJ-PAY-ARM-2403-20250428 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1038 | 68.21 | 4842.66 | Rework and Quality Correction - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2403-20250428 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1045 | 48 | 4104.36 | Project Management and Supervision - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2403-20250428 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 39.41 | 3310.61 | Engineering, BIM and Coordination - field installation time
2025-04-30 | PRJ-PAY-ARM-2403-20250430 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1043 | 46.23 | 3652.28 | Project Management and Supervision - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2403-20250430 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 42.37 | 3283.65 | Engineering, BIM and Coordination - field installation time
2025-04-30 | PRJ-PAY-ARM-2403-20250430 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1083 | 33.61 | 2823.27 | Field Installation Labor - coordination and layout
2025-04-30 | PRJ-PAY-ARM-2403-20250430 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1090 | 31.47 | 2848.28 | Startup, Testing and Commissioning - supervision and planning
2025-05-04 | AP-0004014 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2244 |  | 83.42 | 15015.61 | Insulation and Specialty Material - jobsite material replenishment
2025-05-07 | AP-0004011 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2029 |  | 72.17 | 12990.42 | Hydronic Piping and Valves - fabricated material delivery
2025-05-07 | AP-0004016 | AP | ARM-2403 | 04-300 | Testing and Balancing Subcontract | V-2272 |  | 13523.23 | 13523.23 | Testing and Balancing Subcontract - insulation progress invoice
2025-05-07 | AP-0004018 | AP | ARM-2403 | 05-200 | Permits, Fees and Bonds | V-2296 |  | 5071.46 | 5071.46 | Permits, Fees and Bonds - rental and logistics
2025-05-07 | PRJ-PAY-ARM-2403-20250507 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1024 | 52.71 | 3742.42 | Warranty and Punchlist - field installation time
2025-05-07 | PRJ-PAY-ARM-2403-20250507 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1031 | 38.48 | 2982.38 | Closeout and O&M Documentation - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2403-20250507 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1038 | 46.98 | 3946.07 | Rework and Quality Correction - supervision and planning
2025-05-07 | PRJ-PAY-ARM-2403-20250507 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1045 | 32.61 | 3212.33 | Project Management and Supervision - startup and checkout
2025-05-14 | AP-0004012 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2201 |  | 61.24 | 11022.39 | Insulation and Specialty Material - valves and piping lot
2025-05-14 | PRJ-PAY-ARM-2403-20250514 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1029 | 43.91 | 3117.77 | Closeout and O&M Documentation - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2403-20250514 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1036 | 56.6 | 4386.28 | Rework and Quality Correction - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2403-20250514 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1043 | 53.58 | 4929.28 | Project Management and Supervision - startup and checkout
2025-05-21 | AP-0004013 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2225 |  | 96.71 | 17408.45 | Hydronic Piping and Valves - ductwork release
2025-05-21 | PRJ-PAY-ARM-2403-20250521 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1034 | 41.98 | 2980.55 | Rework and Quality Correction - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2403-20250521 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1041 | 44.39 | 3795 | Project Management and Supervision - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2403-20250521 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1048 | 54.96 | 4616.97 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-05-24 | AP-0004010 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2533 |  | 54.32 | 9778.35 | Insulation and Specialty Material - released equipment package
2025-05-24 | AP-0004015 | AP | ARM-2403 | 04-400 | Crane, Rigging and Specialty Trade | V-2253 |  | 26941.63 | 26941.63 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-05-24 | AP-0004017 | AP | ARM-2403 | 05-400 | Small Tools and Consumables | V-2282 |  | 9643.04 | 9643.04 | Small Tools and Consumables - small tools and field consumables
2025-05-28 | PRJ-PAY-ARM-2403-20250528 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1039 | 40.98 | 3237.44 | Project Management and Supervision - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2403-20250528 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1046 | 47.93 | 3714.69 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2403-20250528 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1053 | 56.73 | 4765.55 | Field Installation Labor - field installation time
2025-05-31 | PRJ-PAY-ARM-2403-20250531 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 50.44 | 3581.22 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2403-20250531 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1051 | 39.86 | 3089.32 | Field Installation Labor - field installation time
2025-05-31 | PRJ-PAY-ARM-2403-20250531 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1084 | 39.54 | 3321.7 | Startup, Testing and Commissioning - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2403-20250531 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1091 | 34.45 | 3117.63 | Sheet Metal Fabrication Labor - supervision and planning
2025-06-03 | AP-0004019 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2308 |  | 59.81 | 10765.55 | Major HVAC Equipment - fabricated material delivery
2025-06-03 | AP-0004025 | AP | ARM-2403 | 04-100 | Insulation Subcontract | V-2381 |  | 24671.07 | 24671.07 | Insulation Subcontract - insulation progress invoice
2025-06-03 | AP-0004027 | AP | ARM-2403 | 06-400 | Temporary Facilities and Protection | V-2405 |  | 6733.05 | 6733.05 | Temporary Facilities and Protection - rental and logistics
2025-06-07 | AP-0004023 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2364 |  | 78.08 | 14054.55 | Major HVAC Equipment - released equipment package
2025-06-07 | PRJ-PAY-ARM-2403-20250607 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1025 | 61.54 | 4369.51 | Closeout and O&M Documentation - field installation time
2025-06-07 | PRJ-PAY-ARM-2403-20250607 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1032 | 55.64 | 4311.91 | Rework and Quality Correction - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2403-20250607 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1039 | 39.66 | 3649.11 | Project Management and Supervision - supervision and planning
2025-06-10 | AP-0004020 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2322 |  | 52.74 | 9494 | Plumbing Fixtures and Piping - valves and piping lot
2025-06-10 | AP-0004026 | AP | ARM-2403 | 04-400 | Crane, Rigging and Specialty Trade | V-2395 |  | 17555.64 | 17555.64 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-06-10 | AP-0004028 | AP | ARM-2403 | 05-300 | Freight and Expediting | V-2419 |  | 6118.56 | 6118.56 | Freight and Expediting - permit and inspection fees
2025-06-14 | AP-0004024 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2377 |  | 75.29 | 13552.43 | Plumbing Fixtures and Piping - fabricated material delivery
2025-06-14 | PRJ-PAY-ARM-2403-20250614 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1030 | 59.77 | 4243.95 | Rework and Quality Correction - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2403-20250614 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1037 | 47.44 | 4056.13 | Project Management and Supervision - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2403-20250614 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 35.69 | 2998.24 | Engineering, BIM and Coordination - startup and checkout
2025-06-17 | AP-0004021 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2336 |  | 57.18 | 10292.36 | Major HVAC Equipment - ductwork release
2025-06-21 | PRJ-PAY-ARM-2403-20250621 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1035 | 52.24 | 4126.74 | Project Management and Supervision - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2403-20250621 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1042 | 44.56 | 3453.3 | Engineering, BIM and Coordination - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2403-20250621 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1049 | 48.1 | 4040.76 | Field Installation Labor - punchlist and closeout labor
2025-06-24 | AP-0004022 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2350 |  | 64.48 | 11606.98 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-06-28 | PRJ-PAY-ARM-2403-20250628 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 53.15 | 3773.43 | Engineering, BIM and Coordination - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2403-20250628 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1047 | 32.31 | 2503.77 | Field Installation Labor - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2403-20250628 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1080 | 33.33 | 2799.63 | Startup, Testing and Commissioning - field installation time
2025-06-28 | PRJ-PAY-ARM-2403-20250628 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1087 | 43.37 | 3924.65 | Sheet Metal Fabrication Labor - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2403-20250630 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1045 | 53.18 | 3775.72 | Field Installation Labor - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2403-20250630 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1052 | 44.22 | 3427.24 | Startup, Testing and Commissioning - field installation time
2025-06-30 | PRJ-PAY-ARM-2403-20250630 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1085 | 34.82 | 2924.6 | Sheet Metal Fabrication Labor - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2403-20250630 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1092 | 44.68 | 4043.41 | Controls Programming and Checkout - supervision and planning
2025-07-03 | AP-0004032 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2471 |  | 55.9 | 10061.51 | Controls Panels and Devices - released equipment package
2025-07-06 | AP-0004029 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2431 |  | 74.23 | 13360.78 | Sheet Metal and Ductwork - valves and piping lot
2025-07-06 | AP-0004034 | AP | ARM-2403 | 04-200 | Electrical and Controls Subcontract | V-2490 |  | 21527.45 | 21527.45 | Electrical and Controls Subcontract - testing and balancing services
2025-07-06 | AP-0004036 | AP | ARM-2403 | 05-100 | Equipment Rental and Rigging | V-2514 |  | 8969.84 | 8969.84 | Equipment Rental and Rigging - permit and inspection fees
2025-07-07 | PRJ-PAY-ARM-2403-20250707 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1026 | 56.82 | 4034.17 | Rework and Quality Correction - field installation time
2025-07-07 | PRJ-PAY-ARM-2403-20250707 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1033 | 51.69 | 4419.11 | Project Management and Supervision - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2403-20250707 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 34.48 | 2896.63 | Engineering, BIM and Coordination - supervision and planning
2025-07-10 | AP-0004033 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2484 |  | 68.56 | 12340.64 | Sheet Metal and Ductwork - fabricated material delivery
2025-07-13 | AP-0004030 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2443 |  | 76.21 | 13717.98 | Controls Panels and Devices - ductwork release
2025-07-13 | AP-0004035 | AP | ARM-2403 | 04-100 | Insulation Subcontract | V-2503 |  | 20168.04 | 20168.04 | Insulation Subcontract - electrical coordination scope
2025-07-13 | AP-0004037 | AP | ARM-2403 | 05-400 | Small Tools and Consumables | V-2528 |  | 8087.41 | 8087.41 | Small Tools and Consumables - freight and expediting
2025-07-14 | PRJ-PAY-ARM-2403-20250714 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1031 | 49.35 | 3898.28 | Project Management and Supervision - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2403-20250714 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1038 | 42.01 | 3255.82 | Engineering, BIM and Coordination - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2403-20250714 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1045 | 53.81 | 4519.76 | Field Installation Labor - startup and checkout
2025-07-20 | AP-0004031 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2457 |  | 83.1 | 14957.57 | Sheet Metal and Ductwork - jobsite material replenishment
2025-07-21 | PRJ-PAY-ARM-2403-20250721 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1036 | 41.02 | 2912.64 | Engineering, BIM and Coordination - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2403-20250721 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1043 | 51.21 | 3968.95 | Field Installation Labor - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2403-20250721 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1050 | 34.04 | 2859.72 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-07-21 | PRJ-PAY-ARM-2403-20250721 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1083 | 36.68 | 3319.53 | Sheet Metal Fabrication Labor - field installation time
2025-07-28 | PRJ-PAY-ARM-2403-20250728 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1041 | 59.22 | 4204.43 | Field Installation Labor - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2403-20250728 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 46 | 3564.75 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2403-20250728 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1081 | 35.2 | 2957.1 | Sheet Metal Fabrication Labor - field installation time
2025-07-28 | PRJ-PAY-ARM-2403-20250728 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1088 | 38.78 | 3509.39 | Controls Programming and Checkout - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2403-20250731 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 57.07 | 4051.9 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2403-20250731 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1053 | 43.45 | 3367.74 | Sheet Metal Fabrication Labor - field installation time
2025-07-31 | PRJ-PAY-ARM-2403-20250731 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1086 | 31.75 | 2667.39 | Controls Programming and Checkout - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2403-20250731 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1093 | 44.54 | 4031.17 | Warranty and Punchlist - supervision and planning
2025-08-06 | AP-0004041 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2234 |  | 79.02 | 14223.11 | Insulation and Specialty Material - fabricated material delivery
2025-08-07 | PRJ-PAY-ARM-2403-20250807 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1027 | 46.13 | 3644.08 | Project Management and Supervision - field installation time
2025-08-07 | PRJ-PAY-ARM-2403-20250807 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1034 | 33.38 | 2587.14 | Engineering, BIM and Coordination - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2403-20250807 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1041 | 39.92 | 3353.49 | Field Installation Labor - supervision and planning
2025-08-09 | AP-0004038 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2014 |  | 53.11 | 9560.32 | Hydronic Piping and Valves - ductwork release
2025-08-09 | AP-0004043 | AP | ARM-2403 | 04-300 | Testing and Balancing Subcontract | V-2262 |  | 15017.46 | 15017.46 | Testing and Balancing Subcontract - electrical coordination scope
2025-08-09 | AP-0004045 | AP | ARM-2403 | 05-200 | Permits, Fees and Bonds | V-2289 |  | 6900.21 | 6900.21 | Permits, Fees and Bonds - freight and expediting
2025-08-13 | AP-0004042 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2255 |  | 62.58 | 11264.61 | Hydronic Piping and Valves - valves and piping lot
2025-08-14 | PRJ-PAY-ARM-2403-20250814 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1032 | 39.88 | 2831.17 | Engineering, BIM and Coordination - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2403-20250814 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1039 | 52.96 | 4104.37 | Field Installation Labor - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2403-20250814 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 45.09 | 3787.94 | Startup, Testing and Commissioning - startup and checkout
2025-08-16 | AP-0004039 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2056 |  | 61.05 | 10988.61 | Insulation and Specialty Material - jobsite material replenishment
2025-08-16 | AP-0004044 | AP | ARM-2403 | 04-200 | Electrical and Controls Subcontract | V-2279 |  | 21586.85 | 21586.85 | Electrical and Controls Subcontract - rigging and specialty support
2025-08-16 | AP-0004046 | AP | ARM-2403 | 06-400 | Temporary Facilities and Protection | V-2303 |  | 5831.73 | 5831.73 | Temporary Facilities and Protection - small tools and field consumables
2025-08-21 | PRJ-PAY-ARM-2403-20250821 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1037 | 61.74 | 4383.62 | Field Installation Labor - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2403-20250821 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1044 | 47.66 | 3693.37 | Startup, Testing and Commissioning - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2403-20250821 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1051 | 42.99 | 3611.07 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-08-23 | AP-0004040 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2213 |  | 62.54 | 11257.06 | Hydronic Piping and Valves - released equipment package
2025-08-28 | PRJ-PAY-ARM-2403-20250828 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 57.93 | 4113.34 | Startup, Testing and Commissioning - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2403-20250828 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 47.96 | 3716.71 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2403-20250828 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1082 | 44.78 | 3761.58 | Controls Programming and Checkout - field installation time
2025-08-31 | PRJ-PAY-ARM-2403-20250831 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 60.22 | 4275.31 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2403-20250831 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1080 | 46.4 | 3596.09 | Controls Programming and Checkout - field installation time
2025-08-31 | PRJ-PAY-ARM-2403-20250831 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1087 | 31.56 | 2651.44 | Warranty and Punchlist - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2403-20250907 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1028 | 52.21 | 3706.71 | Engineering, BIM and Coordination - field installation time
2025-09-07 | PRJ-PAY-ARM-2403-20250907 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1035 | 43.01 | 3333.47 | Field Installation Labor - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2403-20250907 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 40.56 | 3406.77 | Startup, Testing and Commissioning - supervision and planning
2025-09-09 | AP-0004050 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2357 |  | 47.2 | 8496.01 | Major HVAC Equipment - valves and piping lot
2025-09-12 | AP-0004047 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2315 |  | 65.84 | 11851.98 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-09-12 | AP-0004052 | AP | ARM-2403 | 04-400 | Crane, Rigging and Specialty Trade | V-2376 |  | 34034.05 | 34034.05 | Crane, Rigging and Specialty Trade - rigging and specialty support
2025-09-12 | AP-0004053 | AP | ARM-2403 | 05-300 | Freight and Expediting | V-2388 |  | 4582.87 | 4582.87 | Freight and Expediting - small tools and field consumables
2025-09-14 | PRJ-PAY-ARM-2403-20250914 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1033 | 58.59 | 4160.12 | Field Installation Labor - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2403-20250914 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1040 | 45.1 | 3495.59 | Startup, Testing and Commissioning - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2403-20250914 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 44.42 | 3730.95 | Sheet Metal Fabrication Labor - startup and checkout
2025-09-16 | AP-0004051 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2370 |  | 73.3 | 13193.56 | Plumbing Fixtures and Piping - ductwork release
2025-09-19 | AP-0004048 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2329 |  | 45.38 | 8168.69 | Major HVAC Equipment - released equipment package
2025-09-19 | AP-0004054 | AP | ARM-2403 | 05-100 | Equipment Rental and Rigging | V-2402 |  | 6246.14 | 6246.14 | Equipment Rental and Rigging - rental and logistics
2025-09-21 | PRJ-PAY-ARM-2403-20250921 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1038 | 61.34 | 4355.19 | Startup, Testing and Commissioning - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2403-20250921 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1045 | 36.34 | 2816.1 | Sheet Metal Fabrication Labor - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2403-20250921 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1052 | 49.06 | 4121.42 | Controls Programming and Checkout - punchlist and closeout labor
2025-09-25 | AP-0004049 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2343 |  | 94.87 | 17075.85 | Plumbing Fixtures and Piping - fabricated material delivery
2025-09-28 | PRJ-PAY-ARM-2403-20250928 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 54.65 | 3880.49 | Sheet Metal Fabrication Labor - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2403-20250928 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1050 | 49.06 | 3802.38 | Controls Programming and Checkout - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2403-20250928 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1083 | 30.58 | 2568.61 | Warranty and Punchlist - field installation time
2025-09-30 | PRJ-PAY-ARM-2403-20250930 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1048 | 39.01 | 2769.67 | Controls Programming and Checkout - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2403-20250930 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1081 | 40.13 | 3110.35 | Warranty and Punchlist - field installation time
2025-09-30 | PRJ-PAY-ARM-2403-20250930 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1088 | 39.77 | 3340.26 | Closeout and O&M Documentation - coordination and layout
2025-10-05 | AP-0004057 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2440 |  | 88.14 | 15865.41 | Controls Panels and Devices - valves and piping lot
2025-10-07 | PRJ-PAY-ARM-2403-20251007 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1029 | 34.31 | 2435.86 | Field Installation Labor - field installation time
2025-10-07 | PRJ-PAY-ARM-2403-20251007 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1036 | 41.72 | 3233.19 | Startup, Testing and Commissioning - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2403-20251007 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 45.21 | 3797.59 | Sheet Metal Fabrication Labor - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2403-20251014 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1034 | 51.72 | 3672.07 | Startup, Testing and Commissioning - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2403-20251014 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1041 | 39.69 | 3075.97 | Sheet Metal Fabrication Labor - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2403-20251014 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1048 | 31.43 | 2640.49 | Controls Programming and Checkout - startup and checkout
2025-10-15 | AP-0004055 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2414 |  | 54.81 | 9865.05 | Controls Panels and Devices - released equipment package
2025-10-15 | AP-0004058 | AP | ARM-2403 | 04-100 | Insulation Subcontract | V-2448 |  | 28850.37 | 28850.37 | Insulation Subcontract - trade partner progress billing
2025-10-15 | AP-0004059 | AP | ARM-2403 | 05-400 | Small Tools and Consumables | V-2460 |  | 4681.69 | 4681.69 | Small Tools and Consumables - rental and logistics
2025-10-21 | PRJ-PAY-ARM-2403-20251021 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1039 | 34.38 | 2441.25 | Sheet Metal Fabrication Labor - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2403-20251021 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1046 | 47.79 | 3703.35 | Controls Programming and Checkout - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2403-20251021 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1053 | 28.31 | 2378.27 | Warranty and Punchlist - punchlist and closeout labor
2025-10-22 | AP-0004056 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2427 |  | 93.99 | 16917.91 | Sheet Metal and Ductwork - fabricated material delivery
2025-10-22 | AP-0004060 | AP | ARM-2403 | 05-200 | Permits, Fees and Bonds | V-2474 |  | 6607.58 | 6607.58 | Permits, Fees and Bonds - permit and inspection fees
2025-10-28 | PRJ-PAY-ARM-2403-20251028 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1044 | 43.66 | 3100.13 | Controls Programming and Checkout - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2403-20251028 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1051 | 31.24 | 2421.16 | Warranty and Punchlist - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2403-20251028 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1084 | 25.53 | 2144.26 | Closeout and O&M Documentation - field installation time
2025-10-31 | PRJ-PAY-ARM-2403-20251031 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1049 | 30.52 | 2166.57 | Warranty and Punchlist - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2403-20251031 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1082 | 31.1 | 2410.09 | Closeout and O&M Documentation - field installation time
2025-10-31 | PRJ-PAY-ARM-2403-20251031 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1089 | 36.05 | 3028.12 | Rework and Quality Correction - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2403-20251107 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1030 | 46.58 | 3306.83 | Startup, Testing and Commissioning - field installation time
2025-11-07 | PRJ-PAY-ARM-2403-20251107 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1037 | 30.78 | 2385.47 | Sheet Metal Fabrication Labor - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2403-20251107 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1044 | 40.18 | 3375.39 | Controls Programming and Checkout - supervision and planning
2025-11-08 | AP-0004063 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2514 |  | 81.9 | 14742.21 | Insulation and Specialty Material - ductwork release
2025-11-14 | PRJ-PAY-ARM-2403-20251114 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1035 | 40.3 | 2861.55 | Sheet Metal Fabrication Labor - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2403-20251114 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1042 | 36.82 | 2853.37 | Controls Programming and Checkout - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2403-20251114 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1049 | 29.96 | 2516.69 | Warranty and Punchlist - startup and checkout
2025-11-18 | AP-0004061 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2486 |  | 59.65 | 10737.88 | Insulation and Specialty Material - fabricated material delivery
2025-11-18 | AP-0004064 | AP | ARM-2403 | 04-200 | Electrical and Controls Subcontract | V-2522 |  | 25984.12 | 25984.12 | Electrical and Controls Subcontract - insulation progress invoice
2025-11-18 | AP-0004065 | AP | ARM-2403 | 06-400 | Temporary Facilities and Protection | V-2534 |  | 9448.77 | 9448.77 | Temporary Facilities and Protection - permit and inspection fees
2025-11-21 | PRJ-PAY-ARM-2403-20251121 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1040 | 29.96 | 2126.86 | Controls Programming and Checkout - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2403-20251121 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1047 | 34.13 | 2644.84 | Warranty and Punchlist - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2403-20251121 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1080 | 31.33 | 2631.89 | Closeout and O&M Documentation - punchlist and closeout labor
2025-11-25 | AP-0004062 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2500 |  | 94.66 | 17039.37 | Hydronic Piping and Valves - valves and piping lot
2025-11-28 | PRJ-PAY-ARM-2403-20251128 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1045 | 37.69 | 2676.34 | Warranty and Punchlist - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2403-20251128 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1052 | 29.1 | 2255.12 | Closeout and O&M Documentation - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2403-20251128 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1085 | 28.73 | 2413.43 | Rework and Quality Correction - field installation time
2025-11-30 | PRJ-PAY-ARM-2403-20251130 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1050 | 38.17 | 2709.93 | Closeout and O&M Documentation - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2403-20251130 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1083 | 34.73 | 2691.41 | Rework and Quality Correction - field installation time
2025-11-30 | PRJ-PAY-ARM-2403-20251130 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1090 | 29.44 | 2708.15 | Project Management and Supervision - coordination and layout
2025-12-04 | AP-0004067 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2205 |  | 73.01 | 13141.49 | Plumbing Fixtures and Piping - ductwork release
2025-12-07 | PRJ-PAY-ARM-2403-20251207 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 37.54 | 2664.99 | Sheet Metal Fabrication Labor - field installation time
2025-12-07 | PRJ-PAY-ARM-2403-20251207 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1038 | 35.64 | 2762.2 | Controls Programming and Checkout - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2403-20251207 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1045 | 25.27 | 2122.54 | Warranty and Punchlist - supervision and planning
2025-12-11 | AP-0004068 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2229 |  | 85.78 | 15440.36 | Major HVAC Equipment - jobsite material replenishment
2025-12-14 | PRJ-PAY-ARM-2403-20251214 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1036 | 32.97 | 2341.04 | Controls Programming and Checkout - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2403-20251214 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1043 | 25.85 | 2003.08 | Warranty and Punchlist - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2403-20251214 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1050 | 29.12 | 2446.17 | Closeout and O&M Documentation - startup and checkout
2025-12-21 | AP-0004066 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2033 |  | 69.48 | 12506.82 | Major HVAC Equipment - valves and piping lot
2025-12-21 | AP-0004069 | AP | ARM-2403 | 04-300 | Testing and Balancing Subcontract | V-2241 |  | 24869.46 | 24869.46 | Testing and Balancing Subcontract - testing and balancing services
2025-12-21 | AP-0004070 | AP | ARM-2403 | 05-100 | Equipment Rental and Rigging | V-2256 |  | 7568.96 | 7568.96 | Equipment Rental and Rigging - freight and expediting
2025-12-21 | PRJ-PAY-ARM-2403-20251221 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1041 | 36.85 | 2616.1 | Warranty and Punchlist - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2403-20251221 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1048 | 26.7 | 2069.08 | Closeout and O&M Documentation - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2403-20251221 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1081 | 24.42 | 2051.28 | Rework and Quality Correction - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2403-20251228 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1046 | 32.49 | 2306.98 | Closeout and O&M Documentation - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2403-20251228 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1053 | 31.48 | 2439.43 | Rework and Quality Correction - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2403-20251228 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1086 | 29.25 | 2691.31 | Project Management and Supervision - field installation time
2025-12-31 | PRJ-PAY-ARM-2403-20251231 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1051 | 35.8 | 2542.1 | Rework and Quality Correction - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2403-20251231 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1084 | 35.71 | 3053.63 | Project Management and Supervision - field installation time
2025-12-31 | PRJ-PAY-ARM-2403-20251231 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1091 | 31.59 | 2653.62 | Engineering, BIM and Coordination - coordination and layout
2026-01-07 | AP-0004072 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2289 |  | 63.84 | 11491.7 | Controls Panels and Devices - jobsite material replenishment
2026-01-07 | PRJ-PAY-ARM-2403-20260107 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1032 | 32.45 | 2303.64 | Controls Programming and Checkout - field installation time
2026-01-07 | PRJ-PAY-ARM-2403-20260107 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1039 | 22.07 | 1710.21 | Warranty and Punchlist - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2403-20260107 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1046 | 19.58 | 1644.98 | Closeout and O&M Documentation - supervision and planning
2026-01-14 | AP-0004073 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2303 |  | 62.04 | 11166.6 | Sheet Metal and Ductwork - released equipment package
2026-01-14 | PRJ-PAY-ARM-2403-20260114 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1037 | 29.45 | 2090.91 | Warranty and Punchlist - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2403-20260114 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 21.05 | 1631.69 | Closeout and O&M Documentation - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2403-20260114 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1051 | 22.52 | 1891.37 | Rework and Quality Correction - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2403-20260121 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1042 | 28.72 | 2039.23 | Closeout and O&M Documentation - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2403-20260121 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1049 | 26.62 | 2062.71 | Rework and Quality Correction - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2403-20260121 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1082 | 22.79 | 2096.44 | Project Management and Supervision - punchlist and closeout labor
2026-01-24 | AP-0004071 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2275 |  | 48.38 | 8708.89 | Sheet Metal and Ductwork - ductwork release
2026-01-24 | AP-0004074 | AP | ARM-2403 | 04-400 | Crane, Rigging and Specialty Trade | V-2312 |  | 20296.42 | 20296.42 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-01-24 | AP-0004075 | AP | ARM-2403 | 05-200 | Permits, Fees and Bonds | V-2324 |  | 8303.09 | 8303.09 | Permits, Fees and Bonds - small tools and field consumables
2026-01-28 | PRJ-PAY-ARM-2403-20260128 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1047 | 32.87 | 2333.69 | Rework and Quality Correction - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2403-20260128 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1080 | 27.5 | 2351.55 | Project Management and Supervision - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2403-20260128 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1087 | 26.07 | 2189.52 | Engineering, BIM and Coordination - field installation time
2026-01-31 | PRJ-PAY-ARM-2403-20260131 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1052 | 23.43 | 1851.24 | Project Management and Supervision - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2403-20260131 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1085 | 31.71 | 2457.48 | Engineering, BIM and Coordination - field installation time
2026-01-31 | PRJ-PAY-ARM-2403-20260131 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1092 | 32.29 | 2712.53 | Field Installation Labor - coordination and layout
2026-02-03 | AP-0004076 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2338 |  | 80.56 | 14501.2 | Hydronic Piping and Valves - jobsite material replenishment
2026-02-03 | AP-0004079 | AP | ARM-2403 | 04-100 | Insulation Subcontract | V-2374 |  | 22398.71 | 22398.71 | Insulation Subcontract - rigging and specialty support
2026-02-03 | AP-0004080 | AP | ARM-2403 | 05-300 | Freight and Expediting | V-2386 |  | 7790.86 | 7790.86 | Freight and Expediting - rental and logistics
2026-02-07 | PRJ-PAY-ARM-2403-20260207 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1033 | 36.51 | 2592.15 | Warranty and Punchlist - field installation time
2026-02-07 | PRJ-PAY-ARM-2403-20260207 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 33.4 | 2588.22 | Closeout and O&M Documentation - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2403-20260207 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1047 | 24.41 | 2050.15 | Rework and Quality Correction - supervision and planning
2026-02-10 | AP-0004077 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2351 |  | 57.81 | 10406.17 | Insulation and Specialty Material - released equipment package
2026-02-14 | PRJ-PAY-ARM-2403-20260214 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 49.13 | 3488.51 | Closeout and O&M Documentation - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2403-20260214 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1045 | 30.24 | 2343.45 | Rework and Quality Correction - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2403-20260214 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1052 | 23.38 | 2151.26 | Project Management and Supervision - startup and checkout
2026-02-17 | AP-0004078 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2365 |  | 56.4 | 10151.49 | Hydronic Piping and Valves - fabricated material delivery
2026-02-21 | PRJ-PAY-ARM-2403-20260221 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1043 | 39.16 | 2780.52 | Rework and Quality Correction - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2403-20260221 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1050 | 35.42 | 3028.44 | Project Management and Supervision - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2403-20260221 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1083 | 36.25 | 3045.4 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2403-20260228 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1048 | 39.88 | 3150.84 | Project Management and Supervision - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2403-20260228 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1081 | 29.71 | 2302.44 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2403-20260228 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1088 | 42.74 | 3589.76 | Field Installation Labor - field installation time
2026-03-06 | AP-0004081 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2400 |  | 68.8 | 12383.96 | Plumbing Fixtures and Piping - released equipment package
2026-03-06 | AP-0004084 | AP | ARM-2403 | 04-200 | Electrical and Controls Subcontract | V-2436 |  | 22955.21 | 22955.21 | Electrical and Controls Subcontract - trade partner progress billing
2026-03-06 | AP-0004085 | AP | ARM-2403 | 05-400 | Small Tools and Consumables | V-2446 |  | 7303.92 | 7303.92 | Small Tools and Consumables - permit and inspection fees
2026-03-07 | PRJ-PAY-ARM-2403-20260307 | PAY | ARM-2403 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 31.79 | 2256.78 | Closeout and O&M Documentation - field installation time
2026-03-07 | PRJ-PAY-ARM-2403-20260307 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1041 | 26.06 | 2019.85 | Rework and Quality Correction - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2403-20260307 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1048 | 27.3 | 2511.43 | Project Management and Supervision - supervision and planning
2026-03-13 | AP-0004082 | AP | ARM-2403 | 02-110 | Major HVAC Equipment | V-2414 |  | 60.94 | 10969.02 | Major HVAC Equipment - fabricated material delivery
2026-03-14 | PRJ-PAY-ARM-2403-20260314 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1039 | 28.79 | 2043.75 | Rework and Quality Correction - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2403-20260314 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1046 | 36.37 | 3109.71 | Project Management and Supervision - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2403-20260314 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1053 | 28.28 | 2375.33 | Engineering, BIM and Coordination - startup and checkout
2026-03-20 | AP-0004083 | AP | ARM-2403 | 02-410 | Plumbing Fixtures and Piping | V-2427 |  | 90.54 | 16296.92 | Plumbing Fixtures and Piping - valves and piping lot
2026-03-21 | PRJ-PAY-ARM-2403-20260321 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1044 | 32.28 | 2550.45 | Project Management and Supervision - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2403-20260321 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1051 | 33.45 | 2592.21 | Engineering, BIM and Coordination - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2403-20260321 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1084 | 30.32 | 2546.56 | Field Installation Labor - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2403-20260328 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 36.71 | 2606.67 | Engineering, BIM and Coordination - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2403-20260328 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1082 | 30.85 | 2390.67 | Field Installation Labor - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2403-20260328 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1089 | 25.29 | 2124.5 | Startup, Testing and Commissioning - field installation time
2026-03-31 | PRJ-PAY-ARM-2403-20260331 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1080 | 29.6 | 2101.64 | Field Installation Labor - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2403-20260331 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1087 | 29.57 | 2291.96 | Startup, Testing and Commissioning - field installation time
2026-03-31 | PRJ-PAY-ARM-2403-20260331 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1094 | 23.27 | 1954.72 | Sheet Metal Fabrication Labor - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2403-20260407 | PAY | ARM-2403 | 06-300 | Rework and Quality Correction |  | E-1035 | 42.93 | 3047.96 | Rework and Quality Correction - field installation time
2026-04-07 | PRJ-PAY-ARM-2403-20260407 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1042 | 35.24 | 3012.67 | Project Management and Supervision - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2403-20260407 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 32.53 | 2732.88 | Engineering, BIM and Coordination - supervision and planning
2026-04-09 | AP-0004086 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2460 |  | 75.05 | 13508.93 | Controls Panels and Devices - fabricated material delivery
2026-04-09 | AP-0004089 | AP | ARM-2403 | 04-300 | Testing and Balancing Subcontract | V-2496 |  | 27470.42 | 27470.42 | Testing and Balancing Subcontract - insulation progress invoice
2026-04-09 | AP-0004090 | AP | ARM-2403 | 06-400 | Temporary Facilities and Protection | V-2509 |  | 5356.14 | 5356.14 | Temporary Facilities and Protection - freight and expediting
2026-04-14 | PRJ-PAY-ARM-2403-20260414 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1040 | 44.7 | 3531.68 | Project Management and Supervision - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2403-20260414 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 35.38 | 2741.74 | Engineering, BIM and Coordination - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2403-20260414 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1080 | 32.23 | 2707.47 | Field Installation Labor - startup and checkout
2026-04-16 | AP-0004087 | AP | ARM-2403 | 02-210 | Sheet Metal and Ductwork | V-2474 |  | 85.96 | 15472.73 | Sheet Metal and Ductwork - valves and piping lot
2026-04-16 | AP-0004091 | AP | ARM-2403 | 05-300 | Freight and Expediting | V-2522 |  | 5393.17 | 5393.17 | Freight and Expediting - small tools and field consumables
2026-04-21 | PRJ-PAY-ARM-2403-20260421 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1045 | 41.91 | 2975.73 | Engineering, BIM and Coordination - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2403-20260421 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1052 | 37.01 | 2868.65 | Field Installation Labor - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2403-20260421 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1085 | 29.45 | 2473.82 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-04-23 | AP-0004088 | AP | ARM-2403 | 02-510 | Controls Panels and Devices | V-2488 |  | 64.59 | 11626.79 | Controls Panels and Devices - ductwork release
2026-04-28 | PRJ-PAY-ARM-2403-20260428 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1050 | 32.05 | 2275.75 | Field Installation Labor - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2403-20260428 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1083 | 33.73 | 2614.4 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2403-20260428 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1090 | 30.05 | 2524.58 | Sheet Metal Fabrication Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2403-20260430 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 36.99 | 2626.08 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2403-20260430 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1088 | 27.23 | 2110.67 | Sheet Metal Fabrication Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2403-20260430 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1095 | 28.15 | 2364.37 | Controls Programming and Checkout - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2403-20260507 | PAY | ARM-2403 | 01-100 | Project Management and Supervision |  | E-1036 | 36.01 | 2845.09 | Project Management and Supervision - field installation time
2026-05-07 | PRJ-PAY-ARM-2403-20260507 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 42.78 | 3315.46 | Engineering, BIM and Coordination - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2403-20260507 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1050 | 49.57 | 4163.64 | Field Installation Labor - supervision and planning
2026-05-09 | AP-0004095 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2229 |  | 55.94 | 10069.67 | Hydronic Piping and Valves - released equipment package
2026-05-12 | AP-0004092 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2534 |  | 84.08 | 15134.63 | Insulation and Specialty Material - valves and piping lot
2026-05-12 | AP-0004096 | AP | ARM-2403 | 04-400 | Crane, Rigging and Specialty Trade | V-2237 |  | 29367.36 | 29367.36 | Crane, Rigging and Specialty Trade - testing and balancing services
2026-05-12 | AP-0004097 | AP | ARM-2403 | 05-100 | Equipment Rental and Rigging | V-2255 |  | 5503.38 | 5503.38 | Equipment Rental and Rigging - small tools and field consumables
2026-05-14 | PRJ-PAY-ARM-2403-20260514 | PAY | ARM-2403 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 39.1 | 2776.18 | Engineering, BIM and Coordination - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2403-20260514 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1048 | 51.35 | 3979.51 | Field Installation Labor - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2403-20260514 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 33.41 | 2806.7 | Startup, Testing and Commissioning - startup and checkout
2026-05-19 | AP-0004093 | AP | ARM-2403 | 02-310 | Hydronic Piping and Valves | V-2033 |  | 46.4 | 8351.12 | Hydronic Piping and Valves - ductwork release
2026-05-19 | AP-0004098 | AP | ARM-2403 | 05-400 | Small Tools and Consumables | V-2274 |  | 5175.65 | 5175.65 | Small Tools and Consumables - rental and logistics
2026-05-21 | PRJ-PAY-ARM-2403-20260521 | PAY | ARM-2403 | 03-100 | Field Installation Labor |  | E-1046 | 47.79 | 3393.29 | Field Installation Labor - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2403-20260521 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1053 | 40.64 | 3149.29 | Startup, Testing and Commissioning - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2403-20260521 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1086 | 23.59 | 1981.2 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-05-25 | AP-0004094 | AP | ARM-2403 | 02-610 | Insulation and Specialty Material | V-2205 |  | 80.56 | 14500.26 | Insulation and Specialty Material - jobsite material replenishment
2026-05-28 | PRJ-PAY-ARM-2403-20260528 | PAY | ARM-2403 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 28.69 | 2036.67 | Startup, Testing and Commissioning - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2403-20260528 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1084 | 34.77 | 2694.81 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2403-20260528 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1091 | 40.85 | 3431.78 | Controls Programming and Checkout - field installation time
2026-05-31 | PRJ-PAY-ARM-2403-20260531 | PAY | ARM-2403 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 43 | 3053.35 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2403-20260531 | PAY | ARM-2403 | 03-400 | Controls Programming and Checkout |  | E-1089 | 40.59 | 3145.68 | Controls Programming and Checkout - field installation time
2026-05-31 | PRJ-PAY-ARM-2403-20260531 | PAY | ARM-2403 | 06-100 | Warranty and Punchlist |  | E-1096 | 31.11 | 2613.27 | Warranty and Punchlist - coordination and layout
2025-01-03 | AP-0004157 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2279 |  | 61.26 | 11027.46 | Controls Panels and Devices - ductwork release
2025-01-03 | AP-0004161 | AP | ARM-2409 | 04-100 | Insulation Subcontract | V-2327 |  | 15772.83 | 15772.83 | Insulation Subcontract - electrical coordination scope
2025-01-03 | AP-0004163 | AP | ARM-2409 | 05-200 | Permits, Fees and Bonds | V-2351 |  | 4597.63 | 4597.63 | Permits, Fees and Bonds - rental and logistics
2025-01-07 | PRJ-PAY-ARM-2409-20250107 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1016 | 54.06 | 3838.07 | Rework and Quality Correction - field installation time
2025-01-07 | PRJ-PAY-ARM-2409-20250107 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1024 | 43.87 | 3750.71 | Project Management and Supervision - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2409-20250107 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 54.61 | 4587.34 | Engineering, BIM and Coordination - supervision and planning
2025-01-10 | AP-0004158 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2293 |  | 68.29 | 12291.87 | Sheet Metal and Ductwork - jobsite material replenishment
2025-01-10 | AP-0004162 | AP | ARM-2409 | 04-400 | Crane, Rigging and Specialty Trade | V-2341 |  | 20440.5 | 20440.5 | Crane, Rigging and Specialty Trade - rigging and specialty support
2025-01-10 | AP-0004164 | AP | ARM-2409 | 06-400 | Temporary Facilities and Protection | V-2365 |  | 9572.79 | 9572.79 | Temporary Facilities and Protection - permit and inspection fees
2025-01-14 | PRJ-PAY-ARM-2409-20250114 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1022 | 44.53 | 3517.94 | Project Management and Supervision - coordination and layout
2025-01-14 | PRJ-PAY-ARM-2409-20250114 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 51.2 | 3967.83 | Engineering, BIM and Coordination - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2409-20250114 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1036 | 46.86 | 3936.43 | Field Installation Labor - startup and checkout
2025-01-17 | AP-0004159 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2307 |  | 68.13 | 12262.84 | Controls Panels and Devices - released equipment package
2025-01-21 | PRJ-PAY-ARM-2409-20250121 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 41.34 | 2935.19 | Engineering, BIM and Coordination - supervision and planning
2025-01-21 | PRJ-PAY-ARM-2409-20250121 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1034 | 46.56 | 3608.04 | Field Installation Labor - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2409-20250121 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 43.22 | 3630.18 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-24 | AP-0004160 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2320 |  | 99.73 | 17950.58 | Sheet Metal and Ductwork - fabricated material delivery
2025-01-28 | PRJ-PAY-ARM-2409-20250128 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1032 | 49.37 | 3505.04 | Field Installation Labor - startup and checkout
2025-01-28 | PRJ-PAY-ARM-2409-20250128 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 44.07 | 3415.66 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2409-20250128 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 31.63 | 2657.18 | Sheet Metal Fabrication Labor - field installation time
2025-01-31 | PRJ-PAY-ARM-2409-20250131 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 49.14 | 3488.85 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-01-31 | PRJ-PAY-ARM-2409-20250131 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 48.54 | 3761.8 | Sheet Metal Fabrication Labor - field installation time
2025-01-31 | PRJ-PAY-ARM-2409-20250131 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1051 | 34.91 | 2932.49 | Controls Programming and Checkout - coordination and layout
2025-02-03 | AP-0004168 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2419 |  | 56.75 | 10214.48 | Hydronic Piping and Valves - valves and piping lot
2025-02-06 | AP-0004165 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2377 |  | 84.5 | 15210.87 | Insulation and Specialty Material - jobsite material replenishment
2025-02-06 | AP-0004170 | AP | ARM-2409 | 04-200 | Electrical and Controls Subcontract | V-2438 |  | 21219.17 | 21219.17 | Electrical and Controls Subcontract - rigging and specialty support
2025-02-06 | AP-0004172 | AP | ARM-2409 | 05-300 | Freight and Expediting | V-2460 |  | 7462.48 | 7462.48 | Freight and Expediting - permit and inspection fees
2025-02-07 | PRJ-PAY-ARM-2409-20250207 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1018 | 54.45 | 4301.5 | Project Management and Supervision - field installation time
2025-02-07 | PRJ-PAY-ARM-2409-20250207 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 36.98 | 2865.67 | Engineering, BIM and Coordination - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2409-20250207 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1032 | 35.82 | 3008.54 | Field Installation Labor - supervision and planning
2025-02-07 | PRJ-PAY-ARM-2409-20250207 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 40.02 | 3621.91 | Startup, Testing and Commissioning - startup and checkout
2025-02-07 | PRJ-PAY-ARM-2409-20250207 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 32.01 | 3105.2 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-10 | AP-0004169 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2433 |  | 50.28 | 9050.42 | Insulation and Specialty Material - ductwork release
2025-02-13 | AP-0004166 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2391 |  | 80.51 | 14492.19 | Hydronic Piping and Valves - released equipment package
2025-02-13 | AP-0004171 | AP | ARM-2409 | 04-100 | Insulation Subcontract | V-2450 |  | 18381.11 | 18381.11 | Insulation Subcontract - trade partner progress billing
2025-02-13 | AP-0004173 | AP | ARM-2409 | 05-100 | Equipment Rental and Rigging | V-2474 |  | 6937.62 | 6937.62 | Equipment Rental and Rigging - freight and expediting
2025-02-14 | PRJ-PAY-ARM-2409-20250214 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 71.95 | 5108.18 | Engineering, BIM and Coordination - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2409-20250214 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1030 | 41.75 | 3235.89 | Field Installation Labor - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2409-20250214 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 40.48 | 3400.13 | Startup, Testing and Commissioning - startup and checkout
2025-02-14 | PRJ-PAY-ARM-2409-20250214 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 36.58 | 3310.63 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-20 | AP-0004167 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2405 |  | 87.96 | 15832.5 | Insulation and Specialty Material - fabricated material delivery
2025-02-21 | PRJ-PAY-ARM-2409-20250221 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1028 | 45.5 | 3230.23 | Field Installation Labor - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2409-20250221 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 45.23 | 3505.19 | Startup, Testing and Commissioning - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2409-20250221 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 44.23 | 3715.21 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-21 | PRJ-PAY-ARM-2409-20250221 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1049 | 41.14 | 3722.93 | Controls Programming and Checkout - field installation time
2025-02-28 | PRJ-PAY-ARM-2409-20250228 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 40.88 | 2902.66 | Startup, Testing and Commissioning - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2409-20250228 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 51.45 | 3987.07 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2409-20250228 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1047 | 45.4 | 3813.6 | Controls Programming and Checkout - field installation time
2025-02-28 | PRJ-PAY-ARM-2409-20250228 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1080 | 48.24 | 4365.89 | Warranty and Punchlist - coordination and layout
2025-03-06 | AP-0004177 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2528 |  | 78.05 | 14048.67 | Plumbing Fixtures and Piping - ductwork release
2025-03-07 | PRJ-PAY-ARM-2409-20250307 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 47.39 | 3364.95 | Engineering, BIM and Coordination - field installation time
2025-03-07 | PRJ-PAY-ARM-2409-20250307 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1026 | 58.21 | 4511.17 | Field Installation Labor - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2409-20250307 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 38.37 | 3222.71 | Startup, Testing and Commissioning - supervision and planning
2025-03-09 | AP-0004174 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2486 |  | 63.9 | 11501.31 | Major HVAC Equipment - released equipment package
2025-03-09 | AP-0004179 | AP | ARM-2409 | 04-300 | Testing and Balancing Subcontract | V-2029 |  | 25476.08 | 25476.08 | Testing and Balancing Subcontract - trade partner progress billing
2025-03-09 | AP-0004181 | AP | ARM-2409 | 05-400 | Small Tools and Consumables | V-2220 |  | 5920.77 | 5920.77 | Small Tools and Consumables - freight and expediting
2025-03-13 | AP-0004178 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2018 |  | 89.15 | 16047.26 | Major HVAC Equipment - jobsite material replenishment
2025-03-14 | PRJ-PAY-ARM-2409-20250314 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1024 | 41.75 | 2964.49 | Field Installation Labor - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2409-20250314 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 54.01 | 4185.69 | Startup, Testing and Commissioning - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2409-20250314 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 39.27 | 3298.95 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-16 | AP-0004175 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2500 |  | 56.39 | 10150.88 | Plumbing Fixtures and Piping - fabricated material delivery
2025-03-16 | AP-0004180 | AP | ARM-2409 | 04-200 | Electrical and Controls Subcontract | V-2201 |  | 14040.33 | 14040.33 | Electrical and Controls Subcontract - insulation progress invoice
2025-03-16 | AP-0004182 | AP | ARM-2409 | 05-200 | Permits, Fees and Bonds | V-2241 |  | 6105.95 | 6105.95 | Permits, Fees and Bonds - small tools and field consumables
2025-03-21 | PRJ-PAY-ARM-2409-20250321 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 51.97 | 3689.82 | Startup, Testing and Commissioning - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2409-20250321 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 48.15 | 3731.62 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2409-20250321 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1043 | 43.9 | 3688 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-23 | AP-0004176 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2514 |  | 75.22 | 13539.86 | Major HVAC Equipment - valves and piping lot
2025-03-28 | PRJ-PAY-ARM-2409-20250328 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 65.82 | 4673.11 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2409-20250328 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1041 | 44.6 | 3456.31 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2409-20250328 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1048 | 51.71 | 4343.26 | Warranty and Punchlist - field installation time
2025-03-31 | PRJ-PAY-ARM-2409-20250331 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1039 | 52.72 | 3742.93 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2409-20250331 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1046 | 33.44 | 2591.45 | Warranty and Punchlist - field installation time
2025-03-31 | PRJ-PAY-ARM-2409-20250331 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 41.95 | 3523.99 | Closeout and O&M Documentation - coordination and layout
2025-03-31 | PRJ-PAY-ARM-2409-20250331 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1086 | 37.87 | 3427.11 | Rework and Quality Correction - supervision and planning
2025-04-07 | PRJ-PAY-ARM-2409-20250407 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1020 | 51.81 | 3678.35 | Field Installation Labor - field installation time
2025-04-07 | PRJ-PAY-ARM-2409-20250407 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 51.94 | 4025.4 | Startup, Testing and Commissioning - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2409-20250407 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 43.9 | 3687.43 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-09 | AP-0004186 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2303 |  | 74.11 | 13340.61 | Controls Panels and Devices - jobsite material replenishment
2025-04-12 | AP-0004183 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2256 |  | 65.3 | 11754.25 | Sheet Metal and Ductwork - fabricated material delivery
2025-04-12 | AP-0004188 | AP | ARM-2409 | 04-400 | Crane, Rigging and Specialty Trade | V-2322 |  | 19343.3 | 19343.3 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-04-12 | AP-0004190 | AP | ARM-2409 | 06-400 | Temporary Facilities and Protection | V-2346 |  | 6184.35 | 6184.35 | Temporary Facilities and Protection - small tools and field consumables
2025-04-14 | PRJ-PAY-ARM-2409-20250414 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 57.04 | 4049.79 | Startup, Testing and Commissioning - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2409-20250414 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 49.86 | 3863.77 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2409-20250414 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1039 | 49.97 | 4197.46 | Controls Programming and Checkout - startup and checkout
2025-04-16 | AP-0004187 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2317 |  | 94.47 | 17003.99 | Sheet Metal and Ductwork - released equipment package
2025-04-19 | AP-0004184 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2275 |  | 68.56 | 12341.4 | Controls Panels and Devices - valves and piping lot
2025-04-19 | AP-0004189 | AP | ARM-2409 | 04-300 | Testing and Balancing Subcontract | V-2336 |  | 23063.14 | 23063.14 | Testing and Balancing Subcontract - testing and balancing services
2025-04-19 | AP-0004191 | AP | ARM-2409 | 05-300 | Freight and Expediting | V-2360 |  | 11163.74 | 11163.74 | Freight and Expediting - rental and logistics
2025-04-21 | PRJ-PAY-ARM-2409-20250421 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 51.23 | 3637.59 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2409-20250421 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1037 | 45.19 | 3502.4 | Controls Programming and Checkout - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2409-20250421 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1044 | 39.57 | 3324.16 | Warranty and Punchlist - punchlist and closeout labor
2025-04-21 | PRJ-PAY-ARM-2409-20250421 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 34.62 | 3133.01 | Closeout and O&M Documentation - field installation time
2025-04-25 | AP-0004185 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2289 |  | 61.65 | 11096.98 | Sheet Metal and Ductwork - ductwork release
2025-04-28 | PRJ-PAY-ARM-2409-20250428 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1035 | 36.67 | 2603.57 | Controls Programming and Checkout - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2409-20250428 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1042 | 52.72 | 4085.76 | Warranty and Punchlist - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2409-20250428 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 48.72 | 4092.35 | Closeout and O&M Documentation - field installation time
2025-04-28 | PRJ-PAY-ARM-2409-20250428 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1082 | 40.9 | 3701.57 | Rework and Quality Correction - coordination and layout
2025-04-30 | PRJ-PAY-ARM-2409-20250430 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1040 | 51.13 | 3630.35 | Warranty and Punchlist - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2409-20250430 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 39.25 | 3042 | Closeout and O&M Documentation - field installation time
2025-04-30 | PRJ-PAY-ARM-2409-20250430 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1080 | 35.04 | 2943.56 | Rework and Quality Correction - coordination and layout
2025-04-30 | PRJ-PAY-ARM-2409-20250430 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1087 | 44.05 | 4338.71 | Project Management and Supervision - supervision and planning
2025-05-05 | AP-0004194 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2400 |  | 48.1 | 8657.5 | Hydronic Piping and Valves - jobsite material replenishment
2025-05-07 | PRJ-PAY-ARM-2409-20250507 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 52.84 | 3751.34 | Startup, Testing and Commissioning - field installation time
2025-05-07 | PRJ-PAY-ARM-2409-20250507 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 65.03 | 5040.08 | Sheet Metal Fabrication Labor - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2409-20250507 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1035 | 42.79 | 3594.3 | Controls Programming and Checkout - supervision and planning
2025-05-12 | AP-0004195 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2414 |  | 97.25 | 17504.39 | Insulation and Specialty Material - released equipment package
2025-05-14 | PRJ-PAY-ARM-2409-20250514 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 52.96 | 3760.19 | Sheet Metal Fabrication Labor - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2409-20250514 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1033 | 42.3 | 3278.37 | Controls Programming and Checkout - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2409-20250514 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1040 | 41.09 | 3451.71 | Warranty and Punchlist - startup and checkout
2025-05-14 | PRJ-PAY-ARM-2409-20250514 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 37.74 | 3415.3 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-15 | AP-0004192 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2372 |  | 66.1 | 11898.04 | Hydronic Piping and Valves - valves and piping lot
2025-05-15 | AP-0004198 | AP | ARM-2409 | 04-100 | Insulation Subcontract | V-2443 |  | 24085.18 | 24085.18 | Insulation Subcontract - testing and balancing services
2025-05-15 | AP-0004200 | AP | ARM-2409 | 05-100 | Equipment Rental and Rigging | V-2467 |  | 9085.36 | 9085.36 | Equipment Rental and Rigging - rental and logistics
2025-05-19 | AP-0004196 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2427 |  | 42.94 | 7729.81 | Hydronic Piping and Valves - fabricated material delivery
2025-05-21 | PRJ-PAY-ARM-2409-20250521 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1031 | 41.88 | 2973.53 | Controls Programming and Checkout - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2409-20250521 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1038 | 44.36 | 3437.89 | Warranty and Punchlist - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2409-20250521 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 52.06 | 4372.64 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-21 | PRJ-PAY-ARM-2409-20250521 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1052 | 44.5 | 4027.7 | Rework and Quality Correction - field installation time
2025-05-22 | AP-0004193 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2386 |  | 71.77 | 12919.09 | Insulation and Specialty Material - ductwork release
2025-05-22 | AP-0004199 | AP | ARM-2409 | 04-400 | Crane, Rigging and Specialty Trade | V-2457 |  | 22019.63 | 22019.63 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-05-22 | AP-0004201 | AP | ARM-2409 | 05-400 | Small Tools and Consumables | V-2481 |  | 6951.09 | 6951.09 | Small Tools and Consumables - permit and inspection fees
2025-05-25 | AP-0004197 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2440 |  | 74.75 | 13455.22 | Insulation and Specialty Material - valves and piping lot
2025-05-28 | PRJ-PAY-ARM-2409-20250528 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1036 | 58.07 | 4123.3 | Warranty and Punchlist - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2409-20250528 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 46.29 | 3587.76 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2409-20250528 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1050 | 39.77 | 3340.55 | Rework and Quality Correction - field installation time
2025-05-28 | PRJ-PAY-ARM-2409-20250528 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1083 | 32.69 | 3219.53 | Project Management and Supervision - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2409-20250531 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 46.11 | 3273.68 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2409-20250531 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1048 | 39.94 | 3094.97 | Rework and Quality Correction - field installation time
2025-05-31 | PRJ-PAY-ARM-2409-20250531 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1081 | 41.5 | 3818.18 | Project Management and Supervision - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2409-20250531 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1088 | 28.66 | 2593.92 | Engineering, BIM and Coordination - supervision and planning
2025-06-05 | AP-0004207 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2205 |  | 58.09 | 10456.67 | Major HVAC Equipment - ductwork release
2025-06-07 | PRJ-PAY-ARM-2409-20250607 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1022 | 41.62 | 2955.15 | Sheet Metal Fabrication Labor - field installation time
2025-06-07 | PRJ-PAY-ARM-2409-20250607 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1029 | 40.77 | 3160.06 | Controls Programming and Checkout - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2409-20250607 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1036 | 39.6 | 3325.99 | Warranty and Punchlist - supervision and planning
2025-06-07 | PRJ-PAY-ARM-2409-20250607 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 38.27 | 3463.18 | Closeout and O&M Documentation - startup and checkout
2025-06-08 | AP-0004204 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2521 |  | 52.73 | 9490.75 | Plumbing Fixtures and Piping - released equipment package
2025-06-14 | PRJ-PAY-ARM-2409-20250614 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1027 | 48.57 | 3448.25 | Controls Programming and Checkout - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2409-20250614 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1034 | 47.19 | 3657.29 | Warranty and Punchlist - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2409-20250614 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 37.03 | 3110.41 | Closeout and O&M Documentation - startup and checkout
2025-06-14 | PRJ-PAY-ARM-2409-20250614 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1048 | 39 | 3529.37 | Rework and Quality Correction - punchlist and closeout labor
2025-06-15 | AP-0004205 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2534 |  | 80.49 | 14488.23 | Major HVAC Equipment - fabricated material delivery
2025-06-18 | AP-0004202 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2493 |  | 55.49 | 9988.63 | Plumbing Fixtures and Piping - ductwork release
2025-06-18 | AP-0004208 | AP | ARM-2409 | 04-200 | Electrical and Controls Subcontract | V-2210 |  | 22486.15 | 22486.15 | Electrical and Controls Subcontract - electrical coordination scope
2025-06-18 | AP-0004210 | AP | ARM-2409 | 05-200 | Permits, Fees and Bonds | V-2246 |  | 6632.79 | 6632.79 | Permits, Fees and Bonds - permit and inspection fees
2025-06-21 | PRJ-PAY-ARM-2409-20250621 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1032 | 42.65 | 3027.89 | Warranty and Punchlist - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2409-20250621 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 44.57 | 3454.21 | Closeout and O&M Documentation - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2409-20250621 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1046 | 46.1 | 3872.54 | Rework and Quality Correction - punchlist and closeout labor
2025-06-21 | PRJ-PAY-ARM-2409-20250621 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1053 | 29.33 | 2888.98 | Project Management and Supervision - field installation time
2025-06-22 | AP-0004206 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2033 |  | 71.21 | 12818.48 | Plumbing Fixtures and Piping - valves and piping lot
2025-06-25 | AP-0004203 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2507 |  | 70.81 | 12746.02 | Major HVAC Equipment - jobsite material replenishment
2025-06-25 | AP-0004209 | AP | ARM-2409 | 04-100 | Insulation Subcontract | V-2232 |  | 18033.67 | 18033.67 | Insulation Subcontract - rigging and specialty support
2025-06-25 | AP-0004211 | AP | ARM-2409 | 06-400 | Temporary Facilities and Protection | V-2267 |  | 6259.88 | 6259.88 | Temporary Facilities and Protection - freight and expediting
2025-06-28 | PRJ-PAY-ARM-2409-20250628 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 63.55 | 4512.2 | Closeout and O&M Documentation - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2409-20250628 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1044 | 43.89 | 3401.74 | Rework and Quality Correction - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2409-20250628 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1051 | 42.9 | 3946.6 | Project Management and Supervision - field installation time
2025-06-30 | PRJ-PAY-ARM-2409-20250630 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1042 | 49.15 | 3489.41 | Rework and Quality Correction - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2409-20250630 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1049 | 43.28 | 3700.59 | Project Management and Supervision - field installation time
2025-06-30 | PRJ-PAY-ARM-2409-20250630 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 43.78 | 3677.68 | Engineering, BIM and Coordination - coordination and layout
2025-07-04 | AP-0004213 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2294 |  | 102.16 | 18389.64 | Sheet Metal and Ductwork - released equipment package
2025-07-04 | AP-0004218 | AP | ARM-2409 | 04-200 | Electrical and Controls Subcontract | V-2355 |  | 18862.7 | 18862.7 | Electrical and Controls Subcontract - trade partner progress billing
2025-07-04 | AP-0004220 | AP | ARM-2409 | 05-100 | Equipment Rental and Rigging | V-2379 |  | 7428.33 | 7428.33 | Equipment Rental and Rigging - small tools and field consumables
2025-07-07 | PRJ-PAY-ARM-2409-20250707 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1023 | 57.55 | 4085.98 | Controls Programming and Checkout - field installation time
2025-07-07 | PRJ-PAY-ARM-2409-20250707 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1030 | 43.78 | 3392.62 | Warranty and Punchlist - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2409-20250707 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 42.26 | 3549.93 | Closeout and O&M Documentation - supervision and planning
2025-07-07 | PRJ-PAY-ARM-2409-20250707 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1044 | 38.98 | 3527.39 | Rework and Quality Correction - startup and checkout
2025-07-11 | AP-0004214 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2308 |  | 65.54 | 11797.05 | Controls Panels and Devices - fabricated material delivery
2025-07-14 | PRJ-PAY-ARM-2409-20250714 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1028 | 64.91 | 4608.53 | Warranty and Punchlist - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2409-20250714 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 39.4 | 3053.53 | Closeout and O&M Documentation - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2409-20250714 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1042 | 40.18 | 3375.02 | Rework and Quality Correction - startup and checkout
2025-07-14 | PRJ-PAY-ARM-2409-20250714 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1049 | 30.33 | 2987.55 | Project Management and Supervision - punchlist and closeout labor
2025-07-18 | AP-0004215 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2322 |  | 52.38 | 9427.52 | Sheet Metal and Ductwork - valves and piping lot
2025-07-21 | AP-0004212 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2281 |  | 83.72 | 15069.89 | Controls Panels and Devices - jobsite material replenishment
2025-07-21 | AP-0004217 | AP | ARM-2409 | 04-300 | Testing and Balancing Subcontract | V-2341 |  | 24760.3 | 24760.3 | Testing and Balancing Subcontract - rigging and specialty support
2025-07-21 | AP-0004219 | AP | ARM-2409 | 05-300 | Freight and Expediting | V-2365 |  | 9641.53 | 9641.53 | Freight and Expediting - freight and expediting
2025-07-21 | PRJ-PAY-ARM-2409-20250721 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 60.63 | 4304.94 | Closeout and O&M Documentation - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2409-20250721 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1040 | 49.72 | 3853.03 | Rework and Quality Correction - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2409-20250721 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1047 | 47.85 | 4402.02 | Project Management and Supervision - punchlist and closeout labor
2025-07-25 | AP-0004216 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2336 |  | 54.46 | 9802.07 | Controls Panels and Devices - ductwork release
2025-07-28 | PRJ-PAY-ARM-2409-20250728 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1038 | 64.55 | 4582.95 | Rework and Quality Correction - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2409-20250728 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1045 | 33.94 | 2901.52 | Project Management and Supervision - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2409-20250728 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 47.91 | 4024.11 | Engineering, BIM and Coordination - field installation time
2025-07-31 | PRJ-PAY-ARM-2409-20250731 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1043 | 51.66 | 4081.25 | Project Management and Supervision - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2409-20250731 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 56.29 | 4362.47 | Engineering, BIM and Coordination - field installation time
2025-07-31 | PRJ-PAY-ARM-2409-20250731 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1083 | 40.4 | 3393.33 | Field Installation Labor - coordination and layout
2025-08-04 | AP-0004225 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2445 |  | 50.71 | 9128.19 | Insulation and Specialty Material - jobsite material replenishment
2025-08-07 | AP-0004222 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2405 |  | 82.13 | 14783.32 | Hydronic Piping and Valves - fabricated material delivery
2025-08-07 | AP-0004227 | AP | ARM-2409 | 04-300 | Testing and Balancing Subcontract | V-2464 |  | 25245.2 | 25245.2 | Testing and Balancing Subcontract - insulation progress invoice
2025-08-07 | AP-0004229 | AP | ARM-2409 | 05-200 | Permits, Fees and Bonds | V-2488 |  | 7198.7 | 7198.7 | Permits, Fees and Bonds - rental and logistics
2025-08-07 | PRJ-PAY-ARM-2409-20250807 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1024 | 54.75 | 3886.9 | Warranty and Punchlist - field installation time
2025-08-07 | PRJ-PAY-ARM-2409-20250807 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1031 | 53.05 | 4111.59 | Closeout and O&M Documentation - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2409-20250807 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1038 | 53.57 | 4499.76 | Rework and Quality Correction - supervision and planning
2025-08-14 | AP-0004223 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2419 |  | 56.8 | 10224.34 | Insulation and Specialty Material - valves and piping lot
2025-08-14 | PRJ-PAY-ARM-2409-20250814 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1029 | 64.57 | 4584.68 | Closeout and O&M Documentation - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2409-20250814 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1036 | 42.84 | 3320.16 | Rework and Quality Correction - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2409-20250814 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1043 | 35.74 | 3288.18 | Project Management and Supervision - startup and checkout
2025-08-21 | AP-0004224 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2433 |  | 74.64 | 13435.37 | Hydronic Piping and Valves - ductwork release
2025-08-21 | PRJ-PAY-ARM-2409-20250821 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1034 | 45.07 | 3200.03 | Rework and Quality Correction - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2409-20250821 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1041 | 37.2 | 3180.45 | Project Management and Supervision - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2409-20250821 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1048 | 46.14 | 3875.55 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-24 | AP-0004221 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2391 |  | 66.88 | 12038.57 | Insulation and Specialty Material - released equipment package
2025-08-24 | AP-0004226 | AP | ARM-2409 | 04-400 | Crane, Rigging and Specialty Trade | V-2450 |  | 11183 | 11183 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-08-24 | AP-0004228 | AP | ARM-2409 | 05-400 | Small Tools and Consumables | V-2474 |  | 6047.92 | 6047.92 | Small Tools and Consumables - small tools and field consumables
2025-08-28 | PRJ-PAY-ARM-2409-20250828 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1039 | 50.49 | 3988.43 | Project Management and Supervision - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2409-20250828 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1046 | 45.54 | 3529.45 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2409-20250828 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1053 | 36.08 | 3030.88 | Field Installation Labor - field installation time
2025-08-31 | PRJ-PAY-ARM-2409-20250831 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 53.66 | 3810.1 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2409-20250831 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1051 | 47.46 | 3677.9 | Field Installation Labor - field installation time
2025-08-31 | PRJ-PAY-ARM-2409-20250831 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1084 | 51.36 | 4314.07 | Startup, Testing and Commissioning - coordination and layout
2025-09-03 | AP-0004230 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2500 |  | 86.66 | 15598.15 | Major HVAC Equipment - fabricated material delivery
2025-09-03 | AP-0004235 | AP | ARM-2409 | 04-100 | Insulation Subcontract | V-2201 |  | 21854.37 | 21854.37 | Insulation Subcontract - insulation progress invoice
2025-09-03 | AP-0004237 | AP | ARM-2409 | 06-400 | Temporary Facilities and Protection | V-2241 |  | 4455.51 | 4455.51 | Temporary Facilities and Protection - rental and logistics
2025-09-07 | AP-0004234 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2060 |  | 55.01 | 9902.68 | Major HVAC Equipment - released equipment package
2025-09-07 | PRJ-PAY-ARM-2409-20250907 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1025 | 57.82 | 4105.32 | Closeout and O&M Documentation - field installation time
2025-09-07 | PRJ-PAY-ARM-2409-20250907 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1032 | 52.76 | 4089.06 | Rework and Quality Correction - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2409-20250907 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1039 | 27.06 | 2489.31 | Project Management and Supervision - supervision and planning
2025-09-10 | AP-0004231 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2514 |  | 56.83 | 10228.86 | Plumbing Fixtures and Piping - valves and piping lot
2025-09-10 | AP-0004236 | AP | ARM-2409 | 04-400 | Crane, Rigging and Specialty Trade | V-2225 |  | 14732.64 | 14732.64 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-09-10 | AP-0004238 | AP | ARM-2409 | 05-300 | Freight and Expediting | V-2258 |  | 6679.67 | 6679.67 | Freight and Expediting - permit and inspection fees
2025-09-14 | PRJ-PAY-ARM-2409-20250914 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1030 | 53.94 | 3829.81 | Rework and Quality Correction - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2409-20250914 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1037 | 27.38 | 2341.39 | Project Management and Supervision - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2409-20250914 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 43.07 | 3618.14 | Engineering, BIM and Coordination - startup and checkout
2025-09-17 | AP-0004232 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2528 |  | 51.54 | 9276.84 | Major HVAC Equipment - ductwork release
2025-09-21 | PRJ-PAY-ARM-2409-20250921 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1035 | 53.09 | 4193.91 | Project Management and Supervision - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2409-20250921 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1042 | 40.97 | 3175.46 | Engineering, BIM and Coordination - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2409-20250921 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1049 | 32.14 | 2699.38 | Field Installation Labor - punchlist and closeout labor
2025-09-24 | AP-0004233 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2018 |  | 85.79 | 15441.57 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-09-28 | PRJ-PAY-ARM-2409-20250928 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 57.48 | 4081.33 | Engineering, BIM and Coordination - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2409-20250928 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1047 | 52.96 | 4104.65 | Field Installation Labor - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2409-20250928 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1080 | 36.66 | 3079.05 | Startup, Testing and Commissioning - field installation time
2025-09-30 | PRJ-PAY-ARM-2409-20250930 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1045 | 74.46 | 5286.4 | Field Installation Labor - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2409-20250930 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1052 | 46.48 | 3601.87 | Startup, Testing and Commissioning - field installation time
2025-09-30 | PRJ-PAY-ARM-2409-20250930 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1085 | 40.36 | 3390.06 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-03 | AP-0004242 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2317 |  | 98.4 | 17712.21 | Controls Panels and Devices - released equipment package
2025-10-06 | AP-0004239 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2275 |  | 60.93 | 10967.39 | Sheet Metal and Ductwork - valves and piping lot
2025-10-06 | AP-0004243 | AP | ARM-2409 | 04-200 | Electrical and Controls Subcontract | V-2324 |  | 34714.88 | 34714.88 | Electrical and Controls Subcontract - testing and balancing services
2025-10-06 | AP-0004244 | AP | ARM-2409 | 05-100 | Equipment Rental and Rigging | V-2336 |  | 6902.55 | 6902.55 | Equipment Rental and Rigging - permit and inspection fees
2025-10-07 | PRJ-PAY-ARM-2409-20251007 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1026 | 40.3 | 2861.57 | Rework and Quality Correction - field installation time
2025-10-07 | PRJ-PAY-ARM-2409-20251007 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1033 | 42.49 | 3632.53 | Project Management and Supervision - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2409-20251007 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 35.19 | 2955.62 | Engineering, BIM and Coordination - supervision and planning
2025-10-13 | AP-0004240 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2289 |  | 90.93 | 16367.19 | Controls Panels and Devices - ductwork release
2025-10-13 | AP-0004245 | AP | ARM-2409 | 05-400 | Small Tools and Consumables | V-2350 |  | 7298.99 | 7298.99 | Small Tools and Consumables - freight and expediting
2025-10-14 | PRJ-PAY-ARM-2409-20251014 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1031 | 40.63 | 3209.75 | Project Management and Supervision - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2409-20251014 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1038 | 36.54 | 2831.85 | Engineering, BIM and Coordination - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2409-20251014 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1045 | 43.78 | 3677.84 | Field Installation Labor - startup and checkout
2025-10-20 | AP-0004241 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2303 |  | 47.8 | 8603.49 | Sheet Metal and Ductwork - jobsite material replenishment
2025-10-21 | PRJ-PAY-ARM-2409-20251021 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1036 | 58.76 | 4172.11 | Engineering, BIM and Coordination - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2409-20251021 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1043 | 47.66 | 3693.3 | Field Installation Labor - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2409-20251021 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1050 | 35.82 | 3008.8 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2409-20251028 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1041 | 61.46 | 4363.31 | Field Installation Labor - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2409-20251028 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 44.23 | 3427.65 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2409-20251028 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1081 | 48.35 | 4061.39 | Sheet Metal Fabrication Labor - field installation time
2025-10-31 | PRJ-PAY-ARM-2409-20251031 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 47.68 | 3385.32 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2409-20251031 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1053 | 59.83 | 4636.79 | Sheet Metal Fabrication Labor - field installation time
2025-10-31 | PRJ-PAY-ARM-2409-20251031 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1086 | 44.43 | 3732.45 | Controls Programming and Checkout - coordination and layout
2025-11-06 | AP-0004249 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2403 |  | 57.12 | 10281.57 | Insulation and Specialty Material - fabricated material delivery
2025-11-07 | PRJ-PAY-ARM-2409-20251107 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1027 | 32.55 | 2571.15 | Project Management and Supervision - field installation time
2025-11-07 | PRJ-PAY-ARM-2409-20251107 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1034 | 33.62 | 2605.25 | Engineering, BIM and Coordination - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2409-20251107 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1041 | 26.49 | 2225.16 | Field Installation Labor - supervision and planning
2025-11-09 | AP-0004246 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2362 |  | 55.95 | 10070.5 | Hydronic Piping and Valves - ductwork release
2025-11-09 | AP-0004250 | AP | ARM-2409 | 04-300 | Testing and Balancing Subcontract | V-2410 |  | 28266.77 | 28266.77 | Testing and Balancing Subcontract - electrical coordination scope
2025-11-09 | AP-0004251 | AP | ARM-2409 | 05-200 | Permits, Fees and Bonds | V-2422 |  | 9831.92 | 9831.92 | Permits, Fees and Bonds - freight and expediting
2025-11-14 | PRJ-PAY-ARM-2409-20251114 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1032 | 35.19 | 2498.22 | Engineering, BIM and Coordination - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2409-20251114 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1039 | 40.61 | 3147.58 | Field Installation Labor - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2409-20251114 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 31.37 | 2635.14 | Startup, Testing and Commissioning - startup and checkout
2025-11-16 | AP-0004247 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2376 |  | 86.12 | 15500.97 | Insulation and Specialty Material - jobsite material replenishment
2025-11-21 | PRJ-PAY-ARM-2409-20251121 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1037 | 52.66 | 3738.99 | Field Installation Labor - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2409-20251121 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1044 | 34.11 | 2643.24 | Startup, Testing and Commissioning - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2409-20251121 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1051 | 31.47 | 2643.58 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-23 | AP-0004248 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2389 |  | 46.61 | 8390.59 | Hydronic Piping and Valves - released equipment package
2025-11-28 | PRJ-PAY-ARM-2409-20251128 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 43.2 | 3067.4 | Startup, Testing and Commissioning - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2409-20251128 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 37.03 | 2869.55 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2409-20251128 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1082 | 35.89 | 3014.39 | Controls Programming and Checkout - field installation time
2025-11-30 | PRJ-PAY-ARM-2409-20251130 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 32.25 | 2289.64 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2409-20251130 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1080 | 37.53 | 2908.84 | Controls Programming and Checkout - field installation time
2025-11-30 | PRJ-PAY-ARM-2409-20251130 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1087 | 34.85 | 2927.52 | Warranty and Punchlist - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2409-20251207 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1028 | 31.35 | 2225.68 | Engineering, BIM and Coordination - field installation time
2025-12-07 | PRJ-PAY-ARM-2409-20251207 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1035 | 30.67 | 2376.91 | Field Installation Labor - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2409-20251207 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 36.62 | 3076.19 | Startup, Testing and Commissioning - supervision and planning
2025-12-12 | AP-0004252 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2436 |  | 77.76 | 13997.67 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-12-12 | AP-0004255 | AP | ARM-2409 | 04-400 | Crane, Rigging and Specialty Trade | V-2471 |  | 25015.89 | 25015.89 | Crane, Rigging and Specialty Trade - rigging and specialty support
2025-12-12 | AP-0004256 | AP | ARM-2409 | 05-300 | Freight and Expediting | V-2483 |  | 7959.6 | 7959.6 | Freight and Expediting - small tools and field consumables
2025-12-14 | PRJ-PAY-ARM-2409-20251214 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1033 | 40.91 | 2904.44 | Field Installation Labor - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2409-20251214 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1040 | 35.77 | 2772.12 | Startup, Testing and Commissioning - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2409-20251214 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 32.06 | 2692.93 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-19 | AP-0004253 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2448 |  | 82.2 | 14796.79 | Major HVAC Equipment - released equipment package
2025-12-21 | PRJ-PAY-ARM-2409-20251221 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1038 | 43.73 | 3104.87 | Startup, Testing and Commissioning - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2409-20251221 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1045 | 35.42 | 2745.32 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2409-20251221 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1052 | 29.17 | 2450.24 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-25 | AP-0004254 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2462 |  | 80.08 | 14414.81 | Plumbing Fixtures and Piping - fabricated material delivery
2025-12-28 | PRJ-PAY-ARM-2409-20251228 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 37.2 | 2640.91 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2409-20251228 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1050 | 31.11 | 2410.85 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2409-20251228 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1083 | 29.56 | 2483.34 | Warranty and Punchlist - field installation time
2025-12-31 | PRJ-PAY-ARM-2409-20251231 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1048 | 36.6 | 2598.92 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2409-20251231 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1081 | 24.22 | 1876.99 | Warranty and Punchlist - field installation time
2025-12-31 | PRJ-PAY-ARM-2409-20251231 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1088 | 27.4 | 2301.22 | Closeout and O&M Documentation - coordination and layout
2026-01-05 | AP-0004259 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2524 |  | 50.03 | 9006.1 | Controls Panels and Devices - valves and piping lot
2026-01-07 | PRJ-PAY-ARM-2409-20260107 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1029 | 35.33 | 2508.59 | Field Installation Labor - field installation time
2026-01-07 | PRJ-PAY-ARM-2409-20260107 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1036 | 32.4 | 2510.81 | Startup, Testing and Commissioning - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2409-20260107 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 26.19 | 2200.29 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2409-20260114 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1034 | 32.44 | 2302.98 | Startup, Testing and Commissioning - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2409-20260114 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1041 | 37.5 | 2906.5 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2409-20260114 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1048 | 23.22 | 1950.64 | Controls Programming and Checkout - startup and checkout
2026-01-15 | AP-0004257 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2496 |  | 79.68 | 14341.57 | Controls Panels and Devices - released equipment package
2026-01-15 | AP-0004260 | AP | ARM-2409 | 04-100 | Insulation Subcontract | V-2533 |  | 22002.61 | 22002.61 | Insulation Subcontract - trade partner progress billing
2026-01-15 | AP-0004261 | AP | ARM-2409 | 05-400 | Small Tools and Consumables | V-2025 |  | 8609.71 | 8609.71 | Small Tools and Consumables - rental and logistics
2026-01-21 | PRJ-PAY-ARM-2409-20260121 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1039 | 30.34 | 2154.35 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2409-20260121 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1046 | 30.59 | 2371.08 | Controls Programming and Checkout - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2409-20260121 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1053 | 23.51 | 1974.5 | Warranty and Punchlist - punchlist and closeout labor
2026-01-22 | AP-0004258 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2510 |  | 50.99 | 9177.93 | Sheet Metal and Ductwork - fabricated material delivery
2026-01-28 | PRJ-PAY-ARM-2409-20260128 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1044 | 24.15 | 1714.82 | Controls Programming and Checkout - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2409-20260128 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1051 | 24.09 | 1866.82 | Warranty and Punchlist - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2409-20260128 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1084 | 26.96 | 2264.46 | Closeout and O&M Documentation - field installation time
2026-01-31 | PRJ-PAY-ARM-2409-20260131 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1049 | 31.22 | 2216.94 | Warranty and Punchlist - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2409-20260131 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1082 | 20.68 | 1602.84 | Closeout and O&M Documentation - field installation time
2026-01-31 | PRJ-PAY-ARM-2409-20260131 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1089 | 23.57 | 1979.98 | Rework and Quality Correction - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2409-20260207 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1030 | 48.57 | 3448.5 | Startup, Testing and Commissioning - field installation time
2026-02-07 | PRJ-PAY-ARM-2409-20260207 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1037 | 37.35 | 2894.5 | Sheet Metal Fabrication Labor - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2409-20260207 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1044 | 42.47 | 3567.8 | Controls Programming and Checkout - supervision and planning
2026-02-08 | AP-0004264 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2243 |  | 65.55 | 11798.78 | Insulation and Specialty Material - ductwork release
2026-02-14 | PRJ-PAY-ARM-2409-20260214 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1035 | 42.38 | 3009.25 | Sheet Metal Fabrication Labor - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2409-20260214 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1042 | 36.27 | 2811.18 | Controls Programming and Checkout - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2409-20260214 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1049 | 37.82 | 3176.56 | Warranty and Punchlist - startup and checkout
2026-02-18 | AP-0004262 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2098 |  | 76.99 | 13858.12 | Insulation and Specialty Material - fabricated material delivery
2026-02-18 | AP-0004265 | AP | ARM-2409 | 04-200 | Electrical and Controls Subcontract | V-2255 |  | 22664.9 | 22664.9 | Electrical and Controls Subcontract - insulation progress invoice
2026-02-18 | AP-0004266 | AP | ARM-2409 | 06-400 | Temporary Facilities and Protection | V-2272 |  | 8241.78 | 8241.78 | Temporary Facilities and Protection - permit and inspection fees
2026-02-21 | PRJ-PAY-ARM-2409-20260221 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1040 | 34.36 | 2439.6 | Controls Programming and Checkout - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2409-20260221 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1047 | 29.74 | 2305.06 | Warranty and Punchlist - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2409-20260221 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1080 | 39.85 | 3347.31 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-25 | AP-0004263 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2222 |  | 63.51 | 11431.11 | Hydronic Piping and Valves - valves and piping lot
2026-02-28 | PRJ-PAY-ARM-2409-20260228 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1045 | 34.84 | 2473.82 | Warranty and Punchlist - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2409-20260228 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1052 | 27.47 | 2128.89 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2409-20260228 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1085 | 40.77 | 3425.1 | Rework and Quality Correction - field installation time
2026-03-04 | AP-0004268 | AP | ARM-2409 | 02-410 | Plumbing Fixtures and Piping | V-2300 |  | 84.74 | 15253.25 | Plumbing Fixtures and Piping - ductwork release
2026-03-07 | PRJ-PAY-ARM-2409-20260307 | PAY | ARM-2409 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 39.66 | 2816.12 | Sheet Metal Fabrication Labor - field installation time
2026-03-07 | PRJ-PAY-ARM-2409-20260307 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1038 | 32.71 | 2534.93 | Controls Programming and Checkout - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2409-20260307 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1045 | 26.25 | 2204.86 | Warranty and Punchlist - supervision and planning
2026-03-11 | AP-0004269 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2313 |  | 60.36 | 10864.55 | Major HVAC Equipment - jobsite material replenishment
2026-03-14 | PRJ-PAY-ARM-2409-20260314 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1036 | 33.41 | 2372.1 | Controls Programming and Checkout - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2409-20260314 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1043 | 29.29 | 2270.06 | Warranty and Punchlist - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2409-20260314 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1050 | 25.64 | 2153.69 | Closeout and O&M Documentation - startup and checkout
2026-03-21 | AP-0004267 | AP | ARM-2409 | 02-110 | Major HVAC Equipment | V-2286 |  | 83.36 | 15004.53 | Major HVAC Equipment - valves and piping lot
2026-03-21 | AP-0004270 | AP | ARM-2409 | 04-300 | Testing and Balancing Subcontract | V-2322 |  | 24889.83 | 24889.83 | Testing and Balancing Subcontract - testing and balancing services
2026-03-21 | AP-0004271 | AP | ARM-2409 | 05-100 | Equipment Rental and Rigging | V-2334 |  | 7575.17 | 7575.17 | Equipment Rental and Rigging - freight and expediting
2026-03-21 | PRJ-PAY-ARM-2409-20260321 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1041 | 38.15 | 2708.74 | Warranty and Punchlist - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2409-20260321 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1048 | 26.03 | 2017.54 | Closeout and O&M Documentation - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2409-20260321 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1081 | 24 | 2015.7 | Rework and Quality Correction - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2409-20260328 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1046 | 33.07 | 2348.29 | Closeout and O&M Documentation - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2409-20260328 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1053 | 39.86 | 3088.8 | Rework and Quality Correction - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2409-20260328 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1086 | 21.81 | 2006.72 | Project Management and Supervision - field installation time
2026-03-31 | PRJ-PAY-ARM-2409-20260331 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1051 | 37.53 | 2664.76 | Rework and Quality Correction - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2409-20260331 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1084 | 31.38 | 2683.1 | Project Management and Supervision - field installation time
2026-03-31 | PRJ-PAY-ARM-2409-20260331 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1091 | 34.62 | 2908.25 | Engineering, BIM and Coordination - coordination and layout
2026-04-07 | AP-0004273 | AP | ARM-2409 | 02-510 | Controls Panels and Devices | V-2362 |  | 92.98 | 16735.95 | Controls Panels and Devices - jobsite material replenishment
2026-04-07 | AP-0004277 | AP | ARM-2409 | 06-400 | Temporary Facilities and Protection | V-2410 |  | 4479.13 | 4479.13 | Temporary Facilities and Protection - rental and logistics
2026-04-07 | PRJ-PAY-ARM-2409-20260407 | PAY | ARM-2409 | 03-400 | Controls Programming and Checkout |  | E-1032 | 42.1 | 2989.39 | Controls Programming and Checkout - field installation time
2026-04-07 | PRJ-PAY-ARM-2409-20260407 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1039 | 30.31 | 2348.64 | Warranty and Punchlist - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2409-20260407 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1046 | 28.72 | 2412.78 | Closeout and O&M Documentation - supervision and planning
2026-04-14 | AP-0004274 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2376 |  | 74.1 | 13338.51 | Sheet Metal and Ductwork - released equipment package
2026-04-14 | PRJ-PAY-ARM-2409-20260414 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1037 | 28.51 | 2024.41 | Warranty and Punchlist - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2409-20260414 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 33.99 | 2634.38 | Closeout and O&M Documentation - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2409-20260414 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1051 | 36.08 | 3030.57 | Rework and Quality Correction - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2409-20260421 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1042 | 37.99 | 2697.59 | Closeout and O&M Documentation - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2409-20260421 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1049 | 39.02 | 3024.15 | Rework and Quality Correction - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2409-20260421 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1082 | 30.09 | 2768.08 | Project Management and Supervision - punchlist and closeout labor
2026-04-24 | AP-0004272 | AP | ARM-2409 | 02-210 | Sheet Metal and Ductwork | V-2348 |  | 71.6 | 12888.65 | Sheet Metal and Ductwork - ductwork release
2026-04-24 | AP-0004275 | AP | ARM-2409 | 04-400 | Crane, Rigging and Specialty Trade | V-2384 |  | 27799.66 | 27799.66 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-04-24 | AP-0004276 | AP | ARM-2409 | 05-200 | Permits, Fees and Bonds | V-2396 |  | 6893.45 | 6893.45 | Permits, Fees and Bonds - small tools and field consumables
2026-04-28 | PRJ-PAY-ARM-2409-20260428 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1047 | 36.34 | 2580.33 | Rework and Quality Correction - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2409-20260428 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1080 | 38.12 | 3259.58 | Project Management and Supervision - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2409-20260428 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1087 | 42.58 | 3576.33 | Engineering, BIM and Coordination - field installation time
2026-04-30 | PRJ-PAY-ARM-2409-20260430 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1052 | 34.36 | 2714.69 | Project Management and Supervision - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2409-20260430 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1085 | 40.66 | 3151.04 | Engineering, BIM and Coordination - field installation time
2026-04-30 | PRJ-PAY-ARM-2409-20260430 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1092 | 44.66 | 3751.15 | Field Installation Labor - coordination and layout
2026-05-03 | AP-0004278 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2422 |  | 69.94 | 12588.34 | Hydronic Piping and Valves - jobsite material replenishment
2026-05-03 | AP-0004282 | AP | ARM-2409 | 04-100 | Insulation Subcontract | V-2469 |  | 31839.27 | 31839.27 | Insulation Subcontract - rigging and specialty support
2026-05-03 | AP-0004283 | AP | ARM-2409 | 05-300 | Freight and Expediting | V-2481 |  | 4442.24 | 4442.24 | Freight and Expediting - rental and logistics
2026-05-07 | PRJ-PAY-ARM-2409-20260507 | PAY | ARM-2409 | 06-100 | Warranty and Punchlist |  | E-1033 | 43.57 | 3093.76 | Warranty and Punchlist - field installation time
2026-05-07 | PRJ-PAY-ARM-2409-20260507 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 30.26 | 2345.27 | Closeout and O&M Documentation - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2409-20260507 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1047 | 32.9 | 2763.97 | Rework and Quality Correction - supervision and planning
2026-05-10 | AP-0004279 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2436 |  | 55.57 | 10003.09 | Insulation and Specialty Material - released equipment package
2026-05-10 | AP-0004284 | AP | ARM-2409 | 05-100 | Equipment Rental and Rigging | V-2495 |  | 6632.28 | 6632.28 | Equipment Rental and Rigging - permit and inspection fees
2026-05-14 | PRJ-PAY-ARM-2409-20260514 | PAY | ARM-2409 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 44 | 3123.8 | Closeout and O&M Documentation - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2409-20260514 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1045 | 37.26 | 2887.28 | Rework and Quality Correction - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2409-20260514 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1052 | 33.11 | 3045.85 | Project Management and Supervision - startup and checkout
2026-05-17 | AP-0004280 | AP | ARM-2409 | 02-310 | Hydronic Piping and Valves | V-2448 |  | 82.13 | 14783.05 | Hydronic Piping and Valves - fabricated material delivery
2026-05-21 | PRJ-PAY-ARM-2409-20260521 | PAY | ARM-2409 | 06-300 | Rework and Quality Correction |  | E-1043 | 54.1 | 3841.22 | Rework and Quality Correction - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2409-20260521 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1050 | 37.27 | 3186.21 | Project Management and Supervision - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2409-20260521 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1083 | 35.93 | 3017.82 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-24 | AP-0004281 | AP | ARM-2409 | 02-610 | Insulation and Specialty Material | V-2462 |  | 69.23 | 12460.9 | Insulation and Specialty Material - valves and piping lot
2026-05-28 | PRJ-PAY-ARM-2409-20260528 | PAY | ARM-2409 | 01-100 | Project Management and Supervision |  | E-1048 | 45.45 | 3590.19 | Project Management and Supervision - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2409-20260528 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1081 | 43.42 | 3365.08 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2409-20260528 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1088 | 39.33 | 3304.02 | Field Installation Labor - field installation time
2026-05-31 | PRJ-PAY-ARM-2409-20260531 | PAY | ARM-2409 | 01-200 | Engineering, BIM and Coordination |  | E-1053 | 38.31 | 2720.32 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2409-20260531 | PAY | ARM-2409 | 03-100 | Field Installation Labor |  | E-1086 | 49.16 | 3809.57 | Field Installation Labor - field installation time
2026-05-31 | PRJ-PAY-ARM-2409-20260531 | PAY | ARM-2409 | 03-200 | Startup, Testing and Commissioning |  | E-1093 | 35.39 | 2972.39 | Startup, Testing and Commissioning - coordination and layout
2025-01-04 | AP-0004324 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2275 |  | 43.33 | 7799.28 | Insulation and Specialty Material - valves and piping lot
2025-01-07 | PRJ-PAY-ARM-2412-20250107 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1014 | 36.9 | 2620.11 | Warranty and Punchlist - field installation time
2025-01-07 | PRJ-PAY-ARM-2412-20250107 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 30.78 | 2385.4 | Closeout and O&M Documentation - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2412-20250107 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1029 | 37.13 | 3119.18 | Rework and Quality Correction - supervision and planning
2025-01-11 | AP-0004325 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2289 |  | 51.64 | 9296.07 | Hydronic Piping and Valves - ductwork release
2025-01-14 | PRJ-PAY-ARM-2412-20250114 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 51.86 | 3682.04 | Closeout and O&M Documentation - coordination and layout
2025-01-14 | PRJ-PAY-ARM-2412-20250114 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1027 | 38.16 | 2957.47 | Rework and Quality Correction - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2412-20250114 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1034 | 26.41 | 2429.81 | Project Management and Supervision - startup and checkout
2025-01-18 | AP-0004326 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2303 |  | 78.94 | 14209.16 | Insulation and Specialty Material - jobsite material replenishment
2025-01-21 | AP-0004323 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2256 |  | 80.67 | 14519.96 | Hydronic Piping and Valves - fabricated material delivery
2025-01-21 | AP-0004327 | AP | ARM-2412 | 04-300 | Testing and Balancing Subcontract | V-2310 |  | 29276.74 | 29276.74 | Testing and Balancing Subcontract - insulation progress invoice
2025-01-21 | AP-0004328 | AP | ARM-2412 | 06-400 | Temporary Facilities and Protection | V-2322 |  | 10183.22 | 10183.22 | Temporary Facilities and Protection - freight and expediting
2025-01-21 | PRJ-PAY-ARM-2412-20250121 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1025 | 47.75 | 3390.12 | Rework and Quality Correction - supervision and planning
2025-01-21 | PRJ-PAY-ARM-2412-20250121 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1032 | 42.68 | 3649.27 | Project Management and Supervision - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2412-20250121 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 28.16 | 2365.22 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2412-20250128 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1030 | 38.53 | 3043.56 | Project Management and Supervision - startup and checkout
2025-01-28 | PRJ-PAY-ARM-2412-20250128 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 38.93 | 3017.15 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2412-20250128 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1044 | 32.88 | 2761.59 | Field Installation Labor - field installation time
2025-01-31 | PRJ-PAY-ARM-2412-20250131 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 35.38 | 2512.02 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-01-31 | PRJ-PAY-ARM-2412-20250131 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1042 | 28.99 | 2247.01 | Field Installation Labor - field installation time
2025-01-31 | PRJ-PAY-ARM-2412-20250131 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 36.89 | 3098.71 | Startup, Testing and Commissioning - coordination and layout
2025-02-04 | AP-0004333 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2391 |  | 58.4 | 10511.4 | Plumbing Fixtures and Piping - fabricated material delivery
2025-02-07 | AP-0004330 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2350 |  | 79.78 | 14360.2 | Major HVAC Equipment - ductwork release
2025-02-07 | AP-0004336 | AP | ARM-2412 | 05-400 | Small Tools and Consumables | V-2422 |  | 5812.28 | 5812.28 | Small Tools and Consumables - rental and logistics
2025-02-07 | PRJ-PAY-ARM-2412-20250207 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 46.39 | 3294.02 | Closeout and O&M Documentation - field installation time
2025-02-07 | PRJ-PAY-ARM-2412-20250207 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1023 | 48.38 | 3749.26 | Rework and Quality Correction - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2412-20250207 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1030 | 32.39 | 2979.45 | Project Management and Supervision - supervision and planning
2025-02-07 | PRJ-PAY-ARM-2412-20250207 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 36.94 | 3342.73 | Engineering, BIM and Coordination - startup and checkout
2025-02-14 | AP-0004331 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2364 |  | 68.08 | 12255.12 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-02-14 | PRJ-PAY-ARM-2412-20250214 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1021 | 38.31 | 2720.01 | Rework and Quality Correction - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2412-20250214 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1028 | 48.88 | 4179.4 | Project Management and Supervision - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2412-20250214 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 46.13 | 3875.01 | Engineering, BIM and Coordination - startup and checkout
2025-02-14 | PRJ-PAY-ARM-2412-20250214 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1042 | 34.09 | 3085.16 | Field Installation Labor - punchlist and closeout labor
2025-02-21 | AP-0004332 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2377 |  | 50.72 | 9128.8 | Major HVAC Equipment - released equipment package
2025-02-21 | PRJ-PAY-ARM-2412-20250221 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1026 | 43.82 | 3461.9 | Project Management and Supervision - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2412-20250221 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 48.2 | 3735.18 | Engineering, BIM and Coordination - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2412-20250221 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1040 | 40.49 | 3401.58 | Field Installation Labor - punchlist and closeout labor
2025-02-21 | PRJ-PAY-ARM-2412-20250221 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1047 | 26.55 | 2402.77 | Startup, Testing and Commissioning - field installation time
2025-02-24 | AP-0004329 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2336 |  | 64.7 | 11645.81 | Plumbing Fixtures and Piping - valves and piping lot
2025-02-24 | AP-0004334 | AP | ARM-2412 | 04-400 | Crane, Rigging and Specialty Trade | V-2396 |  | 33521.82 | 33521.82 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-02-24 | AP-0004335 | AP | ARM-2412 | 05-100 | Equipment Rental and Rigging | V-2408 |  | 4853.76 | 4853.76 | Equipment Rental and Rigging - small tools and field consumables
2025-02-28 | PRJ-PAY-ARM-2412-20250228 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 52.8 | 3749.02 | Engineering, BIM and Coordination - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2412-20250228 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1038 | 63.4 | 4913.88 | Field Installation Labor - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2412-20250228 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 34.73 | 2917.08 | Startup, Testing and Commissioning - field installation time
2025-03-03 | AP-0004337 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2434 |  | 82.09 | 14776.52 | Controls Panels and Devices - ductwork release
2025-03-03 | AP-0004341 | AP | ARM-2412 | 04-100 | Insulation Subcontract | V-2481 |  | 35506.49 | 35506.49 | Insulation Subcontract - electrical coordination scope
2025-03-03 | AP-0004342 | AP | ARM-2412 | 05-200 | Permits, Fees and Bonds | V-2493 |  | 5609.08 | 5609.08 | Permits, Fees and Bonds - rental and logistics
2025-03-07 | PRJ-PAY-ARM-2412-20250307 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1016 | 61.57 | 4371.62 | Rework and Quality Correction - field installation time
2025-03-07 | PRJ-PAY-ARM-2412-20250307 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1024 | 45.72 | 3908.99 | Project Management and Supervision - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2412-20250307 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 43.55 | 3657.84 | Engineering, BIM and Coordination - supervision and planning
2025-03-10 | AP-0004338 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2446 |  | 79.09 | 14236.03 | Sheet Metal and Ductwork - jobsite material replenishment
2025-03-10 | AP-0004343 | AP | ARM-2412 | 06-400 | Temporary Facilities and Protection | V-2507 |  | 8284.76 | 8284.76 | Temporary Facilities and Protection - permit and inspection fees
2025-03-14 | PRJ-PAY-ARM-2412-20250314 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1022 | 45.23 | 3573.13 | Project Management and Supervision - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2412-20250314 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 45.8 | 3549.68 | Engineering, BIM and Coordination - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2412-20250314 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1036 | 48.53 | 4076.44 | Field Installation Labor - startup and checkout
2025-03-17 | AP-0004339 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2460 |  | 52.42 | 9435.07 | Controls Panels and Devices - released equipment package
2025-03-21 | PRJ-PAY-ARM-2412-20250321 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 61.55 | 4370.4 | Engineering, BIM and Coordination - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2412-20250321 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1034 | 35.8 | 2774.49 | Field Installation Labor - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2412-20250321 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 33.69 | 2829.95 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-03-24 | AP-0004340 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2474 |  | 78 | 14040.24 | Sheet Metal and Ductwork - fabricated material delivery
2025-03-28 | PRJ-PAY-ARM-2412-20250328 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1032 | 41.02 | 2912.54 | Field Installation Labor - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2412-20250328 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 48.42 | 3752.57 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2412-20250328 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 32.45 | 2725.82 | Sheet Metal Fabrication Labor - field installation time
2025-03-31 | PRJ-PAY-ARM-2412-20250331 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 44.73 | 3176.15 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2412-20250331 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 48.66 | 3770.8 | Sheet Metal Fabrication Labor - field installation time
2025-03-31 | PRJ-PAY-ARM-2412-20250331 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1051 | 36.16 | 3037.44 | Controls Programming and Checkout - coordination and layout
2025-04-03 | AP-0004347 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2201 |  | 58.06 | 10450.42 | Hydronic Piping and Valves - valves and piping lot
2025-04-06 | AP-0004344 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2519 |  | 92.23 | 16601.77 | Insulation and Specialty Material - jobsite material replenishment
2025-04-06 | AP-0004349 | AP | ARM-2412 | 04-200 | Electrical and Controls Subcontract | V-2232 |  | 15425.32 | 15425.32 | Electrical and Controls Subcontract - rigging and specialty support
2025-04-06 | AP-0004351 | AP | ARM-2412 | 05-300 | Freight and Expediting | V-2267 |  | 8432.58 | 8432.58 | Freight and Expediting - permit and inspection fees
2025-04-07 | PRJ-PAY-ARM-2412-20250407 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1018 | 37.57 | 2968.07 | Project Management and Supervision - field installation time
2025-04-07 | PRJ-PAY-ARM-2412-20250407 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 44.49 | 3447.77 | Engineering, BIM and Coordination - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2412-20250407 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1032 | 36.53 | 3068.27 | Field Installation Labor - supervision and planning
2025-04-07 | PRJ-PAY-ARM-2412-20250407 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 36.33 | 3287.74 | Startup, Testing and Commissioning - startup and checkout
2025-04-10 | AP-0004348 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2225 |  | 77.42 | 13935.19 | Insulation and Specialty Material - ductwork release
2025-04-13 | AP-0004345 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2533 |  | 62.16 | 11188.77 | Hydronic Piping and Valves - released equipment package
2025-04-13 | AP-0004350 | AP | ARM-2412 | 04-100 | Insulation Subcontract | V-2253 |  | 22768.58 | 22768.58 | Insulation Subcontract - trade partner progress billing
2025-04-13 | AP-0004352 | AP | ARM-2412 | 05-100 | Equipment Rental and Rigging | V-2282 |  | 5456.11 | 5456.11 | Equipment Rental and Rigging - freight and expediting
2025-04-14 | PRJ-PAY-ARM-2412-20250414 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 52.46 | 3724.8 | Engineering, BIM and Coordination - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2412-20250414 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1030 | 46.66 | 3616.22 | Field Installation Labor - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2412-20250414 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 48.03 | 4034.48 | Startup, Testing and Commissioning - startup and checkout
2025-04-20 | AP-0004346 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2029 |  | 57.35 | 10322.96 | Insulation and Specialty Material - fabricated material delivery
2025-04-21 | PRJ-PAY-ARM-2412-20250421 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1028 | 39.66 | 2815.62 | Field Installation Labor - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2412-20250421 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 61.06 | 4732.35 | Startup, Testing and Commissioning - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2412-20250421 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 37.64 | 3161.63 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2412-20250428 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 52.6 | 3734.45 | Startup, Testing and Commissioning - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2412-20250428 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 44.96 | 3484.37 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2412-20250428 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1047 | 49.61 | 4167.56 | Controls Programming and Checkout - field installation time
2025-04-30 | PRJ-PAY-ARM-2412-20250430 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 38.47 | 2731.14 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2412-20250430 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1045 | 46.9 | 3634.51 | Controls Programming and Checkout - field installation time
2025-04-30 | PRJ-PAY-ARM-2412-20250430 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1052 | 37.49 | 3149.18 | Warranty and Punchlist - coordination and layout
2025-04-30 | PRJ-PAY-ARM-2412-20250430 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1085 | 36.12 | 3268.77 | Closeout and O&M Documentation - supervision and planning
2025-05-06 | AP-0004356 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2336 |  | 79.54 | 14317.6 | Plumbing Fixtures and Piping - ductwork release
2025-05-07 | PRJ-PAY-ARM-2412-20250507 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 48.84 | 3467.57 | Engineering, BIM and Coordination - field installation time
2025-05-07 | PRJ-PAY-ARM-2412-20250507 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1026 | 36.92 | 2860.96 | Field Installation Labor - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2412-20250507 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 50.39 | 4232.47 | Startup, Testing and Commissioning - supervision and planning
2025-05-09 | AP-0004353 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2294 |  | 79.68 | 14341.62 | Major HVAC Equipment - released equipment package
2025-05-09 | AP-0004358 | AP | ARM-2412 | 04-300 | Testing and Balancing Subcontract | V-2355 |  | 14979.42 | 14979.42 | Testing and Balancing Subcontract - trade partner progress billing
2025-05-09 | AP-0004360 | AP | ARM-2412 | 05-400 | Small Tools and Consumables | V-2379 |  | 5408.28 | 5408.28 | Small Tools and Consumables - freight and expediting
2025-05-13 | AP-0004357 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2350 |  | 64.93 | 11687.19 | Major HVAC Equipment - jobsite material replenishment
2025-05-14 | PRJ-PAY-ARM-2412-20250514 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1024 | 48.52 | 3444.9 | Field Installation Labor - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2412-20250514 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 41.23 | 3195.27 | Startup, Testing and Commissioning - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2412-20250514 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 39.32 | 3302.61 | Sheet Metal Fabrication Labor - startup and checkout
2025-05-16 | AP-0004354 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2308 |  | 59.96 | 10793.64 | Plumbing Fixtures and Piping - fabricated material delivery
2025-05-16 | AP-0004359 | AP | ARM-2412 | 04-200 | Electrical and Controls Subcontract | V-2369 |  | 22622.11 | 22622.11 | Electrical and Controls Subcontract - insulation progress invoice
2025-05-16 | AP-0004361 | AP | ARM-2412 | 05-200 | Permits, Fees and Bonds | V-2393 |  | 6035.66 | 6035.66 | Permits, Fees and Bonds - small tools and field consumables
2025-05-21 | PRJ-PAY-ARM-2412-20250521 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 41.08 | 2916.74 | Startup, Testing and Commissioning - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2412-20250521 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 48.72 | 3775.85 | Sheet Metal Fabrication Labor - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2412-20250521 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1043 | 46.17 | 3878.51 | Controls Programming and Checkout - punchlist and closeout labor
2025-05-23 | AP-0004355 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2322 |  | 61.02 | 10984.22 | Major HVAC Equipment - valves and piping lot
2025-05-28 | PRJ-PAY-ARM-2412-20250528 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 52.47 | 3725.59 | Sheet Metal Fabrication Labor - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2412-20250528 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1041 | 50.61 | 3921.97 | Controls Programming and Checkout - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2412-20250528 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1048 | 50.25 | 4220.72 | Warranty and Punchlist - field installation time
2025-05-31 | PRJ-PAY-ARM-2412-20250531 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1039 | 53.06 | 3767.37 | Controls Programming and Checkout - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2412-20250531 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1046 | 34.23 | 2652.64 | Warranty and Punchlist - field installation time
2025-05-31 | PRJ-PAY-ARM-2412-20250531 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 39.65 | 3330.85 | Closeout and O&M Documentation - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2412-20250531 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1086 | 31.94 | 2890.85 | Rework and Quality Correction - supervision and planning
2025-06-07 | PRJ-PAY-ARM-2412-20250607 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1020 | 55.55 | 3944.08 | Field Installation Labor - field installation time
2025-06-07 | PRJ-PAY-ARM-2412-20250607 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 49.15 | 3809.22 | Startup, Testing and Commissioning - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2412-20250607 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 34.05 | 2860.14 | Sheet Metal Fabrication Labor - supervision and planning
2025-06-09 | AP-0004365 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2445 |  | 82.12 | 14782.36 | Controls Panels and Devices - jobsite material replenishment
2025-06-12 | AP-0004362 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2405 |  | 72.83 | 13109.03 | Sheet Metal and Ductwork - fabricated material delivery
2025-06-12 | AP-0004367 | AP | ARM-2412 | 04-400 | Crane, Rigging and Specialty Trade | V-2464 |  | 15707.14 | 15707.14 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-06-12 | AP-0004369 | AP | ARM-2412 | 06-400 | Temporary Facilities and Protection | V-2488 |  | 10874.49 | 10874.49 | Temporary Facilities and Protection - small tools and field consumables
2025-06-14 | PRJ-PAY-ARM-2412-20250614 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 52.44 | 3723.54 | Startup, Testing and Commissioning - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2412-20250614 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 54.52 | 4225.38 | Sheet Metal Fabrication Labor - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2412-20250614 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1039 | 39.7 | 3335.22 | Controls Programming and Checkout - startup and checkout
2025-06-16 | AP-0004366 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2458 |  | 52.67 | 9480.61 | Sheet Metal and Ductwork - released equipment package
2025-06-19 | AP-0004363 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2419 |  | 62.35 | 11223.66 | Controls Panels and Devices - valves and piping lot
2025-06-19 | AP-0004368 | AP | ARM-2412 | 04-300 | Testing and Balancing Subcontract | V-2477 |  | 23803.99 | 23803.99 | Testing and Balancing Subcontract - testing and balancing services
2025-06-19 | AP-0004370 | AP | ARM-2412 | 05-300 | Freight and Expediting | V-2502 |  | 5289.16 | 5289.16 | Freight and Expediting - rental and logistics
2025-06-21 | PRJ-PAY-ARM-2412-20250621 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 51.26 | 3639.69 | Sheet Metal Fabrication Labor - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2412-20250621 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1037 | 40.3 | 3123.04 | Controls Programming and Checkout - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2412-20250621 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1044 | 41.35 | 3473.81 | Warranty and Punchlist - punchlist and closeout labor
2025-06-21 | PRJ-PAY-ARM-2412-20250621 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 26.88 | 2432.27 | Closeout and O&M Documentation - field installation time
2025-06-25 | AP-0004364 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2433 |  | 69.26 | 12466.99 | Sheet Metal and Ductwork - ductwork release
2025-06-28 | PRJ-PAY-ARM-2412-20250628 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1035 | 37.2 | 2641.31 | Controls Programming and Checkout - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2412-20250628 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1042 | 37.91 | 2938.32 | Warranty and Punchlist - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2412-20250628 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 54.05 | 4540.58 | Closeout and O&M Documentation - field installation time
2025-06-28 | PRJ-PAY-ARM-2412-20250628 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1082 | 37.28 | 3374.19 | Rework and Quality Correction - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2412-20250630 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1040 | 42.4 | 3010.15 | Warranty and Punchlist - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2412-20250630 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 44.11 | 3418.42 | Closeout and O&M Documentation - field installation time
2025-06-30 | PRJ-PAY-ARM-2412-20250630 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1080 | 46.9 | 3939.52 | Rework and Quality Correction - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2412-20250630 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1087 | 26.74 | 2633.77 | Project Management and Supervision - supervision and planning
2025-07-05 | AP-0004373 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2018 |  | 58.5 | 10529.14 | Hydronic Piping and Valves - jobsite material replenishment
2025-07-07 | PRJ-PAY-ARM-2412-20250707 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 64.58 | 4585.01 | Startup, Testing and Commissioning - field installation time
2025-07-07 | PRJ-PAY-ARM-2412-20250707 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 37.75 | 2925.98 | Sheet Metal Fabrication Labor - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2412-20250707 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1035 | 44.94 | 3774.72 | Controls Programming and Checkout - supervision and planning
2025-07-12 | AP-0004374 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2060 |  | 80.19 | 14433.84 | Insulation and Specialty Material - released equipment package
2025-07-14 | PRJ-PAY-ARM-2412-20250714 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 37 | 2627.13 | Sheet Metal Fabrication Labor - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2412-20250714 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1033 | 46.8 | 3627.35 | Controls Programming and Checkout - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2412-20250714 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1040 | 37.31 | 3134.41 | Warranty and Punchlist - startup and checkout
2025-07-14 | PRJ-PAY-ARM-2412-20250714 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 36.26 | 3281.69 | Closeout and O&M Documentation - punchlist and closeout labor
2025-07-15 | AP-0004371 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2514 |  | 48.26 | 8687.35 | Hydronic Piping and Valves - valves and piping lot
2025-07-15 | AP-0004376 | AP | ARM-2412 | 04-100 | Insulation Subcontract | V-2225 |  | 22094.52 | 22094.52 | Insulation Subcontract - testing and balancing services
2025-07-15 | AP-0004378 | AP | ARM-2412 | 05-100 | Equipment Rental and Rigging | V-2258 |  | 7003.25 | 7003.25 | Equipment Rental and Rigging - rental and logistics
2025-07-19 | AP-0004375 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2217 |  | 86.32 | 15537.25 | Hydronic Piping and Valves - fabricated material delivery
2025-07-21 | PRJ-PAY-ARM-2412-20250721 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1031 | 48.3 | 3429.05 | Controls Programming and Checkout - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2412-20250721 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1038 | 43.94 | 3405.39 | Warranty and Punchlist - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2412-20250721 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 37.54 | 3153.47 | Closeout and O&M Documentation - punchlist and closeout labor
2025-07-21 | PRJ-PAY-ARM-2412-20250721 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1052 | 38.77 | 3508.38 | Rework and Quality Correction - field installation time
2025-07-22 | AP-0004372 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2528 |  | 92.04 | 16567.39 | Insulation and Specialty Material - ductwork release
2025-07-22 | AP-0004377 | AP | ARM-2412 | 04-400 | Crane, Rigging and Specialty Trade | V-2244 |  | 19915.6 | 19915.6 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-07-22 | AP-0004379 | AP | ARM-2412 | 05-400 | Small Tools and Consumables | V-2277 |  | 7608.97 | 7608.97 | Small Tools and Consumables - permit and inspection fees
2025-07-28 | PRJ-PAY-ARM-2412-20250728 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1036 | 46.79 | 3322.23 | Warranty and Punchlist - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2412-20250728 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 39.43 | 3055.88 | Closeout and O&M Documentation - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2412-20250728 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1050 | 44.09 | 3703.66 | Rework and Quality Correction - field installation time
2025-07-28 | PRJ-PAY-ARM-2412-20250728 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1083 | 29.66 | 2921.91 | Project Management and Supervision - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2412-20250731 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 47.83 | 3395.62 | Closeout and O&M Documentation - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2412-20250731 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1048 | 57.12 | 4426.76 | Rework and Quality Correction - field installation time
2025-07-31 | PRJ-PAY-ARM-2412-20250731 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1081 | 41.56 | 3823.28 | Project Management and Supervision - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2412-20250807 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1022 | 56.85 | 4036.67 | Sheet Metal Fabrication Labor - field installation time
2025-08-07 | PRJ-PAY-ARM-2412-20250807 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1029 | 55.35 | 4289.71 | Controls Programming and Checkout - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2412-20250807 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1036 | 36.93 | 3102.05 | Warranty and Punchlist - supervision and planning
2025-08-08 | AP-0004382 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2317 |  | 85.93 | 15467.96 | Plumbing Fixtures and Piping - released equipment package
2025-08-14 | PRJ-PAY-ARM-2412-20250814 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1027 | 48.9 | 3471.82 | Controls Programming and Checkout - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2412-20250814 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1034 | 44.2 | 3425.47 | Warranty and Punchlist - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2412-20250814 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 62.81 | 5275.9 | Closeout and O&M Documentation - startup and checkout
2025-08-15 | AP-0004383 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2331 |  | 59.4 | 10691.6 | Major HVAC Equipment - fabricated material delivery
2025-08-18 | AP-0004380 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2289 |  | 97.43 | 17536.83 | Plumbing Fixtures and Piping - ductwork release
2025-08-18 | AP-0004385 | AP | ARM-2412 | 04-200 | Electrical and Controls Subcontract | V-2350 |  | 35885.34 | 35885.34 | Electrical and Controls Subcontract - electrical coordination scope
2025-08-18 | AP-0004386 | AP | ARM-2412 | 05-200 | Permits, Fees and Bonds | V-2362 |  | 6224.15 | 6224.15 | Permits, Fees and Bonds - permit and inspection fees
2025-08-21 | PRJ-PAY-ARM-2412-20250821 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1032 | 59.27 | 4208.14 | Warranty and Punchlist - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2412-20250821 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 45.96 | 3562.26 | Closeout and O&M Documentation - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2412-20250821 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1046 | 47.12 | 3958.47 | Rework and Quality Correction - punchlist and closeout labor
2025-08-22 | AP-0004384 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2345 |  | 50.43 | 9076.89 | Plumbing Fixtures and Piping - valves and piping lot
2025-08-25 | AP-0004381 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2303 |  | 51.17 | 9210.48 | Major HVAC Equipment - jobsite material replenishment
2025-08-25 | AP-0004387 | AP | ARM-2412 | 06-400 | Temporary Facilities and Protection | V-2376 |  | 5193.91 | 5193.91 | Temporary Facilities and Protection - freight and expediting
2025-08-28 | PRJ-PAY-ARM-2412-20250828 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 42.94 | 3048.59 | Closeout and O&M Documentation - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2412-20250828 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1044 | 56.26 | 4360.38 | Rework and Quality Correction - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2412-20250828 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1051 | 33.64 | 3095.02 | Project Management and Supervision - field installation time
2025-08-31 | PRJ-PAY-ARM-2412-20250831 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1042 | 33.15 | 2353.88 | Rework and Quality Correction - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2412-20250831 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1049 | 42 | 3591.35 | Project Management and Supervision - field installation time
2025-08-31 | PRJ-PAY-ARM-2412-20250831 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 43.8 | 3679.45 | Engineering, BIM and Coordination - coordination and layout
2025-09-04 | AP-0004389 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2402 |  | 68.48 | 12326.37 | Sheet Metal and Ductwork - released equipment package
2025-09-04 | AP-0004393 | AP | ARM-2412 | 04-200 | Electrical and Controls Subcontract | V-2448 |  | 19911.29 | 19911.29 | Electrical and Controls Subcontract - trade partner progress billing
2025-09-04 | AP-0004395 | AP | ARM-2412 | 05-100 | Equipment Rental and Rigging | V-2472 |  | 9394.24 | 9394.24 | Equipment Rental and Rigging - small tools and field consumables
2025-09-07 | PRJ-PAY-ARM-2412-20250907 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1023 | 61.95 | 4398.58 | Controls Programming and Checkout - field installation time
2025-09-07 | PRJ-PAY-ARM-2412-20250907 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1030 | 56.9 | 4409.68 | Warranty and Punchlist - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2412-20250907 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 44.28 | 3719.52 | Closeout and O&M Documentation - supervision and planning
2025-09-11 | AP-0004390 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2415 |  | 74.52 | 13413.29 | Controls Panels and Devices - fabricated material delivery
2025-09-14 | PRJ-PAY-ARM-2412-20250914 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1028 | 57.2 | 4061.09 | Warranty and Punchlist - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2412-20250914 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 51.37 | 3981.52 | Closeout and O&M Documentation - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2412-20250914 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1042 | 47.95 | 4027.91 | Rework and Quality Correction - startup and checkout
2025-09-18 | AP-0004391 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2429 |  | 64.02 | 11523.57 | Sheet Metal and Ductwork - valves and piping lot
2025-09-21 | AP-0004388 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2388 |  | 101.32 | 18237.81 | Controls Panels and Devices - jobsite material replenishment
2025-09-21 | AP-0004392 | AP | ARM-2412 | 04-300 | Testing and Balancing Subcontract | V-2436 |  | 17633.53 | 17633.53 | Testing and Balancing Subcontract - rigging and specialty support
2025-09-21 | AP-0004394 | AP | ARM-2412 | 05-300 | Freight and Expediting | V-2458 |  | 5297.22 | 5297.22 | Freight and Expediting - freight and expediting
2025-09-21 | PRJ-PAY-ARM-2412-20250921 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 53.83 | 3822.16 | Closeout and O&M Documentation - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2412-20250921 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1040 | 43.27 | 3353.63 | Rework and Quality Correction - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2412-20250921 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1047 | 39.5 | 3634.16 | Project Management and Supervision - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2412-20250928 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1038 | 48.06 | 3412.22 | Rework and Quality Correction - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2412-20250928 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1045 | 35.75 | 3056.46 | Project Management and Supervision - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2412-20250928 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 40.91 | 3436.36 | Engineering, BIM and Coordination - field installation time
2025-09-30 | PRJ-PAY-ARM-2412-20250930 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1043 | 36.36 | 2872.12 | Project Management and Supervision - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2412-20250930 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 52.41 | 4061.99 | Engineering, BIM and Coordination - field installation time
2025-09-30 | PRJ-PAY-ARM-2412-20250930 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1083 | 38.73 | 3253.64 | Field Installation Labor - coordination and layout
2025-10-07 | AP-0004397 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2498 |  | 87.79 | 15802.31 | Hydronic Piping and Valves - fabricated material delivery
2025-10-07 | AP-0004402 | AP | ARM-2412 | 05-200 | Permits, Fees and Bonds | V-2098 |  | 5315.29 | 5315.29 | Permits, Fees and Bonds - rental and logistics
2025-10-07 | PRJ-PAY-ARM-2412-20251007 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1024 | 45.97 | 3263.67 | Warranty and Punchlist - field installation time
2025-10-07 | PRJ-PAY-ARM-2412-20251007 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1031 | 38.1 | 2952.96 | Closeout and O&M Documentation - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2412-20251007 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1038 | 48.35 | 4061.61 | Rework and Quality Correction - supervision and planning
2025-10-14 | AP-0004398 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2512 |  | 54.26 | 9766.93 | Insulation and Specialty Material - valves and piping lot
2025-10-14 | PRJ-PAY-ARM-2412-20251014 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1029 | 44.15 | 3134.84 | Closeout and O&M Documentation - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2412-20251014 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1036 | 37.45 | 2902.01 | Rework and Quality Correction - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2412-20251014 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1043 | 34.43 | 3168 | Project Management and Supervision - startup and checkout
2025-10-21 | AP-0004399 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2526 |  | 63.58 | 11443.59 | Hydronic Piping and Valves - ductwork release
2025-10-21 | PRJ-PAY-ARM-2412-20251021 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1034 | 33.44 | 2374.21 | Rework and Quality Correction - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2412-20251021 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1041 | 33.86 | 2894.91 | Project Management and Supervision - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2412-20251021 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1048 | 37.68 | 3165.18 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-10-24 | AP-0004396 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2484 |  | 66.72 | 12008.74 | Insulation and Specialty Material - released equipment package
2025-10-24 | AP-0004400 | AP | ARM-2412 | 04-400 | Crane, Rigging and Specialty Trade | V-2533 |  | 29957.62 | 29957.62 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-10-24 | AP-0004401 | AP | ARM-2412 | 05-400 | Small Tools and Consumables | V-2025 |  | 5578.39 | 5578.39 | Small Tools and Consumables - small tools and field consumables
2025-10-28 | PRJ-PAY-ARM-2412-20251028 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1039 | 34.87 | 2754.96 | Project Management and Supervision - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2412-20251028 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1046 | 35.55 | 2755.38 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2412-20251028 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1053 | 37.67 | 3164.69 | Field Installation Labor - field installation time
2025-10-31 | PRJ-PAY-ARM-2412-20251031 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 42.23 | 2998.33 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2412-20251031 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1051 | 36.29 | 2812.59 | Field Installation Labor - field installation time
2025-10-31 | PRJ-PAY-ARM-2412-20251031 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1084 | 46.37 | 3894.81 | Startup, Testing and Commissioning - coordination and layout
2025-11-03 | AP-0004403 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2220 |  | 85.99 | 15477.53 | Major HVAC Equipment - fabricated material delivery
2025-11-03 | AP-0004407 | AP | ARM-2412 | 04-100 | Insulation Subcontract | V-2284 |  | 28989.72 | 28989.72 | Insulation Subcontract - insulation progress invoice
2025-11-03 | AP-0004408 | AP | ARM-2412 | 06-400 | Temporary Facilities and Protection | V-2296 |  | 8822.96 | 8822.96 | Temporary Facilities and Protection - rental and logistics
2025-11-07 | PRJ-PAY-ARM-2412-20251107 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1025 | 45.22 | 3210.38 | Closeout and O&M Documentation - field installation time
2025-11-07 | PRJ-PAY-ARM-2412-20251107 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1032 | 39.46 | 3058.47 | Rework and Quality Correction - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2412-20251107 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1039 | 23.87 | 2196.37 | Project Management and Supervision - supervision and planning
2025-11-10 | AP-0004404 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2241 |  | 67.85 | 12212.57 | Plumbing Fixtures and Piping - valves and piping lot
2025-11-14 | PRJ-PAY-ARM-2412-20251114 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1030 | 37.53 | 2664.7 | Rework and Quality Correction - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2412-20251114 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1037 | 25.77 | 2203.46 | Project Management and Supervision - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2412-20251114 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 34.39 | 2888.43 | Engineering, BIM and Coordination - startup and checkout
2025-11-17 | AP-0004405 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2258 |  | 37.32 | 6717.31 | Major HVAC Equipment - ductwork release
2025-11-21 | PRJ-PAY-ARM-2412-20251121 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1035 | 35.73 | 2822.76 | Project Management and Supervision - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2412-20251121 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1042 | 35.13 | 2722.4 | Engineering, BIM and Coordination - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2412-20251121 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1049 | 28.96 | 2432.82 | Field Installation Labor - punchlist and closeout labor
2025-11-24 | AP-0004406 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2277 |  | 74.94 | 13488.64 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-11-28 | PRJ-PAY-ARM-2412-20251128 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 35.24 | 2502.02 | Engineering, BIM and Coordination - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2412-20251128 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1047 | 48.9 | 3789.44 | Field Installation Labor - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2412-20251128 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1080 | 31.36 | 2634.39 | Startup, Testing and Commissioning - field installation time
2025-11-30 | PRJ-PAY-ARM-2412-20251130 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1045 | 44.48 | 3157.82 | Field Installation Labor - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2412-20251130 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1052 | 50.47 | 3911.06 | Startup, Testing and Commissioning - field installation time
2025-11-30 | PRJ-PAY-ARM-2412-20251130 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1085 | 31.66 | 2659.84 | Sheet Metal Fabrication Labor - coordination and layout
2025-12-06 | AP-0004409 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2310 |  | 79.28 | 14270.21 | Sheet Metal and Ductwork - valves and piping lot
2025-12-06 | AP-0004412 | AP | ARM-2412 | 04-200 | Electrical and Controls Subcontract | V-2346 |  | 26470.61 | 26470.61 | Electrical and Controls Subcontract - testing and balancing services
2025-12-06 | AP-0004413 | AP | ARM-2412 | 05-100 | Equipment Rental and Rigging | V-2358 |  | 6208.76 | 6208.76 | Equipment Rental and Rigging - permit and inspection fees
2025-12-07 | PRJ-PAY-ARM-2412-20251207 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1026 | 26.84 | 1905.58 | Rework and Quality Correction - field installation time
2025-12-07 | PRJ-PAY-ARM-2412-20251207 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1033 | 31.84 | 2722.56 | Project Management and Supervision - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2412-20251207 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 30.68 | 2577.41 | Engineering, BIM and Coordination - supervision and planning
2025-12-13 | AP-0004410 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2324 |  | 88.13 | 15863.22 | Controls Panels and Devices - ductwork release
2025-12-13 | AP-0004414 | AP | ARM-2412 | 05-400 | Small Tools and Consumables | V-2372 |  | 4620.12 | 4620.12 | Small Tools and Consumables - freight and expediting
2025-12-14 | PRJ-PAY-ARM-2412-20251214 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1031 | 24.95 | 1971.29 | Project Management and Supervision - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2412-20251214 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1038 | 32.35 | 2507.19 | Engineering, BIM and Coordination - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2412-20251214 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1045 | 34.91 | 2932.73 | Field Installation Labor - startup and checkout
2025-12-20 | AP-0004411 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2338 |  | 59.87 | 10775.7 | Sheet Metal and Ductwork - jobsite material replenishment
2025-12-21 | PRJ-PAY-ARM-2412-20251221 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1036 | 35.29 | 2505.84 | Engineering, BIM and Coordination - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2412-20251221 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1043 | 42.52 | 3295.3 | Field Installation Labor - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2412-20251221 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1050 | 29.65 | 2490.61 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2412-20251228 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1041 | 41.11 | 2918.87 | Field Installation Labor - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2412-20251228 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 41.19 | 3192.06 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2412-20251228 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1081 | 34.84 | 2926.66 | Sheet Metal Fabrication Labor - field installation time
2025-12-31 | PRJ-PAY-ARM-2412-20251231 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 45.06 | 3199.19 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2412-20251231 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1053 | 30.23 | 2342.75 | Sheet Metal Fabrication Labor - field installation time
2025-12-31 | PRJ-PAY-ARM-2412-20251231 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1086 | 40.73 | 3421.09 | Controls Programming and Checkout - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2412-20260107 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1027 | 19.5 | 1540.31 | Project Management and Supervision - field installation time
2026-01-07 | PRJ-PAY-ARM-2412-20260107 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1034 | 28.85 | 2236.11 | Engineering, BIM and Coordination - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2412-20260107 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1041 | 23 | 1931.72 | Field Installation Labor - supervision and planning
2026-01-09 | AP-0004415 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2384 |  | 61.15 | 11006.38 | Hydronic Piping and Valves - ductwork release
2026-01-09 | AP-0004418 | AP | ARM-2412 | 04-300 | Testing and Balancing Subcontract | V-2421 |  | 21799.54 | 21799.54 | Testing and Balancing Subcontract - electrical coordination scope
2026-01-09 | AP-0004419 | AP | ARM-2412 | 05-200 | Permits, Fees and Bonds | V-2433 |  | 7582.45 | 7582.45 | Permits, Fees and Bonds - freight and expediting
2026-01-14 | PRJ-PAY-ARM-2412-20260114 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1032 | 31.18 | 2213.79 | Engineering, BIM and Coordination - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2412-20260114 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1039 | 30.79 | 2385.84 | Field Installation Labor - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2412-20260114 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 21.27 | 1786.69 | Startup, Testing and Commissioning - startup and checkout
2026-01-16 | AP-0004416 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2398 |  | 55.28 | 9950.91 | Insulation and Specialty Material - jobsite material replenishment
2026-01-21 | PRJ-PAY-ARM-2412-20260121 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1037 | 36.38 | 2583.28 | Field Installation Labor - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2412-20260121 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1044 | 26.39 | 2045.02 | Startup, Testing and Commissioning - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2412-20260121 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1051 | 27.77 | 2332.48 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-01-23 | AP-0004417 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2412 |  | 73.13 | 13163.73 | Hydronic Piping and Valves - released equipment package
2026-01-28 | PRJ-PAY-ARM-2412-20260128 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 30.87 | 2192.08 | Startup, Testing and Commissioning - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2412-20260128 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 35.44 | 2746.88 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2412-20260128 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1082 | 23.39 | 1964.38 | Controls Programming and Checkout - field installation time
2026-01-31 | PRJ-PAY-ARM-2412-20260131 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 26.92 | 1911.64 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2412-20260131 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1080 | 33.17 | 2570.67 | Controls Programming and Checkout - field installation time
2026-01-31 | PRJ-PAY-ARM-2412-20260131 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1087 | 21.24 | 1784.52 | Warranty and Punchlist - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2412-20260207 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1028 | 34.03 | 2416.15 | Engineering, BIM and Coordination - field installation time
2026-02-07 | PRJ-PAY-ARM-2412-20260207 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1035 | 34.86 | 2701.53 | Field Installation Labor - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2412-20260207 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 38.58 | 3240.37 | Startup, Testing and Commissioning - supervision and planning
2026-02-12 | AP-0004420 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2445 |  | 63.15 | 11366.9 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-02-12 | AP-0004423 | AP | ARM-2412 | 04-400 | Crane, Rigging and Specialty Trade | V-2481 |  | 22455.71 | 22455.71 | Crane, Rigging and Specialty Trade - rigging and specialty support
2026-02-12 | AP-0004424 | AP | ARM-2412 | 05-300 | Freight and Expediting | V-2493 |  | 7145.01 | 7145.01 | Freight and Expediting - small tools and field consumables
2026-02-14 | PRJ-PAY-ARM-2412-20260214 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1033 | 49.49 | 3513.66 | Field Installation Labor - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2412-20260214 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1040 | 34.79 | 2695.86 | Startup, Testing and Commissioning - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2412-20260214 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 34.53 | 2900.34 | Sheet Metal Fabrication Labor - startup and checkout
2026-02-19 | AP-0004421 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2458 |  | 63.69 | 11463.63 | Major HVAC Equipment - released equipment package
2026-02-21 | PRJ-PAY-ARM-2412-20260221 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1038 | 43.37 | 3079.34 | Startup, Testing and Commissioning - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2412-20260221 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1045 | 39.82 | 3086.16 | Sheet Metal Fabrication Labor - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2412-20260221 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1052 | 34.16 | 2869.2 | Controls Programming and Checkout - punchlist and closeout labor
2026-02-25 | AP-0004422 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2472 |  | 88.65 | 15956.61 | Plumbing Fixtures and Piping - fabricated material delivery
2026-02-28 | PRJ-PAY-ARM-2412-20260228 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 38.53 | 2735.93 | Sheet Metal Fabrication Labor - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2412-20260228 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1050 | 30.97 | 2400.24 | Controls Programming and Checkout - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2412-20260228 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1083 | 36.49 | 3065.5 | Warranty and Punchlist - field installation time
2026-03-05 | AP-0004427 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2534 |  | 89.22 | 16058.77 | Controls Panels and Devices - valves and piping lot
2026-03-07 | PRJ-PAY-ARM-2412-20260307 | PAY | ARM-2412 | 03-100 | Field Installation Labor |  | E-1029 | 45.35 | 3220.16 | Field Installation Labor - field installation time
2026-03-07 | PRJ-PAY-ARM-2412-20260307 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1036 | 31.84 | 2467.43 | Startup, Testing and Commissioning - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2412-20260307 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 31.53 | 2648.47 | Sheet Metal Fabrication Labor - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2412-20260314 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1034 | 44.45 | 3156.11 | Startup, Testing and Commissioning - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2412-20260314 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1041 | 25.06 | 1942.4 | Sheet Metal Fabrication Labor - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2412-20260314 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1048 | 37.72 | 3168.77 | Controls Programming and Checkout - startup and checkout
2026-03-15 | AP-0004425 | AP | ARM-2412 | 02-510 | Controls Panels and Devices | V-2507 |  | 65.69 | 11824.56 | Controls Panels and Devices - released equipment package
2026-03-15 | AP-0004428 | AP | ARM-2412 | 04-100 | Insulation Subcontract | V-2021 |  | 25404.85 | 25404.85 | Insulation Subcontract - trade partner progress billing
2026-03-15 | AP-0004429 | AP | ARM-2412 | 05-400 | Small Tools and Consumables | V-2060 |  | 9941.03 | 9941.03 | Small Tools and Consumables - rental and logistics
2026-03-21 | PRJ-PAY-ARM-2412-20260321 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1039 | 44.13 | 3133.54 | Sheet Metal Fabrication Labor - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2412-20260321 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1046 | 24.54 | 1901.7 | Controls Programming and Checkout - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2412-20260321 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1053 | 29.4 | 2469.77 | Warranty and Punchlist - punchlist and closeout labor
2026-03-22 | AP-0004426 | AP | ARM-2412 | 02-210 | Sheet Metal and Ductwork | V-2521 |  | 53.73 | 9671.66 | Sheet Metal and Ductwork - fabricated material delivery
2026-03-28 | PRJ-PAY-ARM-2412-20260328 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1044 | 33.24 | 2360.39 | Controls Programming and Checkout - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2412-20260328 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1051 | 25.76 | 1996.11 | Warranty and Punchlist - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2412-20260328 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1084 | 28.49 | 2393.57 | Closeout and O&M Documentation - field installation time
2026-03-31 | PRJ-PAY-ARM-2412-20260331 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1049 | 34.24 | 2430.78 | Warranty and Punchlist - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2412-20260331 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1082 | 34.64 | 2684.69 | Closeout and O&M Documentation - field installation time
2026-03-31 | PRJ-PAY-ARM-2412-20260331 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1089 | 18.82 | 1581.1 | Rework and Quality Correction - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2412-20260407 | PAY | ARM-2412 | 03-200 | Startup, Testing and Commissioning |  | E-1030 | 41.35 | 2935.9 | Startup, Testing and Commissioning - field installation time
2026-04-07 | PRJ-PAY-ARM-2412-20260407 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1037 | 47.16 | 3654.72 | Sheet Metal Fabrication Labor - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2412-20260407 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1044 | 35.95 | 3020.14 | Controls Programming and Checkout - supervision and planning
2026-04-08 | AP-0004432 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2256 |  | 69.96 | 12592.88 | Insulation and Specialty Material - ductwork release
2026-04-14 | PRJ-PAY-ARM-2412-20260414 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1035 | 36.48 | 2590.41 | Sheet Metal Fabrication Labor - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2412-20260414 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1042 | 49.48 | 3834.6 | Controls Programming and Checkout - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2412-20260414 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1049 | 27.38 | 2299.6 | Warranty and Punchlist - startup and checkout
2026-04-15 | AP-0004433 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2275 |  | 55.67 | 10020.51 | Hydronic Piping and Valves - jobsite material replenishment
2026-04-18 | AP-0004430 | AP | ARM-2412 | 02-610 | Insulation and Specialty Material | V-2217 |  | 70.9 | 12762.63 | Insulation and Specialty Material - fabricated material delivery
2026-04-18 | AP-0004434 | AP | ARM-2412 | 04-200 | Electrical and Controls Subcontract | V-2282 |  | 27540.33 | 27540.33 | Electrical and Controls Subcontract - insulation progress invoice
2026-04-18 | AP-0004435 | AP | ARM-2412 | 06-400 | Temporary Facilities and Protection | V-2294 |  | 10014.66 | 10014.66 | Temporary Facilities and Protection - permit and inspection fees
2026-04-21 | PRJ-PAY-ARM-2412-20260421 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1040 | 33.01 | 2343.77 | Controls Programming and Checkout - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2412-20260421 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1047 | 38.91 | 3015.63 | Warranty and Punchlist - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2412-20260421 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1080 | 29.61 | 2487.59 | Closeout and O&M Documentation - punchlist and closeout labor
2026-04-25 | AP-0004431 | AP | ARM-2412 | 02-310 | Hydronic Piping and Valves | V-2237 |  | 53.83 | 9689.97 | Hydronic Piping and Valves - valves and piping lot
2026-04-28 | PRJ-PAY-ARM-2412-20260428 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1045 | 32.97 | 2340.59 | Warranty and Punchlist - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2412-20260428 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1052 | 28.38 | 2199.73 | Closeout and O&M Documentation - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2412-20260428 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1085 | 38.62 | 3244.46 | Rework and Quality Correction - field installation time
2026-04-30 | PRJ-PAY-ARM-2412-20260430 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1050 | 41.44 | 2942.42 | Closeout and O&M Documentation - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2412-20260430 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1083 | 34.15 | 2646.41 | Rework and Quality Correction - field installation time
2026-04-30 | PRJ-PAY-ARM-2412-20260430 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1090 | 32.68 | 3006.36 | Project Management and Supervision - coordination and layout
2026-05-04 | AP-0004437 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2322 |  | 69.28 | 12471.06 | Plumbing Fixtures and Piping - ductwork release
2026-05-07 | PRJ-PAY-ARM-2412-20260507 | PAY | ARM-2412 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 38.35 | 2723.03 | Sheet Metal Fabrication Labor - field installation time
2026-05-07 | PRJ-PAY-ARM-2412-20260507 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1038 | 50.8 | 3936.96 | Controls Programming and Checkout - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2412-20260507 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1045 | 34.73 | 2917.33 | Warranty and Punchlist - supervision and planning
2026-05-11 | AP-0004438 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2336 |  | 51.21 | 9217.66 | Major HVAC Equipment - jobsite material replenishment
2026-05-14 | PRJ-PAY-ARM-2412-20260514 | PAY | ARM-2412 | 03-400 | Controls Programming and Checkout |  | E-1036 | 40.05 | 2843.65 | Controls Programming and Checkout - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2412-20260514 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1043 | 32.18 | 2493.58 | Warranty and Punchlist - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2412-20260514 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1050 | 39.01 | 3276.69 | Closeout and O&M Documentation - startup and checkout
2026-05-18 | AP-0004439 | AP | ARM-2412 | 02-410 | Plumbing Fixtures and Piping | V-2350 |  | 108.51 | 19532.06 | Plumbing Fixtures and Piping - released equipment package
2026-05-21 | AP-0004436 | AP | ARM-2412 | 02-110 | Major HVAC Equipment | V-2308 |  | 60.57 | 10902.84 | Major HVAC Equipment - valves and piping lot
2026-05-21 | AP-0004440 | AP | ARM-2412 | 04-300 | Testing and Balancing Subcontract | V-2357 |  | 31548.5 | 31548.5 | Testing and Balancing Subcontract - testing and balancing services
2026-05-21 | AP-0004441 | AP | ARM-2412 | 05-100 | Equipment Rental and Rigging | V-2369 |  | 9601.72 | 9601.72 | Equipment Rental and Rigging - freight and expediting
2026-05-21 | PRJ-PAY-ARM-2412-20260521 | PAY | ARM-2412 | 06-100 | Warranty and Punchlist |  | E-1041 | 44.97 | 3192.68 | Warranty and Punchlist - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2412-20260521 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1048 | 36.38 | 2819.75 | Closeout and O&M Documentation - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2412-20260521 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1081 | 30.16 | 2533.2 | Rework and Quality Correction - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2412-20260528 | PAY | ARM-2412 | 06-200 | Closeout and O&M Documentation |  | E-1046 | 40.14 | 2850.1 | Closeout and O&M Documentation - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2412-20260528 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1053 | 42.27 | 3275.58 | Rework and Quality Correction - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2412-20260528 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1086 | 35.97 | 3309.55 | Project Management and Supervision - field installation time
2026-05-31 | PRJ-PAY-ARM-2412-20260531 | PAY | ARM-2412 | 06-300 | Rework and Quality Correction |  | E-1051 | 50.83 | 3609.11 | Rework and Quality Correction - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2412-20260531 | PAY | ARM-2412 | 01-100 | Project Management and Supervision |  | E-1084 | 40.26 | 3442.59 | Project Management and Supervision - field installation time
2026-05-31 | PRJ-PAY-ARM-2412-20260531 | PAY | ARM-2412 | 01-200 | Engineering, BIM and Coordination |  | E-1091 | 40.63 | 3413.12 | Engineering, BIM and Coordination - coordination and layout
2025-01-05 | AP-0004480 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2474 |  | 42.93 | 7727.83 | Major HVAC Equipment - fabricated material delivery
2025-01-07 | PRJ-PAY-ARM-2417-20250107 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 59.52 | 4225.62 | Sheet Metal Fabrication Labor - field installation time
2025-01-07 | PRJ-PAY-ARM-2417-20250107 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1020 | 43.83 | 3397.18 | Controls Programming and Checkout - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2417-20250107 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1027 | 45.86 | 3852.1 | Warranty and Punchlist - supervision and planning
2025-01-12 | AP-0004481 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2488 |  | 76.54 | 13777.09 | Plumbing Fixtures and Piping - valves and piping lot
2025-01-14 | PRJ-PAY-ARM-2417-20250114 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1018 | 54.92 | 3899.18 | Controls Programming and Checkout - coordination and layout
2025-01-14 | PRJ-PAY-ARM-2417-20250114 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1025 | 55.36 | 4290.16 | Warranty and Punchlist - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2417-20250114 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 35.47 | 2979.44 | Closeout and O&M Documentation - startup and checkout
2025-01-15 | AP-0004478 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2446 |  | 43.77 | 7878.08 | Major HVAC Equipment - jobsite material replenishment
2025-01-15 | AP-0004484 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2519 |  | 20200.07 | 20200.07 | Insulation Subcontract - rigging and specialty support
2025-01-15 | AP-0004486 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2021 |  | 6571.04 | 6571.04 | Freight and Expediting - rental and logistics
2025-01-19 | AP-0004482 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2502 |  | 60.91 | 10964.13 | Major HVAC Equipment - ductwork release
2025-01-21 | PRJ-PAY-ARM-2417-20250121 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1023 | 59.65 | 4235.14 | Warranty and Punchlist - supervision and planning
2025-01-21 | PRJ-PAY-ARM-2417-20250121 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 42.93 | 3326.98 | Closeout and O&M Documentation - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2417-20250121 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1037 | 55.19 | 4635.8 | Rework and Quality Correction - punchlist and closeout labor
2025-01-22 | AP-0004479 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2460 |  | 91.16 | 16408.34 | Plumbing Fixtures and Piping - released equipment package
2025-01-22 | AP-0004485 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2533 |  | 22131.61 | 22131.61 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-01-22 | AP-0004487 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2094 |  | 6312.51 | 6312.51 | Equipment Rental and Rigging - permit and inspection fees
2025-01-25 | AP-0004483 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2515 |  | 73.24 | 13183.83 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-01-28 | PRJ-PAY-ARM-2417-20250128 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 51.32 | 3643.79 | Closeout and O&M Documentation - startup and checkout
2025-01-28 | PRJ-PAY-ARM-2417-20250128 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1035 | 40.49 | 3138 | Rework and Quality Correction - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2417-20250128 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1042 | 41.87 | 3852.09 | Project Management and Supervision - field installation time
2025-01-28 | PRJ-PAY-ARM-2417-20250128 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 32.95 | 2982.25 | Engineering, BIM and Coordination - coordination and layout
2025-01-31 | PRJ-PAY-ARM-2417-20250131 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1033 | 56.51 | 4012.23 | Rework and Quality Correction - punchlist and closeout labor
2025-01-31 | PRJ-PAY-ARM-2417-20250131 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1040 | 38.12 | 3259.14 | Project Management and Supervision - field installation time
2025-01-31 | PRJ-PAY-ARM-2417-20250131 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 47.5 | 3989.95 | Engineering, BIM and Coordination - coordination and layout
2025-01-31 | PRJ-PAY-ARM-2417-20250131 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1080 | 31.58 | 2858.22 | Field Installation Labor - supervision and planning
2025-02-05 | AP-0004493 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2303 |  | 53.51 | 9631.43 | Controls Panels and Devices - released equipment package
2025-02-07 | PRJ-PAY-ARM-2417-20250207 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1013 | 44.36 | 3149.45 | Controls Programming and Checkout - field installation time
2025-02-07 | PRJ-PAY-ARM-2417-20250207 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1021 | 41.21 | 3193.76 | Warranty and Punchlist - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2417-20250207 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 50.61 | 4251.29 | Closeout and O&M Documentation - supervision and planning
2025-02-07 | PRJ-PAY-ARM-2417-20250207 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1035 | 49.51 | 4480.24 | Rework and Quality Correction - startup and checkout
2025-02-08 | AP-0004490 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2256 |  | 92.18 | 16592.22 | Sheet Metal and Ductwork - valves and piping lot
2025-02-08 | AP-0004498 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2358 |  | 6666.46 | 6666.46 | Temporary Facilities and Protection - small tools and field consumables
2025-02-14 | PRJ-PAY-ARM-2417-20250214 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1019 | 45.67 | 3242.5 | Warranty and Punchlist - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2417-20250214 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 49.45 | 3832.66 | Closeout and O&M Documentation - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2417-20250214 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1033 | 34.63 | 2909.13 | Rework and Quality Correction - startup and checkout
2025-02-14 | PRJ-PAY-ARM-2417-20250214 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1040 | 30.52 | 3005.74 | Project Management and Supervision - punchlist and closeout labor
2025-02-14 | PRJ-PAY-ARM-2417-20250214 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 35.81 | 3473.75 | Engineering, BIM and Coordination - field installation time
2025-02-15 | AP-0004491 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2275 |  | 78.13 | 14063.89 | Controls Panels and Devices - ductwork release
2025-02-18 | AP-0004488 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2217 |  | 44.72 | 8050.01 | Sheet Metal and Ductwork - released equipment package
2025-02-18 | AP-0004494 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2307 |  | 18612.03 | 18612.03 | Electrical and Controls Subcontract - trade partner progress billing
2025-02-18 | AP-0004496 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2331 |  | 4272.9 | 4272.9 | Small Tools and Consumables - permit and inspection fees
2025-02-21 | PRJ-PAY-ARM-2417-20250221 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 58.51 | 4154.38 | Closeout and O&M Documentation - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2417-20250221 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1031 | 44.04 | 3412.78 | Rework and Quality Correction - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2417-20250221 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1038 | 37.07 | 3410.53 | Project Management and Supervision - punchlist and closeout labor
2025-02-21 | PRJ-PAY-ARM-2417-20250221 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1045 | 43.64 | 3948.98 | Engineering, BIM and Coordination - field installation time
2025-02-21 | PRJ-PAY-ARM-2417-20250221 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1052 | 35.58 | 3451.3 | Field Installation Labor - coordination and layout
2025-02-22 | AP-0004492 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2289 |  | 42.07 | 7571.74 | Sheet Metal and Ductwork - jobsite material replenishment
2025-02-25 | AP-0004489 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2237 |  | 72.58 | 13064.61 | Controls Panels and Devices - fabricated material delivery
2025-02-25 | AP-0004495 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2320 |  | 26018.14 | 26018.14 | Insulation Subcontract - insulation progress invoice
2025-02-25 | AP-0004497 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2345 |  | 7318.45 | 7318.45 | Permits, Fees and Bonds - freight and expediting
2025-02-28 | PRJ-PAY-ARM-2417-20250228 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1029 | 54.2 | 3848 | Rework and Quality Correction - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2417-20250228 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1036 | 41.1 | 3513.85 | Project Management and Supervision - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2417-20250228 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 38.1 | 3200.4 | Engineering, BIM and Coordination - field installation time
2025-02-28 | PRJ-PAY-ARM-2417-20250228 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1050 | 35.95 | 3253.83 | Field Installation Labor - coordination and layout
2025-02-28 | PRJ-PAY-ARM-2417-20250228 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1083 | 54.03 | 5241.33 | Startup, Testing and Commissioning - supervision and planning
2025-03-04 | AP-0004500 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2383 |  | 81.97 | 14754 | Insulation and Specialty Material - valves and piping lot
2025-03-04 | AP-0004507 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2465 |  | 35046.77 | 35046.77 | Electrical and Controls Subcontract - testing and balancing services
2025-03-04 | AP-0004509 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2490 |  | 5512.86 | 5512.86 | Freight and Expediting - small tools and field consumables
2025-03-07 | PRJ-PAY-ARM-2417-20250307 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1014 | 59.48 | 4223.41 | Warranty and Punchlist - field installation time
2025-03-07 | PRJ-PAY-ARM-2417-20250307 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 57.77 | 4477.49 | Closeout and O&M Documentation - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2417-20250307 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1029 | 46.94 | 3942.73 | Rework and Quality Correction - supervision and planning
2025-03-07 | PRJ-PAY-ARM-2417-20250307 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1036 | 32.56 | 3207.29 | Project Management and Supervision - startup and checkout
2025-03-08 | AP-0004504 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2438 |  | 45.05 | 8109.13 | Insulation and Specialty Material - fabricated material delivery
2025-03-11 | AP-0004501 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2396 |  | 70.47 | 12683.92 | Hydronic Piping and Valves - ductwork release
2025-03-11 | AP-0004510 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2503 |  | 7881.22 | 7881.22 | Equipment Rental and Rigging - rental and logistics
2025-03-14 | PRJ-PAY-ARM-2417-20250314 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 45.82 | 3253.29 | Closeout and O&M Documentation - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2417-20250314 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1027 | 33.59 | 2603.13 | Rework and Quality Correction - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2417-20250314 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1034 | 43.79 | 4028.66 | Project Management and Supervision - startup and checkout
2025-03-14 | PRJ-PAY-ARM-2417-20250314 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 42.32 | 3830.34 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-03-14 | PRJ-PAY-ARM-2417-20250314 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1048 | 41.01 | 3978.43 | Field Installation Labor - field installation time
2025-03-15 | AP-0004505 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2450 |  | 58.34 | 10501.13 | Hydronic Piping and Valves - valves and piping lot
2025-03-18 | AP-0004502 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2410 |  | 91.17 | 16411.04 | Insulation and Specialty Material - jobsite material replenishment
2025-03-21 | AP-0004499 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2369 |  | 78.04 | 14046.94 | Hydronic Piping and Valves - fabricated material delivery
2025-03-21 | AP-0004506 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2452 |  | 22070.91 | 22070.91 | Testing and Balancing Subcontract - insulation progress invoice
2025-03-21 | AP-0004508 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2476 |  | 6472.93 | 6472.93 | Temporary Facilities and Protection - freight and expediting
2025-03-21 | PRJ-PAY-ARM-2417-20250321 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1025 | 47.79 | 3392.75 | Rework and Quality Correction - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2417-20250321 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1032 | 34.34 | 2935.93 | Project Management and Supervision - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2417-20250321 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 49.98 | 4198 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-03-21 | PRJ-PAY-ARM-2417-20250321 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1046 | 46.68 | 4224.74 | Field Installation Labor - field installation time
2025-03-21 | PRJ-PAY-ARM-2417-20250321 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1053 | 37.08 | 3596.57 | Startup, Testing and Commissioning - coordination and layout
2025-03-25 | AP-0004503 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2424 |  | 71.64 | 12895.42 | Hydronic Piping and Valves - released equipment package
2025-03-28 | PRJ-PAY-ARM-2417-20250328 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1030 | 55.14 | 4355.83 | Project Management and Supervision - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2417-20250328 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 41.27 | 3198.62 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2417-20250328 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1044 | 31.89 | 2678.61 | Field Installation Labor - field installation time
2025-03-28 | PRJ-PAY-ARM-2417-20250328 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 38.03 | 3441.49 | Startup, Testing and Commissioning - coordination and layout
2025-03-28 | PRJ-PAY-ARM-2417-20250328 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1084 | 36.47 | 3537.38 | Sheet Metal Fabrication Labor - supervision and planning
2025-03-31 | PRJ-PAY-ARM-2417-20250331 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 45.91 | 3259.28 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2417-20250331 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1042 | 40.14 | 3111.11 | Field Installation Labor - field installation time
2025-03-31 | PRJ-PAY-ARM-2417-20250331 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 46.62 | 3916.22 | Startup, Testing and Commissioning - coordination and layout
2025-03-31 | PRJ-PAY-ARM-2417-20250331 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 55.73 | 5043.53 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-04 | AP-0004515 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2217 |  | 75.11 | 13519.7 | Plumbing Fixtures and Piping - fabricated material delivery
2025-04-07 | AP-0004512 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2528 |  | 51.07 | 9192.31 | Major HVAC Equipment - ductwork release
2025-04-07 | AP-0004521 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2301 |  | 24976.54 | 24976.54 | Testing and Balancing Subcontract - electrical coordination scope
2025-04-07 | AP-0004524 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2338 |  | 8205 | 8205 | Small Tools and Consumables - rental and logistics
2025-04-07 | PRJ-PAY-ARM-2417-20250407 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 54.51 | 3869.99 | Closeout and O&M Documentation - field installation time
2025-04-07 | PRJ-PAY-ARM-2417-20250407 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1023 | 49.22 | 3814.82 | Rework and Quality Correction - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2417-20250407 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1030 | 41.52 | 3819.39 | Project Management and Supervision - supervision and planning
2025-04-07 | PRJ-PAY-ARM-2417-20250407 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 36.58 | 3310.08 | Engineering, BIM and Coordination - startup and checkout
2025-04-07 | PRJ-PAY-ARM-2417-20250407 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1044 | 27.78 | 2694.28 | Field Installation Labor - punchlist and closeout labor
2025-04-07 | PRJ-PAY-ARM-2417-20250407 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 35.8 | 3705.34 | Startup, Testing and Commissioning - field installation time
2025-04-08 | AP-0004519 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2289 |  | 83.14 | 14965.63 | Plumbing Fixtures and Piping - released equipment package
2025-04-11 | AP-0004516 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2237 |  | 70.02 | 12603.05 | Major HVAC Equipment - valves and piping lot
2025-04-14 | AP-0004513 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2018 |  | 47.83 | 8609.86 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-04-14 | AP-0004522 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2315 |  | 26554.77 | 26554.77 | Electrical and Controls Subcontract - rigging and specialty support
2025-04-14 | AP-0004525 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2351 |  | 8209.67 | 8209.67 | Permits, Fees and Bonds - permit and inspection fees
2025-04-14 | PRJ-PAY-ARM-2417-20250414 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1021 | 49.86 | 3540.04 | Rework and Quality Correction - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2417-20250414 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1028 | 37.86 | 3236.96 | Project Management and Supervision - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2417-20250414 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 54.93 | 4614.3 | Engineering, BIM and Coordination - startup and checkout
2025-04-14 | PRJ-PAY-ARM-2417-20250414 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1042 | 38.72 | 3504.28 | Field Installation Labor - punchlist and closeout labor
2025-04-14 | PRJ-PAY-ARM-2417-20250414 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 33.95 | 3293.52 | Startup, Testing and Commissioning - field installation time
2025-04-14 | PRJ-PAY-ARM-2417-20250414 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 36.8 | 3809.07 | Sheet Metal Fabrication Labor - coordination and layout
2025-04-18 | AP-0004517 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2256 |  | 86.98 | 15656.34 | Plumbing Fixtures and Piping - ductwork release
2025-04-21 | AP-0004514 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2060 |  | 52.06 | 9371.63 | Major HVAC Equipment - released equipment package
2025-04-21 | PRJ-PAY-ARM-2417-20250421 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1026 | 53.2 | 4203.07 | Project Management and Supervision - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2417-20250421 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 42.79 | 3315.88 | Engineering, BIM and Coordination - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2417-20250421 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1040 | 32.18 | 2703.37 | Field Installation Labor - punchlist and closeout labor
2025-04-21 | PRJ-PAY-ARM-2417-20250421 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1047 | 44.59 | 4035.62 | Startup, Testing and Commissioning - field installation time
2025-04-21 | PRJ-PAY-ARM-2417-20250421 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1080 | 37.1 | 3598.76 | Sheet Metal Fabrication Labor - coordination and layout
2025-04-21 | PRJ-PAY-ARM-2417-20250421 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1087 | 26.85 | 2779.4 | Controls Programming and Checkout - supervision and planning
2025-04-24 | AP-0004511 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2514 |  | 55.36 | 9964.39 | Plumbing Fixtures and Piping - valves and piping lot
2025-04-24 | AP-0004520 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2288 |  | 12871.85 | 12871.85 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-04-24 | AP-0004523 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2324 |  | 4077.24 | 4077.24 | Equipment Rental and Rigging - small tools and field consumables
2025-04-25 | AP-0004518 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2275 |  | 96.44 | 17358.9 | Major HVAC Equipment - jobsite material replenishment
2025-04-28 | PRJ-PAY-ARM-2417-20250428 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 63.07 | 4478.06 | Engineering, BIM and Coordination - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2417-20250428 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1038 | 44.48 | 3446.88 | Field Installation Labor - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2417-20250428 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 44.29 | 3720.64 | Startup, Testing and Commissioning - field installation time
2025-04-28 | PRJ-PAY-ARM-2417-20250428 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 37.77 | 3417.92 | Sheet Metal Fabrication Labor - coordination and layout
2025-04-28 | PRJ-PAY-ARM-2417-20250428 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1085 | 34.19 | 3316.45 | Controls Programming and Checkout - supervision and planning
2025-04-30 | PRJ-PAY-ARM-2417-20250430 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1036 | 57.3 | 4068.58 | Field Installation Labor - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2417-20250430 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 42 | 3255 | Startup, Testing and Commissioning - field installation time
2025-04-30 | PRJ-PAY-ARM-2417-20250430 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 46.46 | 3902.36 | Sheet Metal Fabrication Labor - coordination and layout
2025-04-30 | PRJ-PAY-ARM-2417-20250430 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1083 | 29.69 | 2687.29 | Controls Programming and Checkout - supervision and planning
2025-04-30 | PRJ-PAY-ARM-2417-20250430 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1090 | 34.96 | 3390.8 | Warranty and Punchlist - startup and checkout
2025-05-03 | AP-0004526 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2362 |  | 61.63 | 11092.64 | Controls Panels and Devices - ductwork release
2025-05-03 | AP-0004534 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2457 |  | 22724.66 | 22724.66 | Insulation Subcontract - electrical coordination scope
2025-05-03 | AP-0004537 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2493 |  | 6069.61 | 6069.61 | Permits, Fees and Bonds - rental and logistics
2025-05-04 | AP-0004533 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2457 |  | 43.58 | 7845.05 | Sheet Metal and Ductwork - released equipment package
2025-05-07 | AP-0004530 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2417 |  | 92.09 | 16575.43 | Controls Panels and Devices - valves and piping lot
2025-05-07 | PRJ-PAY-ARM-2417-20250507 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1016 | 57.18 | 4059.63 | Rework and Quality Correction - field installation time
2025-05-07 | PRJ-PAY-ARM-2417-20250507 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1024 | 55.28 | 4726.07 | Project Management and Supervision - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2417-20250507 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 35.03 | 2942.53 | Engineering, BIM and Coordination - supervision and planning
2025-05-07 | PRJ-PAY-ARM-2417-20250507 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1038 | 32.3 | 2923.42 | Field Installation Labor - startup and checkout
2025-05-07 | PRJ-PAY-ARM-2417-20250507 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 39.49 | 3830.54 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-05-07 | PRJ-PAY-ARM-2417-20250507 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 40.89 | 4232.1 | Sheet Metal Fabrication Labor - field installation time
2025-05-10 | AP-0004527 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2376 |  | 75.6 | 13607.61 | Sheet Metal and Ductwork - jobsite material replenishment
2025-05-10 | AP-0004535 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2471 |  | 26731.09 | 26731.09 | Crane, Rigging and Specialty Trade - rigging and specialty support
2025-05-10 | AP-0004538 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2507 |  | 5743.5 | 5743.5 | Temporary Facilities and Protection - permit and inspection fees
2025-05-14 | AP-0004531 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2431 |  | 77.07 | 13872.43 | Sheet Metal and Ductwork - ductwork release
2025-05-14 | PRJ-PAY-ARM-2417-20250514 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1022 | 34.43 | 2719.73 | Project Management and Supervision - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2417-20250514 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 35.54 | 2754.69 | Engineering, BIM and Coordination - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2417-20250514 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1036 | 44.4 | 3729.63 | Field Installation Labor - startup and checkout
2025-05-14 | PRJ-PAY-ARM-2417-20250514 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 41.69 | 3772.96 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-05-14 | PRJ-PAY-ARM-2417-20250514 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 44.27 | 4294.53 | Sheet Metal Fabrication Labor - field installation time
2025-05-14 | PRJ-PAY-ARM-2417-20250514 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1083 | 39 | 4036.33 | Controls Programming and Checkout - coordination and layout
2025-05-17 | AP-0004528 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2389 |  | 66.17 | 11910.7 | Controls Panels and Devices - released equipment package
2025-05-17 | AP-0004536 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2484 |  | 18099.45 | 18099.45 | Testing and Balancing Subcontract - trade partner progress billing
2025-05-17 | AP-0004539 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2521 |  | 4515.7 | 4515.7 | Freight and Expediting - freight and expediting
2025-05-21 | AP-0004532 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2443 |  | 79.44 | 14298.54 | Controls Panels and Devices - jobsite material replenishment
2025-05-21 | PRJ-PAY-ARM-2417-20250521 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 67.87 | 4818.57 | Engineering, BIM and Coordination - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2417-20250521 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1034 | 44.28 | 3431.65 | Field Installation Labor - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2417-20250521 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 47.8 | 4015.03 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-05-21 | PRJ-PAY-ARM-2417-20250521 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1048 | 38.72 | 3504.5 | Sheet Metal Fabrication Labor - field installation time
2025-05-21 | PRJ-PAY-ARM-2417-20250521 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1081 | 33.08 | 3208.53 | Controls Programming and Checkout - coordination and layout
2025-05-24 | AP-0004529 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2403 |  | 59.23 | 10661.8 | Sheet Metal and Ductwork - fabricated material delivery
2025-05-24 | AP-0004540 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2534 |  | 10105.83 | 10105.83 | Equipment Rental and Rigging - small tools and field consumables
2025-05-28 | PRJ-PAY-ARM-2417-20250528 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1032 | 56.59 | 4018.08 | Field Installation Labor - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2417-20250528 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 45.91 | 3557.68 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2417-20250528 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 46.18 | 3879.31 | Sheet Metal Fabrication Labor - field installation time
2025-05-28 | PRJ-PAY-ARM-2417-20250528 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1053 | 40.93 | 3704.16 | Controls Programming and Checkout - coordination and layout
2025-05-28 | PRJ-PAY-ARM-2417-20250528 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1086 | 27.92 | 2708.1 | Warranty and Punchlist - supervision and planning
2025-05-31 | PRJ-PAY-ARM-2417-20250531 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 45 | 3195.07 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2417-20250531 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 48.09 | 3727.34 | Sheet Metal Fabrication Labor - field installation time
2025-05-31 | PRJ-PAY-ARM-2417-20250531 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1051 | 48.67 | 4088.09 | Controls Programming and Checkout - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2417-20250531 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1084 | 36.5 | 3303.61 | Warranty and Punchlist - supervision and planning
2025-05-31 | PRJ-PAY-ARM-2417-20250531 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1091 | 48.27 | 4682.32 | Closeout and O&M Documentation - startup and checkout
2025-06-03 | AP-0004544 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2241 |  | 41.98 | 7556.37 | Hydronic Piping and Valves - valves and piping lot
2025-06-03 | AP-0004556 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2395 |  | 8390.01 | 8390.01 | Permits, Fees and Bonds - rental and logistics
2025-06-06 | AP-0004541 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2021 |  | 81.97 | 14754.28 | Insulation and Specialty Material - jobsite material replenishment
2025-06-06 | AP-0004550 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2317 |  | 28312.1 | 28312.1 | Electrical and Controls Subcontract - rigging and specialty support
2025-06-06 | AP-0004553 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2353 |  | 7935.63 | 7935.63 | Freight and Expediting - permit and inspection fees
2025-06-07 | AP-0004548 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2305 |  | 84.77 | 15258.36 | Hydronic Piping and Valves - fabricated material delivery
2025-06-07 | PRJ-PAY-ARM-2417-20250607 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1018 | 34.27 | 2707.64 | Project Management and Supervision - field installation time
2025-06-07 | PRJ-PAY-ARM-2417-20250607 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 44.82 | 3473.62 | Engineering, BIM and Coordination - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2417-20250607 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1032 | 34.72 | 2916.63 | Field Installation Labor - supervision and planning
2025-06-07 | PRJ-PAY-ARM-2417-20250607 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 42.63 | 3858.13 | Startup, Testing and Commissioning - startup and checkout
2025-06-07 | PRJ-PAY-ARM-2417-20250607 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 45.56 | 4419.44 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-06-07 | PRJ-PAY-ARM-2417-20250607 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1053 | 35.98 | 3724.19 | Controls Programming and Checkout - field installation time
2025-06-07 | PRJ-PAY-ARM-2417-20250607 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1086 | 37.93 | 2693.03 | Warranty and Punchlist - coordination and layout
2025-06-10 | AP-0004545 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2258 |  | 83.16 | 14968.1 | Insulation and Specialty Material - ductwork release
2025-06-13 | AP-0004542 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2094 |  | 56.69 | 10204.89 | Hydronic Piping and Valves - released equipment package
2025-06-13 | AP-0004551 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2331 |  | 20170.54 | 20170.54 | Insulation Subcontract - trade partner progress billing
2025-06-13 | AP-0004554 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2367 |  | 5661.01 | 5661.01 | Equipment Rental and Rigging - freight and expediting
2025-06-14 | AP-0004549 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2319 |  | 80.34 | 14460.63 | Insulation and Specialty Material - valves and piping lot
2025-06-14 | PRJ-PAY-ARM-2417-20250614 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 58.88 | 4180.72 | Engineering, BIM and Coordination - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2417-20250614 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1030 | 38.81 | 3007.54 | Field Installation Labor - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2417-20250614 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 40.86 | 3432.01 | Startup, Testing and Commissioning - startup and checkout
2025-06-14 | PRJ-PAY-ARM-2417-20250614 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 33.17 | 3002.12 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-06-14 | PRJ-PAY-ARM-2417-20250614 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1051 | 35.3 | 3424.26 | Controls Programming and Checkout - field installation time
2025-06-14 | PRJ-PAY-ARM-2417-20250614 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1084 | 40.05 | 4144.78 | Warranty and Punchlist - coordination and layout
2025-06-17 | AP-0004546 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2277 |  | 56.31 | 10135.34 | Hydronic Piping and Valves - jobsite material replenishment
2025-06-20 | AP-0004543 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2220 |  | 70.14 | 12624.79 | Insulation and Specialty Material - fabricated material delivery
2025-06-20 | AP-0004552 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2345 |  | 22668.79 | 22668.79 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-06-20 | AP-0004555 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2381 |  | 3886.6 | 3886.6 | Small Tools and Consumables - small tools and field consumables
2025-06-21 | PRJ-PAY-ARM-2417-20250621 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1028 | 38.31 | 2720.34 | Field Installation Labor - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2417-20250621 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 35.5 | 2750.98 | Startup, Testing and Commissioning - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2417-20250621 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 39.09 | 3283.85 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-06-21 | PRJ-PAY-ARM-2417-20250621 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1049 | 49.7 | 4498.21 | Controls Programming and Checkout - field installation time
2025-06-21 | PRJ-PAY-ARM-2417-20250621 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1082 | 30.7 | 2978.11 | Warranty and Punchlist - coordination and layout
2025-06-21 | PRJ-PAY-ARM-2417-20250621 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1089 | 35.94 | 3719.44 | Closeout and O&M Documentation - supervision and planning
2025-06-24 | AP-0004547 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2291 |  | 91.48 | 16466.86 | Insulation and Specialty Material - released equipment package
2025-06-28 | PRJ-PAY-ARM-2417-20250628 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 45.58 | 3236.52 | Startup, Testing and Commissioning - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2417-20250628 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 54.75 | 4242.79 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2417-20250628 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1047 | 43.33 | 3640.05 | Controls Programming and Checkout - field installation time
2025-06-28 | PRJ-PAY-ARM-2417-20250628 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1080 | 41.32 | 3739.18 | Warranty and Punchlist - coordination and layout
2025-06-28 | PRJ-PAY-ARM-2417-20250628 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1087 | 30.6 | 2968.55 | Closeout and O&M Documentation - supervision and planning
2025-06-28 | PRJ-PAY-ARM-2417-20250628 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1094 | 32.7 | 3384.6 | Rework and Quality Correction - startup and checkout
2025-06-30 | PRJ-PAY-ARM-2417-20250630 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 51.21 | 3635.58 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2417-20250630 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1045 | 48.13 | 3730.12 | Controls Programming and Checkout - field installation time
2025-06-30 | PRJ-PAY-ARM-2417-20250630 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1052 | 33.36 | 2802.23 | Warranty and Punchlist - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2417-20250630 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1085 | 30.34 | 2746.22 | Closeout and O&M Documentation - supervision and planning
2025-06-30 | PRJ-PAY-ARM-2417-20250630 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1092 | 33.49 | 3248.1 | Rework and Quality Correction - startup and checkout
2025-06-30 | PRJ-PAY-ARM-2417-20250630 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1099 | 32.36 | 3608.43 | Project Management and Supervision - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2417-20250630 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 56.96 | 4043.9 | Engineering, BIM and Coordination - field installation time
2025-07-03 | AP-0004563 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2484 |  | 66.02 | 11882.8 | Major HVAC Equipment - fabricated material delivery
2025-07-06 | AP-0004560 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2443 |  | 89.36 | 16084.34 | Plumbing Fixtures and Piping - ductwork release
2025-07-07 | PRJ-PAY-ARM-2417-20250707 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 64.78 | 4599.69 | Engineering, BIM and Coordination - field installation time
2025-07-07 | PRJ-PAY-ARM-2417-20250707 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1026 | 45.83 | 3551.52 | Field Installation Labor - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2417-20250707 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 44.93 | 3774.51 | Startup, Testing and Commissioning - supervision and planning
2025-07-07 | PRJ-PAY-ARM-2417-20250707 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 46.85 | 4240.34 | Sheet Metal Fabrication Labor - startup and checkout
2025-07-07 | PRJ-PAY-ARM-2417-20250707 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1047 | 31.93 | 3096.93 | Controls Programming and Checkout - punchlist and closeout labor
2025-07-09 | AP-0004557 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2403 |  | 69.41 | 12493.17 | Major HVAC Equipment - released equipment package
2025-07-09 | AP-0004566 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2510 |  | 19457.62 | 19457.62 | Testing and Balancing Subcontract - trade partner progress billing
2025-07-09 | AP-0004569 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2029 |  | 7034.39 | 7034.39 | Small Tools and Consumables - freight and expediting
2025-07-10 | AP-0004564 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2498 |  | 84.95 | 15290.93 | Plumbing Fixtures and Piping - valves and piping lot
2025-07-13 | AP-0004561 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2457 |  | 50.19 | 9033.8 | Major HVAC Equipment - jobsite material replenishment
2025-07-14 | PRJ-PAY-ARM-2417-20250714 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1024 | 52.99 | 3762.22 | Field Installation Labor - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2417-20250714 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 46.28 | 3587.07 | Startup, Testing and Commissioning - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2417-20250714 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 43.56 | 3659.1 | Sheet Metal Fabrication Labor - startup and checkout
2025-07-14 | PRJ-PAY-ARM-2417-20250714 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1045 | 34.27 | 3101.14 | Controls Programming and Checkout - punchlist and closeout labor
2025-07-14 | PRJ-PAY-ARM-2417-20250714 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1052 | 41.5 | 4025.84 | Warranty and Punchlist - field installation time
2025-07-16 | AP-0004558 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2417 |  | 84.82 | 15268.3 | Plumbing Fixtures and Piping - fabricated material delivery
2025-07-16 | AP-0004567 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2524 |  | 21573.56 | 21573.56 | Electrical and Controls Subcontract - insulation progress invoice
2025-07-16 | AP-0004570 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2201 |  | 5609.02 | 5609.02 | Permits, Fees and Bonds - small tools and field consumables
2025-07-17 | AP-0004565 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2512 |  | 41.9 | 7541.78 | Major HVAC Equipment - ductwork release
2025-07-20 | AP-0004562 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2471 |  | 86.13 | 15503.43 | Plumbing Fixtures and Piping - released equipment package
2025-07-21 | PRJ-PAY-ARM-2417-20250721 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 61.77 | 4385.97 | Startup, Testing and Commissioning - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2417-20250721 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 45.64 | 3537.23 | Sheet Metal Fabrication Labor - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2417-20250721 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1043 | 48.7 | 4090.86 | Controls Programming and Checkout - punchlist and closeout labor
2025-07-21 | PRJ-PAY-ARM-2417-20250721 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1050 | 47.97 | 4341.68 | Warranty and Punchlist - field installation time
2025-07-21 | PRJ-PAY-ARM-2417-20250721 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1083 | 30.16 | 2925.67 | Closeout and O&M Documentation - coordination and layout
2025-07-23 | AP-0004559 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2431 |  | 56.75 | 10214.46 | Major HVAC Equipment - valves and piping lot
2025-07-23 | AP-0004568 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2010 |  | 27553.01 | 27553.01 | Insulation Subcontract - testing and balancing services
2025-07-23 | AP-0004571 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2225 |  | 8230.04 | 8230.04 | Temporary Facilities and Protection - rental and logistics
2025-07-28 | PRJ-PAY-ARM-2417-20250728 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 44.51 | 3160.31 | Sheet Metal Fabrication Labor - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2417-20250728 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1041 | 50.47 | 3911.39 | Controls Programming and Checkout - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2417-20250728 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1048 | 40.97 | 3441.81 | Warranty and Punchlist - field installation time
2025-07-28 | PRJ-PAY-ARM-2417-20250728 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1081 | 50.66 | 4584.71 | Closeout and O&M Documentation - coordination and layout
2025-07-28 | PRJ-PAY-ARM-2417-20250728 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1088 | 28.92 | 2805.11 | Rework and Quality Correction - supervision and planning
2025-07-28 | PRJ-PAY-ARM-2417-20250728 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1095 | 33.58 | 3744.1 | Project Management and Supervision - startup and checkout
2025-07-31 | PRJ-PAY-ARM-2417-20250731 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1039 | 60.86 | 4321.05 | Controls Programming and Checkout - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2417-20250731 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1046 | 46.13 | 3575.39 | Warranty and Punchlist - field installation time
2025-07-31 | PRJ-PAY-ARM-2417-20250731 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 46.1 | 3872.68 | Closeout and O&M Documentation - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2417-20250731 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1086 | 44.02 | 3983.91 | Rework and Quality Correction - supervision and planning
2025-07-31 | PRJ-PAY-ARM-2417-20250731 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1093 | 35.96 | 3775.59 | Project Management and Supervision - startup and checkout
2025-07-31 | PRJ-PAY-ARM-2417-20250731 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1100 | 34.1 | 3529.5 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-06 | AP-0004578 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2332 |  | 81.53 | 14675.48 | Sheet Metal and Ductwork - valves and piping lot
2025-08-07 | PRJ-PAY-ARM-2417-20250807 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1020 | 41.24 | 2928.28 | Field Installation Labor - field installation time
2025-08-07 | PRJ-PAY-ARM-2417-20250807 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 46.14 | 3576.11 | Startup, Testing and Commissioning - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2417-20250807 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 56.96 | 4784.77 | Sheet Metal Fabrication Labor - supervision and planning
2025-08-07 | PRJ-PAY-ARM-2417-20250807 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1041 | 36.49 | 3301.98 | Controls Programming and Checkout - startup and checkout
2025-08-07 | PRJ-PAY-ARM-2417-20250807 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1048 | 43.69 | 4238.32 | Warranty and Punchlist - punchlist and closeout labor
2025-08-09 | AP-0004575 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2291 |  | 78.66 | 14158.99 | Controls Panels and Devices - jobsite material replenishment
2025-08-09 | AP-0004587 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2436 |  | 8077.26 | 8077.26 | Small Tools and Consumables - freight and expediting
2025-08-12 | AP-0004572 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2241 |  | 108.96 | 19612.46 | Sheet Metal and Ductwork - fabricated material delivery
2025-08-12 | AP-0004581 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2358 |  | 31093.63 | 31093.63 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-08-12 | AP-0004584 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2395 |  | 4247.76 | 4247.76 | Temporary Facilities and Protection - small tools and field consumables
2025-08-13 | AP-0004579 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2346 |  | 66.32 | 11937.25 | Controls Panels and Devices - ductwork release
2025-08-14 | PRJ-PAY-ARM-2417-20250814 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 39.32 | 2791.4 | Startup, Testing and Commissioning - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2417-20250814 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 42.6 | 3301.51 | Sheet Metal Fabrication Labor - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2417-20250814 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1039 | 47.32 | 3975.04 | Controls Programming and Checkout - startup and checkout
2025-08-14 | PRJ-PAY-ARM-2417-20250814 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1046 | 34.61 | 3132.45 | Warranty and Punchlist - punchlist and closeout labor
2025-08-14 | PRJ-PAY-ARM-2417-20250814 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 40.26 | 3905.06 | Closeout and O&M Documentation - field installation time
2025-08-14 | PRJ-PAY-ARM-2417-20250814 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1086 | 28.15 | 2913.89 | Rework and Quality Correction - coordination and layout
2025-08-16 | AP-0004576 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2305 |  | 47.5 | 8550.01 | Sheet Metal and Ductwork - released equipment package
2025-08-19 | AP-0004573 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2258 |  | 46.1 | 8298.26 | Controls Panels and Devices - valves and piping lot
2025-08-19 | AP-0004582 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2372 |  | 19635.22 | 19635.22 | Testing and Balancing Subcontract - testing and balancing services
2025-08-19 | AP-0004585 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2408 |  | 8512.09 | 8512.09 | Freight and Expediting - rental and logistics
2025-08-20 | AP-0004580 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2360 |  | 49.99 | 8998.21 | Sheet Metal and Ductwork - jobsite material replenishment
2025-08-21 | PRJ-PAY-ARM-2417-20250821 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 41.73 | 2962.65 | Sheet Metal Fabrication Labor - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2417-20250821 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1037 | 50.5 | 3913.48 | Controls Programming and Checkout - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2417-20250821 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1044 | 49.93 | 4193.9 | Warranty and Punchlist - punchlist and closeout labor
2025-08-21 | PRJ-PAY-ARM-2417-20250821 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 33.48 | 3030.32 | Closeout and O&M Documentation - field installation time
2025-08-21 | PRJ-PAY-ARM-2417-20250821 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1084 | 43.88 | 4256.74 | Rework and Quality Correction - coordination and layout
2025-08-21 | PRJ-PAY-ARM-2417-20250821 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1091 | 36.94 | 4118.84 | Project Management and Supervision - supervision and planning
2025-08-23 | AP-0004577 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2319 |  | 61.47 | 11065.33 | Controls Panels and Devices - fabricated material delivery
2025-08-25 | AP-0004574 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2277 |  | 61.31 | 11036.17 | Sheet Metal and Ductwork - ductwork release
2025-08-25 | AP-0004583 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2386 |  | 19368.43 | 19368.43 | Electrical and Controls Subcontract - electrical coordination scope
2025-08-25 | AP-0004586 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2422 |  | 7839.04 | 7839.04 | Equipment Rental and Rigging - permit and inspection fees
2025-08-28 | PRJ-PAY-ARM-2417-20250828 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1035 | 44.08 | 3129.69 | Controls Programming and Checkout - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2417-20250828 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1042 | 35.69 | 2765.79 | Warranty and Punchlist - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2417-20250828 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 45.48 | 3820.52 | Closeout and O&M Documentation - field installation time
2025-08-28 | PRJ-PAY-ARM-2417-20250828 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1082 | 37.42 | 3386.22 | Rework and Quality Correction - coordination and layout
2025-08-28 | PRJ-PAY-ARM-2417-20250828 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1089 | 34.82 | 3655.59 | Project Management and Supervision - supervision and planning
2025-08-28 | PRJ-PAY-ARM-2417-20250828 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1096 | 34.53 | 3573.78 | Engineering, BIM and Coordination - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2417-20250828 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1009 | 50.83 | 3609.03 | Field Installation Labor - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2417-20250831 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1040 | 51.54 | 3659.61 | Warranty and Punchlist - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2417-20250831 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 44.94 | 3483.09 | Closeout and O&M Documentation - field installation time
2025-08-31 | PRJ-PAY-ARM-2417-20250831 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1080 | 51.82 | 4353.25 | Rework and Quality Correction - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2417-20250831 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1087 | 41.54 | 4091.78 | Project Management and Supervision - supervision and planning
2025-08-31 | PRJ-PAY-ARM-2417-20250831 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1094 | 43.42 | 4211.87 | Engineering, BIM and Coordination - startup and checkout
2025-08-31 | PRJ-PAY-ARM-2417-20250831 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1007 | 31.57 | 3267.2 | Field Installation Labor - punchlist and closeout labor
2025-09-05 | AP-0004590 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2471 |  | 76.33 | 13739.13 | Hydronic Piping and Valves - jobsite material replenishment
2025-09-05 | AP-0004599 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2232 |  | 23895.31 | 23895.31 | Testing and Balancing Subcontract - rigging and specialty support
2025-09-05 | AP-0004602 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2281 |  | 6061.1 | 6061.1 | Permits, Fees and Bonds - freight and expediting
2025-09-07 | PRJ-PAY-ARM-2417-20250907 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 43.7 | 3103.03 | Startup, Testing and Commissioning - field installation time
2025-09-07 | PRJ-PAY-ARM-2417-20250907 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 58.47 | 4531.74 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2417-20250907 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1035 | 38.28 | 3215.2 | Controls Programming and Checkout - supervision and planning
2025-09-07 | PRJ-PAY-ARM-2417-20250907 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1042 | 52.62 | 4762.54 | Warranty and Punchlist - startup and checkout
2025-09-07 | PRJ-PAY-ARM-2417-20250907 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 39.38 | 3820.18 | Closeout and O&M Documentation - punchlist and closeout labor
2025-09-09 | AP-0004594 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2526 |  | 51.56 | 9280.36 | Hydronic Piping and Valves - ductwork release
2025-09-12 | AP-0004591 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2484 |  | 82.89 | 14919.8 | Insulation and Specialty Material - released equipment package
2025-09-12 | AP-0004603 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2294 |  | 6859.69 | 6859.69 | Temporary Facilities and Protection - small tools and field consumables
2025-09-14 | PRJ-PAY-ARM-2417-20250914 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 44.5 | 3159.52 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2417-20250914 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1033 | 44.79 | 3471.1 | Controls Programming and Checkout - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2417-20250914 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1040 | 46.55 | 3910.45 | Warranty and Punchlist - startup and checkout
2025-09-14 | PRJ-PAY-ARM-2417-20250914 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 40.31 | 3648.24 | Closeout and O&M Documentation - punchlist and closeout labor
2025-09-14 | PRJ-PAY-ARM-2417-20250914 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1080 | 34.64 | 3360.45 | Rework and Quality Correction - field installation time
2025-09-14 | PRJ-PAY-ARM-2417-20250914 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1087 | 38.27 | 4267.51 | Project Management and Supervision - coordination and layout
2025-09-15 | AP-0004588 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2443 |  | 58.57 | 10543.15 | Hydronic Piping and Valves - valves and piping lot
2025-09-15 | AP-0004597 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2047 |  | 16876.47 | 16876.47 | Insulation Subcontract - testing and balancing services
2025-09-15 | AP-0004600 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2244 |  | 6140.29 | 6140.29 | Equipment Rental and Rigging - rental and logistics
2025-09-16 | AP-0004595 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2014 |  | 78.8 | 14184.78 | Insulation and Specialty Material - jobsite material replenishment
2025-09-19 | AP-0004592 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2498 |  | 80.33 | 14459.47 | Hydronic Piping and Valves - fabricated material delivery
2025-09-21 | PRJ-PAY-ARM-2417-20250921 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1031 | 58.55 | 4156.91 | Controls Programming and Checkout - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2417-20250921 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1038 | 48 | 3719.65 | Warranty and Punchlist - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2417-20250921 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 45.87 | 3853.38 | Closeout and O&M Documentation - punchlist and closeout labor
2025-09-21 | PRJ-PAY-ARM-2417-20250921 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1052 | 36.57 | 3309.56 | Rework and Quality Correction - field installation time
2025-09-21 | PRJ-PAY-ARM-2417-20250921 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1085 | 41 | 4304.97 | Project Management and Supervision - coordination and layout
2025-09-21 | PRJ-PAY-ARM-2417-20250921 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1092 | 37.63 | 3894.57 | Engineering, BIM and Coordination - supervision and planning
2025-09-22 | AP-0004589 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2457 |  | 56.64 | 10195.56 | Insulation and Specialty Material - ductwork release
2025-09-22 | AP-0004598 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2210 |  | 31564.78 | 31564.78 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-09-22 | AP-0004601 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2265 |  | 6099.46 | 6099.46 | Small Tools and Consumables - permit and inspection fees
2025-09-23 | AP-0004596 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2056 |  | 84.69 | 15244.18 | Hydronic Piping and Valves - released equipment package
2025-09-25 | AP-0004593 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2512 |  | 59.2 | 10656 | Insulation and Specialty Material - valves and piping lot
2025-09-28 | PRJ-PAY-ARM-2417-20250928 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1036 | 59.39 | 4216.78 | Warranty and Punchlist - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2417-20250928 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 52.47 | 4066.34 | Closeout and O&M Documentation - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2417-20250928 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1050 | 34.62 | 2908.09 | Rework and Quality Correction - field installation time
2025-09-28 | PRJ-PAY-ARM-2417-20250928 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1083 | 40.95 | 4033.54 | Project Management and Supervision - coordination and layout
2025-09-28 | PRJ-PAY-ARM-2417-20250928 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1090 | 35.87 | 3479.27 | Engineering, BIM and Coordination - supervision and planning
2025-09-28 | PRJ-PAY-ARM-2417-20250928 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1097 | 35.62 | 3686.81 | Field Installation Labor - startup and checkout
2025-09-30 | PRJ-PAY-ARM-2417-20250930 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 57.19 | 4060.24 | Closeout and O&M Documentation - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2417-20250930 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1048 | 43.89 | 3401.66 | Rework and Quality Correction - field installation time
2025-09-30 | PRJ-PAY-ARM-2417-20250930 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1081 | 29.89 | 2749.78 | Project Management and Supervision - coordination and layout
2025-09-30 | PRJ-PAY-ARM-2417-20250930 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1088 | 32.32 | 2924.78 | Engineering, BIM and Coordination - supervision and planning
2025-09-30 | PRJ-PAY-ARM-2417-20250930 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1095 | 30.33 | 2941.94 | Field Installation Labor - startup and checkout
2025-09-30 | PRJ-PAY-ARM-2417-20250930 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1008 | 38.4 | 3974.07 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-05 | AP-0004609 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2372 |  | 51.05 | 9189.53 | Major HVAC Equipment - ductwork release
2025-10-07 | PRJ-PAY-ARM-2417-20251007 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1022 | 67.7 | 4806.48 | Sheet Metal Fabrication Labor - field installation time
2025-10-07 | PRJ-PAY-ARM-2417-20251007 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1029 | 49.2 | 3812.83 | Controls Programming and Checkout - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2417-20251007 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1036 | 44.38 | 3727.97 | Warranty and Punchlist - supervision and planning
2025-10-07 | PRJ-PAY-ARM-2417-20251007 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 37.91 | 3430.49 | Closeout and O&M Documentation - startup and checkout
2025-10-07 | PRJ-PAY-ARM-2417-20251007 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1050 | 31.68 | 3072.48 | Rework and Quality Correction - punchlist and closeout labor
2025-10-08 | AP-0004606 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2331 |  | 100.84 | 18151.59 | Plumbing Fixtures and Piping - released equipment package
2025-10-08 | AP-0004616 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2450 |  | 6788.5 | 6788.5 | Freight and Expediting - small tools and field consumables
2025-10-12 | AP-0004610 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2386 |  | 94.02 | 16924.2 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-10-14 | PRJ-PAY-ARM-2417-20251014 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1027 | 48.55 | 3446.72 | Controls Programming and Checkout - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2417-20251014 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1034 | 42.44 | 3289.19 | Warranty and Punchlist - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2417-20251014 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 42.55 | 3574.42 | Closeout and O&M Documentation - startup and checkout
2025-10-14 | PRJ-PAY-ARM-2417-20251014 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1048 | 37.85 | 3425.77 | Rework and Quality Correction - punchlist and closeout labor
2025-10-14 | PRJ-PAY-ARM-2417-20251014 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1081 | 24.7 | 2593.55 | Project Management and Supervision - field installation time
2025-10-14 | PRJ-PAY-ARM-2417-20251014 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1088 | 36.22 | 3749.02 | Engineering, BIM and Coordination - coordination and layout
2025-10-15 | AP-0004607 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2345 |  | 51.84 | 9331.64 | Major HVAC Equipment - fabricated material delivery
2025-10-18 | AP-0004604 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2303 |  | 86.74 | 15612.71 | Plumbing Fixtures and Piping - ductwork release
2025-10-18 | AP-0004612 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2400 |  | 31039.71 | 31039.71 | Electrical and Controls Subcontract - electrical coordination scope
2025-10-18 | AP-0004614 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2424 |  | 5757.6 | 5757.6 | Permits, Fees and Bonds - permit and inspection fees
2025-10-19 | AP-0004611 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2400 |  | 80.39 | 14470.41 | Major HVAC Equipment - released equipment package
2025-10-21 | PRJ-PAY-ARM-2417-20251021 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1032 | 40.64 | 2885.25 | Warranty and Punchlist - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2417-20251021 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 53.3 | 4130.95 | Closeout and O&M Documentation - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2417-20251021 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1046 | 39.36 | 3305.84 | Rework and Quality Correction - punchlist and closeout labor
2025-10-21 | PRJ-PAY-ARM-2417-20251021 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1053 | 47.28 | 4656.77 | Project Management and Supervision - field installation time
2025-10-21 | PRJ-PAY-ARM-2417-20251021 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1086 | 45.02 | 4367 | Engineering, BIM and Coordination - coordination and layout
2025-10-22 | AP-0004608 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2358 |  | 45 | 8099.62 | Plumbing Fixtures and Piping - valves and piping lot
2025-10-25 | AP-0004605 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2317 |  | 58.1 | 10457.4 | Major HVAC Equipment - jobsite material replenishment
2025-10-25 | AP-0004613 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2414 |  | 28150.19 | 28150.19 | Insulation Subcontract - rigging and specialty support
2025-10-25 | AP-0004615 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2438 |  | 6287.04 | 6287.04 | Temporary Facilities and Protection - freight and expediting
2025-10-28 | PRJ-PAY-ARM-2417-20251028 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 61.91 | 4395.95 | Closeout and O&M Documentation - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2417-20251028 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1044 | 34.81 | 2697.5 | Rework and Quality Correction - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2417-20251028 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1051 | 42.34 | 3895.11 | Project Management and Supervision - field installation time
2025-10-28 | PRJ-PAY-ARM-2417-20251028 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1084 | 39.66 | 3589.07 | Engineering, BIM and Coordination - coordination and layout
2025-10-28 | PRJ-PAY-ARM-2417-20251028 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1091 | 28.33 | 2747.83 | Field Installation Labor - supervision and planning
2025-10-31 | PRJ-PAY-ARM-2417-20251031 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1042 | 62.71 | 4452.09 | Rework and Quality Correction - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2417-20251031 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1049 | 38.3 | 3274.51 | Project Management and Supervision - field installation time
2025-10-31 | PRJ-PAY-ARM-2417-20251031 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 42.28 | 3551.13 | Engineering, BIM and Coordination - coordination and layout
2025-10-31 | PRJ-PAY-ARM-2417-20251031 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1089 | 50.8 | 4597.38 | Field Installation Labor - supervision and planning
2025-11-04 | AP-0004618 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2474 |  | 95.52 | 17194.04 | Sheet Metal and Ductwork - released equipment package
2025-11-04 | AP-0004625 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2098 |  | 34947.25 | 34947.25 | Electrical and Controls Subcontract - trade partner progress billing
2025-11-04 | AP-0004627 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2237 |  | 7989.14 | 7989.14 | Equipment Rental and Rigging - small tools and field consumables
2025-11-07 | PRJ-PAY-ARM-2417-20251107 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1023 | 49.83 | 3537.96 | Controls Programming and Checkout - field installation time
2025-11-07 | PRJ-PAY-ARM-2417-20251107 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1030 | 46.88 | 3633.47 | Warranty and Punchlist - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2417-20251107 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 35.11 | 2948.97 | Closeout and O&M Documentation - supervision and planning
2025-11-07 | PRJ-PAY-ARM-2417-20251107 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1044 | 42.07 | 3807.61 | Rework and Quality Correction - startup and checkout
2025-11-07 | PRJ-PAY-ARM-2417-20251107 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1051 | 32.25 | 3386.47 | Project Management and Supervision - punchlist and closeout labor
2025-11-07 | PRJ-PAY-ARM-2417-20251107 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1084 | 24.61 | 2547.13 | Engineering, BIM and Coordination - field installation time
2025-11-08 | AP-0004622 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2529 |  | 56.35 | 10143.45 | Sheet Metal and Ductwork - jobsite material replenishment
2025-11-11 | AP-0004619 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2488 |  | 46.14 | 8305.6 | Controls Panels and Devices - fabricated material delivery
2025-11-11 | AP-0004628 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2256 |  | 8516.72 | 8516.72 | Small Tools and Consumables - rental and logistics
2025-11-14 | PRJ-PAY-ARM-2417-20251114 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1028 | 47.67 | 3384.81 | Warranty and Punchlist - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2417-20251114 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 47.27 | 3663.65 | Closeout and O&M Documentation - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2417-20251114 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1042 | 51.94 | 4362.84 | Rework and Quality Correction - startup and checkout
2025-11-14 | PRJ-PAY-ARM-2417-20251114 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1049 | 39.74 | 3914.4 | Project Management and Supervision - punchlist and closeout labor
2025-11-14 | PRJ-PAY-ARM-2417-20251114 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 39.29 | 3810.97 | Engineering, BIM and Coordination - field installation time
2025-11-15 | AP-0004623 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2021 |  | 69.74 | 12553.31 | Controls Panels and Devices - released equipment package
2025-11-18 | AP-0004620 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2502 |  | 82.66 | 14879.37 | Sheet Metal and Ductwork - valves and piping lot
2025-11-21 | AP-0004617 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2460 |  | 68.1 | 12257.11 | Controls Panels and Devices - jobsite material replenishment
2025-11-21 | AP-0004624 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2025 |  | 24576.51 | 24576.51 | Testing and Balancing Subcontract - rigging and specialty support
2025-11-21 | AP-0004626 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2217 |  | 6786.04 | 6786.04 | Freight and Expediting - freight and expediting
2025-11-21 | PRJ-PAY-ARM-2417-20251121 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 56.67 | 4023.68 | Closeout and O&M Documentation - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2417-20251121 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1040 | 48.8 | 3781.95 | Rework and Quality Correction - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2417-20251121 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1047 | 39.54 | 3637.65 | Project Management and Supervision - punchlist and closeout labor
2025-11-21 | PRJ-PAY-ARM-2417-20251121 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1080 | 31.04 | 2809.09 | Engineering, BIM and Coordination - field installation time
2025-11-21 | PRJ-PAY-ARM-2417-20251121 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1087 | 29.75 | 2885.79 | Field Installation Labor - coordination and layout
2025-11-25 | AP-0004621 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2515 |  | 70.33 | 12658.77 | Controls Panels and Devices - ductwork release
2025-11-28 | PRJ-PAY-ARM-2417-20251128 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1038 | 46.06 | 3270.42 | Rework and Quality Correction - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2417-20251128 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1045 | 41.91 | 3583.06 | Project Management and Supervision - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2417-20251128 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 50.8 | 4267.34 | Engineering, BIM and Coordination - field installation time
2025-11-28 | PRJ-PAY-ARM-2417-20251128 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1085 | 50.64 | 4582.68 | Field Installation Labor - coordination and layout
2025-11-30 | PRJ-PAY-ARM-2417-20251130 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1043 | 62.39 | 4928.63 | Project Management and Supervision - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2417-20251130 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 45.99 | 3564.01 | Engineering, BIM and Coordination - field installation time
2025-11-30 | PRJ-PAY-ARM-2417-20251130 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1083 | 38.59 | 3241.32 | Field Installation Labor - coordination and layout
2025-11-30 | PRJ-PAY-ARM-2417-20251130 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1090 | 48.81 | 4417.75 | Startup, Testing and Commissioning - supervision and planning
2025-12-04 | AP-0004633 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2327 |  | 76.41 | 13752.98 | Insulation and Specialty Material - jobsite material replenishment
2025-12-07 | AP-0004630 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2286 |  | 56.49 | 10168.85 | Hydronic Piping and Valves - fabricated material delivery
2025-12-07 | AP-0004636 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2358 |  | 24610.59 | 24610.59 | Testing and Balancing Subcontract - insulation progress invoice
2025-12-07 | AP-0004638 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2383 |  | 8784.63 | 8784.63 | Permits, Fees and Bonds - rental and logistics
2025-12-07 | PRJ-PAY-ARM-2417-20251207 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1024 | 47.33 | 3360.53 | Warranty and Punchlist - field installation time
2025-12-07 | PRJ-PAY-ARM-2417-20251207 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1031 | 52.02 | 4031.78 | Closeout and O&M Documentation - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2417-20251207 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1038 | 49.46 | 4154.89 | Rework and Quality Correction - supervision and planning
2025-12-07 | PRJ-PAY-ARM-2417-20251207 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1045 | 36.67 | 3611.97 | Project Management and Supervision - startup and checkout
2025-12-11 | AP-0004634 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2341 |  | 53.33 | 9599.68 | Hydronic Piping and Valves - released equipment package
2025-12-14 | AP-0004631 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2300 |  | 98.84 | 17791.12 | Insulation and Specialty Material - valves and piping lot
2025-12-14 | PRJ-PAY-ARM-2417-20251214 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1029 | 40.83 | 2899.14 | Closeout and O&M Documentation - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2417-20251214 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1036 | 45.11 | 3496 | Rework and Quality Correction - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2417-20251214 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1043 | 38.62 | 3553.07 | Project Management and Supervision - startup and checkout
2025-12-14 | PRJ-PAY-ARM-2417-20251214 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 40.09 | 3627.83 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-12-21 | AP-0004632 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2313 |  | 42.39 | 7629.54 | Hydronic Piping and Valves - ductwork release
2025-12-21 | PRJ-PAY-ARM-2417-20251221 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1034 | 51.78 | 3676.26 | Rework and Quality Correction - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2417-20251221 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1041 | 54.88 | 4692.25 | Project Management and Supervision - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2417-20251221 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1048 | 48.46 | 4071.06 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-12-24 | AP-0004629 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2272 |  | 74.22 | 13358.71 | Insulation and Specialty Material - released equipment package
2025-12-24 | AP-0004635 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2345 |  | 19573.28 | 19573.28 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-12-24 | AP-0004637 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2369 |  | 7282.23 | 7282.23 | Small Tools and Consumables - small tools and field consumables
2025-12-28 | PRJ-PAY-ARM-2417-20251228 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1039 | 35.96 | 2840.98 | Project Management and Supervision - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2417-20251228 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1046 | 41.32 | 3202.25 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2417-20251228 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1053 | 43.43 | 3648.13 | Field Installation Labor - field installation time
2025-12-28 | PRJ-PAY-ARM-2417-20251228 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1086 | 34.29 | 3103.26 | Startup, Testing and Commissioning - coordination and layout
2025-12-31 | PRJ-PAY-ARM-2417-20251231 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 53.18 | 3775.43 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2417-20251231 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1051 | 42.6 | 3301.19 | Field Installation Labor - field installation time
2025-12-31 | PRJ-PAY-ARM-2417-20251231 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1084 | 38.77 | 3256.98 | Startup, Testing and Commissioning - coordination and layout
2025-12-31 | PRJ-PAY-ARM-2417-20251231 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1091 | 43.99 | 3981.17 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-03 | AP-0004639 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2395 |  | 65.02 | 11703.26 | Major HVAC Equipment - fabricated material delivery
2026-01-03 | AP-0004645 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2465 |  | 23399.22 | 23399.22 | Insulation Subcontract - insulation progress invoice
2026-01-03 | AP-0004647 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2490 |  | 4920.21 | 4920.21 | Temporary Facilities and Protection - rental and logistics
2026-01-07 | AP-0004643 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2448 |  | 53.95 | 9710.97 | Major HVAC Equipment - released equipment package
2026-01-07 | PRJ-PAY-ARM-2417-20260107 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1025 | 62.3 | 4423.16 | Closeout and O&M Documentation - field installation time
2026-01-07 | PRJ-PAY-ARM-2417-20260107 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1032 | 63.53 | 4923.26 | Rework and Quality Correction - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2417-20260107 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1039 | 33.11 | 3046.2 | Project Management and Supervision - supervision and planning
2026-01-10 | AP-0004640 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2408 |  | 51.61 | 9289.77 | Plumbing Fixtures and Piping - valves and piping lot
2026-01-10 | AP-0004646 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2479 |  | 19040.13 | 19040.13 | Crane, Rigging and Specialty Trade - testing and balancing services
2026-01-10 | AP-0004648 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2503 |  | 7996.11 | 7996.11 | Freight and Expediting - permit and inspection fees
2026-01-14 | AP-0004644 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2462 |  | 68.63 | 12354.16 | Plumbing Fixtures and Piping - fabricated material delivery
2026-01-14 | PRJ-PAY-ARM-2417-20260114 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1030 | 64.38 | 4570.91 | Rework and Quality Correction - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2417-20260114 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1037 | 35.71 | 3053.31 | Project Management and Supervision - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2417-20260114 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 44.42 | 3731 | Engineering, BIM and Coordination - startup and checkout
2026-01-17 | AP-0004641 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2422 |  | 77.33 | 13918.73 | Major HVAC Equipment - ductwork release
2026-01-21 | PRJ-PAY-ARM-2417-20260121 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1035 | 44.47 | 3512.78 | Project Management and Supervision - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2417-20260121 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1042 | 56.04 | 4343.15 | Engineering, BIM and Coordination - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2417-20260121 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1049 | 45.52 | 3823.39 | Field Installation Labor - punchlist and closeout labor
2026-01-24 | AP-0004642 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2436 |  | 73 | 13140.29 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-01-28 | PRJ-PAY-ARM-2417-20260128 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 49.87 | 3540.53 | Engineering, BIM and Coordination - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2417-20260128 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1047 | 35.84 | 2777.58 | Field Installation Labor - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2417-20260128 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1080 | 38.93 | 3270.48 | Startup, Testing and Commissioning - field installation time
2026-01-28 | PRJ-PAY-ARM-2417-20260128 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1087 | 38.43 | 3478.36 | Sheet Metal Fabrication Labor - coordination and layout
2026-01-31 | PRJ-PAY-ARM-2417-20260131 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1045 | 39.96 | 2836.81 | Field Installation Labor - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2417-20260131 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1052 | 51.17 | 3965.31 | Startup, Testing and Commissioning - field installation time
2026-01-31 | PRJ-PAY-ARM-2417-20260131 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1085 | 40.85 | 3431.01 | Sheet Metal Fabrication Labor - coordination and layout
2026-01-31 | PRJ-PAY-ARM-2417-20260131 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1092 | 44.3 | 4009.18 | Controls Programming and Checkout - supervision and planning
2026-02-03 | AP-0004652 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2094 |  | 59.38 | 10688.05 | Controls Panels and Devices - released equipment package
2026-02-06 | AP-0004649 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2515 |  | 74.33 | 13379.02 | Sheet Metal and Ductwork - valves and piping lot
2026-02-06 | AP-0004655 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2244 |  | 22155.25 | 22155.25 | Electrical and Controls Subcontract - testing and balancing services
2026-02-06 | AP-0004657 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2277 |  | 7062.49 | 7062.49 | Equipment Rental and Rigging - permit and inspection fees
2026-02-07 | PRJ-PAY-ARM-2417-20260207 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1026 | 58.17 | 4130.28 | Rework and Quality Correction - field installation time
2026-02-07 | PRJ-PAY-ARM-2417-20260207 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1033 | 43.21 | 3694.22 | Project Management and Supervision - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2417-20260207 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 43.13 | 3622.99 | Engineering, BIM and Coordination - supervision and planning
2026-02-07 | PRJ-PAY-ARM-2417-20260207 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1047 | 47 | 4253.2 | Field Installation Labor - startup and checkout
2026-02-10 | AP-0004653 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2220 |  | 39.4 | 7092.64 | Sheet Metal and Ductwork - fabricated material delivery
2026-02-13 | AP-0004650 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2529 |  | 73.75 | 13275.56 | Controls Panels and Devices - ductwork release
2026-02-13 | AP-0004656 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2265 |  | 22886.29 | 22886.29 | Insulation Subcontract - electrical coordination scope
2026-02-13 | AP-0004658 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2291 |  | 7599.48 | 7599.48 | Small Tools and Consumables - freight and expediting
2026-02-14 | PRJ-PAY-ARM-2417-20260214 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1031 | 54.43 | 4300.26 | Project Management and Supervision - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2417-20260214 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1038 | 49.96 | 3872.21 | Engineering, BIM and Coordination - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2417-20260214 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1045 | 49.83 | 4185.7 | Field Installation Labor - startup and checkout
2026-02-14 | PRJ-PAY-ARM-2417-20260214 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1052 | 41.89 | 3790.65 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-02-17 | AP-0004654 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2241 |  | 77.45 | 13940.8 | Controls Panels and Devices - valves and piping lot
2026-02-20 | AP-0004651 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2021 |  | 62.41 | 11233.58 | Sheet Metal and Ductwork - jobsite material replenishment
2026-02-20 | AP-0004659 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2305 |  | 3764.1 | 3764.1 | Permits, Fees and Bonds - small tools and field consumables
2026-02-21 | PRJ-PAY-ARM-2417-20260221 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1036 | 58.34 | 4141.96 | Engineering, BIM and Coordination - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2417-20260221 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1043 | 44.49 | 3447.64 | Field Installation Labor - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2417-20260221 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1050 | 29.79 | 2502.32 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-02-21 | PRJ-PAY-ARM-2417-20260221 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1083 | 43.95 | 3977.39 | Sheet Metal Fabrication Labor - field installation time
2026-02-21 | PRJ-PAY-ARM-2417-20260221 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1090 | 41.22 | 3998.17 | Controls Programming and Checkout - coordination and layout
2026-02-28 | PRJ-PAY-ARM-2417-20260228 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1041 | 43.19 | 3066.79 | Field Installation Labor - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2417-20260228 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 56.98 | 4415.86 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2417-20260228 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1081 | 41.55 | 3490.21 | Sheet Metal Fabrication Labor - field installation time
2026-02-28 | PRJ-PAY-ARM-2417-20260228 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1088 | 47.22 | 4273.64 | Controls Programming and Checkout - coordination and layout
2026-02-28 | PRJ-PAY-ARM-2417-20260228 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1095 | 45.84 | 4446.16 | Warranty and Punchlist - supervision and planning
2026-03-06 | AP-0004663 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2357 |  | 116.76 | 21016.26 | Insulation and Specialty Material - fabricated material delivery
2026-03-07 | PRJ-PAY-ARM-2417-20260307 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1027 | 40.45 | 3195.43 | Project Management and Supervision - field installation time
2026-03-07 | PRJ-PAY-ARM-2417-20260307 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1034 | 37.38 | 2897.04 | Engineering, BIM and Coordination - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2417-20260307 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1041 | 37.47 | 3147.74 | Field Installation Labor - supervision and planning
2026-03-07 | PRJ-PAY-ARM-2417-20260307 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 40.98 | 3708.97 | Startup, Testing and Commissioning - startup and checkout
2026-03-09 | AP-0004660 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2315 |  | 52.94 | 9528.44 | Hydronic Piping and Valves - ductwork release
2026-03-09 | AP-0004666 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2388 |  | 26599.48 | 26599.48 | Testing and Balancing Subcontract - electrical coordination scope
2026-03-09 | AP-0004668 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2412 |  | 11314.67 | 11314.67 | Permits, Fees and Bonds - freight and expediting
2026-03-13 | AP-0004664 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2370 |  | 59.89 | 10780.99 | Hydronic Piping and Valves - valves and piping lot
2026-03-14 | PRJ-PAY-ARM-2417-20260314 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1032 | 56.05 | 3979.44 | Engineering, BIM and Coordination - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2417-20260314 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1039 | 37.83 | 2931.87 | Field Installation Labor - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2417-20260314 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 35.47 | 2979.74 | Startup, Testing and Commissioning - startup and checkout
2026-03-14 | PRJ-PAY-ARM-2417-20260314 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1053 | 50.79 | 4596.63 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-03-16 | AP-0004661 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2329 |  | 72.34 | 13021.01 | Insulation and Specialty Material - jobsite material replenishment
2026-03-16 | AP-0004667 | AP | ARM-2417 | 04-200 | Electrical and Controls Subcontract | V-2402 |  | 22853.83 | 22853.83 | Electrical and Controls Subcontract - rigging and specialty support
2026-03-16 | AP-0004669 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2426 |  | 5886.48 | 5886.48 | Temporary Facilities and Protection - small tools and field consumables
2026-03-20 | AP-0004665 | AP | ARM-2417 | 02-610 | Insulation and Specialty Material | V-2384 |  | 75.41 | 13573.97 | Insulation and Specialty Material - ductwork release
2026-03-21 | PRJ-PAY-ARM-2417-20260321 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1037 | 38.17 | 2710 | Field Installation Labor - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2417-20260321 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1044 | 55.2 | 4277.67 | Startup, Testing and Commissioning - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2417-20260321 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1051 | 54.89 | 4610.87 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-03-21 | PRJ-PAY-ARM-2417-20260321 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1084 | 46.32 | 4192.32 | Controls Programming and Checkout - field installation time
2026-03-23 | AP-0004662 | AP | ARM-2417 | 02-310 | Hydronic Piping and Valves | V-2343 |  | 52.69 | 9484.52 | Hydronic Piping and Valves - released equipment package
2026-03-28 | PRJ-PAY-ARM-2417-20260328 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 51.94 | 3687.44 | Startup, Testing and Commissioning - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2417-20260328 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 44.21 | 3426.14 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2417-20260328 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1082 | 47.78 | 4013.39 | Controls Programming and Checkout - field installation time
2026-03-28 | PRJ-PAY-ARM-2417-20260328 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1089 | 50.1 | 4533.6 | Warranty and Punchlist - coordination and layout
2026-03-31 | PRJ-PAY-ARM-2417-20260331 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 43.5 | 3088.58 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2417-20260331 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1080 | 41.05 | 3181.73 | Controls Programming and Checkout - field installation time
2026-03-31 | PRJ-PAY-ARM-2417-20260331 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1087 | 46.07 | 3869.5 | Warranty and Punchlist - coordination and layout
2026-03-31 | PRJ-PAY-ARM-2417-20260331 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1094 | 45.05 | 4076.8 | Closeout and O&M Documentation - supervision and planning
2026-04-06 | AP-0004676 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2519 |  | 69.38 | 12487.92 | Plumbing Fixtures and Piping - released equipment package
2026-04-07 | PRJ-PAY-ARM-2417-20260407 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1028 | 48.43 | 3438.43 | Engineering, BIM and Coordination - field installation time
2026-04-07 | PRJ-PAY-ARM-2417-20260407 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1035 | 45.16 | 3499.64 | Field Installation Labor - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2417-20260407 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 43.1 | 3620.35 | Startup, Testing and Commissioning - supervision and planning
2026-04-07 | PRJ-PAY-ARM-2417-20260407 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 39.92 | 3612.68 | Sheet Metal Fabrication Labor - startup and checkout
2026-04-07 | PRJ-PAY-ARM-2417-20260407 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1082 | 23.56 | 2284.89 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-09 | AP-0004673 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2477 |  | 63.66 | 11459.62 | Major HVAC Equipment - valves and piping lot
2026-04-12 | AP-0004670 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2438 |  | 76.48 | 13765.7 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-04-12 | AP-0004677 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2521 |  | 24721.27 | 24721.27 | Crane, Rigging and Specialty Trade - rigging and specialty support
2026-04-12 | AP-0004679 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2025 |  | 9080.86 | 9080.86 | Freight and Expediting - small tools and field consumables
2026-04-14 | PRJ-PAY-ARM-2417-20260414 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1033 | 45.37 | 3221.35 | Field Installation Labor - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2417-20260414 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1040 | 58.17 | 4508.28 | Startup, Testing and Commissioning - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2417-20260414 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 37.78 | 3173.13 | Sheet Metal Fabrication Labor - startup and checkout
2026-04-14 | PRJ-PAY-ARM-2417-20260414 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1080 | 41.87 | 3789.42 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-14 | PRJ-PAY-ARM-2417-20260414 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1087 | 33.44 | 3244.03 | Warranty and Punchlist - field installation time
2026-04-16 | AP-0004674 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2491 |  | 86.36 | 15543.91 | Plumbing Fixtures and Piping - ductwork release
2026-04-19 | AP-0004671 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2450 |  | 47.62 | 8572.45 | Major HVAC Equipment - released equipment package
2026-04-19 | AP-0004678 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2534 |  | 28888.99 | 28888.99 | Testing and Balancing Subcontract - trade partner progress billing
2026-04-19 | AP-0004680 | AP | ARM-2417 | 05-100 | Equipment Rental and Rigging | V-2098 |  | 7976.94 | 7976.94 | Equipment Rental and Rigging - rental and logistics
2026-04-21 | PRJ-PAY-ARM-2417-20260421 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1038 | 41.98 | 2980.24 | Startup, Testing and Commissioning - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2417-20260421 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1045 | 49.3 | 3821.12 | Sheet Metal Fabrication Labor - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2417-20260421 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1052 | 52.9 | 4443.57 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-21 | PRJ-PAY-ARM-2417-20260421 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1085 | 38.42 | 3476.69 | Warranty and Punchlist - field installation time
2026-04-21 | PRJ-PAY-ARM-2417-20260421 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1092 | 31.61 | 3066.6 | Closeout and O&M Documentation - coordination and layout
2026-04-23 | AP-0004675 | AP | ARM-2417 | 02-110 | Major HVAC Equipment | V-2505 |  | 93.01 | 16742.63 | Major HVAC Equipment - jobsite material replenishment
2026-04-25 | AP-0004672 | AP | ARM-2417 | 02-410 | Plumbing Fixtures and Piping | V-2464 |  | 77.93 | 14027.31 | Plumbing Fixtures and Piping - fabricated material delivery
2026-04-28 | PRJ-PAY-ARM-2417-20260428 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 53.52 | 3799.87 | Sheet Metal Fabrication Labor - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2417-20260428 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1050 | 51.46 | 3987.93 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2417-20260428 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1083 | 42.81 | 3595.77 | Warranty and Punchlist - field installation time
2026-04-28 | PRJ-PAY-ARM-2417-20260428 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1090 | 52.65 | 4764.51 | Closeout and O&M Documentation - coordination and layout
2026-04-30 | PRJ-PAY-ARM-2417-20260430 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1048 | 55.96 | 3973.43 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2417-20260430 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1081 | 46.99 | 3642.1 | Warranty and Punchlist - field installation time
2026-04-30 | PRJ-PAY-ARM-2417-20260430 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1088 | 35.86 | 3012.02 | Closeout and O&M Documentation - coordination and layout
2026-04-30 | PRJ-PAY-ARM-2417-20260430 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1095 | 43.05 | 3896.17 | Rework and Quality Correction - supervision and planning
2026-05-05 | AP-0004683 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2258 |  | 59.35 | 10683.43 | Controls Panels and Devices - valves and piping lot
2026-05-05 | AP-0004690 | AP | ARM-2417 | 04-300 | Testing and Balancing Subcontract | V-2348 |  | 20443.55 | 20443.55 | Testing and Balancing Subcontract - testing and balancing services
2026-05-05 | AP-0004693 | AP | ARM-2417 | 06-400 | Temporary Facilities and Protection | V-2384 |  | 4436.43 | 4436.43 | Temporary Facilities and Protection - freight and expediting
2026-05-07 | PRJ-PAY-ARM-2417-20260507 | PAY | ARM-2417 | 03-100 | Field Installation Labor |  | E-1029 | 50.79 | 3605.77 | Field Installation Labor - field installation time
2026-05-07 | PRJ-PAY-ARM-2417-20260507 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1036 | 38.04 | 2948.35 | Startup, Testing and Commissioning - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2417-20260507 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1043 | 33.85 | 2843.44 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-07 | PRJ-PAY-ARM-2417-20260507 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1050 | 47.96 | 4340.29 | Controls Programming and Checkout - startup and checkout
2026-05-07 | PRJ-PAY-ARM-2417-20260507 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1083 | 38.21 | 3706.52 | Warranty and Punchlist - punchlist and closeout labor
2026-05-07 | PRJ-PAY-ARM-2417-20260507 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1090 | 32.03 | 3315.45 | Closeout and O&M Documentation - field installation time
2026-05-09 | AP-0004687 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2319 |  | 62.92 | 11325.14 | Controls Panels and Devices - fabricated material delivery
2026-05-12 | AP-0004684 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2277 |  | 105.14 | 18925.19 | Sheet Metal and Ductwork - ductwork release
2026-05-12 | AP-0004694 | AP | ARM-2417 | 05-300 | Freight and Expediting | V-2398 |  | 7426.23 | 7426.23 | Freight and Expediting - small tools and field consumables
2026-05-14 | PRJ-PAY-ARM-2417-20260514 | PAY | ARM-2417 | 03-200 | Startup, Testing and Commissioning |  | E-1034 | 48.68 | 3455.95 | Startup, Testing and Commissioning - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2417-20260514 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1041 | 46.33 | 3590.71 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2417-20260514 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1048 | 37.67 | 3164.49 | Controls Programming and Checkout - startup and checkout
2026-05-14 | PRJ-PAY-ARM-2417-20260514 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1081 | 30.74 | 2781.71 | Warranty and Punchlist - punchlist and closeout labor
2026-05-14 | PRJ-PAY-ARM-2417-20260514 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1088 | 43.7 | 4238.86 | Closeout and O&M Documentation - field installation time
2026-05-14 | PRJ-PAY-ARM-2417-20260514 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1095 | 32.43 | 3356.81 | Rework and Quality Correction - coordination and layout
2026-05-15 | AP-0004681 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2220 |  | 99.95 | 17991.76 | Controls Panels and Devices - released equipment package
2026-05-15 | AP-0004688 | AP | ARM-2417 | 04-100 | Insulation Subcontract | V-2320 |  | 14722.51 | 14722.51 | Insulation Subcontract - trade partner progress billing
2026-05-15 | AP-0004691 | AP | ARM-2417 | 05-400 | Small Tools and Consumables | V-2357 |  | 7568.43 | 7568.43 | Small Tools and Consumables - rental and logistics
2026-05-19 | AP-0004685 | AP | ARM-2417 | 02-510 | Controls Panels and Devices | V-2291 |  | 65.76 | 11836.56 | Controls Panels and Devices - jobsite material replenishment
2026-05-21 | PRJ-PAY-ARM-2417-20260521 | PAY | ARM-2417 | 03-300 | Sheet Metal Fabrication Labor |  | E-1039 | 55.85 | 3965.19 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2417-20260521 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1046 | 40.65 | 3150.26 | Controls Programming and Checkout - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2417-20260521 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1053 | 49.56 | 4162.85 | Warranty and Punchlist - punchlist and closeout labor
2026-05-21 | PRJ-PAY-ARM-2417-20260521 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1086 | 43.17 | 3907.26 | Closeout and O&M Documentation - field installation time
2026-05-21 | PRJ-PAY-ARM-2417-20260521 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1093 | 36.13 | 3504.63 | Rework and Quality Correction - coordination and layout
2026-05-22 | AP-0004682 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2241 |  | 65.1 | 11717.4 | Sheet Metal and Ductwork - fabricated material delivery
2026-05-22 | AP-0004689 | AP | ARM-2417 | 04-400 | Crane, Rigging and Specialty Trade | V-2334 |  | 28101.21 | 28101.21 | Crane, Rigging and Specialty Trade - insulation progress invoice
2026-05-22 | AP-0004692 | AP | ARM-2417 | 05-200 | Permits, Fees and Bonds | V-2370 |  | 5325.67 | 5325.67 | Permits, Fees and Bonds - permit and inspection fees
2026-05-25 | AP-0004686 | AP | ARM-2417 | 02-210 | Sheet Metal and Ductwork | V-2305 |  | 61.37 | 11046.05 | Sheet Metal and Ductwork - released equipment package
2026-05-28 | PRJ-PAY-ARM-2417-20260528 | PAY | ARM-2417 | 03-400 | Controls Programming and Checkout |  | E-1044 | 37.43 | 2657.84 | Controls Programming and Checkout - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2417-20260528 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1051 | 55.53 | 4303.76 | Warranty and Punchlist - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2417-20260528 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1084 | 37 | 3108.39 | Closeout and O&M Documentation - field installation time
2026-05-28 | PRJ-PAY-ARM-2417-20260528 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1091 | 37.31 | 3376.69 | Rework and Quality Correction - coordination and layout
2026-05-28 | PRJ-PAY-ARM-2417-20260528 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1098 | 32.03 | 3363.45 | Project Management and Supervision - supervision and planning
2026-05-31 | PRJ-PAY-ARM-2417-20260531 | PAY | ARM-2417 | 06-100 | Warranty and Punchlist |  | E-1049 | 43.18 | 3065.73 | Warranty and Punchlist - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2417-20260531 | PAY | ARM-2417 | 06-200 | Closeout and O&M Documentation |  | E-1082 | 41.97 | 3252.42 | Closeout and O&M Documentation - field installation time
2026-05-31 | PRJ-PAY-ARM-2417-20260531 | PAY | ARM-2417 | 06-300 | Rework and Quality Correction |  | E-1089 | 44.68 | 3753.46 | Rework and Quality Correction - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2417-20260531 | PAY | ARM-2417 | 01-100 | Project Management and Supervision |  | E-1096 | 37.22 | 3665.96 | Project Management and Supervision - supervision and planning
2026-05-31 | PRJ-PAY-ARM-2417-20260531 | PAY | ARM-2417 | 01-200 | Engineering, BIM and Coordination |  | E-1009 | 30.3 | 2939.29 | Engineering, BIM and Coordination - startup and checkout
2025-01-07 | PRJ-PAY-ARM-2421-20250107 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 26.41 | 1875.08 | Startup, Testing and Commissioning - field installation time
2025-01-07 | PRJ-PAY-ARM-2421-20250107 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 20.26 | 1570.18 | Sheet Metal Fabrication Labor - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2421-20250107 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1026 | 14.83 | 1245.32 | Controls Programming and Checkout - supervision and planning
2025-01-12 | AP-0004722 | AP | ARM-2421 | 02-610 | Insulation and Specialty Material | V-2365 |  | 60.05 | 10808.1 | Insulation and Specialty Material - ductwork release
2025-01-12 | AP-0004724 | AP | ARM-2421 | 04-400 | Crane, Rigging and Specialty Trade | V-2389 |  | 14494 | 14494 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-01-12 | AP-0004725 | AP | ARM-2421 | 05-200 | Permits, Fees and Bonds | V-2402 |  | 5270.54 | 5270.54 | Permits, Fees and Bonds - small tools and field consumables
2025-01-14 | PRJ-PAY-ARM-2421-20250114 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 19.65 | 1395.41 | Sheet Metal Fabrication Labor - coordination and layout
2025-01-14 | PRJ-PAY-ARM-2421-20250114 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1024 | 16.87 | 1307.61 | Controls Programming and Checkout - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2421-20250114 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1031 | 17.74 | 1490.57 | Warranty and Punchlist - startup and checkout
2025-01-19 | AP-0004723 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2379 |  | 71.72 | 12909.35 | Hydronic Piping and Valves - jobsite material replenishment
2025-01-21 | PRJ-PAY-ARM-2421-20250121 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1022 | 15.21 | 1079.76 | Controls Programming and Checkout - supervision and planning
2025-01-21 | PRJ-PAY-ARM-2421-20250121 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1029 | 19.55 | 1514.74 | Warranty and Punchlist - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2421-20250121 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 17.7 | 1487.21 | Closeout and O&M Documentation - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2421-20250128 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1027 | 21.61 | 1534.42 | Warranty and Punchlist - startup and checkout
2025-01-28 | PRJ-PAY-ARM-2421-20250128 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 16.84 | 1304.99 | Closeout and O&M Documentation - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2421-20250128 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1041 | 19.27 | 1618.41 | Rework and Quality Correction - field installation time
2025-01-31 | PRJ-PAY-ARM-2421-20250131 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 22.94 | 1628.59 | Closeout and O&M Documentation - punchlist and closeout labor
2025-01-31 | PRJ-PAY-ARM-2421-20250131 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1039 | 23.88 | 1850.77 | Rework and Quality Correction - field installation time
2025-01-31 | PRJ-PAY-ARM-2421-20250131 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1046 | 16.27 | 1496.75 | Project Management and Supervision - coordination and layout
2025-02-05 | AP-0004728 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2441 |  | 87.06 | 15670.91 | Major HVAC Equipment - fabricated material delivery
2025-02-07 | PRJ-PAY-ARM-2421-20250207 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 36.81 | 2613.51 | Sheet Metal Fabrication Labor - field installation time
2025-02-07 | PRJ-PAY-ARM-2421-20250207 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1020 | 33.57 | 2601.98 | Controls Programming and Checkout - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2421-20250207 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1027 | 23.08 | 1938.62 | Warranty and Punchlist - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2421-20250214 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1018 | 30.91 | 2194.84 | Controls Programming and Checkout - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2421-20250214 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1025 | 31.99 | 2478.87 | Warranty and Punchlist - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2421-20250214 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 27.26 | 2289.55 | Closeout and O&M Documentation - startup and checkout
2025-02-15 | AP-0004726 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2415 |  | 51.66 | 9298.42 | Major HVAC Equipment - jobsite material replenishment
2025-02-15 | AP-0004729 | AP | ARM-2421 | 04-100 | Insulation Subcontract | V-2450 |  | 20437.07 | 20437.07 | Insulation Subcontract - rigging and specialty support
2025-02-15 | AP-0004730 | AP | ARM-2421 | 05-300 | Freight and Expediting | V-2462 |  | 6219.98 | 6219.98 | Freight and Expediting - rental and logistics
2025-02-21 | PRJ-PAY-ARM-2421-20250221 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1023 | 39.31 | 2791.16 | Warranty and Punchlist - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2421-20250221 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 33.06 | 2562.27 | Closeout and O&M Documentation - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2421-20250221 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1037 | 26.8 | 2251.45 | Rework and Quality Correction - punchlist and closeout labor
2025-02-22 | AP-0004727 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2429 |  | 48.87 | 8796.26 | Plumbing Fixtures and Piping - released equipment package
2025-02-28 | PRJ-PAY-ARM-2421-20250228 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 40.27 | 2859.03 | Closeout and O&M Documentation - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2421-20250228 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1035 | 37.43 | 2900.47 | Rework and Quality Correction - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2421-20250228 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1042 | 29.67 | 2729.57 | Project Management and Supervision - field installation time
2025-03-07 | PRJ-PAY-ARM-2421-20250307 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1013 | 24.92 | 1769.11 | Controls Programming and Checkout - field installation time
2025-03-07 | PRJ-PAY-ARM-2421-20250307 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1021 | 22.1 | 1712.54 | Warranty and Punchlist - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2421-20250307 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 27.62 | 2320.1 | Closeout and O&M Documentation - supervision and planning
2025-03-08 | AP-0004733 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2503 |  | 67.47 | 12144.3 | Sheet Metal and Ductwork - valves and piping lot
2025-03-14 | PRJ-PAY-ARM-2421-20250314 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1019 | 26.53 | 1883.57 | Warranty and Punchlist - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2421-20250314 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 27.57 | 2137.03 | Closeout and O&M Documentation - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2421-20250314 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1033 | 27.57 | 2315.75 | Rework and Quality Correction - startup and checkout
2025-03-18 | AP-0004731 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2476 |  | 55.71 | 10027.32 | Sheet Metal and Ductwork - released equipment package
2025-03-18 | AP-0004734 | AP | ARM-2421 | 04-200 | Electrical and Controls Subcontract | V-2512 |  | 21628.65 | 21628.65 | Electrical and Controls Subcontract - trade partner progress billing
2025-03-18 | AP-0004735 | AP | ARM-2421 | 05-400 | Small Tools and Consumables | V-2524 |  | 8848.09 | 8848.09 | Small Tools and Consumables - permit and inspection fees
2025-03-21 | PRJ-PAY-ARM-2421-20250321 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 41.08 | 2916.89 | Closeout and O&M Documentation - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2421-20250321 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1031 | 29.19 | 2262.12 | Rework and Quality Correction - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2421-20250321 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1038 | 20.59 | 1894.04 | Project Management and Supervision - punchlist and closeout labor
2025-03-25 | AP-0004732 | AP | ARM-2421 | 02-510 | Controls Panels and Devices | V-2490 |  | 62.52 | 11254.48 | Controls Panels and Devices - fabricated material delivery
2025-03-28 | PRJ-PAY-ARM-2421-20250328 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1029 | 36.84 | 2615.83 | Rework and Quality Correction - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2421-20250328 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1036 | 23.35 | 1996.07 | Project Management and Supervision - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2421-20250328 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 32.41 | 2722.64 | Engineering, BIM and Coordination - field installation time
2025-03-31 | PRJ-PAY-ARM-2421-20250331 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1034 | 33.75 | 2666.22 | Project Management and Supervision - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2421-20250331 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 25.89 | 2006.62 | Engineering, BIM and Coordination - field installation time
2025-03-31 | PRJ-PAY-ARM-2421-20250331 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1048 | 26.28 | 2207.57 | Field Installation Labor - coordination and layout
2025-04-04 | AP-0004737 | AP | ARM-2421 | 02-610 | Insulation and Specialty Material | V-2047 |  | 83.54 | 15036.46 | Insulation and Specialty Material - valves and piping lot
2025-04-07 | PRJ-PAY-ARM-2421-20250407 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1014 | 41.29 | 2931.43 | Warranty and Punchlist - field installation time
2025-04-07 | PRJ-PAY-ARM-2421-20250407 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 34.55 | 2677.71 | Closeout and O&M Documentation - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2421-20250407 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1029 | 21.9 | 1839.29 | Rework and Quality Correction - supervision and planning
2025-04-11 | AP-0004738 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2210 |  | 67.97 | 12233.92 | Hydronic Piping and Valves - ductwork release
2025-04-14 | PRJ-PAY-ARM-2421-20250414 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 36.84 | 2615.69 | Closeout and O&M Documentation - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2421-20250414 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1027 | 32.98 | 2556.23 | Rework and Quality Correction - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2421-20250414 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1034 | 34.16 | 3142.52 | Project Management and Supervision - startup and checkout
2025-04-21 | AP-0004736 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2010 |  | 81.89 | 14739.9 | Hydronic Piping and Valves - fabricated material delivery
2025-04-21 | AP-0004739 | AP | ARM-2421 | 04-300 | Testing and Balancing Subcontract | V-2225 |  | 26839.9 | 26839.9 | Testing and Balancing Subcontract - insulation progress invoice
2025-04-21 | AP-0004740 | AP | ARM-2421 | 06-400 | Temporary Facilities and Protection | V-2243 |  | 9335.62 | 9335.62 | Temporary Facilities and Protection - freight and expediting
2025-04-21 | PRJ-PAY-ARM-2421-20250421 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1025 | 33.79 | 2399.35 | Rework and Quality Correction - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2421-20250421 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1032 | 32.53 | 2781.65 | Project Management and Supervision - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2421-20250421 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 40.96 | 3440.82 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2421-20250428 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1030 | 40.85 | 3226.85 | Project Management and Supervision - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2421-20250428 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 36.5 | 2828.45 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2421-20250428 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1044 | 24.2 | 2032.68 | Field Installation Labor - field installation time
2025-04-30 | PRJ-PAY-ARM-2421-20250430 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 35.87 | 2546.82 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2421-20250430 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1042 | 31.54 | 2444.65 | Field Installation Labor - field installation time
2025-04-30 | PRJ-PAY-ARM-2421-20250430 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 26.34 | 2212.24 | Startup, Testing and Commissioning - coordination and layout
2025-05-07 | AP-0004742 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2279 |  | 45.99 | 8278.96 | Major HVAC Equipment - ductwork release
2025-05-07 | PRJ-PAY-ARM-2421-20250507 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 49.4 | 3507.37 | Closeout and O&M Documentation - field installation time
2025-05-07 | PRJ-PAY-ARM-2421-20250507 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1023 | 45.59 | 3533.6 | Rework and Quality Correction - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2421-20250507 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1030 | 28.32 | 2605.31 | Project Management and Supervision - supervision and planning
2025-05-14 | AP-0004743 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2293 |  | 105.51 | 18992.51 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-05-14 | PRJ-PAY-ARM-2421-20250514 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1021 | 38.6 | 2740.56 | Rework and Quality Correction - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2421-20250514 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1028 | 44.59 | 3812.21 | Project Management and Supervision - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2421-20250514 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 41.07 | 3450.14 | Engineering, BIM and Coordination - startup and checkout
2025-05-21 | AP-0004744 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2307 |  | 48.05 | 8648.45 | Major HVAC Equipment - released equipment package
2025-05-21 | PRJ-PAY-ARM-2421-20250521 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1026 | 33.51 | 2647.13 | Project Management and Supervision - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2421-20250521 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 46.82 | 3628.8 | Engineering, BIM and Coordination - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2421-20250521 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1040 | 37 | 3107.62 | Field Installation Labor - punchlist and closeout labor
2025-05-24 | AP-0004741 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2262 |  | 81.46 | 14663.45 | Plumbing Fixtures and Piping - valves and piping lot
2025-05-24 | AP-0004745 | AP | ARM-2421 | 04-400 | Crane, Rigging and Specialty Trade | V-2313 |  | 29285.11 | 29285.11 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-05-24 | AP-0004746 | AP | ARM-2421 | 05-100 | Equipment Rental and Rigging | V-2326 |  | 9317.99 | 9317.99 | Equipment Rental and Rigging - small tools and field consumables
2025-05-28 | PRJ-PAY-ARM-2421-20250528 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 38.59 | 2740.06 | Engineering, BIM and Coordination - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2421-20250528 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1038 | 36.22 | 2806.7 | Field Installation Labor - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2421-20250528 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 33.46 | 2810.89 | Startup, Testing and Commissioning - field installation time
2025-05-31 | PRJ-PAY-ARM-2421-20250531 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1036 | 34.5 | 2449.64 | Field Installation Labor - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2421-20250531 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 37.94 | 2940.05 | Startup, Testing and Commissioning - field installation time
2025-05-31 | PRJ-PAY-ARM-2421-20250531 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 29.51 | 2478.72 | Sheet Metal Fabrication Labor - coordination and layout
2025-06-03 | AP-0004747 | AP | ARM-2421 | 02-510 | Controls Panels and Devices | V-2339 |  | 53.48 | 9626.3 | Controls Panels and Devices - ductwork release
2025-06-03 | AP-0004751 | AP | ARM-2421 | 04-100 | Insulation Subcontract | V-2388 |  | 29813.79 | 29813.79 | Insulation Subcontract - electrical coordination scope
2025-06-03 | AP-0004752 | AP | ARM-2421 | 05-200 | Permits, Fees and Bonds | V-2400 |  | 4588.05 | 4588.05 | Permits, Fees and Bonds - rental and logistics
2025-06-07 | PRJ-PAY-ARM-2421-20250607 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1016 | 59.19 | 4202.81 | Rework and Quality Correction - field installation time
2025-06-07 | PRJ-PAY-ARM-2421-20250607 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1024 | 33.01 | 2822.54 | Project Management and Supervision - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2421-20250607 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 35.7 | 2999.03 | Engineering, BIM and Coordination - supervision and planning
2025-06-10 | AP-0004748 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2353 |  | 42.89 | 7720.62 | Sheet Metal and Ductwork - jobsite material replenishment
2025-06-10 | AP-0004753 | AP | ARM-2421 | 06-400 | Temporary Facilities and Protection | V-2414 |  | 7078.22 | 7078.22 | Temporary Facilities and Protection - permit and inspection fees
2025-06-14 | PRJ-PAY-ARM-2421-20250614 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1022 | 40.26 | 3180.65 | Project Management and Supervision - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2421-20250614 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 40.78 | 3160.16 | Engineering, BIM and Coordination - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2421-20250614 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1036 | 36.46 | 3062.88 | Field Installation Labor - startup and checkout
2025-06-17 | AP-0004749 | AP | ARM-2421 | 02-510 | Controls Panels and Devices | V-2367 |  | 70.26 | 12646.42 | Controls Panels and Devices - released equipment package
2025-06-21 | PRJ-PAY-ARM-2421-20250621 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 40.7 | 2889.82 | Engineering, BIM and Coordination - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2421-20250621 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1034 | 34.34 | 2661.55 | Field Installation Labor - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2421-20250621 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 33.62 | 2824.22 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-06-24 | AP-0004750 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2381 |  | 78.22 | 14079.22 | Sheet Metal and Ductwork - fabricated material delivery
2025-06-28 | PRJ-PAY-ARM-2421-20250628 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1032 | 42.01 | 2982.88 | Field Installation Labor - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2421-20250628 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 31.3 | 2425.53 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2421-20250628 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 29.49 | 2476.89 | Sheet Metal Fabrication Labor - field installation time
2025-06-30 | PRJ-PAY-ARM-2421-20250630 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 39.19 | 2782.64 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2421-20250630 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 29.27 | 2268.78 | Sheet Metal Fabrication Labor - field installation time
2025-06-30 | PRJ-PAY-ARM-2421-20250630 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1051 | 39.67 | 3332.18 | Controls Programming and Checkout - coordination and layout
2025-07-03 | AP-0004757 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2465 |  | 72.15 | 12987 | Hydronic Piping and Valves - valves and piping lot
2025-07-06 | AP-0004754 | AP | ARM-2421 | 02-610 | Insulation and Specialty Material | V-2426 |  | 80.9 | 14562.66 | Insulation and Specialty Material - jobsite material replenishment
2025-07-06 | AP-0004758 | AP | ARM-2421 | 04-200 | Electrical and Controls Subcontract | V-2472 |  | 29982.68 | 29982.68 | Electrical and Controls Subcontract - rigging and specialty support
2025-07-06 | AP-0004759 | AP | ARM-2421 | 05-300 | Freight and Expediting | V-2484 |  | 5413.48 | 5413.48 | Freight and Expediting - permit and inspection fees
2025-07-07 | PRJ-PAY-ARM-2421-20250707 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1018 | 46.2 | 3650.16 | Project Management and Supervision - field installation time
2025-07-07 | PRJ-PAY-ARM-2421-20250707 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 47.26 | 3662.66 | Engineering, BIM and Coordination - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2421-20250707 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1032 | 32.3 | 2713.24 | Field Installation Labor - supervision and planning
2025-07-13 | AP-0004755 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2439 |  | 43.58 | 7843.91 | Hydronic Piping and Valves - released equipment package
2025-07-13 | AP-0004760 | AP | ARM-2421 | 05-100 | Equipment Rental and Rigging | V-2498 |  | 5489.32 | 5489.32 | Equipment Rental and Rigging - freight and expediting
2025-07-14 | PRJ-PAY-ARM-2421-20250714 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 38.25 | 2715.78 | Engineering, BIM and Coordination - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2421-20250714 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1030 | 41.52 | 3217.81 | Field Installation Labor - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2421-20250714 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 35.67 | 2996.32 | Startup, Testing and Commissioning - startup and checkout
2025-07-20 | AP-0004756 | AP | ARM-2421 | 02-610 | Insulation and Specialty Material | V-2452 |  | 75.94 | 13669 | Insulation and Specialty Material - fabricated material delivery
2025-07-21 | PRJ-PAY-ARM-2421-20250721 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1028 | 37.37 | 2653.5 | Field Installation Labor - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2421-20250721 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 39.08 | 3028.56 | Startup, Testing and Commissioning - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2421-20250721 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 32.44 | 2725.11 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2421-20250728 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 53.83 | 3822.11 | Startup, Testing and Commissioning - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2421-20250728 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 35.61 | 2760.05 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2421-20250728 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1047 | 28.05 | 2356.29 | Controls Programming and Checkout - field installation time
2025-07-31 | PRJ-PAY-ARM-2421-20250731 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 35.41 | 2513.98 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2421-20250731 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1045 | 47.97 | 3717.95 | Controls Programming and Checkout - field installation time
2025-07-31 | PRJ-PAY-ARM-2421-20250731 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1052 | 45.28 | 3803.36 | Warranty and Punchlist - coordination and layout
2025-08-06 | AP-0004764 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2047 |  | 62.91 | 11324.02 | Plumbing Fixtures and Piping - ductwork release
2025-08-07 | PRJ-PAY-ARM-2421-20250807 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 27.69 | 1965.99 | Engineering, BIM and Coordination - field installation time
2025-08-07 | PRJ-PAY-ARM-2421-20250807 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1026 | 32.54 | 2521.73 | Field Installation Labor - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2421-20250807 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 37.9 | 3183.49 | Startup, Testing and Commissioning - supervision and planning
2025-08-09 | AP-0004761 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2510 |  | 69 | 12419.94 | Major HVAC Equipment - released equipment package
2025-08-09 | AP-0004765 | AP | ARM-2421 | 04-300 | Testing and Balancing Subcontract | V-2098 |  | 27312.68 | 27312.68 | Testing and Balancing Subcontract - trade partner progress billing
2025-08-09 | AP-0004766 | AP | ARM-2421 | 05-400 | Small Tools and Consumables | V-2220 |  | 8312.55 | 8312.55 | Small Tools and Consumables - freight and expediting
2025-08-14 | PRJ-PAY-ARM-2421-20250814 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1024 | 28.51 | 2024.23 | Field Installation Labor - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2421-20250814 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 35.83 | 2776.91 | Startup, Testing and Commissioning - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2421-20250814 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 28.82 | 2421.01 | Sheet Metal Fabrication Labor - startup and checkout
2025-08-16 | AP-0004762 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2524 |  | 46.69 | 8404.69 | Plumbing Fixtures and Piping - fabricated material delivery
2025-08-21 | PRJ-PAY-ARM-2421-20250821 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 36.5 | 2591.61 | Startup, Testing and Commissioning - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2421-20250821 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 29.57 | 2291.97 | Sheet Metal Fabrication Labor - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2421-20250821 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1043 | 33.27 | 2794.97 | Controls Programming and Checkout - punchlist and closeout labor
2025-08-23 | AP-0004763 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2010 |  | 72.09 | 12976.64 | Major HVAC Equipment - valves and piping lot
2025-08-28 | PRJ-PAY-ARM-2421-20250828 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 46.01 | 3266.92 | Sheet Metal Fabrication Labor - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2421-20250828 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1041 | 33.78 | 2618.19 | Controls Programming and Checkout - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2421-20250828 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1048 | 32.57 | 2735.67 | Warranty and Punchlist - field installation time
2025-08-31 | PRJ-PAY-ARM-2421-20250831 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1039 | 41.23 | 2927.45 | Controls Programming and Checkout - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2421-20250831 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1046 | 47.76 | 3701.31 | Warranty and Punchlist - field installation time
2025-08-31 | PRJ-PAY-ARM-2421-20250831 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 30.4 | 2553.81 | Closeout and O&M Documentation - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2421-20250907 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1020 | 36.48 | 2590.12 | Field Installation Labor - field installation time
2025-09-07 | PRJ-PAY-ARM-2421-20250907 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 26.2 | 2030.33 | Startup, Testing and Commissioning - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2421-20250907 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 28.75 | 2415.11 | Sheet Metal Fabrication Labor - supervision and planning
2025-09-12 | AP-0004767 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2241 |  | 72.3 | 13014.67 | Sheet Metal and Ductwork - fabricated material delivery
2025-09-12 | AP-0004770 | AP | ARM-2421 | 04-400 | Crane, Rigging and Specialty Trade | V-2286 |  | 26191.6 | 26191.6 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-09-12 | AP-0004771 | AP | ARM-2421 | 06-400 | Temporary Facilities and Protection | V-2298 |  | 5701.72 | 5701.72 | Temporary Facilities and Protection - small tools and field consumables
2025-09-14 | PRJ-PAY-ARM-2421-20250914 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 25.8 | 1832.01 | Startup, Testing and Commissioning - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2421-20250914 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 38.84 | 3009.96 | Sheet Metal Fabrication Labor - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2421-20250914 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1039 | 31.41 | 2638.19 | Controls Programming and Checkout - startup and checkout
2025-09-19 | AP-0004768 | AP | ARM-2421 | 02-510 | Controls Panels and Devices | V-2258 |  | 49.81 | 8965.37 | Controls Panels and Devices - valves and piping lot
2025-09-19 | AP-0004772 | AP | ARM-2421 | 05-300 | Freight and Expediting | V-2312 |  | 5013.02 | 5013.02 | Freight and Expediting - rental and logistics
2025-09-21 | PRJ-PAY-ARM-2421-20250921 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 33.28 | 2362.71 | Sheet Metal Fabrication Labor - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2421-20250921 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1037 | 35.66 | 2763.6 | Controls Programming and Checkout - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2421-20250921 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1044 | 38.95 | 3271.74 | Warranty and Punchlist - punchlist and closeout labor
2025-09-25 | AP-0004769 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2277 |  | 102.77 | 18497.88 | Sheet Metal and Ductwork - ductwork release
2025-09-28 | PRJ-PAY-ARM-2421-20250928 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1035 | 43.39 | 3080.91 | Controls Programming and Checkout - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2421-20250928 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1042 | 41.33 | 3203.24 | Warranty and Punchlist - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2421-20250928 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 31.68 | 2661.18 | Closeout and O&M Documentation - field installation time
2025-09-30 | PRJ-PAY-ARM-2421-20250930 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1040 | 48.84 | 3467.36 | Warranty and Punchlist - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2421-20250930 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 38.04 | 2947.95 | Closeout and O&M Documentation - field installation time
2025-09-30 | PRJ-PAY-ARM-2421-20250930 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1080 | 26.23 | 2203.51 | Rework and Quality Correction - coordination and layout
2025-10-05 | AP-0004775 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2351 |  | 55.71 | 10028 | Hydronic Piping and Valves - jobsite material replenishment
2025-10-07 | PRJ-PAY-ARM-2421-20251007 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 33.92 | 2408.07 | Startup, Testing and Commissioning - field installation time
2025-10-07 | PRJ-PAY-ARM-2421-20251007 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 26.46 | 2050.54 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2421-20251007 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1035 | 27.51 | 2310.43 | Controls Programming and Checkout - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2421-20251014 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 34.03 | 2416.2 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2421-20251014 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1033 | 36.57 | 2834.35 | Controls Programming and Checkout - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2421-20251014 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1040 | 27.97 | 2349.11 | Warranty and Punchlist - startup and checkout
2025-10-15 | AP-0004773 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2324 |  | 83.13 | 14964.3 | Hydronic Piping and Valves - valves and piping lot
2025-10-15 | AP-0004776 | AP | ARM-2421 | 04-100 | Insulation Subcontract | V-2360 |  | 25197.17 | 25197.17 | Insulation Subcontract - testing and balancing services
2025-10-15 | AP-0004777 | AP | ARM-2421 | 05-100 | Equipment Rental and Rigging | V-2372 |  | 8764.23 | 8764.23 | Equipment Rental and Rigging - rental and logistics
2025-10-21 | PRJ-PAY-ARM-2421-20251021 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1031 | 34.05 | 2417.68 | Controls Programming and Checkout - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2421-20251021 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1038 | 37.62 | 2915.87 | Warranty and Punchlist - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2421-20251021 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 32.87 | 2761.36 | Closeout and O&M Documentation - punchlist and closeout labor
2025-10-22 | AP-0004774 | AP | ARM-2421 | 02-610 | Insulation and Specialty Material | V-2338 |  | 80.26 | 14446.74 | Insulation and Specialty Material - ductwork release
2025-10-28 | PRJ-PAY-ARM-2421-20251028 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1036 | 42.61 | 3024.96 | Warranty and Punchlist - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2421-20251028 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 31.24 | 2421.4 | Closeout and O&M Documentation - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2421-20251028 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1050 | 28.01 | 2353.09 | Rework and Quality Correction - field installation time
2025-10-31 | PRJ-PAY-ARM-2421-20251031 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 26.21 | 1861.16 | Closeout and O&M Documentation - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2421-20251031 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1048 | 30.46 | 2360.41 | Rework and Quality Correction - field installation time
2025-10-31 | PRJ-PAY-ARM-2421-20251031 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1081 | 30.04 | 2763.36 | Project Management and Supervision - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2421-20251107 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1022 | 30.77 | 2184.6 | Sheet Metal Fabrication Labor - field installation time
2025-11-07 | PRJ-PAY-ARM-2421-20251107 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1029 | 22.74 | 1762.21 | Controls Programming and Checkout - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2421-20251107 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1036 | 22.36 | 1878.47 | Warranty and Punchlist - supervision and planning
2025-11-08 | AP-0004780 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2414 |  | 68.94 | 12409.28 | Plumbing Fixtures and Piping - released equipment package
2025-11-14 | PRJ-PAY-ARM-2421-20251114 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1027 | 33.73 | 2394.82 | Controls Programming and Checkout - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2421-20251114 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1034 | 27.86 | 2158.81 | Warranty and Punchlist - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2421-20251114 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 19.66 | 1651.27 | Closeout and O&M Documentation - startup and checkout
2025-11-18 | AP-0004778 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2386 |  | 73.15 | 13166.38 | Plumbing Fixtures and Piping - ductwork release
2025-11-18 | AP-0004781 | AP | ARM-2421 | 04-200 | Electrical and Controls Subcontract | V-2422 |  | 18291.41 | 18291.41 | Electrical and Controls Subcontract - electrical coordination scope
2025-11-18 | AP-0004782 | AP | ARM-2421 | 05-200 | Permits, Fees and Bonds | V-2434 |  | 5819.99 | 5819.99 | Permits, Fees and Bonds - permit and inspection fees
2025-11-21 | PRJ-PAY-ARM-2421-20251121 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1032 | 26.04 | 1848.94 | Warranty and Punchlist - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2421-20251121 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 30.86 | 2391.35 | Closeout and O&M Documentation - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2421-20251121 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1046 | 20.69 | 1738.13 | Rework and Quality Correction - punchlist and closeout labor
2025-11-25 | AP-0004779 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2400 |  | 33.44 | 6018.6 | Major HVAC Equipment - jobsite material replenishment
2025-11-28 | PRJ-PAY-ARM-2421-20251128 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 23.25 | 1650.55 | Closeout and O&M Documentation - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2421-20251128 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1044 | 19.37 | 1501.45 | Rework and Quality Correction - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2421-20251128 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1051 | 23.94 | 2202.07 | Project Management and Supervision - field installation time
2025-11-30 | PRJ-PAY-ARM-2421-20251130 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1042 | 26.28 | 1866.23 | Rework and Quality Correction - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2421-20251130 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1049 | 16.15 | 1381.23 | Project Management and Supervision - field installation time
2025-11-30 | PRJ-PAY-ARM-2421-20251130 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 19.74 | 1658.42 | Engineering, BIM and Coordination - coordination and layout
2025-12-04 | AP-0004784 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2460 |  | 66.73 | 12011.07 | Sheet Metal and Ductwork - released equipment package
2025-12-07 | PRJ-PAY-ARM-2421-20251207 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1023 | 27.61 | 1960.32 | Controls Programming and Checkout - field installation time
2025-12-07 | PRJ-PAY-ARM-2421-20251207 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1030 | 22.68 | 1757.4 | Warranty and Punchlist - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2421-20251207 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 22.02 | 1849.5 | Closeout and O&M Documentation - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2421-20251214 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1028 | 25.02 | 1776.27 | Warranty and Punchlist - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2421-20251214 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 21.75 | 1685.56 | Closeout and O&M Documentation - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2421-20251214 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1042 | 22.65 | 1902.19 | Rework and Quality Correction - startup and checkout
2025-12-21 | AP-0004783 | AP | ARM-2421 | 02-510 | Controls Panels and Devices | V-2446 |  | 70.29 | 12653.06 | Controls Panels and Devices - jobsite material replenishment
2025-12-21 | AP-0004785 | AP | ARM-2421 | 04-300 | Testing and Balancing Subcontract | V-2471 |  | 16684.56 | 16684.56 | Testing and Balancing Subcontract - rigging and specialty support
2025-12-21 | AP-0004786 | AP | ARM-2421 | 05-300 | Freight and Expediting | V-2483 |  | 6528.73 | 6528.73 | Freight and Expediting - freight and expediting
2025-12-21 | PRJ-PAY-ARM-2421-20251221 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 28.62 | 2032.27 | Closeout and O&M Documentation - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2421-20251221 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1040 | 19.99 | 1548.95 | Rework and Quality Correction - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2421-20251221 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1047 | 13.29 | 1222.62 | Project Management and Supervision - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2421-20251228 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1038 | 19.38 | 1376.02 | Rework and Quality Correction - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2421-20251228 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1045 | 19.18 | 1639.92 | Project Management and Supervision - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2421-20251228 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 16.5 | 1385.76 | Engineering, BIM and Coordination - field installation time
2025-12-31 | PRJ-PAY-ARM-2421-20251231 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1043 | 20.2 | 1595.89 | Project Management and Supervision - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2421-20251231 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 18.35 | 1422.26 | Engineering, BIM and Coordination - field installation time
2025-12-31 | PRJ-PAY-ARM-2421-20251231 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1083 | 17.97 | 1509.2 | Field Installation Labor - coordination and layout
2026-01-07 | AP-0004788 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2510 |  | 84.63 | 15232.73 | Hydronic Piping and Valves - fabricated material delivery
2026-01-07 | PRJ-PAY-ARM-2421-20260107 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1024 | 22.6 | 1604.51 | Warranty and Punchlist - field installation time
2026-01-07 | PRJ-PAY-ARM-2421-20260107 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1031 | 20.83 | 1614.02 | Closeout and O&M Documentation - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2421-20260107 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1038 | 20.93 | 1758.08 | Rework and Quality Correction - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2421-20260114 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1029 | 23.28 | 1652.73 | Closeout and O&M Documentation - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2421-20260114 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1036 | 17.29 | 1340.25 | Rework and Quality Correction - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2421-20260114 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1043 | 15.91 | 1463.91 | Project Management and Supervision - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2421-20260121 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1034 | 19.21 | 1363.59 | Rework and Quality Correction - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2421-20260121 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1041 | 15.01 | 1282.95 | Project Management and Supervision - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2421-20260121 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1048 | 17.11 | 1437.26 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-01-24 | AP-0004787 | AP | ARM-2421 | 02-610 | Insulation and Specialty Material | V-2496 |  | 47.24 | 8502.98 | Insulation and Specialty Material - released equipment package
2026-01-24 | AP-0004789 | AP | ARM-2421 | 04-400 | Crane, Rigging and Specialty Trade | V-2521 |  | 14505.16 | 14505.16 | Crane, Rigging and Specialty Trade - trade partner progress billing
2026-01-24 | AP-0004790 | AP | ARM-2421 | 05-400 | Small Tools and Consumables | V-2533 |  | 5274.61 | 5274.61 | Small Tools and Consumables - small tools and field consumables
2026-01-28 | PRJ-PAY-ARM-2421-20260128 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1039 | 17.75 | 1402.48 | Project Management and Supervision - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2421-20260128 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1046 | 15.25 | 1181.64 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2421-20260128 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1053 | 19.24 | 1616.24 | Field Installation Labor - field installation time
2026-01-31 | PRJ-PAY-ARM-2421-20260131 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 18.01 | 1278.52 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2421-20260131 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1051 | 21.4 | 1658.21 | Field Installation Labor - field installation time
2026-01-31 | PRJ-PAY-ARM-2421-20260131 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1084 | 20.98 | 1762.67 | Startup, Testing and Commissioning - coordination and layout
2026-02-03 | AP-0004791 | AP | ARM-2421 | 02-110 | Major HVAC Equipment | V-2029 |  | 58.6 | 10547.49 | Major HVAC Equipment - fabricated material delivery
2026-02-03 | AP-0004793 | AP | ARM-2421 | 04-100 | Insulation Subcontract | V-2220 |  | 16010.77 | 16010.77 | Insulation Subcontract - insulation progress invoice
2026-02-03 | AP-0004794 | AP | ARM-2421 | 06-400 | Temporary Facilities and Protection | V-2237 |  | 4872.84 | 4872.84 | Temporary Facilities and Protection - rental and logistics
2026-02-07 | PRJ-PAY-ARM-2421-20260207 | PAY | ARM-2421 | 06-200 | Closeout and O&M Documentation |  | E-1025 | 24.31 | 1725.68 | Closeout and O&M Documentation - field installation time
2026-02-07 | PRJ-PAY-ARM-2421-20260207 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1032 | 26.1 | 2023.13 | Rework and Quality Correction - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2421-20260207 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1039 | 25 | 2299.55 | Project Management and Supervision - supervision and planning
2026-02-10 | AP-0004792 | AP | ARM-2421 | 02-410 | Plumbing Fixtures and Piping | V-2201 |  | 88.36 | 15905.08 | Plumbing Fixtures and Piping - valves and piping lot
2026-02-14 | PRJ-PAY-ARM-2421-20260214 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1030 | 27.11 | 1925.02 | Rework and Quality Correction - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2421-20260214 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1037 | 20.8 | 1777.99 | Project Management and Supervision - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2421-20260214 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 21.89 | 1839.03 | Engineering, BIM and Coordination - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2421-20260221 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1035 | 22.67 | 1790.79 | Project Management and Supervision - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2421-20260221 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1042 | 27.04 | 2095.27 | Engineering, BIM and Coordination - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2421-20260221 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1049 | 21.6 | 1814.16 | Field Installation Labor - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2421-20260228 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 30.01 | 2130.5 | Engineering, BIM and Coordination - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2421-20260228 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1047 | 22.97 | 1780.15 | Field Installation Labor - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2421-20260228 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1080 | 29.37 | 2466.82 | Startup, Testing and Commissioning - field installation time
2026-03-06 | AP-0004795 | AP | ARM-2421 | 02-210 | Sheet Metal and Ductwork | V-2256 |  | 80.49 | 14487.46 | Sheet Metal and Ductwork - valves and piping lot
2026-03-06 | AP-0004797 | AP | ARM-2421 | 04-200 | Electrical and Controls Subcontract | V-2286 |  | 16905.78 | 16905.78 | Electrical and Controls Subcontract - testing and balancing services
2026-03-06 | AP-0004798 | AP | ARM-2421 | 05-100 | Equipment Rental and Rigging | V-2298 |  | 6916.01 | 6916.01 | Equipment Rental and Rigging - permit and inspection fees
2026-03-07 | PRJ-PAY-ARM-2421-20260307 | PAY | ARM-2421 | 06-300 | Rework and Quality Correction |  | E-1026 | 19.62 | 1392.84 | Rework and Quality Correction - field installation time
2026-03-07 | PRJ-PAY-ARM-2421-20260307 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1033 | 20.34 | 1739.23 | Project Management and Supervision - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2421-20260307 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 17.5 | 1469.84 | Engineering, BIM and Coordination - supervision and planning
2026-03-13 | AP-0004796 | AP | ARM-2421 | 02-510 | Controls Panels and Devices | V-2275 |  | 64.66 | 11639.65 | Controls Panels and Devices - ductwork release
2026-03-14 | PRJ-PAY-ARM-2421-20260314 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1031 | 19.54 | 1544.03 | Project Management and Supervision - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2421-20260314 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1038 | 21.84 | 1692.39 | Engineering, BIM and Coordination - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2421-20260314 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1045 | 17.82 | 1496.84 | Field Installation Labor - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2421-20260321 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1036 | 29.49 | 2094.05 | Engineering, BIM and Coordination - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2421-20260321 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1043 | 18.1 | 1402.83 | Field Installation Labor - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2421-20260321 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1050 | 21.41 | 1798.74 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2421-20260328 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1041 | 27.51 | 1953.13 | Field Installation Labor - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2421-20260328 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1048 | 21.79 | 1688.39 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2421-20260328 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1081 | 25.36 | 2130.45 | Sheet Metal Fabrication Labor - field installation time
2026-03-31 | PRJ-PAY-ARM-2421-20260331 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 29.38 | 2085.87 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2421-20260331 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1053 | 21.44 | 1661.62 | Sheet Metal Fabrication Labor - field installation time
2026-03-31 | PRJ-PAY-ARM-2421-20260331 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1086 | 23.53 | 1976.86 | Controls Programming and Checkout - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2421-20260407 | PAY | ARM-2421 | 01-100 | Project Management and Supervision |  | E-1027 | 25.49 | 2013.73 | Project Management and Supervision - field installation time
2026-04-07 | PRJ-PAY-ARM-2421-20260407 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1034 | 21 | 1627.34 | Engineering, BIM and Coordination - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2421-20260407 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1041 | 17.86 | 1500.06 | Field Installation Labor - supervision and planning
2026-04-09 | AP-0004799 | AP | ARM-2421 | 02-310 | Hydronic Piping and Valves | V-2312 |  | 96.15 | 17306.38 | Hydronic Piping and Valves - ductwork release
2026-04-09 | AP-0004801 | AP | ARM-2421 | 04-300 | Testing and Balancing Subcontract | V-2336 |  | 19634.13 | 19634.13 | Testing and Balancing Subcontract - electrical coordination scope
2026-04-09 | AP-0004802 | AP | ARM-2421 | 05-200 | Permits, Fees and Bonds | V-2348 |  | 6829.27 | 6829.27 | Permits, Fees and Bonds - freight and expediting
2026-04-14 | PRJ-PAY-ARM-2421-20260414 | PAY | ARM-2421 | 01-200 | Engineering, BIM and Coordination |  | E-1032 | 27.3 | 1938.59 | Engineering, BIM and Coordination - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2421-20260414 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1039 | 25.86 | 2004.25 | Field Installation Labor - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2421-20260414 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1046 | 21.54 | 1809.11 | Startup, Testing and Commissioning - startup and checkout
2026-04-16 | AP-0004800 | AP | ARM-2421 | 02-610 | Insulation and Specialty Material | V-2326 |  | 74.59 | 13425.31 | Insulation and Specialty Material - jobsite material replenishment
2026-04-21 | PRJ-PAY-ARM-2421-20260421 | PAY | ARM-2421 | 03-100 | Field Installation Labor |  | E-1037 | 33.32 | 2365.41 | Field Installation Labor - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2421-20260421 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1044 | 25.58 | 1982.47 | Startup, Testing and Commissioning - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2421-20260421 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1051 | 22.87 | 1921.46 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2421-20260428 | PAY | ARM-2421 | 03-200 | Startup, Testing and Commissioning |  | E-1042 | 28.79 | 2044.07 | Startup, Testing and Commissioning - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2421-20260428 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1049 | 22.86 | 1771.93 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2421-20260428 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1082 | 28.59 | 2401.62 | Controls Programming and Checkout - field installation time
2026-04-30 | PRJ-PAY-ARM-2421-20260430 | PAY | ARM-2421 | 03-300 | Sheet Metal Fabrication Labor |  | E-1047 | 25.03 | 1776.81 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2421-20260430 | PAY | ARM-2421 | 03-400 | Controls Programming and Checkout |  | E-1080 | 24.41 | 1891.59 | Controls Programming and Checkout - field installation time
2026-04-30 | PRJ-PAY-ARM-2421-20260430 | PAY | ARM-2421 | 06-100 | Warranty and Punchlist |  | E-1087 | 23.52 | 1975.93 | Warranty and Punchlist - coordination and layout
2025-01-03 | AP-0004803 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2329 |  | 34.85 | 6272.79 | Hydronic Piping and Valves - released equipment package
2025-01-03 | AP-0004804 | AP | ARM-2501 | 04-100 | Insulation Subcontract | V-2341 |  | 4007.62 | 4007.62 | Insulation Subcontract - trade partner progress billing
2025-01-03 | AP-0004805 | AP | ARM-2501 | 05-400 | Small Tools and Consumables | V-2353 |  | 1393.96 | 1393.96 | Small Tools and Consumables - rental and logistics
2025-01-07 | PRJ-PAY-ARM-2501-20250107 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1007 | 3.54 | 280 | Project Management and Supervision - field installation time
2025-01-07 | PRJ-PAY-ARM-2501-20250107 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1014 | 5.26 | 407.29 | Engineering, BIM and Coordination - coordination and layout
2025-01-07 | PRJ-PAY-ARM-2501-20250107 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1021 | 5.55 | 466.15 | Field Installation Labor - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2501-20250114 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1012 | 6.26 | 444.13 | Engineering, BIM and Coordination - coordination and layout
2025-01-14 | PRJ-PAY-ARM-2501-20250114 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1019 | 5.13 | 397.96 | Field Installation Labor - supervision and planning
2025-01-14 | PRJ-PAY-ARM-2501-20250114 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 5.09 | 427.82 | Startup, Testing and Commissioning - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2501-20250121 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1017 | 5.06 | 359.38 | Field Installation Labor - supervision and planning
2025-01-21 | PRJ-PAY-ARM-2501-20250121 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 7.43 | 575.51 | Startup, Testing and Commissioning - startup and checkout
2025-01-21 | PRJ-PAY-ARM-2501-20250121 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 4.1 | 344.41 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2501-20250128 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 5.84 | 414.9 | Startup, Testing and Commissioning - startup and checkout
2025-01-28 | PRJ-PAY-ARM-2501-20250128 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 4.05 | 313.82 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-01-28 | PRJ-PAY-ARM-2501-20250128 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1036 | 5.29 | 444.25 | Controls Programming and Checkout - field installation time
2025-01-31 | PRJ-PAY-ARM-2501-20250131 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 5.25 | 372.77 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-01-31 | PRJ-PAY-ARM-2501-20250131 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1034 | 4.47 | 346.19 | Controls Programming and Checkout - field installation time
2025-01-31 | PRJ-PAY-ARM-2501-20250131 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1041 | 3.93 | 329.72 | Warranty and Punchlist - coordination and layout
2025-02-06 | AP-0004806 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2367 |  | 80.38 | 14469.11 | Plumbing Fixtures and Piping - fabricated material delivery
2025-02-06 | AP-0004807 | AP | ARM-2501 | 04-200 | Electrical and Controls Subcontract | V-2379 |  | 8376.85 | 8376.85 | Electrical and Controls Subcontract - insulation progress invoice
2025-02-06 | AP-0004808 | AP | ARM-2501 | 06-400 | Temporary Facilities and Protection | V-2391 |  | 2665.36 | 2665.36 | Temporary Facilities and Protection - permit and inspection fees
2025-02-07 | PRJ-PAY-ARM-2501-20250207 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 17.25 | 1224.4 | Engineering, BIM and Coordination - field installation time
2025-02-07 | PRJ-PAY-ARM-2501-20250207 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1015 | 16.84 | 1305.45 | Field Installation Labor - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2501-20250207 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 10.91 | 916.13 | Startup, Testing and Commissioning - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2501-20250214 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1013 | 15.46 | 1097.75 | Field Installation Labor - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2501-20250214 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 16.39 | 1270.02 | Startup, Testing and Commissioning - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2501-20250214 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 13.14 | 1103.68 | Sheet Metal Fabrication Labor - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2501-20250221 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 11.84 | 840.5 | Startup, Testing and Commissioning - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2501-20250221 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 15.48 | 1199.85 | Sheet Metal Fabrication Labor - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2501-20250221 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1032 | 13.6 | 1142.58 | Controls Programming and Checkout - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2501-20250228 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 14.82 | 1052.02 | Sheet Metal Fabrication Labor - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2501-20250228 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1030 | 13.28 | 1028.83 | Controls Programming and Checkout - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2501-20250228 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1037 | 9.11 | 764.83 | Warranty and Punchlist - field installation time
2025-03-07 | PRJ-PAY-ARM-2501-20250307 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1009 | 23.77 | 1687.59 | Field Installation Labor - field installation time
2025-03-07 | PRJ-PAY-ARM-2501-20250307 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1016 | 18.62 | 1443.17 | Startup, Testing and Commissioning - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2501-20250307 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 20.98 | 1762.53 | Sheet Metal Fabrication Labor - supervision and planning
2025-03-09 | AP-0004809 | AP | ARM-2501 | 02-510 | Controls Panels and Devices | V-2405 |  | 71.35 | 12843.58 | Controls Panels and Devices - valves and piping lot
2025-03-09 | AP-0004811 | AP | ARM-2501 | 04-300 | Testing and Balancing Subcontract | V-2429 |  | 14584.19 | 14584.19 | Testing and Balancing Subcontract - testing and balancing services
2025-03-09 | AP-0004812 | AP | ARM-2501 | 05-100 | Equipment Rental and Rigging | V-2440 |  | 5706.86 | 5706.86 | Equipment Rental and Rigging - freight and expediting
2025-03-14 | PRJ-PAY-ARM-2501-20250314 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1014 | 20.38 | 1446.63 | Startup, Testing and Commissioning - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2501-20250314 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 17.98 | 1393.23 | Sheet Metal Fabrication Labor - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2501-20250314 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1028 | 19.6 | 1646.73 | Controls Programming and Checkout - startup and checkout
2025-03-16 | AP-0004810 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2419 |  | 48.42 | 8715.66 | Sheet Metal and Ductwork - ductwork release
2025-03-21 | PRJ-PAY-ARM-2501-20250321 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 21.75 | 1544.51 | Sheet Metal Fabrication Labor - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2501-20250321 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1026 | 16.61 | 1287.24 | Controls Programming and Checkout - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2501-20250321 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1033 | 14.04 | 1179.46 | Warranty and Punchlist - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2501-20250328 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1024 | 14.8 | 1050.95 | Controls Programming and Checkout - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2501-20250328 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1031 | 19.95 | 1546.27 | Warranty and Punchlist - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2501-20250328 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 15.56 | 1306.98 | Closeout and O&M Documentation - field installation time
2025-03-31 | PRJ-PAY-ARM-2501-20250331 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1029 | 18.37 | 1304.15 | Warranty and Punchlist - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2501-20250331 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 21.53 | 1668.52 | Closeout and O&M Documentation - field installation time
2025-03-31 | PRJ-PAY-ARM-2501-20250331 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1043 | 15.37 | 1291.28 | Rework and Quality Correction - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2501-20250407 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 28.18 | 2000.82 | Startup, Testing and Commissioning - field installation time
2025-04-07 | PRJ-PAY-ARM-2501-20250407 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1017 | 19.73 | 1529.22 | Sheet Metal Fabrication Labor - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2501-20250407 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1024 | 19.74 | 1658.31 | Controls Programming and Checkout - supervision and planning
2025-04-12 | AP-0004813 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2453 |  | 72.97 | 13135.42 | Insulation and Specialty Material - ductwork release
2025-04-12 | AP-0004815 | AP | ARM-2501 | 04-400 | Crane, Rigging and Specialty Trade | V-2477 |  | 16032.12 | 16032.12 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-04-12 | AP-0004816 | AP | ARM-2501 | 05-200 | Permits, Fees and Bonds | V-2490 |  | 5829.86 | 5829.86 | Permits, Fees and Bonds - small tools and field consumables
2025-04-14 | PRJ-PAY-ARM-2501-20250414 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1015 | 18.02 | 1279.53 | Sheet Metal Fabrication Labor - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2501-20250414 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1022 | 21.62 | 1675.89 | Controls Programming and Checkout - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2501-20250414 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1029 | 20.04 | 1683.19 | Warranty and Punchlist - startup and checkout
2025-04-19 | AP-0004814 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2467 |  | 72.77 | 13098.96 | Hydronic Piping and Valves - jobsite material replenishment
2025-04-21 | PRJ-PAY-ARM-2501-20250421 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1020 | 21 | 1491.25 | Controls Programming and Checkout - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2501-20250421 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1027 | 19.39 | 1502.48 | Warranty and Punchlist - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2501-20250421 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 18.11 | 1521.14 | Closeout and O&M Documentation - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2501-20250428 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1025 | 21.8 | 1547.97 | Warranty and Punchlist - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2501-20250428 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 22.76 | 1764.19 | Closeout and O&M Documentation - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2501-20250428 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1039 | 19.27 | 1618.73 | Rework and Quality Correction - field installation time
2025-04-30 | PRJ-PAY-ARM-2501-20250430 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 26.87 | 1908.03 | Closeout and O&M Documentation - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2501-20250430 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1037 | 22.7 | 1758.88 | Rework and Quality Correction - field installation time
2025-04-30 | PRJ-PAY-ARM-2501-20250430 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1044 | 19.97 | 1837.28 | Project Management and Supervision - coordination and layout
2025-05-05 | AP-0004819 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2531 |  | 79.21 | 14258.63 | Major HVAC Equipment - fabricated material delivery
2025-05-07 | PRJ-PAY-ARM-2501-20250507 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1011 | 26.35 | 1870.79 | Sheet Metal Fabrication Labor - field installation time
2025-05-07 | PRJ-PAY-ARM-2501-20250507 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1018 | 29.64 | 2297.31 | Controls Programming and Checkout - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2501-20250507 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1025 | 22.76 | 1911.96 | Warranty and Punchlist - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2501-20250514 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1016 | 26.06 | 1850.48 | Controls Programming and Checkout - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2501-20250514 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1023 | 24.21 | 1875.9 | Warranty and Punchlist - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2501-20250514 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 26.09 | 2191.48 | Closeout and O&M Documentation - startup and checkout
2025-05-15 | AP-0004817 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2503 |  | 75.61 | 13609.38 | Major HVAC Equipment - jobsite material replenishment
2025-05-15 | AP-0004820 | AP | ARM-2501 | 04-100 | Insulation Subcontract | V-2014 |  | 22429.74 | 22429.74 | Insulation Subcontract - rigging and specialty support
2025-05-15 | AP-0004821 | AP | ARM-2501 | 05-300 | Freight and Expediting | V-2047 |  | 6826.45 | 6826.45 | Freight and Expediting - rental and logistics
2025-05-21 | PRJ-PAY-ARM-2501-20250521 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1021 | 24.67 | 1751.37 | Warranty and Punchlist - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2501-20250521 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 27.04 | 2095.97 | Closeout and O&M Documentation - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2501-20250521 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1035 | 31.14 | 2615.82 | Rework and Quality Correction - punchlist and closeout labor
2025-05-22 | AP-0004818 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2517 |  | 51.05 | 9189.83 | Plumbing Fixtures and Piping - released equipment package
2025-05-28 | PRJ-PAY-ARM-2501-20250528 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 32.8 | 2328.85 | Closeout and O&M Documentation - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2501-20250528 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1033 | 34.96 | 2709.65 | Rework and Quality Correction - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2501-20250528 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1040 | 23.65 | 2176.11 | Project Management and Supervision - field installation time
2025-05-31 | PRJ-PAY-ARM-2501-20250531 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1031 | 35.06 | 2489.17 | Rework and Quality Correction - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2501-20250531 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1038 | 25.05 | 2142.05 | Project Management and Supervision - field installation time
2025-05-31 | PRJ-PAY-ARM-2501-20250531 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1045 | 33.93 | 2850.1 | Engineering, BIM and Coordination - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2501-20250607 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1012 | 37.37 | 2653.04 | Controls Programming and Checkout - field installation time
2025-06-07 | PRJ-PAY-ARM-2501-20250607 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1019 | 20.98 | 1626.05 | Warranty and Punchlist - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2501-20250607 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 24.71 | 2076.05 | Closeout and O&M Documentation - supervision and planning
2025-06-08 | AP-0004824 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2253 |  | 71.95 | 12951.59 | Sheet Metal and Ductwork - valves and piping lot
2025-06-14 | PRJ-PAY-ARM-2501-20250614 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1017 | 25.2 | 1789.02 | Warranty and Punchlist - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2501-20250614 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 34.22 | 2651.82 | Closeout and O&M Documentation - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2501-20250614 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1031 | 29.76 | 2499.89 | Rework and Quality Correction - startup and checkout
2025-06-18 | AP-0004822 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2210 |  | 72.44 | 13038.72 | Sheet Metal and Ductwork - released equipment package
2025-06-18 | AP-0004825 | AP | ARM-2501 | 04-200 | Electrical and Controls Subcontract | V-2265 |  | 23691.65 | 23691.65 | Electrical and Controls Subcontract - trade partner progress billing
2025-06-18 | AP-0004826 | AP | ARM-2501 | 05-400 | Small Tools and Consumables | V-2279 |  | 9692.03 | 9692.03 | Small Tools and Consumables - permit and inspection fees
2025-06-21 | PRJ-PAY-ARM-2501-20250621 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 40.23 | 2856.58 | Closeout and O&M Documentation - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2501-20250621 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1029 | 34.74 | 2692.5 | Rework and Quality Correction - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2501-20250621 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1036 | 23.9 | 2198.62 | Project Management and Supervision - punchlist and closeout labor
2025-06-25 | AP-0004823 | AP | ARM-2501 | 02-510 | Controls Panels and Devices | V-2232 |  | 59.02 | 10624.06 | Controls Panels and Devices - fabricated material delivery
2025-06-28 | PRJ-PAY-ARM-2501-20250628 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1027 | 43.88 | 3115.24 | Rework and Quality Correction - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2501-20250628 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1034 | 28.59 | 2444.42 | Project Management and Supervision - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2501-20250628 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 29.46 | 2474.47 | Engineering, BIM and Coordination - field installation time
2025-06-30 | PRJ-PAY-ARM-2501-20250630 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1032 | 24.47 | 1933.34 | Project Management and Supervision - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2501-20250630 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 39.71 | 3077.81 | Engineering, BIM and Coordination - field installation time
2025-06-30 | PRJ-PAY-ARM-2501-20250630 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1046 | 30.07 | 2525.52 | Field Installation Labor - coordination and layout
2025-07-04 | AP-0004828 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2307 |  | 65.22 | 11739.75 | Insulation and Specialty Material - valves and piping lot
2025-07-07 | PRJ-PAY-ARM-2501-20250707 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1013 | 43.21 | 3067.86 | Warranty and Punchlist - field installation time
2025-07-07 | PRJ-PAY-ARM-2501-20250707 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 28.37 | 2198.73 | Closeout and O&M Documentation - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2501-20250707 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1027 | 33.12 | 2782.12 | Rework and Quality Correction - supervision and planning
2025-07-11 | AP-0004829 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2320 |  | 81.62 | 14691.14 | Hydronic Piping and Valves - ductwork release
2025-07-14 | PRJ-PAY-ARM-2501-20250714 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1018 | 49.93 | 3544.69 | Closeout and O&M Documentation - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2501-20250714 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1025 | 33.05 | 2561.58 | Rework and Quality Correction - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2501-20250714 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1032 | 31.29 | 2878.24 | Project Management and Supervision - startup and checkout
2025-07-18 | AP-0004830 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2334 |  | 53.57 | 9641.9 | Insulation and Specialty Material - jobsite material replenishment
2025-07-21 | AP-0004827 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2293 |  | 51.8 | 9323.18 | Hydronic Piping and Valves - fabricated material delivery
2025-07-21 | AP-0004831 | AP | ARM-2501 | 04-300 | Testing and Balancing Subcontract | V-2341 |  | 29002.98 | 29002.98 | Testing and Balancing Subcontract - insulation progress invoice
2025-07-21 | AP-0004832 | AP | ARM-2501 | 06-400 | Temporary Facilities and Protection | V-2353 |  | 10088 | 10088 | Temporary Facilities and Protection - freight and expediting
2025-07-21 | PRJ-PAY-ARM-2501-20250721 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1023 | 38.3 | 2718.97 | Rework and Quality Correction - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2501-20250721 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1030 | 32.98 | 2819.64 | Project Management and Supervision - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2501-20250721 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 44.98 | 3778.06 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2501-20250728 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1028 | 42.39 | 3349.01 | Project Management and Supervision - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2501-20250728 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 32.41 | 2511.98 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2501-20250728 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1042 | 34.27 | 2878.81 | Field Installation Labor - field installation time
2025-07-31 | PRJ-PAY-ARM-2501-20250731 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 39.18 | 2781.57 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2501-20250731 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1040 | 28.25 | 2189.11 | Field Installation Labor - field installation time
2025-07-31 | PRJ-PAY-ARM-2501-20250731 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1047 | 33.5 | 2813.6 | Startup, Testing and Commissioning - coordination and layout
2025-08-07 | AP-0004834 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2381 |  | 73.2 | 13175.81 | Major HVAC Equipment - ductwork release
2025-08-07 | PRJ-PAY-ARM-2501-20250807 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1014 | 54.35 | 3858.6 | Closeout and O&M Documentation - field installation time
2025-08-07 | PRJ-PAY-ARM-2501-20250807 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1021 | 31.08 | 2408.75 | Rework and Quality Correction - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2501-20250807 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1028 | 43.49 | 4000.97 | Project Management and Supervision - supervision and planning
2025-08-14 | AP-0004835 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2395 |  | 89.83 | 16170.05 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-08-14 | PRJ-PAY-ARM-2501-20250814 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1019 | 50.52 | 3586.66 | Rework and Quality Correction - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2501-20250814 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1026 | 48.24 | 4124.49 | Project Management and Supervision - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2501-20250814 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 34.96 | 2936.79 | Engineering, BIM and Coordination - startup and checkout
2025-08-21 | AP-0004836 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2408 |  | 48.65 | 8756.33 | Major HVAC Equipment - released equipment package
2025-08-21 | PRJ-PAY-ARM-2501-20250821 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1024 | 39.6 | 3128.22 | Project Management and Supervision - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2501-20250821 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 41.87 | 3244.56 | Engineering, BIM and Coordination - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2501-20250821 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1038 | 43.05 | 3615.86 | Field Installation Labor - punchlist and closeout labor
2025-08-24 | AP-0004833 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2367 |  | 87.46 | 15743.02 | Plumbing Fixtures and Piping - valves and piping lot
2025-08-24 | AP-0004837 | AP | ARM-2501 | 04-400 | Crane, Rigging and Specialty Trade | V-2415 |  | 31173.54 | 31173.54 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-08-24 | AP-0004838 | AP | ARM-2501 | 05-100 | Equipment Rental and Rigging | V-2427 |  | 9918.86 | 9918.86 | Equipment Rental and Rigging - small tools and field consumables
2025-08-28 | PRJ-PAY-ARM-2501-20250828 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 45.2 | 3209.06 | Engineering, BIM and Coordination - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2501-20250828 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1036 | 30.96 | 2399.31 | Field Installation Labor - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2501-20250828 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 39.15 | 3288.22 | Startup, Testing and Commissioning - field installation time
2025-08-31 | PRJ-PAY-ARM-2501-20250831 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1034 | 40.12 | 2848.43 | Field Installation Labor - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2501-20250831 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 38.73 | 3001.45 | Startup, Testing and Commissioning - field installation time
2025-08-31 | PRJ-PAY-ARM-2501-20250831 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1048 | 30.07 | 2525.92 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-03 | AP-0004839 | AP | ARM-2501 | 02-510 | Controls Panels and Devices | V-2440 |  | 56.25 | 10124.82 | Controls Panels and Devices - ductwork release
2025-09-03 | AP-0004843 | AP | ARM-2501 | 04-100 | Insulation Subcontract | V-2488 |  | 31219.23 | 31219.23 | Insulation Subcontract - electrical coordination scope
2025-09-03 | AP-0004844 | AP | ARM-2501 | 05-200 | Permits, Fees and Bonds | V-2500 |  | 7215.53 | 7215.53 | Permits, Fees and Bonds - rental and logistics
2025-09-07 | PRJ-PAY-ARM-2501-20250907 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1015 | 65.92 | 4680.11 | Rework and Quality Correction - field installation time
2025-09-07 | PRJ-PAY-ARM-2501-20250907 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1022 | 34.37 | 2938.46 | Project Management and Supervision - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2501-20250907 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 34.27 | 2878.37 | Engineering, BIM and Coordination - supervision and planning
2025-09-10 | AP-0004840 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2453 |  | 50 | 8999.27 | Sheet Metal and Ductwork - jobsite material replenishment
2025-09-10 | AP-0004845 | AP | ARM-2501 | 06-400 | Temporary Facilities and Protection | V-2514 |  | 5000.68 | 5000.68 | Temporary Facilities and Protection - permit and inspection fees
2025-09-14 | PRJ-PAY-ARM-2501-20250914 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1020 | 44.06 | 3480.48 | Project Management and Supervision - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2501-20250914 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 37.26 | 2887.36 | Engineering, BIM and Coordination - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2501-20250914 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1034 | 41.42 | 3479.15 | Field Installation Labor - startup and checkout
2025-09-17 | AP-0004841 | AP | ARM-2501 | 02-510 | Controls Panels and Devices | V-2467 |  | 74.74 | 13453.04 | Controls Panels and Devices - released equipment package
2025-09-21 | PRJ-PAY-ARM-2501-20250921 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 36.09 | 2562.57 | Engineering, BIM and Coordination - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2501-20250921 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1032 | 42.76 | 3313.54 | Field Installation Labor - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2501-20250921 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 34.46 | 2894.31 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-09-24 | AP-0004842 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2481 |  | 75.41 | 13573.04 | Sheet Metal and Ductwork - fabricated material delivery
2025-09-28 | PRJ-PAY-ARM-2501-20250928 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1030 | 30.75 | 2183.24 | Field Installation Labor - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2501-20250928 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 41.75 | 3235.34 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2501-20250928 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 33.79 | 2838.44 | Sheet Metal Fabrication Labor - field installation time
2025-09-30 | PRJ-PAY-ARM-2501-20250930 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 32.48 | 2306.35 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2501-20250930 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 45.36 | 3515.02 | Sheet Metal Fabrication Labor - field installation time
2025-09-30 | PRJ-PAY-ARM-2501-20250930 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1049 | 35.21 | 2957.43 | Controls Programming and Checkout - coordination and layout
2025-10-03 | AP-0004849 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2213 |  | 56.14 | 10105.1 | Hydronic Piping and Valves - valves and piping lot
2025-10-06 | AP-0004846 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2526 |  | 76.93 | 13847.17 | Insulation and Specialty Material - jobsite material replenishment
2025-10-06 | AP-0004850 | AP | ARM-2501 | 04-200 | Electrical and Controls Subcontract | V-2225 |  | 30722.04 | 30722.04 | Electrical and Controls Subcontract - rigging and specialty support
2025-10-06 | AP-0004851 | AP | ARM-2501 | 05-300 | Freight and Expediting | V-2243 |  | 5942.63 | 5942.63 | Freight and Expediting - permit and inspection fees
2025-10-07 | PRJ-PAY-ARM-2501-20251007 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1016 | 48.87 | 3860.93 | Project Management and Supervision - field installation time
2025-10-07 | PRJ-PAY-ARM-2501-20251007 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 38.91 | 3015.71 | Engineering, BIM and Coordination - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2501-20251007 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1030 | 40.44 | 3396.65 | Field Installation Labor - supervision and planning
2025-10-13 | AP-0004847 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2014 |  | 74.07 | 13331.93 | Hydronic Piping and Valves - released equipment package
2025-10-13 | AP-0004852 | AP | ARM-2501 | 05-100 | Equipment Rental and Rigging | V-2262 |  | 5229.02 | 5229.02 | Equipment Rental and Rigging - freight and expediting
2025-10-14 | PRJ-PAY-ARM-2501-20251014 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1021 | 43.16 | 3064.49 | Engineering, BIM and Coordination - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2501-20251014 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1028 | 39.03 | 3024.75 | Field Installation Labor - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2501-20251014 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 36.44 | 3060.88 | Startup, Testing and Commissioning - startup and checkout
2025-10-20 | AP-0004848 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2056 |  | 72.16 | 12988.22 | Insulation and Specialty Material - fabricated material delivery
2025-10-21 | PRJ-PAY-ARM-2501-20251021 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1026 | 33.58 | 2384.03 | Field Installation Labor - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2501-20251021 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 37.73 | 2924.42 | Startup, Testing and Commissioning - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2501-20251021 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 39.36 | 3306.04 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2501-20251028 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 42.8 | 3038.48 | Startup, Testing and Commissioning - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2501-20251028 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 40.25 | 3119.23 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2501-20251028 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1045 | 35.73 | 3001.15 | Controls Programming and Checkout - field installation time
2025-10-31 | PRJ-PAY-ARM-2501-20251031 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 46.93 | 3332.2 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2501-20251031 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1043 | 45.01 | 3488.1 | Controls Programming and Checkout - field installation time
2025-10-31 | PRJ-PAY-ARM-2501-20251031 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1050 | 41.22 | 3462.45 | Warranty and Punchlist - coordination and layout
2025-11-06 | AP-0004856 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2319 |  | 85.32 | 15357.61 | Plumbing Fixtures and Piping - ductwork release
2025-11-07 | PRJ-PAY-ARM-2501-20251107 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1017 | 37.69 | 2676.16 | Engineering, BIM and Coordination - field installation time
2025-11-07 | PRJ-PAY-ARM-2501-20251107 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1024 | 35.09 | 2719.31 | Field Installation Labor - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2501-20251107 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 26.56 | 2231.19 | Startup, Testing and Commissioning - supervision and planning
2025-11-09 | AP-0004853 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2277 |  | 46.83 | 8429.81 | Major HVAC Equipment - released equipment package
2025-11-09 | AP-0004857 | AP | ARM-2501 | 04-300 | Testing and Balancing Subcontract | V-2326 |  | 27154.06 | 27154.06 | Testing and Balancing Subcontract - trade partner progress billing
2025-11-09 | AP-0004858 | AP | ARM-2501 | 05-400 | Small Tools and Consumables | V-2338 |  | 8264.28 | 8264.28 | Small Tools and Consumables - freight and expediting
2025-11-14 | PRJ-PAY-ARM-2501-20251114 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1022 | 33.12 | 2351.25 | Field Installation Labor - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2501-20251114 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 34.39 | 2665.31 | Startup, Testing and Commissioning - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2501-20251114 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 25.76 | 2163.65 | Sheet Metal Fabrication Labor - startup and checkout
2025-11-16 | AP-0004854 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2291 |  | 37 | 6660.06 | Plumbing Fixtures and Piping - fabricated material delivery
2025-11-21 | PRJ-PAY-ARM-2501-20251121 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 31 | 2200.89 | Startup, Testing and Commissioning - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2501-20251121 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 34.84 | 2699.86 | Sheet Metal Fabrication Labor - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2501-20251121 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1041 | 32.54 | 2733.2 | Controls Programming and Checkout - punchlist and closeout labor
2025-11-23 | AP-0004855 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2305 |  | 80.09 | 14415.75 | Major HVAC Equipment - valves and piping lot
2025-11-28 | PRJ-PAY-ARM-2501-20251128 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 36.27 | 2575.16 | Sheet Metal Fabrication Labor - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2501-20251128 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1039 | 42.11 | 3263.57 | Controls Programming and Checkout - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2501-20251128 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1046 | 32.52 | 2731.98 | Warranty and Punchlist - field installation time
2025-11-30 | PRJ-PAY-ARM-2501-20251130 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1037 | 44.61 | 3167.12 | Controls Programming and Checkout - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2501-20251130 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1044 | 43.95 | 3405.83 | Warranty and Punchlist - field installation time
2025-11-30 | PRJ-PAY-ARM-2501-20251130 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 30.43 | 2556.3 | Closeout and O&M Documentation - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2501-20251207 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1018 | 35.11 | 2493.1 | Field Installation Labor - field installation time
2025-12-07 | PRJ-PAY-ARM-2501-20251207 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 30.06 | 2329.37 | Startup, Testing and Commissioning - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2501-20251207 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 23.28 | 1955.74 | Sheet Metal Fabrication Labor - supervision and planning
2025-12-12 | AP-0004859 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2351 |  | 52.11 | 9380.16 | Sheet Metal and Ductwork - fabricated material delivery
2025-12-12 | AP-0004862 | AP | ARM-2501 | 04-400 | Crane, Rigging and Specialty Trade | V-2388 |  | 25233.55 | 25233.55 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-12-12 | AP-0004863 | AP | ARM-2501 | 06-400 | Temporary Facilities and Protection | V-2400 |  | 10322.82 | 10322.82 | Temporary Facilities and Protection - small tools and field consumables
2025-12-14 | PRJ-PAY-ARM-2501-20251214 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1023 | 35.24 | 2502.11 | Startup, Testing and Commissioning - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2501-20251214 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 29.99 | 2324.37 | Sheet Metal Fabrication Labor - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2501-20251214 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1037 | 28.33 | 2380.07 | Controls Programming and Checkout - startup and checkout
2025-12-19 | AP-0004860 | AP | ARM-2501 | 02-510 | Controls Panels and Devices | V-2365 |  | 70.85 | 12752.48 | Controls Panels and Devices - valves and piping lot
2025-12-21 | PRJ-PAY-ARM-2501-20251221 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 41.84 | 2970.86 | Sheet Metal Fabrication Labor - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2501-20251221 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1035 | 27.61 | 2139.88 | Controls Programming and Checkout - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2501-20251221 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1042 | 35.48 | 2980.12 | Warranty and Punchlist - punchlist and closeout labor
2025-12-25 | AP-0004861 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2379 |  | 93.69 | 16864.67 | Sheet Metal and Ductwork - ductwork release
2025-12-28 | PRJ-PAY-ARM-2501-20251228 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1033 | 48.71 | 3458.47 | Controls Programming and Checkout - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2501-20251228 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1040 | 33.85 | 2623.29 | Warranty and Punchlist - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2501-20251228 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 30.19 | 2536.36 | Closeout and O&M Documentation - field installation time
2025-12-31 | PRJ-PAY-ARM-2501-20251231 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1038 | 43.69 | 3101.9 | Warranty and Punchlist - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2501-20251231 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 33.9 | 2627.4 | Closeout and O&M Documentation - field installation time
2025-12-31 | PRJ-PAY-ARM-2501-20251231 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1052 | 30.65 | 2574.27 | Rework and Quality Correction - coordination and layout
2026-01-05 | AP-0004866 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2440 |  | 50.79 | 9142.06 | Hydronic Piping and Valves - jobsite material replenishment
2026-01-07 | PRJ-PAY-ARM-2501-20260107 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1019 | 29.66 | 2105.77 | Startup, Testing and Commissioning - field installation time
2026-01-07 | PRJ-PAY-ARM-2501-20260107 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 29.73 | 2303.77 | Sheet Metal Fabrication Labor - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2501-20260107 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1033 | 20.22 | 1698.65 | Controls Programming and Checkout - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2501-20260114 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1024 | 32.8 | 2328.94 | Sheet Metal Fabrication Labor - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2501-20260114 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1031 | 33.8 | 2619.8 | Controls Programming and Checkout - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2501-20260114 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1038 | 22.73 | 1908.99 | Warranty and Punchlist - startup and checkout
2026-01-15 | AP-0004864 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2414 |  | 73.78 | 13279.61 | Hydronic Piping and Valves - valves and piping lot
2026-01-15 | AP-0004867 | AP | ARM-2501 | 04-100 | Insulation Subcontract | V-2448 |  | 22737.24 | 22737.24 | Insulation Subcontract - testing and balancing services
2026-01-15 | AP-0004868 | AP | ARM-2501 | 05-100 | Equipment Rental and Rigging | V-2460 |  | 7908.6 | 7908.6 | Equipment Rental and Rigging - rental and logistics
2026-01-21 | PRJ-PAY-ARM-2501-20260121 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1029 | 29.21 | 2073.57 | Controls Programming and Checkout - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2501-20260121 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1036 | 33.76 | 2616.14 | Warranty and Punchlist - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2501-20260121 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 31.13 | 2614.92 | Closeout and O&M Documentation - punchlist and closeout labor
2026-01-22 | AP-0004865 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2427 |  | 73.15 | 13167.05 | Insulation and Specialty Material - ductwork release
2026-01-28 | PRJ-PAY-ARM-2501-20260128 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1034 | 25.39 | 1802.44 | Warranty and Punchlist - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2501-20260128 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 35.96 | 2786.73 | Closeout and O&M Documentation - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2501-20260128 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1048 | 29.15 | 2448.84 | Rework and Quality Correction - field installation time
2026-01-31 | PRJ-PAY-ARM-2501-20260131 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 23.47 | 1666.5 | Closeout and O&M Documentation - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2501-20260131 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1046 | 28.22 | 2186.87 | Rework and Quality Correction - field installation time
2026-01-31 | PRJ-PAY-ARM-2501-20260131 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1053 | 26.63 | 2449.64 | Project Management and Supervision - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2501-20260207 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1020 | 46.95 | 3333.71 | Sheet Metal Fabrication Labor - field installation time
2026-02-07 | PRJ-PAY-ARM-2501-20260207 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1027 | 34.53 | 2676.33 | Controls Programming and Checkout - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2501-20260207 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1034 | 35.9 | 3015.39 | Warranty and Punchlist - supervision and planning
2026-02-08 | AP-0004871 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2502 |  | 64.08 | 11533.66 | Plumbing Fixtures and Piping - released equipment package
2026-02-14 | PRJ-PAY-ARM-2501-20260214 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1025 | 40.66 | 2887.18 | Controls Programming and Checkout - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2501-20260214 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1032 | 49.59 | 3843.17 | Warranty and Punchlist - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2501-20260214 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 34.32 | 2883.24 | Closeout and O&M Documentation - startup and checkout
2026-02-18 | AP-0004869 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2474 |  | 111.23 | 20021.57 | Plumbing Fixtures and Piping - ductwork release
2026-02-18 | AP-0004872 | AP | ARM-2501 | 04-200 | Electrical and Controls Subcontract | V-2510 |  | 23421.64 | 23421.64 | Electrical and Controls Subcontract - electrical coordination scope
2026-02-18 | AP-0004873 | AP | ARM-2501 | 05-200 | Permits, Fees and Bonds | V-2522 |  | 7452.34 | 7452.34 | Permits, Fees and Bonds - permit and inspection fees
2026-02-21 | PRJ-PAY-ARM-2501-20260221 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1030 | 43.03 | 3055.01 | Warranty and Punchlist - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2501-20260221 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 47.24 | 3661.03 | Closeout and O&M Documentation - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2501-20260221 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1044 | 30.32 | 2546.66 | Rework and Quality Correction - punchlist and closeout labor
2026-02-25 | AP-0004870 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2488 |  | 49.45 | 8900.32 | Major HVAC Equipment - jobsite material replenishment
2026-02-28 | PRJ-PAY-ARM-2501-20260228 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 33.78 | 2398.06 | Closeout and O&M Documentation - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2501-20260228 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1042 | 39.64 | 3072.02 | Rework and Quality Correction - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2501-20260228 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1049 | 30.71 | 2825.27 | Project Management and Supervision - field installation time
2026-03-04 | AP-0004875 | AP | ARM-2501 | 02-210 | Sheet Metal and Ductwork | V-2037 |  | 69.97 | 12593.89 | Sheet Metal and Ductwork - released equipment package
2026-03-07 | PRJ-PAY-ARM-2501-20260307 | PAY | ARM-2501 | 03-400 | Controls Programming and Checkout |  | E-1021 | 38.6 | 2740.29 | Controls Programming and Checkout - field installation time
2026-03-07 | PRJ-PAY-ARM-2501-20260307 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1028 | 43.33 | 3358.01 | Warranty and Punchlist - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2501-20260307 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 32.66 | 2743.3 | Closeout and O&M Documentation - supervision and planning
2026-03-11 | AP-0004876 | AP | ARM-2501 | 02-510 | Controls Panels and Devices | V-2208 |  | 87.82 | 15808.32 | Controls Panels and Devices - fabricated material delivery
2026-03-14 | PRJ-PAY-ARM-2501-20260314 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1026 | 34.56 | 2453.54 | Warranty and Punchlist - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2501-20260314 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 29.53 | 2288.22 | Closeout and O&M Documentation - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2501-20260314 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1040 | 44.97 | 3777.13 | Rework and Quality Correction - startup and checkout
2026-03-21 | AP-0004874 | AP | ARM-2501 | 02-510 | Controls Panels and Devices | V-2001 |  | 59.82 | 10768.19 | Controls Panels and Devices - jobsite material replenishment
2026-03-21 | AP-0004877 | AP | ARM-2501 | 04-300 | Testing and Balancing Subcontract | V-2222 |  | 26497.63 | 26497.63 | Testing and Balancing Subcontract - rigging and specialty support
2026-03-21 | AP-0004878 | AP | ARM-2501 | 05-300 | Freight and Expediting | V-2241 |  | 10368.64 | 10368.64 | Freight and Expediting - freight and expediting
2026-03-21 | PRJ-PAY-ARM-2501-20260321 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1031 | 40.05 | 2843.39 | Closeout and O&M Documentation - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2501-20260321 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1038 | 29.96 | 2321.61 | Rework and Quality Correction - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2501-20260321 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1045 | 26.79 | 2464.23 | Project Management and Supervision - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2501-20260328 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1036 | 29.54 | 2097.05 | Rework and Quality Correction - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2501-20260328 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1043 | 24.54 | 2098.04 | Project Management and Supervision - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2501-20260328 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 33.28 | 2795.49 | Engineering, BIM and Coordination - field installation time
2026-03-31 | PRJ-PAY-ARM-2501-20260331 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1041 | 35.03 | 2767.65 | Project Management and Supervision - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2501-20260331 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1048 | 22.95 | 1778.95 | Engineering, BIM and Coordination - field installation time
2026-03-31 | PRJ-PAY-ARM-2501-20260331 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1069 | 31.47 | 2643.5 | Field Installation Labor - coordination and layout
2026-04-07 | AP-0004880 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2277 |  | 48.53 | 8735.89 | Hydronic Piping and Valves - fabricated material delivery
2026-04-07 | PRJ-PAY-ARM-2501-20260407 | PAY | ARM-2501 | 06-100 | Warranty and Punchlist |  | E-1022 | 59.56 | 4228.86 | Warranty and Punchlist - field installation time
2026-04-07 | PRJ-PAY-ARM-2501-20260407 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1029 | 39.22 | 3039.85 | Closeout and O&M Documentation - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2501-20260407 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1036 | 30.79 | 2586.62 | Rework and Quality Correction - supervision and planning
2026-04-14 | AP-0004881 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2291 |  | 60.73 | 10931.59 | Insulation and Specialty Material - valves and piping lot
2026-04-14 | PRJ-PAY-ARM-2501-20260414 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1027 | 33.4 | 2371.63 | Closeout and O&M Documentation - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2501-20260414 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1034 | 49.46 | 3833.46 | Rework and Quality Correction - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2501-20260414 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1041 | 28.49 | 2621.01 | Project Management and Supervision - startup and checkout
2026-04-21 | AP-0004882 | AP | ARM-2501 | 02-310 | Hydronic Piping and Valves | V-2305 |  | 67.29 | 12112.46 | Hydronic Piping and Valves - ductwork release
2026-04-21 | PRJ-PAY-ARM-2501-20260421 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1032 | 28.88 | 2050.37 | Rework and Quality Correction - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2501-20260421 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1039 | 33.58 | 2870.83 | Project Management and Supervision - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2501-20260421 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1046 | 37.69 | 3166.06 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-04-24 | AP-0004879 | AP | ARM-2501 | 02-610 | Insulation and Specialty Material | V-2258 |  | 84.58 | 15224.55 | Insulation and Specialty Material - released equipment package
2026-04-24 | AP-0004883 | AP | ARM-2501 | 04-400 | Crane, Rigging and Specialty Trade | V-2312 |  | 28724.96 | 28724.96 | Crane, Rigging and Specialty Trade - trade partner progress billing
2026-04-24 | AP-0004884 | AP | ARM-2501 | 05-400 | Small Tools and Consumables | V-2324 |  | 10445.44 | 10445.44 | Small Tools and Consumables - small tools and field consumables
2026-04-28 | PRJ-PAY-ARM-2501-20260428 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1037 | 29.5 | 2330.47 | Project Management and Supervision - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2501-20260428 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 39.6 | 3068.75 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2501-20260428 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1051 | 34.75 | 2918.86 | Field Installation Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2501-20260430 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1042 | 36.97 | 2624.87 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2501-20260430 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1049 | 51.42 | 3985.11 | Field Installation Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2501-20260430 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1070 | 32.1 | 2696.38 | Startup, Testing and Commissioning - coordination and layout
2026-05-03 | AP-0004885 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2338 |  | 95.41 | 17174.19 | Major HVAC Equipment - fabricated material delivery
2026-05-03 | AP-0004889 | AP | ARM-2501 | 04-100 | Insulation Subcontract | V-2386 |  | 32905.55 | 32905.55 | Insulation Subcontract - insulation progress invoice
2026-05-03 | AP-0004890 | AP | ARM-2501 | 06-400 | Temporary Facilities and Protection | V-2398 |  | 10014.73 | 10014.73 | Temporary Facilities and Protection - rental and logistics
2026-05-07 | PRJ-PAY-ARM-2501-20260507 | PAY | ARM-2501 | 06-200 | Closeout and O&M Documentation |  | E-1023 | 59.15 | 4199.47 | Closeout and O&M Documentation - field installation time
2026-05-07 | PRJ-PAY-ARM-2501-20260507 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1030 | 36.52 | 2830.39 | Rework and Quality Correction - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2501-20260507 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1037 | 28.03 | 2578.82 | Project Management and Supervision - supervision and planning
2026-05-10 | AP-0004886 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2351 |  | 56.32 | 10137.7 | Plumbing Fixtures and Piping - valves and piping lot
2026-05-14 | PRJ-PAY-ARM-2501-20260514 | PAY | ARM-2501 | 06-300 | Rework and Quality Correction |  | E-1028 | 34.55 | 2452.82 | Rework and Quality Correction - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2501-20260514 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1035 | 27.67 | 2365.58 | Project Management and Supervision - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2501-20260514 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1042 | 47.45 | 3985.92 | Engineering, BIM and Coordination - startup and checkout
2026-05-17 | AP-0004887 | AP | ARM-2501 | 02-110 | Major HVAC Equipment | V-2365 |  | 76.53 | 13775.23 | Major HVAC Equipment - ductwork release
2026-05-21 | PRJ-PAY-ARM-2501-20260521 | PAY | ARM-2501 | 01-100 | Project Management and Supervision |  | E-1033 | 38.42 | 3035.27 | Project Management and Supervision - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2501-20260521 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1040 | 29.86 | 2314.22 | Engineering, BIM and Coordination - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2501-20260521 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1047 | 44.12 | 3706.13 | Field Installation Labor - punchlist and closeout labor
2026-05-24 | AP-0004888 | AP | ARM-2501 | 02-410 | Plumbing Fixtures and Piping | V-2379 |  | 73.77 | 13278.57 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-05-28 | PRJ-PAY-ARM-2501-20260528 | PAY | ARM-2501 | 01-200 | Engineering, BIM and Coordination |  | E-1038 | 35.14 | 2494.82 | Engineering, BIM and Coordination - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2501-20260528 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1045 | 54.5 | 4223.66 | Field Installation Labor - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2501-20260528 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1052 | 40.63 | 3413.04 | Startup, Testing and Commissioning - field installation time
2026-05-31 | PRJ-PAY-ARM-2501-20260531 | PAY | ARM-2501 | 03-100 | Field Installation Labor |  | E-1043 | 47.73 | 3388.92 | Field Installation Labor - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2501-20260531 | PAY | ARM-2501 | 03-200 | Startup, Testing and Commissioning |  | E-1050 | 57.52 | 4458.11 | Startup, Testing and Commissioning - field installation time
2026-05-31 | PRJ-PAY-ARM-2501-20260531 | PAY | ARM-2501 | 03-300 | Sheet Metal Fabrication Labor |  | E-1071 | 38.05 | 3195.82 | Sheet Metal Fabrication Labor - coordination and layout
2025-02-03 | AP-0004900 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2490 |  | 82.85 | 14913.34 | Hydronic Piping and Valves - released equipment package
2025-02-03 | AP-0004901 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2502 |  | 9527.97 | 9527.97 | Insulation Subcontract - trade partner progress billing
2025-02-03 | AP-0004902 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2514 |  | 3314.07 | 3314.07 | Small Tools and Consumables - rental and logistics
2025-02-07 | PRJ-PAY-ARM-2506-20250207 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1007 | 15.81 | 1248.86 | Project Management and Supervision - field installation time
2025-02-07 | PRJ-PAY-ARM-2506-20250207 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 15.76 | 1221.75 | Engineering, BIM and Coordination - coordination and layout
2025-02-07 | PRJ-PAY-ARM-2506-20250207 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1023 | 10.26 | 861.48 | Field Installation Labor - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2506-20250214 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 18.47 | 1311.7 | Engineering, BIM and Coordination - coordination and layout
2025-02-14 | PRJ-PAY-ARM-2506-20250214 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1021 | 16.43 | 1273.46 | Field Installation Labor - supervision and planning
2025-02-14 | PRJ-PAY-ARM-2506-20250214 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 12.9 | 1083.39 | Startup, Testing and Commissioning - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2506-20250221 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1019 | 17.11 | 1214.64 | Field Installation Labor - supervision and planning
2025-02-21 | PRJ-PAY-ARM-2506-20250221 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 15.88 | 1230.59 | Startup, Testing and Commissioning - startup and checkout
2025-02-21 | PRJ-PAY-ARM-2506-20250221 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 14.89 | 1250.44 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2506-20250228 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 13.11 | 930.76 | Startup, Testing and Commissioning - startup and checkout
2025-02-28 | PRJ-PAY-ARM-2506-20250228 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 13.4 | 1038.42 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-02-28 | PRJ-PAY-ARM-2506-20250228 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1038 | 16.9 | 1419.33 | Controls Programming and Checkout - field installation time
2025-03-06 | AP-0004903 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2528 |  | 48.28 | 8691.02 | Plumbing Fixtures and Piping - fabricated material delivery
2025-03-06 | AP-0004906 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2208 |  | 20169.36 | 20169.36 | Electrical and Controls Subcontract - insulation progress invoice
2025-03-06 | AP-0004907 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2229 |  | 6417.53 | 6417.53 | Temporary Facilities and Protection - permit and inspection fees
2025-03-07 | PRJ-PAY-ARM-2506-20250307 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 33.33 | 2366.4 | Engineering, BIM and Coordination - field installation time
2025-03-07 | PRJ-PAY-ARM-2506-20250307 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1016 | 29.12 | 2256.55 | Field Installation Labor - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2506-20250307 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 26.33 | 2211.83 | Startup, Testing and Commissioning - supervision and planning
2025-03-13 | AP-0004904 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2018 |  | 69.42 | 12496.47 | Major HVAC Equipment - valves and piping lot
2025-03-14 | PRJ-PAY-ARM-2506-20250314 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1014 | 29.97 | 2127.81 | Field Installation Labor - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2506-20250314 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 24.09 | 1867.27 | Startup, Testing and Commissioning - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2506-20250314 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 34.41 | 2890.22 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-20 | AP-0004905 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2060 |  | 75.84 | 13650.5 | Plumbing Fixtures and Piping - ductwork release
2025-03-21 | PRJ-PAY-ARM-2506-20250321 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 33.55 | 2382.31 | Startup, Testing and Commissioning - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2506-20250321 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 28.17 | 2183.19 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2506-20250321 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1034 | 20.8 | 1747.55 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2506-20250328 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 32.24 | 2289.27 | Sheet Metal Fabrication Labor - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2506-20250328 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1032 | 22.21 | 1721.09 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2506-20250328 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1039 | 19.45 | 1633.78 | Warranty and Punchlist - field installation time
2025-03-31 | PRJ-PAY-ARM-2506-20250331 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1030 | 32.9 | 2335.83 | Controls Programming and Checkout - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2506-20250331 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1037 | 19.99 | 1549.23 | Warranty and Punchlist - field installation time
2025-03-31 | PRJ-PAY-ARM-2506-20250331 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 19.15 | 1608.51 | Closeout and O&M Documentation - coordination and layout
2025-04-06 | AP-0004911 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2296 |  | 78.12 | 14060.94 | Sheet Metal and Ductwork - released equipment package
2025-04-07 | PRJ-PAY-ARM-2506-20250407 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1009 | 64.46 | 4576.71 | Field Installation Labor - field installation time
2025-04-07 | PRJ-PAY-ARM-2506-20250407 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 43.94 | 3405.68 | Startup, Testing and Commissioning - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2506-20250407 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 45.68 | 3837.2 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-09 | AP-0004908 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2246 |  | 50.55 | 9098.86 | Controls Panels and Devices - valves and piping lot
2025-04-09 | AP-0004912 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2303 |  | 35227.69 | 35227.69 | Testing and Balancing Subcontract - testing and balancing services
2025-04-09 | AP-0004913 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2315 |  | 7288.71 | 7288.71 | Equipment Rental and Rigging - freight and expediting
2025-04-14 | PRJ-PAY-ARM-2506-20250414 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 44.98 | 3193.55 | Startup, Testing and Commissioning - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2506-20250414 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 59.15 | 4584.46 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2506-20250414 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1030 | 36.42 | 3059.23 | Controls Programming and Checkout - startup and checkout
2025-04-16 | AP-0004909 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2267 |  | 59.48 | 10705.64 | Sheet Metal and Ductwork - ductwork release
2025-04-16 | AP-0004914 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2329 |  | 6496.03 | 6496.03 | Small Tools and Consumables - small tools and field consumables
2025-04-21 | PRJ-PAY-ARM-2506-20250421 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 43.32 | 3075.38 | Sheet Metal Fabrication Labor - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2506-20250421 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1028 | 42.59 | 3301.06 | Controls Programming and Checkout - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2506-20250421 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1035 | 39.43 | 3312.52 | Warranty and Punchlist - punchlist and closeout labor
2025-04-23 | AP-0004910 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2282 |  | 101.17 | 18210.28 | Controls Panels and Devices - jobsite material replenishment
2025-04-28 | PRJ-PAY-ARM-2506-20250428 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1026 | 50.74 | 3602.8 | Controls Programming and Checkout - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2506-20250428 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1033 | 33.92 | 2628.84 | Warranty and Punchlist - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2506-20250428 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 38.08 | 3198.84 | Closeout and O&M Documentation - field installation time
2025-04-30 | PRJ-PAY-ARM-2506-20250430 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1031 | 53.5 | 3798.42 | Warranty and Punchlist - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2506-20250430 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 35.49 | 2750.15 | Closeout and O&M Documentation - field installation time
2025-04-30 | PRJ-PAY-ARM-2506-20250430 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1045 | 44.65 | 3750.88 | Rework and Quality Correction - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2506-20250507 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 50.88 | 3612.37 | Startup, Testing and Commissioning - field installation time
2025-05-07 | PRJ-PAY-ARM-2506-20250507 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 40.83 | 3164.49 | Sheet Metal Fabrication Labor - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2506-20250507 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1026 | 38.54 | 3237.03 | Controls Programming and Checkout - supervision and planning
2025-05-07 | PRJ-PAY-ARM-2506-20250507 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1033 | 29.22 | 2644.66 | Warranty and Punchlist - startup and checkout
2025-05-09 | AP-0004918 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2383 |  | 59.92 | 10786.43 | Hydronic Piping and Valves - fabricated material delivery
2025-05-12 | AP-0004915 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2341 |  | 47.26 | 8507.34 | Insulation and Specialty Material - ductwork release
2025-05-12 | AP-0004920 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2402 |  | 16848.61 | 16848.61 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-05-12 | AP-0004922 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2426 |  | 6544.98 | 6544.98 | Permits, Fees and Bonds - small tools and field consumables
2025-05-14 | PRJ-PAY-ARM-2506-20250514 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 58.25 | 4135.62 | Sheet Metal Fabrication Labor - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2506-20250514 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1024 | 47.05 | 3646.63 | Controls Programming and Checkout - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2506-20250514 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1031 | 42.08 | 3535.04 | Warranty and Punchlist - startup and checkout
2025-05-16 | AP-0004919 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2396 |  | 73.74 | 13272.88 | Insulation and Specialty Material - valves and piping lot
2025-05-19 | AP-0004916 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2355 |  | 97.58 | 17563.72 | Hydronic Piping and Valves - jobsite material replenishment
2025-05-19 | AP-0004921 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2415 |  | 22266.56 | 22266.56 | Testing and Balancing Subcontract - rigging and specialty support
2025-05-19 | AP-0004923 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2439 |  | 7678.72 | 7678.72 | Temporary Facilities and Protection - rental and logistics
2025-05-21 | PRJ-PAY-ARM-2506-20250521 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1022 | 57.56 | 4086.73 | Controls Programming and Checkout - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2506-20250521 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1029 | 49.53 | 3838.91 | Warranty and Punchlist - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2506-20250521 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 36.78 | 3089.74 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-25 | AP-0004917 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2369 |  | 77.09 | 13876.27 | Insulation and Specialty Material - released equipment package
2025-05-28 | PRJ-PAY-ARM-2506-20250528 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1027 | 73.44 | 5214.32 | Warranty and Punchlist - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2506-20250528 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 42.91 | 3325.28 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2506-20250528 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1041 | 41.56 | 3490.78 | Rework and Quality Correction - field installation time
2025-05-31 | PRJ-PAY-ARM-2506-20250531 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 41.79 | 2966.81 | Closeout and O&M Documentation - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2506-20250531 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1039 | 50.55 | 3917.9 | Rework and Quality Correction - field installation time
2025-05-31 | PRJ-PAY-ARM-2506-20250531 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1046 | 28.13 | 2588.27 | Project Management and Supervision - coordination and layout
2025-05-31 | PRJ-PAY-ARM-2506-20250531 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1053 | 43.71 | 3956.13 | Engineering, BIM and Coordination - supervision and planning
2025-06-05 | AP-0004926 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2477 |  | 61.64 | 11095.77 | Major HVAC Equipment - fabricated material delivery
2025-06-07 | PRJ-PAY-ARM-2506-20250607 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 55.63 | 3949.38 | Sheet Metal Fabrication Labor - field installation time
2025-06-07 | PRJ-PAY-ARM-2506-20250607 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1020 | 50.76 | 3933.73 | Controls Programming and Checkout - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2506-20250607 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1027 | 39.31 | 3301.99 | Warranty and Punchlist - supervision and planning
2025-06-07 | PRJ-PAY-ARM-2506-20250607 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 38.8 | 3511.62 | Closeout and O&M Documentation - startup and checkout
2025-06-09 | AP-0004930 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2533 |  | 72.5 | 13049.41 | Major HVAC Equipment - released equipment package
2025-06-12 | AP-0004927 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2491 |  | 72.47 | 13044.9 | Plumbing Fixtures and Piping - valves and piping lot
2025-06-14 | PRJ-PAY-ARM-2506-20250614 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1018 | 43.51 | 3088.88 | Controls Programming and Checkout - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2506-20250614 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1025 | 43.36 | 3360.77 | Warranty and Punchlist - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2506-20250614 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 43.73 | 3673.25 | Closeout and O&M Documentation - startup and checkout
2025-06-14 | PRJ-PAY-ARM-2506-20250614 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1039 | 46.21 | 4181.75 | Rework and Quality Correction - punchlist and closeout labor
2025-06-15 | AP-0004924 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2450 |  | 70.87 | 12756.02 | Major HVAC Equipment - jobsite material replenishment
2025-06-15 | AP-0004931 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2534 |  | 31035.28 | 31035.28 | Insulation Subcontract - rigging and specialty support
2025-06-15 | AP-0004933 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2098 |  | 6572.62 | 6572.62 | Freight and Expediting - rental and logistics
2025-06-19 | AP-0004928 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2505 |  | 94.36 | 16984.59 | Major HVAC Equipment - ductwork release
2025-06-21 | PRJ-PAY-ARM-2506-20250621 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1023 | 56.43 | 4006.85 | Warranty and Punchlist - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2506-20250621 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 50.97 | 3950.36 | Closeout and O&M Documentation - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2506-20250621 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1037 | 54.64 | 4589.39 | Rework and Quality Correction - punchlist and closeout labor
2025-06-21 | PRJ-PAY-ARM-2506-20250621 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1044 | 31.23 | 3076.14 | Project Management and Supervision - field installation time
2025-06-22 | AP-0004925 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2464 |  | 61.09 | 10996.69 | Plumbing Fixtures and Piping - released equipment package
2025-06-22 | AP-0004932 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2033 |  | 23181.88 | 23181.88 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-06-22 | AP-0004934 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2222 |  | 9928.26 | 9928.26 | Equipment Rental and Rigging - permit and inspection fees
2025-06-25 | AP-0004929 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2519 |  | 64.72 | 11648.8 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-06-28 | PRJ-PAY-ARM-2506-20250628 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 50.49 | 3585.08 | Closeout and O&M Documentation - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2506-20250628 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1035 | 52.11 | 4038.26 | Rework and Quality Correction - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2506-20250628 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1042 | 41.61 | 3828.13 | Project Management and Supervision - field installation time
2025-06-28 | PRJ-PAY-ARM-2506-20250628 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 29.83 | 2699.2 | Engineering, BIM and Coordination - coordination and layout
2025-06-28 | PRJ-PAY-ARM-2506-20250628 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1082 | 33.9 | 3288.47 | Field Installation Labor - supervision and planning
2025-06-30 | PRJ-PAY-ARM-2506-20250630 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1033 | 59.79 | 4244.97 | Rework and Quality Correction - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2506-20250630 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1040 | 37.22 | 3182.37 | Project Management and Supervision - field installation time
2025-06-30 | PRJ-PAY-ARM-2506-20250630 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 33.98 | 2854.32 | Engineering, BIM and Coordination - coordination and layout
2025-06-30 | PRJ-PAY-ARM-2506-20250630 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1080 | 37.23 | 3369.19 | Field Installation Labor - supervision and planning
2025-06-30 | PRJ-PAY-ARM-2506-20250630 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1087 | 45.7 | 4433.01 | Startup, Testing and Commissioning - startup and checkout
2025-07-05 | AP-0004940 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2319 |  | 82.66 | 14878.22 | Controls Panels and Devices - released equipment package
2025-07-07 | PRJ-PAY-ARM-2506-20250707 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1013 | 55.25 | 3922.66 | Controls Programming and Checkout - field installation time
2025-07-07 | PRJ-PAY-ARM-2506-20250707 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1021 | 48.79 | 3781.15 | Warranty and Punchlist - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2506-20250707 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 44.49 | 3737.27 | Closeout and O&M Documentation - supervision and planning
2025-07-07 | PRJ-PAY-ARM-2506-20250707 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1035 | 42.6 | 3855.41 | Rework and Quality Correction - startup and checkout
2025-07-08 | AP-0004937 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2277 |  | 82.51 | 14851.87 | Sheet Metal and Ductwork - valves and piping lot
2025-07-08 | AP-0004946 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2386 |  | 10253.31 | 10253.31 | Temporary Facilities and Protection - small tools and field consumables
2025-07-12 | AP-0004941 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2332 |  | 83.93 | 15107 | Sheet Metal and Ductwork - fabricated material delivery
2025-07-14 | PRJ-PAY-ARM-2506-20250714 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1019 | 49.22 | 3494.72 | Warranty and Punchlist - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2506-20250714 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 50.95 | 3948.29 | Closeout and O&M Documentation - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2506-20250714 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1033 | 40.29 | 3383.99 | Rework and Quality Correction - startup and checkout
2025-07-14 | PRJ-PAY-ARM-2506-20250714 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1040 | 31.4 | 3093.25 | Project Management and Supervision - punchlist and closeout labor
2025-07-14 | PRJ-PAY-ARM-2506-20250714 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 28.72 | 2785.72 | Engineering, BIM and Coordination - field installation time
2025-07-15 | AP-0004938 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2291 |  | 72.22 | 12999.18 | Controls Panels and Devices - ductwork release
2025-07-18 | AP-0004935 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2241 |  | 50.23 | 9041.08 | Sheet Metal and Ductwork - released equipment package
2025-07-18 | AP-0004942 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2334 |  | 29093.58 | 29093.58 | Electrical and Controls Subcontract - trade partner progress billing
2025-07-18 | AP-0004944 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2358 |  | 6276.36 | 6276.36 | Small Tools and Consumables - permit and inspection fees
2025-07-21 | PRJ-PAY-ARM-2506-20250721 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 49.49 | 3513.51 | Closeout and O&M Documentation - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2506-20250721 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1031 | 49.5 | 3835.91 | Rework and Quality Correction - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2506-20250721 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1038 | 43.27 | 3981.11 | Project Management and Supervision - punchlist and closeout labor
2025-07-21 | PRJ-PAY-ARM-2506-20250721 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1045 | 41.35 | 3742.41 | Engineering, BIM and Coordination - field installation time
2025-07-21 | PRJ-PAY-ARM-2506-20250721 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1052 | 36.86 | 3575.37 | Field Installation Labor - coordination and layout
2025-07-22 | AP-0004939 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2305 |  | 66.01 | 11882.17 | Sheet Metal and Ductwork - jobsite material replenishment
2025-07-25 | AP-0004936 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2258 |  | 52.05 | 9369.38 | Controls Panels and Devices - fabricated material delivery
2025-07-25 | AP-0004943 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2348 |  | 27931 | 27931 | Insulation Subcontract - insulation progress invoice
2025-07-25 | AP-0004945 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2372 |  | 6798.58 | 6798.58 | Permits, Fees and Bonds - freight and expediting
2025-07-28 | PRJ-PAY-ARM-2506-20250728 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1029 | 47.29 | 3357.55 | Rework and Quality Correction - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2506-20250728 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1036 | 39.34 | 3363.76 | Project Management and Supervision - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2506-20250728 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 61.02 | 5125.41 | Engineering, BIM and Coordination - field installation time
2025-07-28 | PRJ-PAY-ARM-2506-20250728 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1050 | 35.03 | 3170.21 | Field Installation Labor - coordination and layout
2025-07-28 | PRJ-PAY-ARM-2506-20250728 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1083 | 44.54 | 4320.81 | Startup, Testing and Commissioning - supervision and planning
2025-07-31 | PRJ-PAY-ARM-2506-20250731 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1034 | 58.34 | 4609.07 | Project Management and Supervision - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2506-20250731 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 38.42 | 2977.87 | Engineering, BIM and Coordination - field installation time
2025-07-31 | PRJ-PAY-ARM-2506-20250731 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1048 | 43.24 | 3632.37 | Field Installation Labor - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2506-20250731 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 37.49 | 3392.83 | Startup, Testing and Commissioning - supervision and planning
2025-07-31 | PRJ-PAY-ARM-2506-20250731 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1088 | 36.37 | 3528.25 | Sheet Metal Fabrication Labor - startup and checkout
2025-08-04 | AP-0004948 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2410 |  | 77.73 | 13990.95 | Insulation and Specialty Material - valves and piping lot
2025-08-04 | AP-0004957 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2517 |  | 30147.7 | 30147.7 | Electrical and Controls Subcontract - testing and balancing services
2025-08-04 | AP-0004960 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2056 |  | 5848.95 | 5848.95 | Freight and Expediting - small tools and field consumables
2025-08-05 | AP-0004955 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2505 |  | 46.79 | 8421.73 | Hydronic Piping and Valves - jobsite material replenishment
2025-08-07 | PRJ-PAY-ARM-2506-20250807 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1014 | 49.79 | 3534.82 | Warranty and Punchlist - field installation time
2025-08-07 | PRJ-PAY-ARM-2506-20250807 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 41.88 | 3245.73 | Closeout and O&M Documentation - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2506-20250807 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1029 | 40.85 | 3431.39 | Rework and Quality Correction - supervision and planning
2025-08-07 | PRJ-PAY-ARM-2506-20250807 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1036 | 47.46 | 4674.49 | Project Management and Supervision - startup and checkout
2025-08-07 | PRJ-PAY-ARM-2506-20250807 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 43.07 | 4178.05 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-08 | AP-0004952 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2464 |  | 63.68 | 11461.8 | Insulation and Specialty Material - fabricated material delivery
2025-08-11 | AP-0004949 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2424 |  | 65.15 | 11727.57 | Hydronic Piping and Valves - ductwork release
2025-08-11 | AP-0004958 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2531 |  | 18174.83 | 18174.83 | Insulation Subcontract - electrical coordination scope
2025-08-11 | AP-0004961 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2213 |  | 8900.03 | 8900.03 | Equipment Rental and Rigging - rental and logistics
2025-08-14 | PRJ-PAY-ARM-2506-20250814 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 52.5 | 3727.6 | Closeout and O&M Documentation - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2506-20250814 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1027 | 50.95 | 3948.96 | Rework and Quality Correction - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2506-20250814 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1034 | 43.92 | 4041.07 | Project Management and Supervision - startup and checkout
2025-08-14 | PRJ-PAY-ARM-2506-20250814 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 38.49 | 3483.65 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-14 | PRJ-PAY-ARM-2506-20250814 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1048 | 33.93 | 3290.77 | Field Installation Labor - field installation time
2025-08-14 | PRJ-PAY-ARM-2506-20250814 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 26.95 | 2788.99 | Startup, Testing and Commissioning - coordination and layout
2025-08-15 | AP-0004953 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2477 |  | 66.64 | 11995.69 | Hydronic Piping and Valves - valves and piping lot
2025-08-18 | AP-0004950 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2438 |  | 60.93 | 10966.8 | Insulation and Specialty Material - jobsite material replenishment
2025-08-21 | AP-0004947 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2396 |  | 90.19 | 16234.35 | Hydronic Piping and Valves - fabricated material delivery
2025-08-21 | AP-0004956 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2503 |  | 20374.99 | 20374.99 | Testing and Balancing Subcontract - insulation progress invoice
2025-08-21 | AP-0004959 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2014 |  | 9145.81 | 9145.81 | Temporary Facilities and Protection - freight and expediting
2025-08-21 | PRJ-PAY-ARM-2506-20250821 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1025 | 60.38 | 4286.99 | Rework and Quality Correction - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2506-20250821 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1032 | 50.57 | 4323.79 | Project Management and Supervision - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2506-20250821 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 44.91 | 3772.53 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-21 | PRJ-PAY-ARM-2506-20250821 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1046 | 33.69 | 3049.28 | Field Installation Labor - field installation time
2025-08-21 | PRJ-PAY-ARM-2506-20250821 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1053 | 35.96 | 3487.7 | Startup, Testing and Commissioning - coordination and layout
2025-08-21 | PRJ-PAY-ARM-2506-20250821 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1086 | 30.41 | 3147.51 | Sheet Metal Fabrication Labor - supervision and planning
2025-08-22 | AP-0004954 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2491 |  | 53.87 | 9696.8 | Insulation and Specialty Material - ductwork release
2025-08-25 | AP-0004951 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2450 |  | 72.39 | 13030.86 | Hydronic Piping and Valves - released equipment package
2025-08-28 | PRJ-PAY-ARM-2506-20250828 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1030 | 43.22 | 3414.64 | Project Management and Supervision - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2506-20250828 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 37.23 | 2885.48 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2506-20250828 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1044 | 51.44 | 4320.63 | Field Installation Labor - field installation time
2025-08-28 | PRJ-PAY-ARM-2506-20250828 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 31.27 | 2830.32 | Startup, Testing and Commissioning - coordination and layout
2025-08-28 | PRJ-PAY-ARM-2506-20250828 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1084 | 36.27 | 3518.53 | Sheet Metal Fabrication Labor - supervision and planning
2025-08-28 | PRJ-PAY-ARM-2506-20250828 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1091 | 36.06 | 3731.81 | Controls Programming and Checkout - startup and checkout
2025-08-31 | PRJ-PAY-ARM-2506-20250831 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 47.14 | 3346.77 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2506-20250831 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1042 | 38.32 | 2969.59 | Field Installation Labor - field installation time
2025-08-31 | PRJ-PAY-ARM-2506-20250831 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 51.41 | 4318.32 | Startup, Testing and Commissioning - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2506-20250831 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 38.69 | 3501.49 | Sheet Metal Fabrication Labor - supervision and planning
2025-08-31 | PRJ-PAY-ARM-2506-20250831 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1089 | 44.35 | 4301.96 | Controls Programming and Checkout - startup and checkout
2025-09-04 | AP-0004966 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2298 |  | 68.94 | 12409.85 | Plumbing Fixtures and Piping - fabricated material delivery
2025-09-07 | AP-0004963 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2250 |  | 56.86 | 10234.95 | Major HVAC Equipment - ductwork release
2025-09-07 | AP-0004973 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2377 |  | 17856.59 | 17856.59 | Testing and Balancing Subcontract - electrical coordination scope
2025-09-07 | AP-0004976 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2414 |  | 5298.78 | 5298.78 | Small Tools and Consumables - rental and logistics
2025-09-07 | PRJ-PAY-ARM-2506-20250907 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 54.67 | 3881.28 | Closeout and O&M Documentation - field installation time
2025-09-07 | PRJ-PAY-ARM-2506-20250907 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1023 | 40.92 | 3171.36 | Rework and Quality Correction - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2506-20250907 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1030 | 34.05 | 3133.01 | Project Management and Supervision - supervision and planning
2025-09-07 | PRJ-PAY-ARM-2506-20250907 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 31.74 | 2872.24 | Engineering, BIM and Coordination - startup and checkout
2025-09-07 | PRJ-PAY-ARM-2506-20250907 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1044 | 35.77 | 3469.46 | Field Installation Labor - punchlist and closeout labor
2025-09-07 | PRJ-PAY-ARM-2506-20250907 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 31.58 | 3268.44 | Startup, Testing and Commissioning - field installation time
2025-09-07 | PRJ-PAY-ARM-2506-20250907 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1084 | 57.62 | 4090.99 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-08 | AP-0004970 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2353 |  | 53.86 | 9694.72 | Plumbing Fixtures and Piping - released equipment package
2025-09-11 | AP-0004967 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2312 |  | 77.36 | 13924.15 | Major HVAC Equipment - valves and piping lot
2025-09-14 | AP-0004964 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2270 |  | 89.65 | 16136.39 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-09-14 | AP-0004974 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2391 |  | 25332.74 | 25332.74 | Electrical and Controls Subcontract - rigging and specialty support
2025-09-14 | AP-0004977 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2427 |  | 8034.62 | 8034.62 | Permits, Fees and Bonds - permit and inspection fees
2025-09-14 | PRJ-PAY-ARM-2506-20250914 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1021 | 59.51 | 4225.12 | Rework and Quality Correction - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2506-20250914 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1028 | 37.08 | 3170.37 | Project Management and Supervision - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2506-20250914 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 31.96 | 2684.79 | Engineering, BIM and Coordination - startup and checkout
2025-09-14 | PRJ-PAY-ARM-2506-20250914 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1042 | 40.06 | 3625.68 | Field Installation Labor - punchlist and closeout labor
2025-09-14 | PRJ-PAY-ARM-2506-20250914 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 39.37 | 3819.09 | Startup, Testing and Commissioning - field installation time
2025-09-14 | PRJ-PAY-ARM-2506-20250914 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 37.21 | 3851.08 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2506-20250914 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1089 | 47.8 | 3393.74 | Controls Programming and Checkout - supervision and planning
2025-09-15 | AP-0004971 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2367 |  | 45.44 | 8179.03 | Major HVAC Equipment - fabricated material delivery
2025-09-18 | AP-0004968 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2326 |  | 61.14 | 11004.68 | Plumbing Fixtures and Piping - ductwork release
2025-09-21 | AP-0004965 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2284 |  | 87.19 | 15694.55 | Major HVAC Equipment - released equipment package
2025-09-21 | PRJ-PAY-ARM-2506-20250921 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1026 | 37.76 | 2982.84 | Project Management and Supervision - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2506-20250921 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 51.39 | 3982.46 | Engineering, BIM and Coordination - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2506-20250921 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1040 | 53.38 | 4484.19 | Field Installation Labor - punchlist and closeout labor
2025-09-21 | PRJ-PAY-ARM-2506-20250921 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1047 | 47.12 | 4264.19 | Startup, Testing and Commissioning - field installation time
2025-09-21 | PRJ-PAY-ARM-2506-20250921 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1080 | 45.3 | 4393.68 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-21 | PRJ-PAY-ARM-2506-20250921 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1087 | 30.23 | 3128.82 | Controls Programming and Checkout - supervision and planning
2025-09-24 | AP-0004962 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2231 |  | 99.18 | 17852.39 | Plumbing Fixtures and Piping - valves and piping lot
2025-09-24 | AP-0004972 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2364 |  | 29328.42 | 29328.42 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-09-24 | AP-0004975 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2400 |  | 9740.42 | 9740.42 | Equipment Rental and Rigging - small tools and field consumables
2025-09-25 | AP-0004969 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2339 |  | 56.26 | 10127.22 | Major HVAC Equipment - jobsite material replenishment
2025-09-28 | PRJ-PAY-ARM-2506-20250928 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 38.58 | 2738.94 | Engineering, BIM and Coordination - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2506-20250928 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1038 | 46.5 | 3604.11 | Field Installation Labor - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2506-20250928 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 45.06 | 3785 | Startup, Testing and Commissioning - field installation time
2025-09-28 | PRJ-PAY-ARM-2506-20250928 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 31 | 2805.93 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-28 | PRJ-PAY-ARM-2506-20250928 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1085 | 41.53 | 4028.39 | Controls Programming and Checkout - supervision and planning
2025-09-28 | PRJ-PAY-ARM-2506-20250928 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1092 | 36.07 | 3733.4 | Warranty and Punchlist - startup and checkout
2025-09-30 | PRJ-PAY-ARM-2506-20250930 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1036 | 49.35 | 3503.6 | Field Installation Labor - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2506-20250930 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 36.68 | 2842.73 | Startup, Testing and Commissioning - field installation time
2025-09-30 | PRJ-PAY-ARM-2506-20250930 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 56.07 | 4710.26 | Sheet Metal Fabrication Labor - coordination and layout
2025-09-30 | PRJ-PAY-ARM-2506-20250930 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1083 | 49.37 | 4468.24 | Controls Programming and Checkout - supervision and planning
2025-09-30 | PRJ-PAY-ARM-2506-20250930 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1090 | 40.82 | 3959.45 | Warranty and Punchlist - startup and checkout
2025-10-03 | AP-0004978 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2438 |  | 55.67 | 10019.89 | Controls Panels and Devices - ductwork release
2025-10-03 | AP-0004986 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2533 |  | 27258.22 | 27258.22 | Insulation Subcontract - electrical coordination scope
2025-10-03 | AP-0004989 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2217 |  | 7968.36 | 7968.36 | Permits, Fees and Bonds - rental and logistics
2025-10-04 | AP-0004985 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2533 |  | 87.43 | 15737.12 | Sheet Metal and Ductwork - released equipment package
2025-10-07 | AP-0004982 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2491 |  | 65.63 | 11812.55 | Controls Panels and Devices - valves and piping lot
2025-10-07 | PRJ-PAY-ARM-2506-20251007 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1016 | 52.02 | 3693.7 | Rework and Quality Correction - field installation time
2025-10-07 | PRJ-PAY-ARM-2506-20251007 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1024 | 39.73 | 3396.71 | Project Management and Supervision - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2506-20251007 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 34.38 | 2887.88 | Engineering, BIM and Coordination - supervision and planning
2025-10-07 | PRJ-PAY-ARM-2506-20251007 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1038 | 37.7 | 3411.56 | Field Installation Labor - startup and checkout
2025-10-07 | PRJ-PAY-ARM-2506-20251007 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 41.98 | 4071.97 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-07 | PRJ-PAY-ARM-2506-20251007 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 34.26 | 3545.8 | Sheet Metal Fabrication Labor - field installation time
2025-10-07 | PRJ-PAY-ARM-2506-20251007 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1085 | 40.76 | 2894.14 | Controls Programming and Checkout - coordination and layout
2025-10-10 | AP-0004979 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2450 |  | 87.29 | 15712.98 | Sheet Metal and Ductwork - jobsite material replenishment
2025-10-10 | AP-0004987 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2029 |  | 19109.58 | 19109.58 | Crane, Rigging and Specialty Trade - rigging and specialty support
2025-10-10 | AP-0004990 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2237 |  | 6189.03 | 6189.03 | Temporary Facilities and Protection - permit and inspection fees
2025-10-14 | AP-0004983 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2505 |  | 85.6 | 15407.19 | Sheet Metal and Ductwork - ductwork release
2025-10-14 | PRJ-PAY-ARM-2506-20251014 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1022 | 51.88 | 4098.83 | Project Management and Supervision - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2506-20251014 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 56.11 | 4348.22 | Engineering, BIM and Coordination - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2506-20251014 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1036 | 39.34 | 3304.88 | Field Installation Labor - startup and checkout
2025-10-14 | PRJ-PAY-ARM-2506-20251014 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 33.13 | 2997.82 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-14 | PRJ-PAY-ARM-2506-20251014 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 33.07 | 3208.11 | Sheet Metal Fabrication Labor - field installation time
2025-10-14 | PRJ-PAY-ARM-2506-20251014 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1083 | 43.13 | 4463.96 | Controls Programming and Checkout - coordination and layout
2025-10-17 | AP-0004980 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2464 |  | 47.6 | 8567.8 | Controls Panels and Devices - released equipment package
2025-10-17 | AP-0004988 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2201 |  | 24719.1 | 24719.1 | Testing and Balancing Subcontract - trade partner progress billing
2025-10-17 | AP-0004991 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2256 |  | 7643.71 | 7643.71 | Freight and Expediting - freight and expediting
2025-10-21 | AP-0004984 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2519 |  | 83.25 | 14984.98 | Controls Panels and Devices - jobsite material replenishment
2025-10-21 | PRJ-PAY-ARM-2506-20251021 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 59.37 | 4215.1 | Engineering, BIM and Coordination - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2506-20251021 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1034 | 42.96 | 3329.36 | Field Installation Labor - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2506-20251021 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 35.59 | 2989.8 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-21 | PRJ-PAY-ARM-2506-20251021 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1048 | 36.96 | 3344.6 | Sheet Metal Fabrication Labor - field installation time
2025-10-21 | PRJ-PAY-ARM-2506-20251021 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1081 | 29.43 | 2855.08 | Controls Programming and Checkout - coordination and layout
2025-10-21 | PRJ-PAY-ARM-2506-20251021 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1088 | 31.27 | 3236.51 | Warranty and Punchlist - supervision and planning
2025-10-24 | AP-0004981 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2477 |  | 71.35 | 12842.48 | Sheet Metal and Ductwork - fabricated material delivery
2025-10-24 | AP-0004992 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2275 |  | 6015.51 | 6015.51 | Equipment Rental and Rigging - small tools and field consumables
2025-10-28 | PRJ-PAY-ARM-2506-20251028 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1032 | 45.8 | 3251.92 | Field Installation Labor - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2506-20251028 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 52 | 4029.62 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2506-20251028 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 39.13 | 3286.57 | Sheet Metal Fabrication Labor - field installation time
2025-10-28 | PRJ-PAY-ARM-2506-20251028 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1053 | 46.33 | 4193.27 | Controls Programming and Checkout - coordination and layout
2025-10-28 | PRJ-PAY-ARM-2506-20251028 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1086 | 41.65 | 4040.04 | Warranty and Punchlist - supervision and planning
2025-10-31 | PRJ-PAY-ARM-2506-20251031 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 50.58 | 3590.96 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2506-20251031 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 50.16 | 3887.04 | Sheet Metal Fabrication Labor - field installation time
2025-10-31 | PRJ-PAY-ARM-2506-20251031 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1051 | 41.09 | 3451.43 | Controls Programming and Checkout - coordination and layout
2025-10-31 | PRJ-PAY-ARM-2506-20251031 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1084 | 38.53 | 3486.89 | Warranty and Punchlist - supervision and planning
2025-10-31 | PRJ-PAY-ARM-2506-20251031 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1091 | 28.72 | 2785.79 | Closeout and O&M Documentation - startup and checkout
2025-10-31 | PRJ-PAY-ARM-2506-20251031 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1098 | 26.93 | 2787.43 | Rework and Quality Correction - punchlist and closeout labor
2025-11-03 | AP-0004996 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2326 |  | 77.66 | 13977.94 | Hydronic Piping and Valves - valves and piping lot
2025-11-03 | AP-0005008 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2469 |  | 4372.31 | 4372.31 | Permits, Fees and Bonds - rental and logistics
2025-11-06 | AP-0004993 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2284 |  | 63.26 | 11387.69 | Insulation and Specialty Material - jobsite material replenishment
2025-11-06 | AP-0005002 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2393 |  | 16314.87 | 16314.87 | Electrical and Controls Subcontract - rigging and specialty support
2025-11-06 | AP-0005005 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2429 |  | 4630.66 | 4630.66 | Freight and Expediting - permit and inspection fees
2025-11-07 | AP-0005000 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2381 |  | 51.11 | 9199.54 | Hydronic Piping and Valves - fabricated material delivery
2025-11-07 | PRJ-PAY-ARM-2506-20251107 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1018 | 47.67 | 3765.65 | Project Management and Supervision - field installation time
2025-11-07 | PRJ-PAY-ARM-2506-20251107 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 46.73 | 3621.34 | Engineering, BIM and Coordination - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2506-20251107 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1032 | 41.93 | 3522.1 | Field Installation Labor - supervision and planning
2025-11-07 | PRJ-PAY-ARM-2506-20251107 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 38.27 | 3463.2 | Startup, Testing and Commissioning - startup and checkout
2025-11-07 | PRJ-PAY-ARM-2506-20251107 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 50.39 | 4887.46 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-07 | PRJ-PAY-ARM-2506-20251107 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1053 | 33.99 | 3518.13 | Controls Programming and Checkout - field installation time
2025-11-10 | AP-0004997 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2339 |  | 51.1 | 9198.72 | Insulation and Specialty Material - ductwork release
2025-11-13 | AP-0004994 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2298 |  | 83.29 | 14991.77 | Hydronic Piping and Valves - released equipment package
2025-11-13 | AP-0005003 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2407 |  | 26282.35 | 26282.35 | Insulation Subcontract - trade partner progress billing
2025-11-13 | AP-0005006 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2441 |  | 8039.67 | 8039.67 | Equipment Rental and Rigging - freight and expediting
2025-11-14 | AP-0005001 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2395 |  | 79.22 | 14259.18 | Insulation and Specialty Material - valves and piping lot
2025-11-14 | PRJ-PAY-ARM-2506-20251114 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 47.77 | 3391.47 | Engineering, BIM and Coordination - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2506-20251114 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1030 | 34.66 | 2686.34 | Field Installation Labor - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2506-20251114 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 40.31 | 3385.64 | Startup, Testing and Commissioning - startup and checkout
2025-11-14 | PRJ-PAY-ARM-2506-20251114 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 44.37 | 4015.17 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-14 | PRJ-PAY-ARM-2506-20251114 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1051 | 32.29 | 3132.43 | Controls Programming and Checkout - field installation time
2025-11-14 | PRJ-PAY-ARM-2506-20251114 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1084 | 35.52 | 3676.53 | Warranty and Punchlist - coordination and layout
2025-11-17 | AP-0004998 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2353 |  | 59.32 | 10677.69 | Hydronic Piping and Valves - jobsite material replenishment
2025-11-20 | AP-0004995 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2312 |  | 83.85 | 15092.77 | Insulation and Specialty Material - fabricated material delivery
2025-11-20 | AP-0005004 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2421 |  | 25519.47 | 25519.47 | Crane, Rigging and Specialty Trade - insulation progress invoice
2025-11-20 | AP-0005007 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2455 |  | 7727.07 | 7727.07 | Small Tools and Consumables - small tools and field consumables
2025-11-21 | PRJ-PAY-ARM-2506-20251121 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1028 | 58.92 | 4183.4 | Field Installation Labor - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2506-20251121 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 47.1 | 3650.61 | Startup, Testing and Commissioning - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2506-20251121 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 50.16 | 4213.53 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-21 | PRJ-PAY-ARM-2506-20251121 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1049 | 38.83 | 3514.17 | Controls Programming and Checkout - field installation time
2025-11-21 | PRJ-PAY-ARM-2506-20251121 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1082 | 36.48 | 3538.28 | Warranty and Punchlist - coordination and layout
2025-11-24 | AP-0004999 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2367 |  | 70.44 | 12678.38 | Insulation and Specialty Material - released equipment package
2025-11-28 | PRJ-PAY-ARM-2506-20251128 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 53.79 | 3818.81 | Startup, Testing and Commissioning - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2506-20251128 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 47.14 | 3653.44 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2506-20251128 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1047 | 35.45 | 2977.72 | Controls Programming and Checkout - field installation time
2025-11-28 | PRJ-PAY-ARM-2506-20251128 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1080 | 35.63 | 3224.15 | Warranty and Punchlist - coordination and layout
2025-11-28 | PRJ-PAY-ARM-2506-20251128 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1087 | 35.21 | 3415.5 | Closeout and O&M Documentation - supervision and planning
2025-11-28 | PRJ-PAY-ARM-2506-20251128 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1094 | 31.09 | 3217.36 | Rework and Quality Correction - startup and checkout
2025-11-30 | PRJ-PAY-ARM-2506-20251130 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 69.68 | 4947.17 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2506-20251130 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1045 | 42.04 | 3257.95 | Controls Programming and Checkout - field installation time
2025-11-30 | PRJ-PAY-ARM-2506-20251130 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1052 | 42.67 | 3584.54 | Warranty and Punchlist - coordination and layout
2025-11-30 | PRJ-PAY-ARM-2506-20251130 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1085 | 39.6 | 3583.8 | Closeout and O&M Documentation - supervision and planning
2025-11-30 | PRJ-PAY-ARM-2506-20251130 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1092 | 43.03 | 4174.3 | Rework and Quality Correction - startup and checkout
2025-11-30 | PRJ-PAY-ARM-2506-20251130 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1099 | 29.16 | 3251.07 | Project Management and Supervision - punchlist and closeout labor
2025-12-03 | AP-0005015 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2201 |  | 62.44 | 11238.81 | Major HVAC Equipment - fabricated material delivery
2025-12-06 | AP-0005012 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2519 |  | 65.37 | 11766.97 | Plumbing Fixtures and Piping - ductwork release
2025-12-07 | PRJ-PAY-ARM-2506-20251207 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 56.29 | 3996.84 | Engineering, BIM and Coordination - field installation time
2025-12-07 | PRJ-PAY-ARM-2506-20251207 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1026 | 37.86 | 2934.24 | Field Installation Labor - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2506-20251207 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 38.66 | 3247.26 | Startup, Testing and Commissioning - supervision and planning
2025-12-07 | PRJ-PAY-ARM-2506-20251207 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 38.61 | 3493.83 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-07 | PRJ-PAY-ARM-2506-20251207 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1047 | 26.59 | 2579.65 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-09 | AP-0005009 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2477 |  | 74.21 | 13358.65 | Major HVAC Equipment - released equipment package
2025-12-09 | AP-0005017 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2225 |  | 25536.96 | 25536.96 | Testing and Balancing Subcontract - trade partner progress billing
2025-12-09 | AP-0005019 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2258 |  | 4645.3 | 4645.3 | Small Tools and Consumables - freight and expediting
2025-12-10 | AP-0005016 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2225 |  | 45.5 | 8189.26 | Plumbing Fixtures and Piping - valves and piping lot
2025-12-13 | AP-0005013 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2533 |  | 57.97 | 10434.61 | Major HVAC Equipment - jobsite material replenishment
2025-12-14 | PRJ-PAY-ARM-2506-20251214 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1024 | 60.29 | 4280.3 | Field Installation Labor - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2506-20251214 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 51 | 3952.32 | Startup, Testing and Commissioning - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2506-20251214 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 38.26 | 3213.77 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-14 | PRJ-PAY-ARM-2506-20251214 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1045 | 42.59 | 3854.08 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-16 | AP-0005010 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2491 |  | 74.44 | 13398.35 | Plumbing Fixtures and Piping - fabricated material delivery
2025-12-16 | AP-0005018 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2244 |  | 32326.22 | 32326.22 | Electrical and Controls Subcontract - insulation progress invoice
2025-12-16 | AP-0005020 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2277 |  | 4161.07 | 4161.07 | Permits, Fees and Bonds - small tools and field consumables
2025-12-20 | AP-0005014 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2029 |  | 81.83 | 14728.52 | Plumbing Fixtures and Piping - released equipment package
2025-12-21 | PRJ-PAY-ARM-2506-20251221 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 56.44 | 4007.22 | Startup, Testing and Commissioning - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2506-20251221 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 41.62 | 3225.52 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2506-20251221 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1043 | 34.56 | 2903.18 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-21 | PRJ-PAY-ARM-2506-20251221 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1050 | 33.28 | 3012.28 | Warranty and Punchlist - field installation time
2025-12-21 | PRJ-PAY-ARM-2506-20251221 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1083 | 32.16 | 3119.16 | Closeout and O&M Documentation - coordination and layout
2025-12-23 | AP-0005011 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2505 |  | 69.36 | 12484.87 | Major HVAC Equipment - valves and piping lot
2025-12-23 | AP-0005021 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2291 |  | 8804.16 | 8804.16 | Temporary Facilities and Protection - rental and logistics
2025-12-28 | PRJ-PAY-ARM-2506-20251228 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 48.09 | 3414.71 | Sheet Metal Fabrication Labor - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2506-20251228 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1041 | 46.05 | 3569.06 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2506-20251228 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1048 | 39 | 3275.64 | Warranty and Punchlist - field installation time
2025-12-28 | PRJ-PAY-ARM-2506-20251228 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1081 | 48.38 | 4378.23 | Closeout and O&M Documentation - coordination and layout
2025-12-28 | PRJ-PAY-ARM-2506-20251228 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1088 | 37.38 | 3625.88 | Rework and Quality Correction - supervision and planning
2025-12-31 | PRJ-PAY-ARM-2506-20251231 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1039 | 39.78 | 2824.31 | Controls Programming and Checkout - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2506-20251231 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1046 | 50.79 | 3935.97 | Warranty and Punchlist - field installation time
2025-12-31 | PRJ-PAY-ARM-2506-20251231 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 50.52 | 4243.45 | Closeout and O&M Documentation - coordination and layout
2025-12-31 | PRJ-PAY-ARM-2506-20251231 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1086 | 45.95 | 4158.67 | Rework and Quality Correction - supervision and planning
2025-12-31 | PRJ-PAY-ARM-2506-20251231 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1093 | 40.87 | 4291.31 | Project Management and Supervision - startup and checkout
2026-01-07 | PRJ-PAY-ARM-2506-20260107 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1020 | 52.47 | 3725.05 | Field Installation Labor - field installation time
2026-01-07 | PRJ-PAY-ARM-2506-20260107 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 51.41 | 3984.25 | Startup, Testing and Commissioning - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2506-20260107 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 38.79 | 3258.61 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-07 | PRJ-PAY-ARM-2506-20260107 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1041 | 34.14 | 3089.93 | Controls Programming and Checkout - startup and checkout
2026-01-09 | AP-0005025 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2343 |  | 45.6 | 8208.64 | Controls Panels and Devices - jobsite material replenishment
2026-01-12 | AP-0005022 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2301 |  | 58.98 | 10615.74 | Sheet Metal and Ductwork - fabricated material delivery
2026-01-12 | AP-0005028 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2374 |  | 29096.48 | 29096.48 | Crane, Rigging and Specialty Trade - insulation progress invoice
2026-01-12 | AP-0005030 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2398 |  | 6216.99 | 6216.99 | Temporary Facilities and Protection - small tools and field consumables
2026-01-14 | PRJ-PAY-ARM-2506-20260114 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 68.48 | 4862 | Startup, Testing and Commissioning - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2506-20260114 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 40.19 | 3115.02 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2506-20260114 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1039 | 34.75 | 2919.36 | Controls Programming and Checkout - startup and checkout
2026-01-14 | PRJ-PAY-ARM-2506-20260114 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1046 | 44.75 | 4049.81 | Warranty and Punchlist - punchlist and closeout labor
2026-01-16 | AP-0005026 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2357 |  | 98.15 | 17666.2 | Sheet Metal and Ductwork - released equipment package
2026-01-19 | AP-0005023 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2315 |  | 92.54 | 16657.2 | Controls Panels and Devices - valves and piping lot
2026-01-19 | AP-0005029 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2388 |  | 23237.26 | 23237.26 | Testing and Balancing Subcontract - testing and balancing services
2026-01-19 | AP-0005031 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2412 |  | 7211.76 | 7211.76 | Freight and Expediting - rental and logistics
2026-01-21 | PRJ-PAY-ARM-2506-20260121 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 41.66 | 2957.87 | Sheet Metal Fabrication Labor - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2506-20260121 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1037 | 51.37 | 3980.87 | Controls Programming and Checkout - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2506-20260121 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1044 | 36.17 | 3038.52 | Warranty and Punchlist - punchlist and closeout labor
2026-01-21 | PRJ-PAY-ARM-2506-20260121 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 36.85 | 3335.29 | Closeout and O&M Documentation - field installation time
2026-01-21 | PRJ-PAY-ARM-2506-20260121 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1084 | 35.75 | 3467.69 | Rework and Quality Correction - coordination and layout
2026-01-23 | AP-0005027 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2370 |  | 64.81 | 11666.59 | Controls Panels and Devices - fabricated material delivery
2026-01-25 | AP-0005024 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2329 |  | 89.25 | 16065.04 | Sheet Metal and Ductwork - ductwork release
2026-01-25 | AP-0005032 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2426 |  | 7980.51 | 7980.51 | Equipment Rental and Rigging - permit and inspection fees
2026-01-28 | PRJ-PAY-ARM-2506-20260128 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1035 | 45.2 | 3209.36 | Controls Programming and Checkout - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2506-20260128 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1042 | 44.9 | 3480.12 | Warranty and Punchlist - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2506-20260128 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 44.4 | 3729.53 | Closeout and O&M Documentation - field installation time
2026-01-28 | PRJ-PAY-ARM-2506-20260128 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1082 | 48.17 | 4359.26 | Rework and Quality Correction - coordination and layout
2026-01-28 | PRJ-PAY-ARM-2506-20260128 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1089 | 29.48 | 3095.49 | Project Management and Supervision - supervision and planning
2026-01-31 | PRJ-PAY-ARM-2506-20260131 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1040 | 44.39 | 3151.68 | Warranty and Punchlist - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2506-20260131 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 42.2 | 3270.88 | Closeout and O&M Documentation - field installation time
2026-01-31 | PRJ-PAY-ARM-2506-20260131 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1080 | 52.41 | 4402.04 | Rework and Quality Correction - coordination and layout
2026-01-31 | PRJ-PAY-ARM-2506-20260131 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1087 | 36.27 | 3572.53 | Project Management and Supervision - supervision and planning
2026-01-31 | PRJ-PAY-ARM-2506-20260131 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1094 | 29.12 | 2824.25 | Engineering, BIM and Coordination - startup and checkout
2026-02-05 | AP-0005035 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2462 |  | 80.03 | 14404.93 | Hydronic Piping and Valves - jobsite material replenishment
2026-02-05 | AP-0005044 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2220 |  | 4382.75 | 4382.75 | Permits, Fees and Bonds - freight and expediting
2026-02-07 | PRJ-PAY-ARM-2506-20260207 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 44.36 | 3149.3 | Startup, Testing and Commissioning - field installation time
2026-02-07 | PRJ-PAY-ARM-2506-20260207 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 53.21 | 4123.8 | Sheet Metal Fabrication Labor - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2506-20260207 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1035 | 53.19 | 4467.65 | Controls Programming and Checkout - supervision and planning
2026-02-07 | PRJ-PAY-ARM-2506-20260207 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1042 | 43.4 | 3927.82 | Warranty and Punchlist - startup and checkout
2026-02-07 | PRJ-PAY-ARM-2506-20260207 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 35.34 | 3427.78 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-09 | AP-0005039 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2517 |  | 87.51 | 15751.94 | Hydronic Piping and Valves - ductwork release
2026-02-12 | AP-0005036 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2476 |  | 64.75 | 11655.06 | Insulation and Specialty Material - released equipment package
2026-02-14 | PRJ-PAY-ARM-2506-20260214 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 61.6 | 4373.45 | Sheet Metal Fabrication Labor - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2506-20260214 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1033 | 40.04 | 3103.14 | Controls Programming and Checkout - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2506-20260214 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1040 | 39.4 | 3309.27 | Warranty and Punchlist - startup and checkout
2026-02-14 | PRJ-PAY-ARM-2506-20260214 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 44.91 | 4063.99 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-14 | PRJ-PAY-ARM-2506-20260214 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1080 | 38.59 | 3743.04 | Rework and Quality Correction - field installation time
2026-02-14 | PRJ-PAY-ARM-2506-20260214 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1087 | 25.53 | 2846.77 | Project Management and Supervision - coordination and layout
2026-02-15 | AP-0005033 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2436 |  | 81.35 | 14642.44 | Hydronic Piping and Valves - valves and piping lot
2026-02-15 | AP-0005040 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2519 |  | 23526.23 | 23526.23 | Insulation Subcontract - testing and balancing services
2026-02-15 | AP-0005042 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2021 |  | 6049.69 | 6049.69 | Equipment Rental and Rigging - rental and logistics
2026-02-19 | AP-0005037 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2490 |  | 78.67 | 14160.92 | Hydronic Piping and Valves - fabricated material delivery
2026-02-21 | PRJ-PAY-ARM-2506-20260221 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1031 | 49.51 | 3515.41 | Controls Programming and Checkout - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2506-20260221 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1038 | 43.97 | 3407.42 | Warranty and Punchlist - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2506-20260221 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 45.3 | 3805.22 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-21 | PRJ-PAY-ARM-2506-20260221 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1052 | 53.2 | 4814.26 | Rework and Quality Correction - field installation time
2026-02-21 | PRJ-PAY-ARM-2506-20260221 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1085 | 37.91 | 3980.32 | Project Management and Supervision - coordination and layout
2026-02-21 | PRJ-PAY-ARM-2506-20260221 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1092 | 32.02 | 3314.19 | Engineering, BIM and Coordination - supervision and planning
2026-02-22 | AP-0005034 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2448 |  | 65 | 11699.78 | Insulation and Specialty Material - ductwork release
2026-02-22 | AP-0005041 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2533 |  | 34228.21 | 34228.21 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-02-22 | AP-0005043 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2094 |  | 9656.07 | 9656.07 | Small Tools and Consumables - permit and inspection fees
2026-02-25 | AP-0005038 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2503 |  | 44.91 | 8083.19 | Insulation and Specialty Material - valves and piping lot
2026-02-28 | PRJ-PAY-ARM-2506-20260228 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1036 | 61.79 | 4386.81 | Warranty and Punchlist - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2506-20260228 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 44 | 3409.68 | Closeout and O&M Documentation - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2506-20260228 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1050 | 50.33 | 4228.09 | Rework and Quality Correction - field installation time
2026-02-28 | PRJ-PAY-ARM-2506-20260228 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1083 | 27.87 | 2745 | Project Management and Supervision - coordination and layout
2026-02-28 | PRJ-PAY-ARM-2506-20260228 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1090 | 46.71 | 4530.53 | Engineering, BIM and Coordination - supervision and planning
2026-02-28 | PRJ-PAY-ARM-2506-20260228 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1097 | 26.12 | 2703.19 | Field Installation Labor - startup and checkout
2026-03-05 | AP-0005050 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2315 |  | 51.3 | 9234.16 | Major HVAC Equipment - ductwork release
2026-03-07 | PRJ-PAY-ARM-2506-20260307 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1022 | 53.93 | 3829.17 | Sheet Metal Fabrication Labor - field installation time
2026-03-07 | PRJ-PAY-ARM-2506-20260307 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1029 | 54.18 | 4198.93 | Controls Programming and Checkout - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2506-20260307 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1036 | 44.98 | 3778.23 | Warranty and Punchlist - supervision and planning
2026-03-07 | PRJ-PAY-ARM-2506-20260307 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 30.57 | 2766.53 | Closeout and O&M Documentation - startup and checkout
2026-03-07 | PRJ-PAY-ARM-2506-20260307 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1050 | 44.09 | 4277.21 | Rework and Quality Correction - punchlist and closeout labor
2026-03-08 | AP-0005047 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2274 |  | 72.58 | 13064.63 | Plumbing Fixtures and Piping - released equipment package
2026-03-08 | AP-0005057 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2395 |  | 5612.43 | 5612.43 | Freight and Expediting - small tools and field consumables
2026-03-12 | AP-0005051 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2329 |  | 103.19 | 18573.85 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-03-14 | PRJ-PAY-ARM-2506-20260314 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1027 | 41 | 2910.88 | Controls Programming and Checkout - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2506-20260314 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1034 | 50 | 3875.15 | Warranty and Punchlist - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2506-20260314 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 31.96 | 2684.99 | Closeout and O&M Documentation - startup and checkout
2026-03-14 | PRJ-PAY-ARM-2506-20260314 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1048 | 33.99 | 3076.15 | Rework and Quality Correction - punchlist and closeout labor
2026-03-14 | PRJ-PAY-ARM-2506-20260314 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1081 | 32.5 | 3412.17 | Project Management and Supervision - field installation time
2026-03-14 | PRJ-PAY-ARM-2506-20260314 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1088 | 39.8 | 4119.14 | Engineering, BIM and Coordination - coordination and layout
2026-03-15 | AP-0005048 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2288 |  | 105.88 | 19058.32 | Major HVAC Equipment - fabricated material delivery
2026-03-18 | AP-0005045 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2234 |  | 48.66 | 8759.52 | Plumbing Fixtures and Piping - ductwork release
2026-03-18 | AP-0005053 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2343 |  | 39206.26 | 39206.26 | Electrical and Controls Subcontract - electrical coordination scope
2026-03-18 | AP-0005055 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2367 |  | 6573.91 | 6573.91 | Permits, Fees and Bonds - permit and inspection fees
2026-03-19 | AP-0005052 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2343 |  | 75.88 | 13657.99 | Major HVAC Equipment - released equipment package
2026-03-21 | PRJ-PAY-ARM-2506-20260321 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1032 | 45.23 | 3211.25 | Warranty and Punchlist - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2506-20260321 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 47.06 | 3646.97 | Closeout and O&M Documentation - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2506-20260321 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1046 | 54.34 | 4564.4 | Rework and Quality Correction - punchlist and closeout labor
2026-03-21 | PRJ-PAY-ARM-2506-20260321 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1053 | 31.01 | 3054.75 | Project Management and Supervision - field installation time
2026-03-21 | PRJ-PAY-ARM-2506-20260321 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1086 | 50.19 | 4868.25 | Engineering, BIM and Coordination - coordination and layout
2026-03-22 | AP-0005049 | AP | ARM-2506 | 02-410 | Plumbing Fixtures and Piping | V-2301 |  | 51.76 | 9316.53 | Plumbing Fixtures and Piping - valves and piping lot
2026-03-25 | AP-0005046 | AP | ARM-2506 | 02-110 | Major HVAC Equipment | V-2255 |  | 58.73 | 10571.13 | Major HVAC Equipment - jobsite material replenishment
2026-03-25 | AP-0005054 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2357 |  | 19983.08 | 19983.08 | Insulation Subcontract - rigging and specialty support
2026-03-25 | AP-0005056 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2381 |  | 6646.63 | 6646.63 | Temporary Facilities and Protection - freight and expediting
2026-03-28 | PRJ-PAY-ARM-2506-20260328 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 48.47 | 3441.25 | Closeout and O&M Documentation - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2506-20260328 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1044 | 39.18 | 3036.69 | Rework and Quality Correction - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2506-20260328 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1051 | 40.17 | 3695.32 | Project Management and Supervision - field installation time
2026-03-28 | PRJ-PAY-ARM-2506-20260328 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1084 | 38.29 | 3465.39 | Engineering, BIM and Coordination - coordination and layout
2026-03-28 | PRJ-PAY-ARM-2506-20260328 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1091 | 38.01 | 3686.64 | Field Installation Labor - supervision and planning
2026-03-31 | PRJ-PAY-ARM-2506-20260331 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1042 | 61.65 | 4377.41 | Rework and Quality Correction - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2506-20260331 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1049 | 43.08 | 3683.37 | Project Management and Supervision - field installation time
2026-03-31 | PRJ-PAY-ARM-2506-20260331 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 52.73 | 4429.03 | Engineering, BIM and Coordination - coordination and layout
2026-03-31 | PRJ-PAY-ARM-2506-20260331 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1089 | 37.41 | 3385.16 | Field Installation Labor - supervision and planning
2026-04-04 | AP-0005059 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2419 |  | 46.49 | 8368.99 | Sheet Metal and Ductwork - released equipment package
2026-04-04 | AP-0005067 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2514 |  | 24572.06 | 24572.06 | Electrical and Controls Subcontract - trade partner progress billing
2026-04-04 | AP-0005070 | AP | ARM-2506 | 05-100 | Equipment Rental and Rigging | V-2037 |  | 5903.7 | 5903.7 | Equipment Rental and Rigging - small tools and field consumables
2026-04-07 | PRJ-PAY-ARM-2506-20260407 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1023 | 53.76 | 3817.21 | Controls Programming and Checkout - field installation time
2026-04-07 | PRJ-PAY-ARM-2506-20260407 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1030 | 52.9 | 4099.77 | Warranty and Punchlist - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2506-20260407 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 35.4 | 2973.46 | Closeout and O&M Documentation - supervision and planning
2026-04-07 | PRJ-PAY-ARM-2506-20260407 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1044 | 28.81 | 2606.89 | Rework and Quality Correction - startup and checkout
2026-04-07 | PRJ-PAY-ARM-2506-20260407 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1051 | 34.22 | 3593.5 | Project Management and Supervision - punchlist and closeout labor
2026-04-07 | PRJ-PAY-ARM-2506-20260407 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1084 | 27 | 2794.09 | Engineering, BIM and Coordination - field installation time
2026-04-07 | PRJ-PAY-ARM-2506-20260407 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1091 | 52.82 | 3749.87 | Field Installation Labor - coordination and layout
2026-04-08 | AP-0005063 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2472 |  | 91.23 | 16421.89 | Sheet Metal and Ductwork - jobsite material replenishment
2026-04-11 | AP-0005060 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2433 |  | 68.11 | 12260.55 | Controls Panels and Devices - fabricated material delivery
2026-04-11 | AP-0005068 | AP | ARM-2506 | 04-100 | Insulation Subcontract | V-2528 |  | 20742.78 | 20742.78 | Insulation Subcontract - insulation progress invoice
2026-04-11 | AP-0005071 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2208 |  | 9175.89 | 9175.89 | Small Tools and Consumables - rental and logistics
2026-04-14 | PRJ-PAY-ARM-2506-20260414 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1028 | 63.96 | 4541.3 | Warranty and Punchlist - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2506-20260414 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 47.79 | 3703.64 | Closeout and O&M Documentation - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2506-20260414 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1042 | 41.59 | 3493.61 | Rework and Quality Correction - startup and checkout
2026-04-14 | PRJ-PAY-ARM-2506-20260414 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1049 | 40.14 | 3953.8 | Project Management and Supervision - punchlist and closeout labor
2026-04-14 | PRJ-PAY-ARM-2506-20260414 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 41.47 | 4022.73 | Engineering, BIM and Coordination - field installation time
2026-04-14 | PRJ-PAY-ARM-2506-20260414 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1089 | 29.54 | 3057.05 | Field Installation Labor - coordination and layout
2026-04-15 | AP-0005064 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2486 |  | 58.35 | 10503.3 | Controls Panels and Devices - released equipment package
2026-04-18 | AP-0005061 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2445 |  | 99.78 | 17959.54 | Sheet Metal and Ductwork - valves and piping lot
2026-04-18 | AP-0005072 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2231 |  | 6251.24 | 6251.24 | Permits, Fees and Bonds - permit and inspection fees
2026-04-21 | AP-0005058 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2405 |  | 76.1 | 13698.03 | Controls Panels and Devices - jobsite material replenishment
2026-04-21 | AP-0005066 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2500 |  | 25516.86 | 25516.86 | Testing and Balancing Subcontract - rigging and specialty support
2026-04-21 | AP-0005069 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2001 |  | 6385.93 | 6385.93 | Freight and Expediting - freight and expediting
2026-04-21 | PRJ-PAY-ARM-2506-20260421 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 45.62 | 3238.87 | Closeout and O&M Documentation - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2506-20260421 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1040 | 49.2 | 3812.75 | Rework and Quality Correction - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2506-20260421 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1047 | 37.47 | 3447.69 | Project Management and Supervision - punchlist and closeout labor
2026-04-21 | PRJ-PAY-ARM-2506-20260421 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1080 | 32.15 | 2909.29 | Engineering, BIM and Coordination - field installation time
2026-04-21 | PRJ-PAY-ARM-2506-20260421 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1087 | 35.93 | 3484.78 | Field Installation Labor - coordination and layout
2026-04-21 | PRJ-PAY-ARM-2506-20260421 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1094 | 33.82 | 3500.58 | Startup, Testing and Commissioning - supervision and planning
2026-04-22 | AP-0005065 | AP | ARM-2506 | 02-210 | Sheet Metal and Ductwork | V-2500 |  | 73.1 | 13157.2 | Sheet Metal and Ductwork - fabricated material delivery
2026-04-25 | AP-0005062 | AP | ARM-2506 | 02-510 | Controls Panels and Devices | V-2458 |  | 68.55 | 12338.23 | Controls Panels and Devices - ductwork release
2026-04-28 | PRJ-PAY-ARM-2506-20260428 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1038 | 54.45 | 3865.65 | Rework and Quality Correction - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2506-20260428 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1045 | 43.79 | 3743.73 | Project Management and Supervision - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2506-20260428 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 44.4 | 3729.19 | Engineering, BIM and Coordination - field installation time
2026-04-28 | PRJ-PAY-ARM-2506-20260428 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1085 | 43.54 | 3940.58 | Field Installation Labor - coordination and layout
2026-04-28 | PRJ-PAY-ARM-2506-20260428 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1092 | 35.13 | 3407.6 | Startup, Testing and Commissioning - supervision and planning
2026-04-30 | PRJ-PAY-ARM-2506-20260430 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1043 | 51.24 | 4047.79 | Project Management and Supervision - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2506-20260430 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 46.89 | 3634.15 | Engineering, BIM and Coordination - field installation time
2026-04-30 | PRJ-PAY-ARM-2506-20260430 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1083 | 44.85 | 3767.72 | Field Installation Labor - coordination and layout
2026-04-30 | PRJ-PAY-ARM-2506-20260430 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1090 | 37.23 | 3369.58 | Startup, Testing and Commissioning - supervision and planning
2026-04-30 | PRJ-PAY-ARM-2506-20260430 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1097 | 45.37 | 4400.86 | Sheet Metal Fabrication Labor - startup and checkout
2026-05-04 | AP-0005077 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2307 |  | 87.18 | 15692.15 | Insulation and Specialty Material - jobsite material replenishment
2026-05-07 | AP-0005074 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2262 |  | 48.98 | 8817.03 | Hydronic Piping and Valves - fabricated material delivery
2026-05-07 | AP-0005084 | AP | ARM-2506 | 04-300 | Testing and Balancing Subcontract | V-2386 |  | 23696.36 | 23696.36 | Testing and Balancing Subcontract - insulation progress invoice
2026-05-07 | AP-0005087 | AP | ARM-2506 | 05-200 | Permits, Fees and Bonds | V-2422 |  | 8537.84 | 8537.84 | Permits, Fees and Bonds - rental and logistics
2026-05-07 | PRJ-PAY-ARM-2506-20260507 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1024 | 60.93 | 4325.73 | Warranty and Punchlist - field installation time
2026-05-07 | PRJ-PAY-ARM-2506-20260507 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1031 | 58.57 | 4539.5 | Closeout and O&M Documentation - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2506-20260507 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1038 | 39.77 | 3340.5 | Rework and Quality Correction - supervision and planning
2026-05-07 | PRJ-PAY-ARM-2506-20260507 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1045 | 33.87 | 3335.79 | Project Management and Supervision - startup and checkout
2026-05-07 | PRJ-PAY-ARM-2506-20260507 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 34.17 | 3314.05 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-07 | PRJ-PAY-ARM-2506-20260507 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1085 | 34.09 | 3528.05 | Field Installation Labor - field installation time
2026-05-07 | PRJ-PAY-ARM-2506-20260507 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1092 | 50.65 | 3596.36 | Startup, Testing and Commissioning - coordination and layout
2026-05-08 | AP-0005081 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2362 |  | 60.69 | 10923.6 | Insulation and Specialty Material - ductwork release
2026-05-11 | AP-0005078 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2320 |  | 44.5 | 8009.35 | Hydronic Piping and Valves - released equipment package
2026-05-14 | AP-0005075 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2279 |  | 74.8 | 13464.27 | Insulation and Specialty Material - valves and piping lot
2026-05-14 | AP-0005085 | AP | ARM-2506 | 04-200 | Electrical and Controls Subcontract | V-2400 |  | 25914.51 | 25914.51 | Electrical and Controls Subcontract - testing and balancing services
2026-05-14 | AP-0005088 | AP | ARM-2506 | 06-400 | Temporary Facilities and Protection | V-2436 |  | 6567.84 | 6567.84 | Temporary Facilities and Protection - permit and inspection fees
2026-05-14 | PRJ-PAY-ARM-2506-20260514 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1029 | 60.77 | 4314.83 | Closeout and O&M Documentation - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2506-20260514 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1036 | 34.16 | 2647.4 | Rework and Quality Correction - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2506-20260514 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1043 | 45.86 | 4218.93 | Project Management and Supervision - startup and checkout
2026-05-14 | PRJ-PAY-ARM-2506-20260514 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 48.31 | 4371.73 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-14 | PRJ-PAY-ARM-2506-20260514 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1083 | 41.36 | 4012.39 | Field Installation Labor - field installation time
2026-05-14 | PRJ-PAY-ARM-2506-20260514 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1090 | 35.76 | 3701.52 | Startup, Testing and Commissioning - coordination and layout
2026-05-15 | AP-0005082 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2376 |  | 59.53 | 10716.22 | Hydronic Piping and Valves - jobsite material replenishment
2026-05-18 | AP-0005079 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2334 |  | 86.32 | 15537.2 | Insulation and Specialty Material - fabricated material delivery
2026-05-21 | AP-0005076 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2293 |  | 88.81 | 15985.27 | Hydronic Piping and Valves - ductwork release
2026-05-21 | AP-0005089 | AP | ARM-2506 | 05-300 | Freight and Expediting | V-2448 |  | 4367.68 | 4367.68 | Freight and Expediting - freight and expediting
2026-05-21 | PRJ-PAY-ARM-2506-20260521 | PAY | ARM-2506 | 06-300 | Rework and Quality Correction |  | E-1034 | 44.79 | 3180.09 | Rework and Quality Correction - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2506-20260521 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1041 | 49.18 | 4204.63 | Project Management and Supervision - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2506-20260521 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1048 | 42.2 | 3544.66 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-21 | PRJ-PAY-ARM-2506-20260521 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1081 | 37.59 | 3402.25 | Field Installation Labor - field installation time
2026-05-21 | PRJ-PAY-ARM-2506-20260521 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1088 | 34.37 | 3334.28 | Startup, Testing and Commissioning - coordination and layout
2026-05-21 | PRJ-PAY-ARM-2506-20260521 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1095 | 35.3 | 3653.19 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-24 | AP-0005073 | AP | ARM-2506 | 02-610 | Insulation and Specialty Material | V-2243 |  | 53.27 | 9588 | Insulation and Specialty Material - released equipment package
2026-05-24 | AP-0005083 | AP | ARM-2506 | 04-400 | Crane, Rigging and Specialty Trade | V-2372 |  | 26112.02 | 26112.02 | Crane, Rigging and Specialty Trade - trade partner progress billing
2026-05-24 | AP-0005086 | AP | ARM-2506 | 05-400 | Small Tools and Consumables | V-2408 |  | 8062.24 | 8062.24 | Small Tools and Consumables - small tools and field consumables
2026-05-25 | AP-0005080 | AP | ARM-2506 | 02-310 | Hydronic Piping and Valves | V-2348 |  | 84.32 | 15177.1 | Hydronic Piping and Valves - valves and piping lot
2026-05-28 | PRJ-PAY-ARM-2506-20260528 | PAY | ARM-2506 | 01-100 | Project Management and Supervision |  | E-1039 | 36.56 | 2887.91 | Project Management and Supervision - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2506-20260528 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1046 | 49.12 | 3806.95 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2506-20260528 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1053 | 47.85 | 4019.68 | Field Installation Labor - field installation time
2026-05-28 | PRJ-PAY-ARM-2506-20260528 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1086 | 30.39 | 2750.63 | Startup, Testing and Commissioning - coordination and layout
2026-05-28 | PRJ-PAY-ARM-2506-20260528 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1093 | 43.46 | 4215.62 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-28 | PRJ-PAY-ARM-2506-20260528 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1100 | 41.03 | 4246.8 | Controls Programming and Checkout - startup and checkout
2026-05-31 | PRJ-PAY-ARM-2506-20260531 | PAY | ARM-2506 | 01-200 | Engineering, BIM and Coordination |  | E-1044 | 56.23 | 3992.07 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2506-20260531 | PAY | ARM-2506 | 03-100 | Field Installation Labor |  | E-1051 | 41.38 | 3206.88 | Field Installation Labor - field installation time
2026-05-31 | PRJ-PAY-ARM-2506-20260531 | PAY | ARM-2506 | 03-200 | Startup, Testing and Commissioning |  | E-1084 | 41.03 | 3446.29 | Startup, Testing and Commissioning - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2506-20260531 | PAY | ARM-2506 | 03-300 | Sheet Metal Fabrication Labor |  | E-1091 | 37.34 | 3379.49 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-31 | PRJ-PAY-ARM-2506-20260531 | PAY | ARM-2506 | 03-400 | Controls Programming and Checkout |  | E-1098 | 37.05 | 3593.6 | Controls Programming and Checkout - startup and checkout
2026-05-31 | PRJ-PAY-ARM-2506-20260531 | PAY | ARM-2506 | 06-100 | Warranty and Punchlist |  | E-1012 | 37.86 | 3918.08 | Warranty and Punchlist - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2506-20260531 | PAY | ARM-2506 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 42.2 | 2996.41 | Closeout and O&M Documentation - field installation time
2025-03-03 | AP-0005110 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2336 |  | 59.36 | 10685.09 | Hydronic Piping and Valves - released equipment package
2025-03-03 | AP-0005111 | AP | ARM-2510 | 04-100 | Insulation Subcontract | V-2348 |  | 6826.58 | 6826.58 | Insulation Subcontract - trade partner progress billing
2025-03-03 | AP-0005112 | AP | ARM-2510 | 05-400 | Small Tools and Consumables | V-2360 |  | 2374.46 | 2374.46 | Small Tools and Consumables - rental and logistics
2025-03-07 | PRJ-PAY-ARM-2510-20250307 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1007 | 7.14 | 563.71 | Project Management and Supervision - field installation time
2025-03-07 | PRJ-PAY-ARM-2510-20250307 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 8.76 | 678.91 | Engineering, BIM and Coordination - coordination and layout
2025-03-07 | PRJ-PAY-ARM-2510-20250307 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1023 | 8.6 | 722.15 | Field Installation Labor - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2510-20250314 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 10.73 | 761.87 | Engineering, BIM and Coordination - coordination and layout
2025-03-14 | PRJ-PAY-ARM-2510-20250314 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1021 | 8.98 | 695.71 | Field Installation Labor - supervision and planning
2025-03-14 | PRJ-PAY-ARM-2510-20250314 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 8.4 | 705.59 | Startup, Testing and Commissioning - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2510-20250321 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1019 | 10.13 | 719.56 | Field Installation Labor - supervision and planning
2025-03-21 | PRJ-PAY-ARM-2510-20250321 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 8.43 | 653.6 | Startup, Testing and Commissioning - startup and checkout
2025-03-21 | PRJ-PAY-ARM-2510-20250321 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 9.6 | 806 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2510-20250328 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 10.09 | 716.28 | Startup, Testing and Commissioning - startup and checkout
2025-03-28 | PRJ-PAY-ARM-2510-20250328 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 7.77 | 602.11 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-03-28 | PRJ-PAY-ARM-2510-20250328 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1038 | 8.09 | 679.65 | Controls Programming and Checkout - field installation time
2025-03-31 | PRJ-PAY-ARM-2510-20250331 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 7.05 | 500.6 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-03-31 | PRJ-PAY-ARM-2510-20250331 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1036 | 9.56 | 740.9 | Controls Programming and Checkout - field installation time
2025-03-31 | PRJ-PAY-ARM-2510-20250331 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1043 | 6.49 | 544.83 | Warranty and Punchlist - coordination and layout
2025-04-06 | AP-0005113 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2374 |  | 71.87 | 12936.11 | Plumbing Fixtures and Piping - fabricated material delivery
2025-04-06 | AP-0005115 | AP | ARM-2510 | 04-200 | Electrical and Controls Subcontract | V-2398 |  | 14640.88 | 14640.88 | Electrical and Controls Subcontract - insulation progress invoice
2025-04-06 | AP-0005116 | AP | ARM-2510 | 06-400 | Temporary Facilities and Protection | V-2410 |  | 4658.47 | 4658.47 | Temporary Facilities and Protection - permit and inspection fees
2025-04-07 | PRJ-PAY-ARM-2510-20250407 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 28.9 | 2052.08 | Engineering, BIM and Coordination - field installation time
2025-04-07 | PRJ-PAY-ARM-2510-20250407 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1016 | 18.74 | 1452.7 | Field Installation Labor - coordination and layout
2025-04-07 | PRJ-PAY-ARM-2510-20250407 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 17.34 | 1456.56 | Startup, Testing and Commissioning - supervision and planning
2025-04-13 | AP-0005114 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2388 |  | 68.63 | 12352.69 | Major HVAC Equipment - valves and piping lot
2025-04-14 | PRJ-PAY-ARM-2510-20250414 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1014 | 22.75 | 1615.21 | Field Installation Labor - coordination and layout
2025-04-14 | PRJ-PAY-ARM-2510-20250414 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 22.57 | 1749.53 | Startup, Testing and Commissioning - supervision and planning
2025-04-14 | PRJ-PAY-ARM-2510-20250414 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 19.44 | 1633.28 | Sheet Metal Fabrication Labor - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2510-20250421 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 25.95 | 1842.49 | Startup, Testing and Commissioning - supervision and planning
2025-04-21 | PRJ-PAY-ARM-2510-20250421 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 14.46 | 1120.57 | Sheet Metal Fabrication Labor - startup and checkout
2025-04-21 | PRJ-PAY-ARM-2510-20250421 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1034 | 19.28 | 1619.56 | Controls Programming and Checkout - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2510-20250428 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 19.14 | 1359.13 | Sheet Metal Fabrication Labor - startup and checkout
2025-04-28 | PRJ-PAY-ARM-2510-20250428 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1032 | 21.16 | 1639.72 | Controls Programming and Checkout - punchlist and closeout labor
2025-04-28 | PRJ-PAY-ARM-2510-20250428 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1039 | 13.07 | 1098.22 | Warranty and Punchlist - field installation time
2025-04-30 | PRJ-PAY-ARM-2510-20250430 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1030 | 16.66 | 1182.67 | Controls Programming and Checkout - punchlist and closeout labor
2025-04-30 | PRJ-PAY-ARM-2510-20250430 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1037 | 18.7 | 1449.34 | Warranty and Punchlist - field installation time
2025-04-30 | PRJ-PAY-ARM-2510-20250430 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 16.14 | 1355.76 | Closeout and O&M Documentation - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2510-20250507 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1009 | 42.64 | 3027.33 | Field Installation Labor - field installation time
2025-05-07 | PRJ-PAY-ARM-2510-20250507 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 39.94 | 3095.04 | Startup, Testing and Commissioning - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2510-20250507 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 29.52 | 2479.27 | Sheet Metal Fabrication Labor - supervision and planning
2025-05-09 | AP-0005117 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2424 |  | 77.2 | 13896.89 | Controls Panels and Devices - valves and piping lot
2025-05-09 | AP-0005120 | AP | ARM-2510 | 04-300 | Testing and Balancing Subcontract | V-2458 |  | 25636.75 | 25636.75 | Testing and Balancing Subcontract - testing and balancing services
2025-05-09 | AP-0005121 | AP | ARM-2510 | 05-100 | Equipment Rental and Rigging | V-2471 |  | 10031.78 | 10031.78 | Equipment Rental and Rigging - freight and expediting
2025-05-14 | PRJ-PAY-ARM-2510-20250514 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 30.99 | 2200.17 | Startup, Testing and Commissioning - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2510-20250514 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 43.4 | 3363.41 | Sheet Metal Fabrication Labor - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2510-20250514 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1030 | 27.66 | 2323.16 | Controls Programming and Checkout - startup and checkout
2025-05-16 | AP-0005118 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2438 |  | 68.52 | 12332.76 | Sheet Metal and Ductwork - ductwork release
2025-05-21 | PRJ-PAY-ARM-2510-20250521 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 33.06 | 2347.07 | Sheet Metal Fabrication Labor - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2510-20250521 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1028 | 29.14 | 2258.38 | Controls Programming and Checkout - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2510-20250521 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1035 | 29.11 | 2445.64 | Warranty and Punchlist - punchlist and closeout labor
2025-05-23 | AP-0005119 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2450 |  | 64.82 | 11668.16 | Controls Panels and Devices - jobsite material replenishment
2025-05-28 | PRJ-PAY-ARM-2510-20250528 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1026 | 41.7 | 2960.35 | Controls Programming and Checkout - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2510-20250528 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1033 | 24.65 | 1910.05 | Warranty and Punchlist - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2510-20250528 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 23.72 | 1992.58 | Closeout and O&M Documentation - field installation time
2025-05-31 | PRJ-PAY-ARM-2510-20250531 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1031 | 29.92 | 2124.6 | Warranty and Punchlist - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2510-20250531 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 35.21 | 2728.76 | Closeout and O&M Documentation - field installation time
2025-05-31 | PRJ-PAY-ARM-2510-20250531 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1045 | 31.45 | 2642 | Rework and Quality Correction - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2510-20250607 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 49.32 | 3501.62 | Startup, Testing and Commissioning - field installation time
2025-06-07 | PRJ-PAY-ARM-2510-20250607 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 37.1 | 2875.56 | Sheet Metal Fabrication Labor - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2510-20250607 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1026 | 34.71 | 2915.28 | Controls Programming and Checkout - supervision and planning
2025-06-09 | AP-0005125 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2526 |  | 73.06 | 13151.69 | Hydronic Piping and Valves - fabricated material delivery
2025-06-12 | AP-0005122 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2484 |  | 61.86 | 11134.99 | Insulation and Specialty Material - ductwork release
2025-06-12 | AP-0005126 | AP | ARM-2510 | 04-400 | Crane, Rigging and Specialty Trade | V-2533 |  | 28713.89 | 28713.89 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-06-12 | AP-0005127 | AP | ARM-2510 | 05-200 | Permits, Fees and Bonds | V-2025 |  | 10441.41 | 10441.41 | Permits, Fees and Bonds - small tools and field consumables
2025-06-14 | PRJ-PAY-ARM-2510-20250614 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 35.22 | 2500.52 | Sheet Metal Fabrication Labor - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2510-20250614 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1024 | 38.84 | 3009.81 | Controls Programming and Checkout - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2510-20250614 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1031 | 33.3 | 2797.53 | Warranty and Punchlist - startup and checkout
2025-06-19 | AP-0005123 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2498 |  | 77.72 | 13990.44 | Hydronic Piping and Valves - jobsite material replenishment
2025-06-21 | PRJ-PAY-ARM-2510-20250621 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1022 | 31.72 | 2252.44 | Controls Programming and Checkout - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2510-20250621 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1029 | 37.25 | 2886.81 | Warranty and Punchlist - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2510-20250621 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 35.08 | 2946.98 | Closeout and O&M Documentation - punchlist and closeout labor
2025-06-25 | AP-0005124 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2512 |  | 48.38 | 8709.24 | Insulation and Specialty Material - released equipment package
2025-06-28 | PRJ-PAY-ARM-2510-20250628 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1027 | 36.61 | 2599.13 | Warranty and Punchlist - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2510-20250628 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 43.17 | 3345.93 | Closeout and O&M Documentation - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2510-20250628 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1041 | 34.36 | 2886.27 | Rework and Quality Correction - field installation time
2025-06-30 | PRJ-PAY-ARM-2510-20250630 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 50.26 | 3568.65 | Closeout and O&M Documentation - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2510-20250630 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1039 | 43.05 | 3335.99 | Rework and Quality Correction - field installation time
2025-06-30 | PRJ-PAY-ARM-2510-20250630 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1046 | 32.1 | 2953.48 | Project Management and Supervision - coordination and layout
2025-07-05 | AP-0005130 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2243 |  | 98.74 | 17773.81 | Major HVAC Equipment - fabricated material delivery
2025-07-07 | PRJ-PAY-ARM-2510-20250707 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 39.11 | 2777.08 | Sheet Metal Fabrication Labor - field installation time
2025-07-07 | PRJ-PAY-ARM-2510-20250707 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1020 | 51.52 | 3992.8 | Controls Programming and Checkout - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2510-20250707 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1027 | 46.41 | 3898.55 | Warranty and Punchlist - supervision and planning
2025-07-12 | AP-0005131 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2262 |  | 80.62 | 14511.96 | Plumbing Fixtures and Piping - valves and piping lot
2025-07-14 | PRJ-PAY-ARM-2510-20250714 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1018 | 53.3 | 3784.03 | Controls Programming and Checkout - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2510-20250714 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1025 | 43.45 | 3367.16 | Warranty and Punchlist - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2510-20250714 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 38.48 | 3232.63 | Closeout and O&M Documentation - startup and checkout
2025-07-15 | AP-0005128 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2098 |  | 64.49 | 11607.78 | Major HVAC Equipment - jobsite material replenishment
2025-07-15 | AP-0005133 | AP | ARM-2510 | 04-100 | Insulation Subcontract | V-2284 |  | 21596.8 | 21596.8 | Insulation Subcontract - rigging and specialty support
2025-07-15 | AP-0005135 | AP | ARM-2510 | 05-300 | Freight and Expediting | V-2308 |  | 8136.94 | 8136.94 | Freight and Expediting - rental and logistics
2025-07-19 | AP-0005132 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2279 |  | 55.95 | 10071.84 | Major HVAC Equipment - ductwork release
2025-07-21 | PRJ-PAY-ARM-2510-20250721 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1023 | 67.71 | 4807.76 | Warranty and Punchlist - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2510-20250721 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 41.69 | 3231.27 | Closeout and O&M Documentation - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2510-20250721 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1037 | 39.3 | 3301.6 | Rework and Quality Correction - punchlist and closeout labor
2025-07-22 | AP-0005129 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2222 |  | 61.44 | 11058.45 | Plumbing Fixtures and Piping - released equipment package
2025-07-22 | AP-0005134 | AP | ARM-2510 | 04-400 | Crane, Rigging and Specialty Trade | V-2298 |  | 17759.74 | 17759.74 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-07-22 | AP-0005136 | AP | ARM-2510 | 05-100 | Equipment Rental and Rigging | V-2322 |  | 3841.13 | 3841.13 | Equipment Rental and Rigging - permit and inspection fees
2025-07-28 | PRJ-PAY-ARM-2510-20250728 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 48.76 | 3461.69 | Closeout and O&M Documentation - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2510-20250728 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1035 | 30.39 | 2354.96 | Rework and Quality Correction - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2510-20250728 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1042 | 41.5 | 3817.92 | Project Management and Supervision - field installation time
2025-07-28 | PRJ-PAY-ARM-2510-20250728 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 33.42 | 3024.6 | Engineering, BIM and Coordination - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2510-20250731 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1033 | 45.16 | 3206.69 | Rework and Quality Correction - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2510-20250731 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1040 | 35.69 | 3051.28 | Project Management and Supervision - field installation time
2025-07-31 | PRJ-PAY-ARM-2510-20250731 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 43.89 | 3686.51 | Engineering, BIM and Coordination - coordination and layout
2025-07-31 | PRJ-PAY-ARM-2510-20250731 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1080 | 35.17 | 3182.7 | Field Installation Labor - supervision and planning
2025-08-07 | PRJ-PAY-ARM-2510-20250807 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1013 | 63.8 | 4529.89 | Controls Programming and Checkout - field installation time
2025-08-07 | PRJ-PAY-ARM-2510-20250807 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1021 | 44.08 | 3416.4 | Warranty and Punchlist - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2510-20250807 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 36.64 | 3077.54 | Closeout and O&M Documentation - supervision and planning
2025-08-08 | AP-0005139 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2362 |  | 69.93 | 12586.89 | Sheet Metal and Ductwork - valves and piping lot
2025-08-14 | PRJ-PAY-ARM-2510-20250814 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1019 | 43.03 | 3055.23 | Warranty and Punchlist - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2510-20250814 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 59.71 | 4627.69 | Closeout and O&M Documentation - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2510-20250814 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1033 | 51.87 | 4356.7 | Rework and Quality Correction - startup and checkout
2025-08-15 | AP-0005140 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2376 |  | 55.88 | 10057.89 | Controls Panels and Devices - ductwork release
2025-08-18 | AP-0005137 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2334 |  | 84.42 | 15196 | Sheet Metal and Ductwork - released equipment package
2025-08-18 | AP-0005142 | AP | ARM-2510 | 04-200 | Electrical and Controls Subcontract | V-2395 |  | 27243.35 | 27243.35 | Electrical and Controls Subcontract - trade partner progress billing
2025-08-18 | AP-0005144 | AP | ARM-2510 | 05-400 | Small Tools and Consumables | V-2419 |  | 10156.97 | 10156.97 | Small Tools and Consumables - permit and inspection fees
2025-08-21 | PRJ-PAY-ARM-2510-20250821 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 45.28 | 3214.57 | Closeout and O&M Documentation - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2510-20250821 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1031 | 46.04 | 3567.81 | Rework and Quality Correction - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2510-20250821 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1038 | 31.94 | 2938.49 | Project Management and Supervision - punchlist and closeout labor
2025-08-21 | PRJ-PAY-ARM-2510-20250821 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1045 | 41.09 | 3718.55 | Engineering, BIM and Coordination - field installation time
2025-08-22 | AP-0005141 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2389 |  | 56.46 | 10163.11 | Sheet Metal and Ductwork - jobsite material replenishment
2025-08-25 | AP-0005138 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2348 |  | 86.16 | 15508.63 | Controls Panels and Devices - fabricated material delivery
2025-08-25 | AP-0005143 | AP | ARM-2510 | 04-100 | Insulation Subcontract | V-2408 |  | 13852.98 | 13852.98 | Insulation Subcontract - insulation progress invoice
2025-08-25 | AP-0005145 | AP | ARM-2510 | 05-200 | Permits, Fees and Bonds | V-2433 |  | 6655.16 | 6655.16 | Permits, Fees and Bonds - freight and expediting
2025-08-28 | PRJ-PAY-ARM-2510-20250828 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1029 | 54.87 | 3896.03 | Rework and Quality Correction - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2510-20250828 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1036 | 34.31 | 2933.74 | Project Management and Supervision - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2510-20250828 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 33.23 | 2791.23 | Engineering, BIM and Coordination - field installation time
2025-08-28 | PRJ-PAY-ARM-2510-20250828 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1050 | 47.68 | 4315.28 | Field Installation Labor - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2510-20250831 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1034 | 49.26 | 3891.69 | Project Management and Supervision - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2510-20250831 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 36.88 | 2858.1 | Engineering, BIM and Coordination - field installation time
2025-08-31 | PRJ-PAY-ARM-2510-20250831 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1048 | 43.3 | 3637.08 | Field Installation Labor - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2510-20250831 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 29.69 | 2686.5 | Startup, Testing and Commissioning - supervision and planning
2025-09-04 | AP-0005147 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2457 |  | 71.34 | 12840.56 | Insulation and Specialty Material - valves and piping lot
2025-09-04 | AP-0005153 | AP | ARM-2510 | 04-200 | Electrical and Controls Subcontract | V-2529 |  | 28314.15 | 28314.15 | Electrical and Controls Subcontract - testing and balancing services
2025-09-04 | AP-0005155 | AP | ARM-2510 | 05-300 | Freight and Expediting | V-2056 |  | 11078.47 | 11078.47 | Freight and Expediting - small tools and field consumables
2025-09-07 | PRJ-PAY-ARM-2510-20250907 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1014 | 52.62 | 3736.22 | Warranty and Punchlist - field installation time
2025-09-07 | PRJ-PAY-ARM-2510-20250907 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 50.86 | 3941.51 | Closeout and O&M Documentation - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2510-20250907 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1029 | 30.55 | 2566.58 | Rework and Quality Correction - supervision and planning
2025-09-07 | PRJ-PAY-ARM-2510-20250907 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1036 | 32.82 | 3233.02 | Project Management and Supervision - startup and checkout
2025-09-08 | AP-0005151 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2512 |  | 57.8 | 10403.8 | Insulation and Specialty Material - fabricated material delivery
2025-09-11 | AP-0005148 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2471 |  | 62.24 | 11202.67 | Hydronic Piping and Valves - ductwork release
2025-09-14 | PRJ-PAY-ARM-2510-20250914 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 62.7 | 4451.81 | Closeout and O&M Documentation - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2510-20250914 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1027 | 44.37 | 3438.52 | Rework and Quality Correction - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2510-20250914 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1034 | 39.94 | 3674.49 | Project Management and Supervision - startup and checkout
2025-09-14 | PRJ-PAY-ARM-2510-20250914 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 38.45 | 3479.48 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-09-18 | AP-0005149 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2484 |  | 70.05 | 12608.37 | Insulation and Specialty Material - jobsite material replenishment
2025-09-21 | AP-0005146 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2443 |  | 103.46 | 18623.59 | Hydronic Piping and Valves - fabricated material delivery
2025-09-21 | AP-0005152 | AP | ARM-2510 | 04-300 | Testing and Balancing Subcontract | V-2515 |  | 20250.48 | 20250.48 | Testing and Balancing Subcontract - insulation progress invoice
2025-09-21 | AP-0005154 | AP | ARM-2510 | 06-400 | Temporary Facilities and Protection | V-2014 |  | 5813.58 | 5813.58 | Temporary Facilities and Protection - freight and expediting
2025-09-21 | PRJ-PAY-ARM-2510-20250921 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1025 | 41.58 | 2952.42 | Rework and Quality Correction - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2510-20250921 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1032 | 55.53 | 4747.64 | Project Management and Supervision - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2510-20250921 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 51.77 | 4348.81 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-09-21 | PRJ-PAY-ARM-2510-20250921 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1046 | 39.24 | 3551.61 | Field Installation Labor - field installation time
2025-09-25 | AP-0005150 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2498 |  | 57.42 | 10335.21 | Hydronic Piping and Valves - released equipment package
2025-09-28 | PRJ-PAY-ARM-2510-20250928 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1030 | 41.83 | 3304.34 | Project Management and Supervision - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2510-20250928 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 55.88 | 4330.66 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2510-20250928 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1044 | 42.14 | 3539.9 | Field Installation Labor - field installation time
2025-09-28 | PRJ-PAY-ARM-2510-20250928 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 38.23 | 3459.64 | Startup, Testing and Commissioning - coordination and layout
2025-09-30 | PRJ-PAY-ARM-2510-20250930 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 35.27 | 2504.47 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2510-20250930 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1042 | 44.41 | 3441.54 | Field Installation Labor - field installation time
2025-09-30 | PRJ-PAY-ARM-2510-20250930 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 40.56 | 3406.95 | Startup, Testing and Commissioning - coordination and layout
2025-09-30 | PRJ-PAY-ARM-2510-20250930 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 40.68 | 3681.58 | Sheet Metal Fabrication Labor - supervision and planning
2025-10-04 | AP-0005160 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2286 |  | 75.14 | 13525.92 | Plumbing Fixtures and Piping - fabricated material delivery
2025-10-07 | AP-0005157 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2232 |  | 43.53 | 7835.61 | Major HVAC Equipment - ductwork release
2025-10-07 | AP-0005164 | AP | ARM-2510 | 04-300 | Testing and Balancing Subcontract | V-2329 |  | 28271.32 | 28271.32 | Testing and Balancing Subcontract - electrical coordination scope
2025-10-07 | AP-0005166 | AP | ARM-2510 | 05-400 | Small Tools and Consumables | V-2353 |  | 9063.97 | 9063.97 | Small Tools and Consumables - rental and logistics
2025-10-07 | PRJ-PAY-ARM-2510-20251007 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 43.87 | 3114.87 | Closeout and O&M Documentation - field installation time
2025-10-07 | PRJ-PAY-ARM-2510-20251007 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1023 | 42.48 | 3291.86 | Rework and Quality Correction - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2510-20251007 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1030 | 32.37 | 2977.66 | Project Management and Supervision - supervision and planning
2025-10-07 | PRJ-PAY-ARM-2510-20251007 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 39.91 | 3611.63 | Engineering, BIM and Coordination - startup and checkout
2025-10-07 | PRJ-PAY-ARM-2510-20251007 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1044 | 36.31 | 3521.9 | Field Installation Labor - punchlist and closeout labor
2025-10-11 | AP-0005161 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2300 |  | 93.35 | 16803.47 | Major HVAC Equipment - valves and piping lot
2025-10-14 | AP-0005158 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2253 |  | 77.16 | 13888.78 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-10-14 | PRJ-PAY-ARM-2510-20251014 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1021 | 53.96 | 3831.22 | Rework and Quality Correction - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2510-20251014 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1028 | 44.75 | 3826.13 | Project Management and Supervision - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2510-20251014 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 34.64 | 2909.56 | Engineering, BIM and Coordination - startup and checkout
2025-10-14 | PRJ-PAY-ARM-2510-20251014 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1042 | 32.96 | 2983.14 | Field Installation Labor - punchlist and closeout labor
2025-10-14 | PRJ-PAY-ARM-2510-20251014 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 36.89 | 3578.54 | Startup, Testing and Commissioning - field installation time
2025-10-18 | AP-0005162 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2313 |  | 53.66 | 9659.48 | Plumbing Fixtures and Piping - ductwork release
2025-10-21 | AP-0005159 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2272 |  | 62.56 | 11260.49 | Major HVAC Equipment - released equipment package
2025-10-21 | PRJ-PAY-ARM-2510-20251021 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1026 | 51.46 | 4065.02 | Project Management and Supervision - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2510-20251021 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 40.98 | 3176.16 | Engineering, BIM and Coordination - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2510-20251021 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1040 | 61.57 | 5171.68 | Field Installation Labor - punchlist and closeout labor
2025-10-21 | PRJ-PAY-ARM-2510-20251021 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1047 | 40.39 | 3655.16 | Startup, Testing and Commissioning - field installation time
2025-10-24 | AP-0005156 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2210 |  | 75.8 | 13643.21 | Plumbing Fixtures and Piping - valves and piping lot
2025-10-24 | AP-0005163 | AP | ARM-2510 | 04-400 | Crane, Rigging and Specialty Trade | V-2315 |  | 21875.34 | 21875.34 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-10-24 | AP-0005165 | AP | ARM-2510 | 05-100 | Equipment Rental and Rigging | V-2339 |  | 6891.79 | 6891.79 | Equipment Rental and Rigging - small tools and field consumables
2025-10-28 | PRJ-PAY-ARM-2510-20251028 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 48.72 | 3459.45 | Engineering, BIM and Coordination - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2510-20251028 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1038 | 45.25 | 3507.03 | Field Installation Labor - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2510-20251028 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 40.45 | 3397.79 | Startup, Testing and Commissioning - field installation time
2025-10-28 | PRJ-PAY-ARM-2510-20251028 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 43.61 | 3947.04 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-31 | PRJ-PAY-ARM-2510-20251031 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1036 | 56.95 | 4043.72 | Field Installation Labor - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2510-20251031 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 39.8 | 3084.86 | Startup, Testing and Commissioning - field installation time
2025-10-31 | PRJ-PAY-ARM-2510-20251031 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 34.75 | 2919.17 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-31 | PRJ-PAY-ARM-2510-20251031 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1083 | 37.85 | 3425.8 | Controls Programming and Checkout - supervision and planning
2025-11-03 | AP-0005167 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2365 |  | 48.49 | 8728.11 | Controls Panels and Devices - ductwork release
2025-11-03 | AP-0005173 | AP | ARM-2510 | 04-100 | Insulation Subcontract | V-2438 |  | 28591.23 | 28591.23 | Insulation Subcontract - electrical coordination scope
2025-11-03 | AP-0005175 | AP | ARM-2510 | 05-200 | Permits, Fees and Bonds | V-2460 |  | 5586.88 | 5586.88 | Permits, Fees and Bonds - rental and logistics
2025-11-07 | AP-0005171 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2421 |  | 75.73 | 13631 | Controls Panels and Devices - valves and piping lot
2025-11-07 | PRJ-PAY-ARM-2510-20251107 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1016 | 62.99 | 4472.03 | Rework and Quality Correction - field installation time
2025-11-07 | PRJ-PAY-ARM-2510-20251107 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1024 | 52.27 | 4468.82 | Project Management and Supervision - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2510-20251107 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 38.57 | 3240.07 | Engineering, BIM and Coordination - supervision and planning
2025-11-07 | PRJ-PAY-ARM-2510-20251107 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1038 | 42.97 | 3888.76 | Field Installation Labor - startup and checkout
2025-11-10 | AP-0005168 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2379 |  | 66.28 | 11930.49 | Sheet Metal and Ductwork - jobsite material replenishment
2025-11-10 | AP-0005174 | AP | ARM-2510 | 04-400 | Crane, Rigging and Specialty Trade | V-2450 |  | 19202.07 | 19202.07 | Crane, Rigging and Specialty Trade - rigging and specialty support
2025-11-10 | AP-0005176 | AP | ARM-2510 | 06-400 | Temporary Facilities and Protection | V-2474 |  | 6043.91 | 6043.91 | Temporary Facilities and Protection - permit and inspection fees
2025-11-14 | AP-0005172 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2434 |  | 69.03 | 12425.51 | Sheet Metal and Ductwork - ductwork release
2025-11-14 | PRJ-PAY-ARM-2510-20251114 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1022 | 38.51 | 3042.23 | Project Management and Supervision - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2510-20251114 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 39.29 | 3045.27 | Engineering, BIM and Coordination - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2510-20251114 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1036 | 59.09 | 4963.81 | Field Installation Labor - startup and checkout
2025-11-14 | PRJ-PAY-ARM-2510-20251114 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 44.46 | 4023.38 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-11-17 | AP-0005169 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2393 |  | 76.09 | 13697.09 | Controls Panels and Devices - released equipment package
2025-11-17 | AP-0005177 | AP | ARM-2510 | 05-300 | Freight and Expediting | V-2488 |  | 7070.93 | 7070.93 | Freight and Expediting - freight and expediting
2025-11-21 | PRJ-PAY-ARM-2510-20251121 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 39.56 | 2808.86 | Engineering, BIM and Coordination - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2510-20251121 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1034 | 48.44 | 3754.37 | Field Installation Labor - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2510-20251121 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 49.1 | 4124.1 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-11-21 | PRJ-PAY-ARM-2510-20251121 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1048 | 30.27 | 2739.24 | Sheet Metal Fabrication Labor - field installation time
2025-11-24 | AP-0005170 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2407 |  | 56.88 | 10238.76 | Sheet Metal and Ductwork - fabricated material delivery
2025-11-28 | PRJ-PAY-ARM-2510-20251128 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1032 | 44.9 | 3187.93 | Field Installation Labor - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2510-20251128 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 44.68 | 3462.88 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2510-20251128 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 32.83 | 2758.06 | Sheet Metal Fabrication Labor - field installation time
2025-11-28 | PRJ-PAY-ARM-2510-20251128 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1053 | 35.71 | 3231.74 | Controls Programming and Checkout - coordination and layout
2025-11-30 | PRJ-PAY-ARM-2510-20251130 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 54.56 | 3873.68 | Startup, Testing and Commissioning - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2510-20251130 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 34.01 | 2635.81 | Sheet Metal Fabrication Labor - field installation time
2025-11-30 | PRJ-PAY-ARM-2510-20251130 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1051 | 42.6 | 3578.07 | Controls Programming and Checkout - coordination and layout
2025-11-30 | PRJ-PAY-ARM-2510-20251130 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1084 | 37.04 | 3351.85 | Warranty and Punchlist - supervision and planning
2025-12-03 | AP-0005181 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2014 |  | 69.58 | 12524.4 | Hydronic Piping and Valves - valves and piping lot
2025-12-06 | AP-0005178 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2498 |  | 62.91 | 11324.44 | Insulation and Specialty Material - jobsite material replenishment
2025-12-06 | AP-0005184 | AP | ARM-2510 | 04-200 | Electrical and Controls Subcontract | V-2220 |  | 22613.47 | 22613.47 | Electrical and Controls Subcontract - rigging and specialty support
2025-12-06 | AP-0005186 | AP | ARM-2510 | 05-300 | Freight and Expediting | V-2255 |  | 6176.62 | 6176.62 | Freight and Expediting - permit and inspection fees
2025-12-07 | PRJ-PAY-ARM-2510-20251207 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1018 | 53.63 | 4236.99 | Project Management and Supervision - field installation time
2025-12-07 | PRJ-PAY-ARM-2510-20251207 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 47.59 | 3688.28 | Engineering, BIM and Coordination - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2510-20251207 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1032 | 44.84 | 3766.75 | Field Installation Labor - supervision and planning
2025-12-07 | PRJ-PAY-ARM-2510-20251207 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 34.47 | 3119.12 | Startup, Testing and Commissioning - startup and checkout
2025-12-10 | AP-0005182 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2056 |  | 77.9 | 14022.16 | Insulation and Specialty Material - ductwork release
2025-12-13 | AP-0005179 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2512 |  | 76.19 | 13714.56 | Hydronic Piping and Valves - released equipment package
2025-12-13 | AP-0005185 | AP | ARM-2510 | 04-100 | Insulation Subcontract | V-2241 |  | 21678.89 | 21678.89 | Insulation Subcontract - trade partner progress billing
2025-12-13 | AP-0005187 | AP | ARM-2510 | 05-100 | Equipment Rental and Rigging | V-2274 |  | 9929.69 | 9929.69 | Equipment Rental and Rigging - freight and expediting
2025-12-14 | PRJ-PAY-ARM-2510-20251214 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 57.3 | 4068.09 | Engineering, BIM and Coordination - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2510-20251214 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1030 | 32.44 | 2514.24 | Field Installation Labor - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2510-20251214 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 46.15 | 3876.59 | Startup, Testing and Commissioning - startup and checkout
2025-12-14 | PRJ-PAY-ARM-2510-20251214 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 30.2 | 2732.92 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-12-17 | AP-0005183 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2213 |  | 60.74 | 10932.46 | Hydronic Piping and Valves - jobsite material replenishment
2025-12-20 | AP-0005180 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2526 |  | 55.34 | 9960.38 | Insulation and Specialty Material - fabricated material delivery
2025-12-21 | PRJ-PAY-ARM-2510-20251221 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1028 | 43.73 | 3104.48 | Field Installation Labor - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2510-20251221 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 58.61 | 4542.49 | Startup, Testing and Commissioning - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2510-20251221 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 56.82 | 4772.65 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2510-20251228 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 41.91 | 2975.92 | Startup, Testing and Commissioning - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2510-20251228 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 46.59 | 3610.63 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2510-20251228 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1047 | 40.92 | 3437.32 | Controls Programming and Checkout - field installation time
2025-12-28 | PRJ-PAY-ARM-2510-20251228 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1080 | 35.14 | 3180.58 | Warranty and Punchlist - coordination and layout
2025-12-31 | PRJ-PAY-ARM-2510-20251231 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 56.07 | 3981.04 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2510-20251231 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1045 | 45.2 | 3503.36 | Controls Programming and Checkout - field installation time
2025-12-31 | PRJ-PAY-ARM-2510-20251231 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1052 | 37.74 | 3169.87 | Warranty and Punchlist - coordination and layout
2025-12-31 | PRJ-PAY-ARM-2510-20251231 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1085 | 46.08 | 4170.51 | Closeout and O&M Documentation - supervision and planning
2026-01-06 | AP-0005191 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2327 |  | 78.57 | 14142.29 | Plumbing Fixtures and Piping - ductwork release
2026-01-07 | PRJ-PAY-ARM-2510-20260107 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 64.15 | 4554.73 | Engineering, BIM and Coordination - field installation time
2026-01-07 | PRJ-PAY-ARM-2510-20260107 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1026 | 35.62 | 2760.77 | Field Installation Labor - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2510-20260107 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 39.15 | 3288.48 | Startup, Testing and Commissioning - supervision and planning
2026-01-09 | AP-0005188 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2286 |  | 84.47 | 15203.93 | Major HVAC Equipment - released equipment package
2026-01-09 | AP-0005193 | AP | ARM-2510 | 04-300 | Testing and Balancing Subcontract | V-2346 |  | 24777.97 | 24777.97 | Testing and Balancing Subcontract - trade partner progress billing
2026-01-09 | AP-0005195 | AP | ARM-2510 | 05-400 | Small Tools and Consumables | V-2370 |  | 3922.03 | 3922.03 | Small Tools and Consumables - freight and expediting
2026-01-13 | AP-0005192 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2341 |  | 60.53 | 10895.84 | Major HVAC Equipment - jobsite material replenishment
2026-01-14 | PRJ-PAY-ARM-2510-20260114 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1024 | 55.22 | 3920.47 | Field Installation Labor - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2510-20260114 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 35.4 | 2743.81 | Startup, Testing and Commissioning - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2510-20260114 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 39.51 | 3318.97 | Sheet Metal Fabrication Labor - startup and checkout
2026-01-16 | AP-0005189 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2300 |  | 58.9 | 10601.62 | Plumbing Fixtures and Piping - fabricated material delivery
2026-01-16 | AP-0005194 | AP | ARM-2510 | 04-200 | Electrical and Controls Subcontract | V-2360 |  | 12976.58 | 12976.58 | Electrical and Controls Subcontract - insulation progress invoice
2026-01-16 | AP-0005196 | AP | ARM-2510 | 05-200 | Permits, Fees and Bonds | V-2384 |  | 7568.48 | 7568.48 | Permits, Fees and Bonds - small tools and field consumables
2026-01-21 | PRJ-PAY-ARM-2510-20260121 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 47.17 | 3348.91 | Startup, Testing and Commissioning - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2510-20260121 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 48.7 | 3774.18 | Sheet Metal Fabrication Labor - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2510-20260121 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1043 | 41.56 | 3491.03 | Controls Programming and Checkout - punchlist and closeout labor
2026-01-23 | AP-0005190 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2313 |  | 64.07 | 11533.4 | Major HVAC Equipment - valves and piping lot
2026-01-28 | PRJ-PAY-ARM-2510-20260128 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 60.22 | 4275.72 | Sheet Metal Fabrication Labor - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2510-20260128 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1041 | 55.32 | 4287.28 | Controls Programming and Checkout - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2510-20260128 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1048 | 39.92 | 3353.58 | Warranty and Punchlist - field installation time
2026-01-31 | PRJ-PAY-ARM-2510-20260131 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1039 | 39.11 | 2776.82 | Controls Programming and Checkout - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2510-20260131 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1046 | 52.18 | 4043.61 | Warranty and Punchlist - field installation time
2026-01-31 | PRJ-PAY-ARM-2510-20260131 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 32.84 | 2758.81 | Closeout and O&M Documentation - coordination and layout
2026-01-31 | PRJ-PAY-ARM-2510-20260131 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1086 | 34.41 | 3113.9 | Rework and Quality Correction - supervision and planning
2026-02-07 | PRJ-PAY-ARM-2510-20260207 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1020 | 34.06 | 2418.51 | Field Installation Labor - field installation time
2026-02-07 | PRJ-PAY-ARM-2510-20260207 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 43.8 | 3394.87 | Startup, Testing and Commissioning - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2510-20260207 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 46.33 | 3892.04 | Sheet Metal Fabrication Labor - supervision and planning
2026-02-07 | PRJ-PAY-ARM-2510-20260207 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1041 | 43.87 | 3969.83 | Controls Programming and Checkout - startup and checkout
2026-02-09 | AP-0005200 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2438 |  | 82.22 | 14798.75 | Controls Panels and Devices - jobsite material replenishment
2026-02-12 | AP-0005197 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2396 |  | 64.42 | 11594.78 | Sheet Metal and Ductwork - fabricated material delivery
2026-02-12 | AP-0005202 | AP | ARM-2510 | 04-400 | Crane, Rigging and Specialty Trade | V-2455 |  | 23975.07 | 23975.07 | Crane, Rigging and Specialty Trade - insulation progress invoice
2026-02-12 | AP-0005204 | AP | ARM-2510 | 06-400 | Temporary Facilities and Protection | V-2479 |  | 7235.2 | 7235.2 | Temporary Facilities and Protection - small tools and field consumables
2026-02-14 | PRJ-PAY-ARM-2510-20260214 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 48.3 | 3429.57 | Startup, Testing and Commissioning - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2510-20260214 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 38.26 | 2965.34 | Sheet Metal Fabrication Labor - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2510-20260214 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1039 | 53.98 | 4534.42 | Controls Programming and Checkout - startup and checkout
2026-02-14 | PRJ-PAY-ARM-2510-20260214 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1046 | 39.89 | 3610.1 | Warranty and Punchlist - punchlist and closeout labor
2026-02-16 | AP-0005201 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2450 |  | 91.54 | 16476.83 | Sheet Metal and Ductwork - released equipment package
2026-02-19 | AP-0005198 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2410 |  | 48.66 | 8758.58 | Controls Panels and Devices - valves and piping lot
2026-02-19 | AP-0005203 | AP | ARM-2510 | 04-300 | Testing and Balancing Subcontract | V-2469 |  | 16094.42 | 16094.42 | Testing and Balancing Subcontract - testing and balancing services
2026-02-19 | AP-0005205 | AP | ARM-2510 | 05-300 | Freight and Expediting | V-2493 |  | 9156.86 | 9156.86 | Freight and Expediting - rental and logistics
2026-02-21 | PRJ-PAY-ARM-2510-20260221 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 39.83 | 2827.58 | Sheet Metal Fabrication Labor - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2510-20260221 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1037 | 50.52 | 3915.58 | Controls Programming and Checkout - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2510-20260221 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1044 | 41.95 | 3523.59 | Warranty and Punchlist - punchlist and closeout labor
2026-02-21 | PRJ-PAY-ARM-2510-20260221 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 37.12 | 3359.14 | Closeout and O&M Documentation - field installation time
2026-02-21 | PRJ-PAY-ARM-2510-20260221 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1084 | 27.81 | 2697.67 | Rework and Quality Correction - coordination and layout
2026-02-25 | AP-0005199 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2424 |  | 57.2 | 10296.63 | Sheet Metal and Ductwork - ductwork release
2026-02-28 | PRJ-PAY-ARM-2510-20260228 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1035 | 39.1 | 2776.44 | Controls Programming and Checkout - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2510-20260228 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1042 | 55.77 | 4321.8 | Warranty and Punchlist - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2510-20260228 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 51.49 | 4325.5 | Closeout and O&M Documentation - field installation time
2026-02-28 | PRJ-PAY-ARM-2510-20260228 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1082 | 28.14 | 2546.55 | Rework and Quality Correction - coordination and layout
2026-02-28 | PRJ-PAY-ARM-2510-20260228 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1089 | 32.54 | 3417.04 | Project Management and Supervision - supervision and planning
2026-03-05 | AP-0005208 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2533 |  | 68.48 | 12327.15 | Hydronic Piping and Valves - jobsite material replenishment
2026-03-07 | PRJ-PAY-ARM-2510-20260307 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 57.06 | 4051.07 | Startup, Testing and Commissioning - field installation time
2026-03-07 | PRJ-PAY-ARM-2510-20260307 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 51.49 | 3990.67 | Sheet Metal Fabrication Labor - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2510-20260307 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1035 | 44.96 | 3777 | Controls Programming and Checkout - supervision and planning
2026-03-12 | AP-0005209 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2029 |  | 63.28 | 11389.76 | Insulation and Specialty Material - released equipment package
2026-03-14 | PRJ-PAY-ARM-2510-20260314 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 49.33 | 3502.48 | Sheet Metal Fabrication Labor - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2510-20260314 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1033 | 33.58 | 2602.69 | Controls Programming and Checkout - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2510-20260314 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1040 | 47.72 | 4008.88 | Warranty and Punchlist - startup and checkout
2026-03-14 | PRJ-PAY-ARM-2510-20260314 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 34.86 | 3154.96 | Closeout and O&M Documentation - punchlist and closeout labor
2026-03-15 | AP-0005206 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2505 |  | 49.36 | 8884.81 | Hydronic Piping and Valves - valves and piping lot
2026-03-15 | AP-0005212 | AP | ARM-2510 | 04-100 | Insulation Subcontract | V-2231 |  | 28258.6 | 28258.6 | Insulation Subcontract - testing and balancing services
2026-03-15 | AP-0005214 | AP | ARM-2510 | 05-100 | Equipment Rental and Rigging | V-2265 |  | 9634.7 | 9634.7 | Equipment Rental and Rigging - rental and logistics
2026-03-19 | AP-0005210 | AP | ARM-2510 | 02-310 | Hydronic Piping and Valves | V-2201 |  | 73.54 | 13236.88 | Hydronic Piping and Valves - fabricated material delivery
2026-03-21 | PRJ-PAY-ARM-2510-20260321 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1031 | 53.94 | 3829.55 | Controls Programming and Checkout - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2510-20260321 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1038 | 45.1 | 3495.05 | Warranty and Punchlist - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2510-20260321 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 46.95 | 3943.99 | Closeout and O&M Documentation - punchlist and closeout labor
2026-03-21 | PRJ-PAY-ARM-2510-20260321 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1052 | 31.66 | 2865.13 | Rework and Quality Correction - field installation time
2026-03-22 | AP-0005207 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2519 |  | 79.59 | 14326.11 | Insulation and Specialty Material - ductwork release
2026-03-22 | AP-0005213 | AP | ARM-2510 | 04-400 | Crane, Rigging and Specialty Trade | V-2250 |  | 15735.66 | 15735.66 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-03-22 | AP-0005215 | AP | ARM-2510 | 05-400 | Small Tools and Consumables | V-2281 |  | 5667.64 | 5667.64 | Small Tools and Consumables - permit and inspection fees
2026-03-25 | AP-0005211 | AP | ARM-2510 | 02-610 | Insulation and Specialty Material | V-2225 |  | 48.31 | 8695.87 | Insulation and Specialty Material - valves and piping lot
2026-03-28 | PRJ-PAY-ARM-2510-20260328 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1036 | 37.34 | 2650.96 | Warranty and Punchlist - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2510-20260328 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 52.3 | 4053.59 | Closeout and O&M Documentation - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2510-20260328 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1050 | 32.52 | 2731.94 | Rework and Quality Correction - field installation time
2026-03-28 | PRJ-PAY-ARM-2510-20260328 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1083 | 42.45 | 4181.35 | Project Management and Supervision - coordination and layout
2026-03-31 | PRJ-PAY-ARM-2510-20260331 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 54.26 | 3852.14 | Closeout and O&M Documentation - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2510-20260331 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1048 | 48.35 | 3747.33 | Rework and Quality Correction - field installation time
2026-03-31 | PRJ-PAY-ARM-2510-20260331 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1081 | 49.96 | 4596.21 | Project Management and Supervision - coordination and layout
2026-04-05 | AP-0005221 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2362 |  | 83.79 | 15081.5 | Major HVAC Equipment - ductwork release
2026-04-07 | PRJ-PAY-ARM-2510-20260407 | PAY | ARM-2510 | 03-300 | Sheet Metal Fabrication Labor |  | E-1022 | 66.39 | 4713.72 | Sheet Metal Fabrication Labor - field installation time
2026-04-07 | PRJ-PAY-ARM-2510-20260407 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1029 | 59.44 | 4606.76 | Controls Programming and Checkout - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2510-20260407 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1036 | 34.39 | 2888.76 | Warranty and Punchlist - supervision and planning
2026-04-07 | PRJ-PAY-ARM-2510-20260407 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 32.92 | 2979.37 | Closeout and O&M Documentation - startup and checkout
2026-04-08 | AP-0005218 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2320 |  | 63.78 | 11479.6 | Plumbing Fixtures and Piping - released equipment package
2026-04-12 | AP-0005222 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2376 |  | 54.24 | 9763.36 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-04-14 | PRJ-PAY-ARM-2510-20260414 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1027 | 72.57 | 5152.28 | Controls Programming and Checkout - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2510-20260414 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1034 | 44.32 | 3434.62 | Warranty and Punchlist - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2510-20260414 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 42.07 | 3534.2 | Closeout and O&M Documentation - startup and checkout
2026-04-14 | PRJ-PAY-ARM-2510-20260414 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1048 | 44.83 | 4057.31 | Rework and Quality Correction - punchlist and closeout labor
2026-04-15 | AP-0005219 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2334 |  | 55.69 | 10023.67 | Major HVAC Equipment - fabricated material delivery
2026-04-18 | AP-0005216 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2293 |  | 58.54 | 10536.65 | Plumbing Fixtures and Piping - ductwork release
2026-04-18 | AP-0005223 | AP | ARM-2510 | 04-200 | Electrical and Controls Subcontract | V-2377 |  | 17675.94 | 17675.94 | Electrical and Controls Subcontract - electrical coordination scope
2026-04-18 | AP-0005225 | AP | ARM-2510 | 05-200 | Permits, Fees and Bonds | V-2402 |  | 5696.71 | 5696.71 | Permits, Fees and Bonds - permit and inspection fees
2026-04-21 | PRJ-PAY-ARM-2510-20260421 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1032 | 63.43 | 4503.5 | Warranty and Punchlist - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2510-20260421 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1039 | 48.08 | 3725.92 | Closeout and O&M Documentation - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2510-20260421 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1046 | 50.06 | 4205.26 | Rework and Quality Correction - punchlist and closeout labor
2026-04-21 | PRJ-PAY-ARM-2510-20260421 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1053 | 32.01 | 3153.22 | Project Management and Supervision - field installation time
2026-04-22 | AP-0005220 | AP | ARM-2510 | 02-410 | Plumbing Fixtures and Piping | V-2348 |  | 50.35 | 9063.36 | Plumbing Fixtures and Piping - valves and piping lot
2026-04-25 | AP-0005217 | AP | ARM-2510 | 02-110 | Major HVAC Equipment | V-2307 |  | 91.28 | 16429.51 | Major HVAC Equipment - jobsite material replenishment
2026-04-25 | AP-0005224 | AP | ARM-2510 | 04-100 | Insulation Subcontract | V-2391 |  | 30016.38 | 30016.38 | Insulation Subcontract - rigging and specialty support
2026-04-25 | AP-0005226 | AP | ARM-2510 | 06-400 | Temporary Facilities and Protection | V-2415 |  | 9478.12 | 9478.12 | Temporary Facilities and Protection - freight and expediting
2026-04-28 | PRJ-PAY-ARM-2510-20260428 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 39.82 | 2827.28 | Closeout and O&M Documentation - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2510-20260428 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1044 | 46.66 | 3616.11 | Rework and Quality Correction - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2510-20260428 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1051 | 45.52 | 4187.71 | Project Management and Supervision - field installation time
2026-04-28 | PRJ-PAY-ARM-2510-20260428 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1084 | 36.78 | 3328.9 | Engineering, BIM and Coordination - coordination and layout
2026-04-30 | PRJ-PAY-ARM-2510-20260430 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1042 | 43.65 | 3099.43 | Rework and Quality Correction - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2510-20260430 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1049 | 37.74 | 3226.74 | Project Management and Supervision - field installation time
2026-04-30 | PRJ-PAY-ARM-2510-20260430 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 46.27 | 3886.54 | Engineering, BIM and Coordination - coordination and layout
2026-04-30 | PRJ-PAY-ARM-2510-20260430 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1089 | 28.49 | 2578.69 | Field Installation Labor - supervision and planning
2026-05-04 | AP-0005228 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2440 |  | 93.3 | 16794.24 | Sheet Metal and Ductwork - released equipment package
2026-05-04 | AP-0005235 | AP | ARM-2510 | 04-200 | Electrical and Controls Subcontract | V-2524 |  | 30354.27 | 30354.27 | Electrical and Controls Subcontract - trade partner progress billing
2026-05-04 | AP-0005237 | AP | ARM-2510 | 05-100 | Equipment Rental and Rigging | V-2033 |  | 6964.79 | 6964.79 | Equipment Rental and Rigging - small tools and field consumables
2026-05-07 | PRJ-PAY-ARM-2510-20260507 | PAY | ARM-2510 | 03-400 | Controls Programming and Checkout |  | E-1023 | 54.19 | 3847.59 | Controls Programming and Checkout - field installation time
2026-05-07 | PRJ-PAY-ARM-2510-20260507 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1030 | 40.81 | 3162.81 | Warranty and Punchlist - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2510-20260507 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1037 | 40.1 | 3368.12 | Closeout and O&M Documentation - supervision and planning
2026-05-07 | PRJ-PAY-ARM-2510-20260507 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1044 | 35.49 | 3212.1 | Rework and Quality Correction - startup and checkout
2026-05-07 | PRJ-PAY-ARM-2510-20260507 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1051 | 49.43 | 5189.73 | Project Management and Supervision - punchlist and closeout labor
2026-05-08 | AP-0005232 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2495 |  | 43.28 | 7790.26 | Sheet Metal and Ductwork - jobsite material replenishment
2026-05-11 | AP-0005229 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2453 |  | 75.31 | 13556.6 | Controls Panels and Devices - fabricated material delivery
2026-05-11 | AP-0005238 | AP | ARM-2510 | 05-400 | Small Tools and Consumables | V-2205 |  | 5610.98 | 5610.98 | Small Tools and Consumables - rental and logistics
2026-05-14 | PRJ-PAY-ARM-2510-20260514 | PAY | ARM-2510 | 06-100 | Warranty and Punchlist |  | E-1028 | 43.73 | 3104.93 | Warranty and Punchlist - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2510-20260514 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1035 | 47.68 | 3694.93 | Closeout and O&M Documentation - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2510-20260514 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1042 | 47.73 | 4008.9 | Rework and Quality Correction - startup and checkout
2026-05-14 | PRJ-PAY-ARM-2510-20260514 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1049 | 39.44 | 3885.23 | Project Management and Supervision - punchlist and closeout labor
2026-05-14 | PRJ-PAY-ARM-2510-20260514 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1082 | 35.06 | 3400.89 | Engineering, BIM and Coordination - field installation time
2026-05-15 | AP-0005233 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2509 |  | 54.09 | 9735.35 | Controls Panels and Devices - released equipment package
2026-05-18 | AP-0005230 | AP | ARM-2510 | 02-210 | Sheet Metal and Ductwork | V-2467 |  | 79.33 | 14279.41 | Sheet Metal and Ductwork - valves and piping lot
2026-05-21 | AP-0005227 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2427 |  | 42.59 | 7667.07 | Controls Panels and Devices - jobsite material replenishment
2026-05-21 | AP-0005234 | AP | ARM-2510 | 04-300 | Testing and Balancing Subcontract | V-2510 |  | 25929.05 | 25929.05 | Testing and Balancing Subcontract - rigging and specialty support
2026-05-21 | AP-0005236 | AP | ARM-2510 | 05-300 | Freight and Expediting | V-2534 |  | 9448.13 | 9448.13 | Freight and Expediting - freight and expediting
2026-05-21 | PRJ-PAY-ARM-2510-20260521 | PAY | ARM-2510 | 06-200 | Closeout and O&M Documentation |  | E-1033 | 62.2 | 4416.43 | Closeout and O&M Documentation - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2510-20260521 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1040 | 35.78 | 2772.97 | Rework and Quality Correction - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2510-20260521 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1047 | 31.94 | 2938.9 | Project Management and Supervision - punchlist and closeout labor
2026-05-21 | PRJ-PAY-ARM-2510-20260521 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1080 | 36.53 | 3306.25 | Engineering, BIM and Coordination - field installation time
2026-05-21 | PRJ-PAY-ARM-2510-20260521 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1087 | 28.56 | 2770.62 | Field Installation Labor - coordination and layout
2026-05-25 | AP-0005231 | AP | ARM-2510 | 02-510 | Controls Panels and Devices | V-2481 |  | 74.33 | 13378.5 | Controls Panels and Devices - ductwork release
2026-05-28 | PRJ-PAY-ARM-2510-20260528 | PAY | ARM-2510 | 06-300 | Rework and Quality Correction |  | E-1038 | 57.15 | 4057.88 | Rework and Quality Correction - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2510-20260528 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1045 | 51.35 | 4390.75 | Project Management and Supervision - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2510-20260528 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1052 | 40.57 | 3408.24 | Engineering, BIM and Coordination - field installation time
2026-05-28 | PRJ-PAY-ARM-2510-20260528 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1085 | 33.06 | 2991.74 | Field Installation Labor - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2510-20260531 | PAY | ARM-2510 | 01-100 | Project Management and Supervision |  | E-1043 | 54.06 | 4270.55 | Project Management and Supervision - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2510-20260531 | PAY | ARM-2510 | 01-200 | Engineering, BIM and Coordination |  | E-1050 | 44.97 | 3485.06 | Engineering, BIM and Coordination - field installation time
2026-05-31 | PRJ-PAY-ARM-2510-20260531 | PAY | ARM-2510 | 03-100 | Field Installation Labor |  | E-1083 | 56.5 | 4745.85 | Field Installation Labor - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2510-20260531 | PAY | ARM-2510 | 03-200 | Startup, Testing and Commissioning |  | E-1090 | 30.62 | 2770.96 | Startup, Testing and Commissioning - supervision and planning
2025-05-03 | AP-0005253 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2381 |  | 95.74 | 17232.73 | Hydronic Piping and Valves - released equipment package
2025-05-03 | AP-0005254 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2393 |  | 11009.8 | 11009.8 | Insulation Subcontract - trade partner progress billing
2025-05-03 | AP-0005255 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2405 |  | 3829.49 | 3829.49 | Small Tools and Consumables - rental and logistics
2025-05-07 | PRJ-PAY-ARM-2514-20250507 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1007 | 13.83 | 1092.74 | Project Management and Supervision - field installation time
2025-05-07 | PRJ-PAY-ARM-2514-20250507 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 16.46 | 1275.74 | Engineering, BIM and Coordination - coordination and layout
2025-05-07 | PRJ-PAY-ARM-2514-20250507 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1023 | 9.53 | 800.27 | Field Installation Labor - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2514-20250514 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 15.7 | 1114.64 | Engineering, BIM and Coordination - coordination and layout
2025-05-14 | PRJ-PAY-ARM-2514-20250514 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1021 | 12.79 | 990.85 | Field Installation Labor - supervision and planning
2025-05-14 | PRJ-PAY-ARM-2514-20250514 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 16.47 | 1383.23 | Startup, Testing and Commissioning - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2514-20250521 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1019 | 14.12 | 1002.19 | Field Installation Labor - supervision and planning
2025-05-21 | PRJ-PAY-ARM-2514-20250521 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 16.13 | 1249.98 | Startup, Testing and Commissioning - startup and checkout
2025-05-21 | PRJ-PAY-ARM-2514-20250521 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 15.03 | 1262.34 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2514-20250528 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 15.68 | 1113.54 | Startup, Testing and Commissioning - startup and checkout
2025-05-28 | PRJ-PAY-ARM-2514-20250528 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 13.81 | 1069.89 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-05-28 | PRJ-PAY-ARM-2514-20250528 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1038 | 12.37 | 1038.98 | Controls Programming and Checkout - field installation time
2025-05-31 | PRJ-PAY-ARM-2514-20250531 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 13.49 | 957.6 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-05-31 | PRJ-PAY-ARM-2514-20250531 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1036 | 12.23 | 948.05 | Controls Programming and Checkout - field installation time
2025-05-31 | PRJ-PAY-ARM-2514-20250531 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1043 | 11.61 | 975.31 | Warranty and Punchlist - coordination and layout
2025-06-06 | AP-0005256 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2419 |  | 90.72 | 16330.41 | Plumbing Fixtures and Piping - fabricated material delivery
2025-06-06 | AP-0005259 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2453 |  | 24253.32 | 24253.32 | Electrical and Controls Subcontract - insulation progress invoice
2025-06-06 | AP-0005260 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2465 |  | 7716.96 | 7716.96 | Temporary Facilities and Protection - permit and inspection fees
2025-06-07 | PRJ-PAY-ARM-2514-20250607 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 34.2 | 2428.21 | Engineering, BIM and Coordination - field installation time
2025-06-07 | PRJ-PAY-ARM-2514-20250607 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1016 | 44.07 | 3415.61 | Field Installation Labor - coordination and layout
2025-06-07 | PRJ-PAY-ARM-2514-20250607 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 28.27 | 2374.88 | Startup, Testing and Commissioning - supervision and planning
2025-06-13 | AP-0005257 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2433 |  | 63.13 | 11363.04 | Major HVAC Equipment - valves and piping lot
2025-06-14 | PRJ-PAY-ARM-2514-20250614 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1014 | 32.87 | 2333.47 | Field Installation Labor - coordination and layout
2025-06-14 | PRJ-PAY-ARM-2514-20250614 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 29.08 | 2253.46 | Startup, Testing and Commissioning - supervision and planning
2025-06-14 | PRJ-PAY-ARM-2514-20250614 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 43.96 | 3692.53 | Sheet Metal Fabrication Labor - startup and checkout
2025-06-20 | AP-0005258 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2445 |  | 78.88 | 14198.64 | Plumbing Fixtures and Piping - ductwork release
2025-06-21 | PRJ-PAY-ARM-2514-20250621 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 37.25 | 2644.58 | Startup, Testing and Commissioning - supervision and planning
2025-06-21 | PRJ-PAY-ARM-2514-20250621 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 33.37 | 2586.05 | Sheet Metal Fabrication Labor - startup and checkout
2025-06-21 | PRJ-PAY-ARM-2514-20250621 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1034 | 28.1 | 2360.7 | Controls Programming and Checkout - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2514-20250628 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 31.02 | 2202.72 | Sheet Metal Fabrication Labor - startup and checkout
2025-06-28 | PRJ-PAY-ARM-2514-20250628 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1032 | 36.01 | 2790.6 | Controls Programming and Checkout - punchlist and closeout labor
2025-06-28 | PRJ-PAY-ARM-2514-20250628 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1039 | 21.35 | 1793.66 | Warranty and Punchlist - field installation time
2025-06-30 | PRJ-PAY-ARM-2514-20250630 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1030 | 39.9 | 2832.6 | Controls Programming and Checkout - punchlist and closeout labor
2025-06-30 | PRJ-PAY-ARM-2514-20250630 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1037 | 24.21 | 1876.64 | Warranty and Punchlist - field installation time
2025-06-30 | PRJ-PAY-ARM-2514-20250630 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 22.58 | 1896.69 | Closeout and O&M Documentation - coordination and layout
2025-07-06 | AP-0005264 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2521 |  | 84.41 | 15194.58 | Sheet Metal and Ductwork - released equipment package
2025-07-07 | PRJ-PAY-ARM-2514-20250707 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1009 | 45.02 | 3196.21 | Field Installation Labor - field installation time
2025-07-07 | PRJ-PAY-ARM-2514-20250707 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 42.13 | 3264.93 | Startup, Testing and Commissioning - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2514-20250707 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 45.46 | 3818.52 | Sheet Metal Fabrication Labor - supervision and planning
2025-07-07 | PRJ-PAY-ARM-2514-20250707 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1032 | 44.15 | 3995.85 | Controls Programming and Checkout - startup and checkout
2025-07-09 | AP-0005261 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2479 |  | 36.95 | 6650.98 | Controls Panels and Devices - valves and piping lot
2025-07-09 | AP-0005266 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2014 |  | 24122.26 | 24122.26 | Testing and Balancing Subcontract - testing and balancing services
2025-07-09 | AP-0005268 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2208 |  | 10166.49 | 10166.49 | Equipment Rental and Rigging - freight and expediting
2025-07-13 | AP-0005265 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2534 |  | 81.42 | 14656.14 | Controls Panels and Devices - fabricated material delivery
2025-07-14 | PRJ-PAY-ARM-2514-20250714 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 40.04 | 2842.55 | Startup, Testing and Commissioning - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2514-20250714 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 45.83 | 3551.66 | Sheet Metal Fabrication Labor - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2514-20250714 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1030 | 38.49 | 3233.5 | Controls Programming and Checkout - startup and checkout
2025-07-14 | PRJ-PAY-ARM-2514-20250714 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1037 | 38.25 | 3461.33 | Warranty and Punchlist - punchlist and closeout labor
2025-07-16 | AP-0005262 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2493 |  | 72.8 | 13104.21 | Sheet Metal and Ductwork - ductwork release
2025-07-16 | AP-0005267 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2056 |  | 18425.18 | 18425.18 | Electrical and Controls Subcontract - electrical coordination scope
2025-07-16 | AP-0005269 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2231 |  | 6482.52 | 6482.52 | Small Tools and Consumables - small tools and field consumables
2025-07-21 | PRJ-PAY-ARM-2514-20250721 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 61.46 | 4363.43 | Sheet Metal Fabrication Labor - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2514-20250721 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1028 | 50.92 | 3946.44 | Controls Programming and Checkout - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2514-20250721 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1035 | 40.38 | 3392.3 | Warranty and Punchlist - punchlist and closeout labor
2025-07-23 | AP-0005263 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2507 |  | 73.84 | 13290.31 | Controls Panels and Devices - jobsite material replenishment
2025-07-28 | PRJ-PAY-ARM-2514-20250728 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1026 | 57.35 | 4072.17 | Controls Programming and Checkout - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2514-20250728 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1033 | 45 | 3487.51 | Warranty and Punchlist - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2514-20250728 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 45.6 | 3830.31 | Closeout and O&M Documentation - field installation time
2025-07-31 | PRJ-PAY-ARM-2514-20250731 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1031 | 49.69 | 3527.86 | Warranty and Punchlist - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2514-20250731 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 54.73 | 4241.2 | Closeout and O&M Documentation - field installation time
2025-07-31 | PRJ-PAY-ARM-2514-20250731 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1045 | 55.6 | 4670.45 | Rework and Quality Correction - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2514-20250807 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 57.35 | 4071.76 | Startup, Testing and Commissioning - field installation time
2025-08-07 | PRJ-PAY-ARM-2514-20250807 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 56.44 | 4374.3 | Sheet Metal Fabrication Labor - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2514-20250807 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1026 | 42.95 | 3608.18 | Controls Programming and Checkout - supervision and planning
2025-08-07 | PRJ-PAY-ARM-2514-20250807 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1033 | 39.13 | 3540.84 | Warranty and Punchlist - startup and checkout
2025-08-09 | AP-0005273 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2296 |  | 69.11 | 12440.46 | Hydronic Piping and Valves - fabricated material delivery
2025-08-12 | AP-0005270 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2246 |  | 57.05 | 10268.31 | Insulation and Specialty Material - ductwork release
2025-08-12 | AP-0005276 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2327 |  | 25306.26 | 25306.26 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-08-12 | AP-0005278 | AP | ARM-2514 | 05-200 | Permits, Fees and Bonds | V-2351 |  | 6449.57 | 6449.57 | Permits, Fees and Bonds - small tools and field consumables
2025-08-14 | PRJ-PAY-ARM-2514-20250814 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 50.13 | 3559.46 | Sheet Metal Fabrication Labor - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2514-20250814 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1024 | 39.94 | 3095.53 | Controls Programming and Checkout - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2514-20250814 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1031 | 45.77 | 3844.27 | Warranty and Punchlist - startup and checkout
2025-08-14 | PRJ-PAY-ARM-2514-20250814 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 38.05 | 3443.42 | Closeout and O&M Documentation - punchlist and closeout labor
2025-08-16 | AP-0005274 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2310 |  | 73.15 | 13167.15 | Insulation and Specialty Material - valves and piping lot
2025-08-19 | AP-0005271 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2267 |  | 94.94 | 17089.71 | Hydronic Piping and Valves - jobsite material replenishment
2025-08-19 | AP-0005277 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2341 |  | 22882.87 | 22882.87 | Testing and Balancing Subcontract - rigging and specialty support
2025-08-19 | AP-0005279 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2365 |  | 6540.72 | 6540.72 | Temporary Facilities and Protection - rental and logistics
2025-08-21 | PRJ-PAY-ARM-2514-20250821 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1022 | 39.4 | 2797.11 | Controls Programming and Checkout - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2514-20250821 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1029 | 51.6 | 3998.78 | Warranty and Punchlist - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2514-20250821 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 46.79 | 3930.03 | Closeout and O&M Documentation - punchlist and closeout labor
2025-08-21 | PRJ-PAY-ARM-2514-20250821 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1043 | 31.43 | 2844.81 | Rework and Quality Correction - field installation time
2025-08-23 | AP-0005275 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2324 |  | 54.67 | 9840.87 | Hydronic Piping and Valves - ductwork release
2025-08-25 | AP-0005272 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2282 |  | 89.16 | 16048.43 | Insulation and Specialty Material - released equipment package
2025-08-25 | AP-0005280 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2379 |  | 4533.03 | 4533.03 | Freight and Expediting - permit and inspection fees
2025-08-28 | PRJ-PAY-ARM-2514-20250828 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1027 | 52.25 | 3709.58 | Warranty and Punchlist - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2514-20250828 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 43.94 | 3405.37 | Closeout and O&M Documentation - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2514-20250828 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1041 | 52.57 | 4415.95 | Rework and Quality Correction - field installation time
2025-08-28 | PRJ-PAY-ARM-2514-20250828 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1048 | 33.4 | 3290.29 | Project Management and Supervision - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2514-20250831 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 36.33 | 2579.38 | Closeout and O&M Documentation - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2514-20250831 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1039 | 31.61 | 2449.64 | Rework and Quality Correction - field installation time
2025-08-31 | PRJ-PAY-ARM-2514-20250831 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1046 | 39.17 | 3603.62 | Project Management and Supervision - coordination and layout
2025-08-31 | PRJ-PAY-ARM-2514-20250831 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1053 | 42.6 | 3855.08 | Engineering, BIM and Coordination - supervision and planning
2025-08-31 | PRJ-PAY-ARM-2514-20250831 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1086 | 41.82 | 4056.7 | Field Installation Labor - startup and checkout
2025-09-05 | AP-0005283 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2417 |  | 76.49 | 13767.4 | Major HVAC Equipment - fabricated material delivery
2025-09-05 | AP-0005291 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2512 |  | 19521.98 | 19521.98 | Testing and Balancing Subcontract - insulation progress invoice
2025-09-05 | AP-0005294 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2033 |  | 8115.31 | 8115.31 | Small Tools and Consumables - freight and expediting
2025-09-07 | PRJ-PAY-ARM-2514-20250907 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 52.55 | 3731.02 | Sheet Metal Fabrication Labor - field installation time
2025-09-07 | PRJ-PAY-ARM-2514-20250907 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1020 | 34.35 | 2662.35 | Controls Programming and Checkout - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2514-20250907 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1027 | 44.72 | 3756.6 | Warranty and Punchlist - supervision and planning
2025-09-07 | PRJ-PAY-ARM-2514-20250907 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 40.5 | 3665.66 | Closeout and O&M Documentation - startup and checkout
2025-09-07 | PRJ-PAY-ARM-2514-20250907 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1041 | 36.58 | 3548.37 | Rework and Quality Correction - punchlist and closeout labor
2025-09-09 | AP-0005287 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2471 |  | 82.91 | 14923.71 | Major HVAC Equipment - released equipment package
2025-09-12 | AP-0005284 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2431 |  | 72.2 | 12996.76 | Plumbing Fixtures and Piping - valves and piping lot
2025-09-14 | PRJ-PAY-ARM-2514-20250914 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1018 | 58.87 | 4179.58 | Controls Programming and Checkout - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2514-20250914 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1025 | 51.55 | 3994.85 | Warranty and Punchlist - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2514-20250914 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 35.22 | 2958.58 | Closeout and O&M Documentation - startup and checkout
2025-09-14 | PRJ-PAY-ARM-2514-20250914 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1039 | 30.48 | 2757.99 | Rework and Quality Correction - punchlist and closeout labor
2025-09-14 | PRJ-PAY-ARM-2514-20250914 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1046 | 28.66 | 3009.77 | Project Management and Supervision - field installation time
2025-09-15 | AP-0005281 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2389 |  | 56.93 | 10247.26 | Major HVAC Equipment - jobsite material replenishment
2025-09-15 | AP-0005289 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2484 |  | 23082.6 | 23082.6 | Insulation Subcontract - rigging and specialty support
2025-09-15 | AP-0005292 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2521 |  | 4123.73 | 4123.73 | Freight and Expediting - rental and logistics
2025-09-16 | AP-0005288 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2484 |  | 103.7 | 18666.31 | Plumbing Fixtures and Piping - fabricated material delivery
2025-09-19 | AP-0005285 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2443 |  | 56.98 | 10255.82 | Major HVAC Equipment - ductwork release
2025-09-21 | PRJ-PAY-ARM-2514-20250921 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1023 | 60.91 | 4324.58 | Warranty and Punchlist - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2514-20250921 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 41.8 | 3239.88 | Closeout and O&M Documentation - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2514-20250921 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1037 | 44.6 | 3746.56 | Rework and Quality Correction - punchlist and closeout labor
2025-09-21 | PRJ-PAY-ARM-2514-20250921 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1044 | 44.56 | 4389.55 | Project Management and Supervision - field installation time
2025-09-21 | PRJ-PAY-ARM-2514-20250921 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1051 | 28.43 | 2757.51 | Engineering, BIM and Coordination - coordination and layout
2025-09-22 | AP-0005282 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2403 |  | 56.9 | 10241.72 | Plumbing Fixtures and Piping - released equipment package
2025-09-22 | AP-0005290 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2498 |  | 21452.35 | 21452.35 | Crane, Rigging and Specialty Trade - trade partner progress billing
2025-09-22 | AP-0005293 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2534 |  | 7256.55 | 7256.55 | Equipment Rental and Rigging - permit and inspection fees
2025-09-25 | AP-0005286 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2457 |  | 81.86 | 14734.21 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-09-28 | PRJ-PAY-ARM-2514-20250928 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 46.91 | 3330.93 | Closeout and O&M Documentation - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2514-20250928 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1035 | 51.36 | 3980.54 | Rework and Quality Correction - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2514-20250928 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1042 | 29.73 | 2735.55 | Project Management and Supervision - field installation time
2025-09-28 | PRJ-PAY-ARM-2514-20250928 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 32.29 | 2922.59 | Engineering, BIM and Coordination - coordination and layout
2025-09-28 | PRJ-PAY-ARM-2514-20250928 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1082 | 34.07 | 3305.06 | Field Installation Labor - supervision and planning
2025-09-28 | PRJ-PAY-ARM-2514-20250928 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1089 | 41.83 | 4329.47 | Startup, Testing and Commissioning - startup and checkout
2025-09-30 | PRJ-PAY-ARM-2514-20250930 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1033 | 43.22 | 3068.49 | Rework and Quality Correction - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2514-20250930 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1040 | 42.71 | 3652.07 | Project Management and Supervision - field installation time
2025-09-30 | PRJ-PAY-ARM-2514-20250930 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 40.41 | 3394.58 | Engineering, BIM and Coordination - coordination and layout
2025-09-30 | PRJ-PAY-ARM-2514-20250930 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1080 | 47.84 | 4329.85 | Field Installation Labor - supervision and planning
2025-09-30 | PRJ-PAY-ARM-2514-20250930 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1087 | 38.73 | 3756.84 | Startup, Testing and Commissioning - startup and checkout
2025-09-30 | PRJ-PAY-ARM-2514-20250930 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1094 | 30.57 | 3164.03 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-10-05 | AP-0005300 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2293 |  | 97.81 | 17606.21 | Controls Panels and Devices - released equipment package
2025-10-07 | PRJ-PAY-ARM-2514-20251007 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1013 | 59.6 | 4231.39 | Controls Programming and Checkout - field installation time
2025-10-07 | PRJ-PAY-ARM-2514-20251007 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1021 | 49.79 | 3858.73 | Warranty and Punchlist - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2514-20251007 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 43.83 | 3681.55 | Closeout and O&M Documentation - supervision and planning
2025-10-07 | PRJ-PAY-ARM-2514-20251007 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1035 | 34.61 | 3132.26 | Rework and Quality Correction - startup and checkout
2025-10-07 | PRJ-PAY-ARM-2514-20251007 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1042 | 24.3 | 2551.69 | Project Management and Supervision - punchlist and closeout labor
2025-10-08 | AP-0005297 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2243 |  | 65.29 | 11752.69 | Sheet Metal and Ductwork - valves and piping lot
2025-10-08 | AP-0005305 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2348 |  | 25455.72 | 25455.72 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-10-08 | AP-0005308 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2384 |  | 8983.49 | 8983.49 | Temporary Facilities and Protection - small tools and field consumables
2025-10-12 | AP-0005301 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2307 |  | 44.22 | 7960.1 | Sheet Metal and Ductwork - fabricated material delivery
2025-10-14 | PRJ-PAY-ARM-2514-20251014 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1019 | 46.81 | 3323.5 | Warranty and Punchlist - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2514-20251014 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 40.68 | 3152.72 | Closeout and O&M Documentation - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2514-20251014 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1033 | 54.74 | 4598.3 | Rework and Quality Correction - startup and checkout
2025-10-14 | PRJ-PAY-ARM-2514-20251014 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1040 | 34.84 | 3431.44 | Project Management and Supervision - punchlist and closeout labor
2025-10-14 | PRJ-PAY-ARM-2514-20251014 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 46.99 | 4558.1 | Engineering, BIM and Coordination - field installation time
2025-10-15 | AP-0005298 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2262 |  | 49.67 | 8939.93 | Controls Panels and Devices - ductwork release
2025-10-15 | AP-0005309 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2398 |  | 5847.98 | 5847.98 | Freight and Expediting - rental and logistics
2025-10-18 | AP-0005295 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2098 |  | 83.18 | 14971.59 | Sheet Metal and Ductwork - released equipment package
2025-10-18 | AP-0005303 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2320 |  | 23040.76 | 23040.76 | Electrical and Controls Subcontract - trade partner progress billing
2025-10-18 | AP-0005306 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2357 |  | 6031.76 | 6031.76 | Small Tools and Consumables - permit and inspection fees
2025-10-19 | AP-0005302 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2320 |  | 59.63 | 10732.65 | Controls Panels and Devices - valves and piping lot
2025-10-21 | PRJ-PAY-ARM-2514-20251021 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 40.7 | 2889.48 | Closeout and O&M Documentation - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2514-20251021 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1031 | 60.72 | 4705.73 | Rework and Quality Correction - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2514-20251021 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1038 | 37.1 | 3412.85 | Project Management and Supervision - punchlist and closeout labor
2025-10-21 | PRJ-PAY-ARM-2514-20251021 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1045 | 37.43 | 3387.57 | Engineering, BIM and Coordination - field installation time
2025-10-21 | PRJ-PAY-ARM-2514-20251021 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1052 | 30.84 | 2991.61 | Field Installation Labor - coordination and layout
2025-10-21 | PRJ-PAY-ARM-2514-20251021 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1085 | 37.62 | 3893.33 | Startup, Testing and Commissioning - supervision and planning
2025-10-22 | AP-0005299 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2279 |  | 82.42 | 14834.76 | Sheet Metal and Ductwork - jobsite material replenishment
2025-10-25 | AP-0005296 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2222 |  | 76.5 | 13770.58 | Controls Panels and Devices - fabricated material delivery
2025-10-25 | AP-0005304 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2334 |  | 16577.26 | 16577.26 | Insulation Subcontract - insulation progress invoice
2025-10-25 | AP-0005307 | AP | ARM-2514 | 05-200 | Permits, Fees and Bonds | V-2370 |  | 5757.84 | 5757.84 | Permits, Fees and Bonds - freight and expediting
2025-10-28 | PRJ-PAY-ARM-2514-20251028 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1029 | 43.81 | 3110.81 | Rework and Quality Correction - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2514-20251028 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1036 | 40.99 | 3504.74 | Project Management and Supervision - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2514-20251028 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 51.22 | 4302.4 | Engineering, BIM and Coordination - field installation time
2025-10-28 | PRJ-PAY-ARM-2514-20251028 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1050 | 47.72 | 4318.22 | Field Installation Labor - coordination and layout
2025-10-28 | PRJ-PAY-ARM-2514-20251028 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1083 | 29.2 | 2832.3 | Startup, Testing and Commissioning - supervision and planning
2025-10-28 | PRJ-PAY-ARM-2514-20251028 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1090 | 38.64 | 3998.84 | Sheet Metal Fabrication Labor - startup and checkout
2025-10-31 | PRJ-PAY-ARM-2514-20251031 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1034 | 47.29 | 3736.12 | Project Management and Supervision - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2514-20251031 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 50.11 | 3883.21 | Engineering, BIM and Coordination - field installation time
2025-10-31 | PRJ-PAY-ARM-2514-20251031 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1048 | 34.4 | 2889.78 | Field Installation Labor - coordination and layout
2025-10-31 | PRJ-PAY-ARM-2514-20251031 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 30.45 | 2756.02 | Startup, Testing and Commissioning - supervision and planning
2025-10-31 | PRJ-PAY-ARM-2514-20251031 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1088 | 35.18 | 3412.61 | Sheet Metal Fabrication Labor - startup and checkout
2025-10-31 | PRJ-PAY-ARM-2514-20251031 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1095 | 38.87 | 4023.21 | Controls Programming and Checkout - punchlist and closeout labor
2025-11-04 | AP-0005311 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2421 |  | 75.71 | 13627.12 | Insulation and Specialty Material - valves and piping lot
2025-11-04 | AP-0005320 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2528 |  | 23908.33 | 23908.33 | Electrical and Controls Subcontract - testing and balancing services
2025-11-04 | AP-0005323 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2208 |  | 4540.02 | 4540.02 | Freight and Expediting - small tools and field consumables
2025-11-05 | AP-0005318 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2515 |  | 57.47 | 10344.06 | Hydronic Piping and Valves - jobsite material replenishment
2025-11-07 | PRJ-PAY-ARM-2514-20251107 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1014 | 37.9 | 2691.17 | Warranty and Punchlist - field installation time
2025-11-07 | PRJ-PAY-ARM-2514-20251107 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 48.32 | 3745.18 | Closeout and O&M Documentation - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2514-20251107 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1029 | 35.25 | 2960.72 | Rework and Quality Correction - supervision and planning
2025-11-07 | PRJ-PAY-ARM-2514-20251107 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1036 | 38.36 | 3777.97 | Project Management and Supervision - startup and checkout
2025-11-07 | PRJ-PAY-ARM-2514-20251107 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 43.32 | 4202.26 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-11-07 | PRJ-PAY-ARM-2514-20251107 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1050 | 27.65 | 2861.68 | Field Installation Labor - field installation time
2025-11-08 | AP-0005315 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2474 |  | 59.67 | 10741.3 | Insulation and Specialty Material - fabricated material delivery
2025-11-11 | AP-0005312 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2434 |  | 58.89 | 10600.33 | Hydronic Piping and Valves - ductwork release
2025-11-11 | AP-0005321 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2018 |  | 18767.82 | 18767.82 | Insulation Subcontract - electrical coordination scope
2025-11-11 | AP-0005324 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2231 |  | 7485.36 | 7485.36 | Equipment Rental and Rigging - rental and logistics
2025-11-14 | PRJ-PAY-ARM-2514-20251114 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 42.48 | 3016.33 | Closeout and O&M Documentation - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2514-20251114 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1027 | 46.64 | 3614.47 | Rework and Quality Correction - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2514-20251114 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1034 | 49.78 | 4579.37 | Project Management and Supervision - startup and checkout
2025-11-14 | PRJ-PAY-ARM-2514-20251114 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 45.14 | 4085.35 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-11-14 | PRJ-PAY-ARM-2514-20251114 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1048 | 43.09 | 4179.83 | Field Installation Labor - field installation time
2025-11-14 | PRJ-PAY-ARM-2514-20251114 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1081 | 30.11 | 3116.75 | Startup, Testing and Commissioning - coordination and layout
2025-11-15 | AP-0005316 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2488 |  | 58.15 | 10467.59 | Hydronic Piping and Valves - valves and piping lot
2025-11-18 | AP-0005313 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2446 |  | 98.82 | 17787.27 | Insulation and Specialty Material - jobsite material replenishment
2025-11-18 | AP-0005325 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2250 |  | 8281.74 | 8281.74 | Small Tools and Consumables - permit and inspection fees
2025-11-21 | AP-0005310 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2407 |  | 46.51 | 8372.46 | Hydronic Piping and Valves - fabricated material delivery
2025-11-21 | AP-0005319 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2514 |  | 30253.62 | 30253.62 | Testing and Balancing Subcontract - insulation progress invoice
2025-11-21 | AP-0005322 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2037 |  | 5059.76 | 5059.76 | Temporary Facilities and Protection - freight and expediting
2025-11-21 | PRJ-PAY-ARM-2514-20251121 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1025 | 47.2 | 3351.15 | Rework and Quality Correction - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2514-20251121 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1032 | 35.41 | 3027.15 | Project Management and Supervision - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2514-20251121 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 49.36 | 4146.08 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-11-21 | PRJ-PAY-ARM-2514-20251121 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1046 | 37.64 | 3406.18 | Field Installation Labor - field installation time
2025-11-21 | PRJ-PAY-ARM-2514-20251121 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1053 | 31.02 | 3008.54 | Startup, Testing and Commissioning - coordination and layout
2025-11-21 | PRJ-PAY-ARM-2514-20251121 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1086 | 32.02 | 3313.92 | Sheet Metal Fabrication Labor - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2514-20251121 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1093 | 44.71 | 3174.31 | Controls Programming and Checkout - startup and checkout
2025-11-22 | AP-0005317 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2502 |  | 106.53 | 19174.64 | Insulation and Specialty Material - ductwork release
2025-11-25 | AP-0005314 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2460 |  | 72.42 | 13036.18 | Hydronic Piping and Valves - released equipment package
2025-11-28 | PRJ-PAY-ARM-2514-20251128 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1030 | 53.91 | 4258.97 | Project Management and Supervision - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2514-20251128 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 44.46 | 3445.79 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2514-20251128 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1044 | 51.15 | 4296.89 | Field Installation Labor - field installation time
2025-11-28 | PRJ-PAY-ARM-2514-20251128 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 37.33 | 3378.63 | Startup, Testing and Commissioning - coordination and layout
2025-11-28 | PRJ-PAY-ARM-2514-20251128 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1084 | 34.31 | 3328.51 | Sheet Metal Fabrication Labor - supervision and planning
2025-11-28 | PRJ-PAY-ARM-2514-20251128 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1091 | 31.57 | 3267.97 | Controls Programming and Checkout - startup and checkout
2025-11-30 | PRJ-PAY-ARM-2514-20251130 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 49.34 | 3503.27 | Engineering, BIM and Coordination - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2514-20251130 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1042 | 60.52 | 4690.12 | Field Installation Labor - field installation time
2025-11-30 | PRJ-PAY-ARM-2514-20251130 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 46.71 | 3923.41 | Startup, Testing and Commissioning - coordination and layout
2025-11-30 | PRJ-PAY-ARM-2514-20251130 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 39.81 | 3602.67 | Sheet Metal Fabrication Labor - supervision and planning
2025-11-30 | PRJ-PAY-ARM-2514-20251130 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1089 | 39.74 | 3854.59 | Controls Programming and Checkout - startup and checkout
2025-12-04 | AP-0005330 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2320 |  | 73.95 | 13311.28 | Plumbing Fixtures and Piping - fabricated material delivery
2025-12-07 | AP-0005327 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2279 |  | 61.81 | 11126.12 | Major HVAC Equipment - ductwork release
2025-12-07 | AP-0005337 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2400 |  | 27720.79 | 27720.79 | Testing and Balancing Subcontract - electrical coordination scope
2025-12-07 | AP-0005340 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2436 |  | 8329.17 | 8329.17 | Small Tools and Consumables - rental and logistics
2025-12-07 | PRJ-PAY-ARM-2514-20251207 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 56.79 | 4031.97 | Closeout and O&M Documentation - field installation time
2025-12-07 | PRJ-PAY-ARM-2514-20251207 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1023 | 54.97 | 4260.26 | Rework and Quality Correction - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2514-20251207 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1030 | 44.32 | 4077.66 | Project Management and Supervision - supervision and planning
2025-12-07 | PRJ-PAY-ARM-2514-20251207 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 43.57 | 3943.38 | Engineering, BIM and Coordination - startup and checkout
2025-12-07 | PRJ-PAY-ARM-2514-20251207 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1044 | 40.44 | 3922.23 | Field Installation Labor - punchlist and closeout labor
2025-12-07 | PRJ-PAY-ARM-2514-20251207 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1051 | 29.62 | 3065.48 | Startup, Testing and Commissioning - field installation time
2025-12-08 | AP-0005334 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2376 |  | 81.67 | 14701.08 | Plumbing Fixtures and Piping - released equipment package
2025-12-11 | AP-0005331 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2334 |  | 73.68 | 13262.28 | Major HVAC Equipment - valves and piping lot
2025-12-14 | AP-0005328 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2293 |  | 75.22 | 13538.92 | Plumbing Fixtures and Piping - jobsite material replenishment
2025-12-14 | AP-0005338 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2414 |  | 22812.1 | 22812.1 | Electrical and Controls Subcontract - rigging and specialty support
2025-12-14 | AP-0005341 | AP | ARM-2514 | 05-200 | Permits, Fees and Bonds | V-2448 |  | 5603.9 | 5603.9 | Permits, Fees and Bonds - permit and inspection fees
2025-12-14 | PRJ-PAY-ARM-2514-20251214 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1021 | 52.37 | 3718.11 | Rework and Quality Correction - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2514-20251214 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1028 | 45.37 | 3879.24 | Project Management and Supervision - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2514-20251214 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 42.85 | 3599.47 | Engineering, BIM and Coordination - startup and checkout
2025-12-14 | PRJ-PAY-ARM-2514-20251214 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1042 | 34.91 | 3159.17 | Field Installation Labor - punchlist and closeout labor
2025-12-14 | PRJ-PAY-ARM-2514-20251214 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 32.92 | 3193.47 | Startup, Testing and Commissioning - field installation time
2025-12-14 | PRJ-PAY-ARM-2514-20251214 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1082 | 30.65 | 3172.11 | Sheet Metal Fabrication Labor - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2514-20251214 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1089 | 48.46 | 3440.84 | Controls Programming and Checkout - supervision and planning
2025-12-15 | AP-0005335 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2389 |  | 39.04 | 7027.16 | Major HVAC Equipment - fabricated material delivery
2025-12-18 | AP-0005332 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2348 |  | 81.21 | 14617.02 | Plumbing Fixtures and Piping - ductwork release
2025-12-21 | AP-0005329 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2307 |  | 57.62 | 10371.42 | Major HVAC Equipment - released equipment package
2025-12-21 | PRJ-PAY-ARM-2514-20251221 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1026 | 50.37 | 3979.19 | Project Management and Supervision - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2514-20251221 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 44.4 | 3441.36 | Engineering, BIM and Coordination - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2514-20251221 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1040 | 40.05 | 3364.57 | Field Installation Labor - punchlist and closeout labor
2025-12-21 | PRJ-PAY-ARM-2514-20251221 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1047 | 51.07 | 4621.5 | Startup, Testing and Commissioning - field installation time
2025-12-21 | PRJ-PAY-ARM-2514-20251221 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1080 | 45.91 | 4453.54 | Sheet Metal Fabrication Labor - coordination and layout
2025-12-21 | PRJ-PAY-ARM-2514-20251221 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1087 | 27.11 | 2806.17 | Controls Programming and Checkout - supervision and planning
2025-12-24 | AP-0005326 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2262 |  | 81.45 | 14660.27 | Plumbing Fixtures and Piping - valves and piping lot
2025-12-24 | AP-0005336 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2386 |  | 20206.42 | 20206.42 | Crane, Rigging and Specialty Trade - testing and balancing services
2025-12-24 | AP-0005339 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2422 |  | 8574.89 | 8574.89 | Equipment Rental and Rigging - small tools and field consumables
2025-12-25 | AP-0005333 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2362 |  | 53.17 | 9570.53 | Major HVAC Equipment - jobsite material replenishment
2025-12-28 | PRJ-PAY-ARM-2514-20251228 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 54.28 | 3853.73 | Engineering, BIM and Coordination - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2514-20251228 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1038 | 48.18 | 3733.68 | Field Installation Labor - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2514-20251228 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 34.66 | 2911.8 | Startup, Testing and Commissioning - field installation time
2025-12-28 | PRJ-PAY-ARM-2514-20251228 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 33.3 | 3013.95 | Sheet Metal Fabrication Labor - coordination and layout
2025-12-28 | PRJ-PAY-ARM-2514-20251228 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1085 | 27.48 | 2665.08 | Controls Programming and Checkout - supervision and planning
2025-12-28 | PRJ-PAY-ARM-2514-20251228 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1092 | 38.74 | 4009.98 | Warranty and Punchlist - startup and checkout
2025-12-31 | PRJ-PAY-ARM-2514-20251231 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1036 | 58.9 | 4182.23 | Field Installation Labor - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2514-20251231 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 46.92 | 3636.36 | Startup, Testing and Commissioning - field installation time
2025-12-31 | PRJ-PAY-ARM-2514-20251231 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 46.08 | 3870.52 | Sheet Metal Fabrication Labor - coordination and layout
2025-12-31 | PRJ-PAY-ARM-2514-20251231 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1083 | 32.45 | 2936.7 | Controls Programming and Checkout - supervision and planning
2025-12-31 | PRJ-PAY-ARM-2514-20251231 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1090 | 45.16 | 4380.64 | Warranty and Punchlist - startup and checkout
2026-01-03 | AP-0005342 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2458 |  | 60.67 | 10921.15 | Controls Panels and Devices - ductwork release
2026-01-03 | AP-0005350 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2060 |  | 24501.82 | 24501.82 | Insulation Subcontract - electrical coordination scope
2026-01-03 | AP-0005353 | AP | ARM-2514 | 05-200 | Permits, Fees and Bonds | V-2250 |  | 6372 | 6372 | Permits, Fees and Bonds - rental and logistics
2026-01-04 | AP-0005349 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2060 |  | 60.49 | 10888.06 | Sheet Metal and Ductwork - released equipment package
2026-01-07 | AP-0005346 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2514 |  | 67.12 | 12082.14 | Controls Panels and Devices - valves and piping lot
2026-01-07 | PRJ-PAY-ARM-2514-20260107 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1016 | 61.29 | 4351.49 | Rework and Quality Correction - field installation time
2026-01-07 | PRJ-PAY-ARM-2514-20260107 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1024 | 43.07 | 3682.06 | Project Management and Supervision - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2514-20260107 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 37.21 | 3125.67 | Engineering, BIM and Coordination - supervision and planning
2026-01-07 | PRJ-PAY-ARM-2514-20260107 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1038 | 29.31 | 2652.94 | Field Installation Labor - startup and checkout
2026-01-07 | PRJ-PAY-ARM-2514-20260107 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 41.28 | 4004.15 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-01-07 | PRJ-PAY-ARM-2514-20260107 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1052 | 35.44 | 3668.26 | Sheet Metal Fabrication Labor - field installation time
2026-01-10 | AP-0005343 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2472 |  | 77.5 | 13950.79 | Sheet Metal and Ductwork - jobsite material replenishment
2026-01-10 | AP-0005351 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2217 |  | 22618.2 | 22618.2 | Crane, Rigging and Specialty Trade - rigging and specialty support
2026-01-10 | AP-0005354 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2270 |  | 5136.42 | 5136.42 | Temporary Facilities and Protection - permit and inspection fees
2026-01-14 | AP-0005347 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2528 |  | 46.78 | 8420.05 | Sheet Metal and Ductwork - ductwork release
2026-01-14 | PRJ-PAY-ARM-2514-20260114 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1022 | 37.85 | 2989.86 | Project Management and Supervision - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2514-20260114 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 42.83 | 3319.42 | Engineering, BIM and Coordination - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2514-20260114 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1036 | 42.8 | 3595.04 | Field Installation Labor - startup and checkout
2026-01-14 | PRJ-PAY-ARM-2514-20260114 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 35.23 | 3188.16 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-01-14 | PRJ-PAY-ARM-2514-20260114 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 39.86 | 3866.28 | Sheet Metal Fabrication Labor - field installation time
2026-01-14 | PRJ-PAY-ARM-2514-20260114 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1083 | 30.87 | 3195.54 | Controls Programming and Checkout - coordination and layout
2026-01-17 | AP-0005344 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2486 |  | 86.7 | 15605.23 | Controls Panels and Devices - released equipment package
2026-01-17 | AP-0005352 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2237 |  | 16777.85 | 16777.85 | Testing and Balancing Subcontract - trade partner progress billing
2026-01-17 | AP-0005355 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2284 |  | 8229.15 | 8229.15 | Freight and Expediting - freight and expediting
2026-01-21 | AP-0005348 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2018 |  | 55.52 | 9992.83 | Controls Panels and Devices - jobsite material replenishment
2026-01-21 | PRJ-PAY-ARM-2514-20260121 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 40.02 | 2841.45 | Engineering, BIM and Coordination - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2514-20260121 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1034 | 55.54 | 4304.71 | Field Installation Labor - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2514-20260121 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 42.12 | 3537.78 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-01-21 | PRJ-PAY-ARM-2514-20260121 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1048 | 47.4 | 4289.75 | Sheet Metal Fabrication Labor - field installation time
2026-01-21 | PRJ-PAY-ARM-2514-20260121 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1081 | 30.69 | 2977.14 | Controls Programming and Checkout - coordination and layout
2026-01-24 | AP-0005345 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2500 |  | 69.99 | 12597.47 | Sheet Metal and Ductwork - fabricated material delivery
2026-01-24 | AP-0005356 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2298 |  | 5265.95 | 5265.95 | Equipment Rental and Rigging - small tools and field consumables
2026-01-28 | PRJ-PAY-ARM-2514-20260128 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1032 | 48.29 | 3428.77 | Field Installation Labor - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2514-20260128 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 55.02 | 4264 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2514-20260128 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 35.06 | 2945.3 | Sheet Metal Fabrication Labor - field installation time
2026-01-28 | PRJ-PAY-ARM-2514-20260128 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1053 | 29.88 | 2704.55 | Controls Programming and Checkout - coordination and layout
2026-01-28 | PRJ-PAY-ARM-2514-20260128 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1086 | 36.67 | 3557.41 | Warranty and Punchlist - supervision and planning
2026-01-31 | PRJ-PAY-ARM-2514-20260131 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 56.23 | 3992.5 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2514-20260131 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 43.81 | 3395.52 | Sheet Metal Fabrication Labor - field installation time
2026-01-31 | PRJ-PAY-ARM-2514-20260131 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1051 | 43.22 | 3630.81 | Controls Programming and Checkout - coordination and layout
2026-01-31 | PRJ-PAY-ARM-2514-20260131 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1084 | 44.87 | 4060.37 | Warranty and Punchlist - supervision and planning
2026-01-31 | PRJ-PAY-ARM-2514-20260131 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1091 | 29.78 | 2888.79 | Closeout and O&M Documentation - startup and checkout
2026-02-03 | AP-0005360 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2348 |  | 40.57 | 7302.31 | Hydronic Piping and Valves - valves and piping lot
2026-02-06 | AP-0005357 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2307 |  | 84.35 | 15182.43 | Insulation and Specialty Material - jobsite material replenishment
2026-02-06 | AP-0005366 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2415 |  | 28886.54 | 28886.54 | Electrical and Controls Subcontract - rigging and specialty support
2026-02-06 | AP-0005369 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2450 |  | 9080.31 | 9080.31 | Freight and Expediting - permit and inspection fees
2026-02-07 | AP-0005364 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2403 |  | 45.15 | 8126.12 | Hydronic Piping and Valves - fabricated material delivery
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1018 | 34.74 | 2744.56 | Project Management and Supervision - field installation time
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 54.29 | 4207.21 | Engineering, BIM and Coordination - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1032 | 33.05 | 2776.24 | Field Installation Labor - supervision and planning
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 35.15 | 3180.9 | Startup, Testing and Commissioning - startup and checkout
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 29.44 | 2855.7 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1053 | 36.95 | 3824.29 | Controls Programming and Checkout - field installation time
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1086 | 60.63 | 4304.74 | Warranty and Punchlist - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2514-20260207 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1093 | 54.21 | 4201.21 | Closeout and O&M Documentation - supervision and planning
2026-02-10 | AP-0005361 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2362 |  | 76.58 | 13784.19 | Insulation and Specialty Material - ductwork release
2026-02-13 | AP-0005358 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2320 |  | 75.52 | 13593.61 | Hydronic Piping and Valves - released equipment package
2026-02-13 | AP-0005367 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2429 |  | 17075.87 | 17075.87 | Insulation Subcontract - trade partner progress billing
2026-02-13 | AP-0005370 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2464 |  | 6219.02 | 6219.02 | Equipment Rental and Rigging - freight and expediting
2026-02-14 | AP-0005365 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2417 |  | 44.11 | 7940.46 | Insulation and Specialty Material - valves and piping lot
2026-02-14 | PRJ-PAY-ARM-2514-20260214 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 54.03 | 3835.97 | Engineering, BIM and Coordination - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2514-20260214 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1030 | 38.83 | 3008.97 | Field Installation Labor - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2514-20260214 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 36.23 | 3043 | Startup, Testing and Commissioning - startup and checkout
2026-02-14 | PRJ-PAY-ARM-2514-20260214 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 44.01 | 3983 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-02-14 | PRJ-PAY-ARM-2514-20260214 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1051 | 35.95 | 3487.5 | Controls Programming and Checkout - field installation time
2026-02-14 | PRJ-PAY-ARM-2514-20260214 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1084 | 40.04 | 4144.56 | Warranty and Punchlist - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2514-20260214 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1091 | 49.58 | 3520.24 | Closeout and O&M Documentation - supervision and planning
2026-02-17 | AP-0005362 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2376 |  | 45.78 | 8241.23 | Hydronic Piping and Valves - jobsite material replenishment
2026-02-20 | AP-0005359 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2334 |  | 93.38 | 16807.95 | Insulation and Specialty Material - fabricated material delivery
2026-02-20 | AP-0005368 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2441 |  | 19858.81 | 19858.81 | Crane, Rigging and Specialty Trade - insulation progress invoice
2026-02-20 | AP-0005371 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2477 |  | 8635.65 | 8635.65 | Small Tools and Consumables - small tools and field consumables
2026-02-21 | PRJ-PAY-ARM-2514-20260221 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1028 | 46.32 | 3289 | Field Installation Labor - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2514-20260221 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 40.67 | 3152.15 | Startup, Testing and Commissioning - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2514-20260221 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 46.82 | 3932.87 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-02-21 | PRJ-PAY-ARM-2514-20260221 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1049 | 41 | 3710.8 | Controls Programming and Checkout - field installation time
2026-02-21 | PRJ-PAY-ARM-2514-20260221 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1082 | 28.24 | 2739.2 | Warranty and Punchlist - coordination and layout
2026-02-21 | PRJ-PAY-ARM-2514-20260221 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1089 | 25.19 | 2607.47 | Closeout and O&M Documentation - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2514-20260221 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1096 | 58.13 | 4126.95 | Rework and Quality Correction - startup and checkout
2026-02-24 | AP-0005363 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2389 |  | 92.94 | 16729.15 | Insulation and Specialty Material - released equipment package
2026-02-28 | PRJ-PAY-ARM-2514-20260228 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 45.5 | 3230.26 | Startup, Testing and Commissioning - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2514-20260228 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 40.31 | 3124.01 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2514-20260228 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1047 | 47.71 | 4008 | Controls Programming and Checkout - field installation time
2026-02-28 | PRJ-PAY-ARM-2514-20260228 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1080 | 42.68 | 3862.96 | Warranty and Punchlist - coordination and layout
2026-02-28 | PRJ-PAY-ARM-2514-20260228 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1087 | 40.15 | 3894.41 | Closeout and O&M Documentation - supervision and planning
2026-02-28 | PRJ-PAY-ARM-2514-20260228 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1094 | 40.43 | 4184.08 | Rework and Quality Correction - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2514-20260228 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1007 | 34.73 | 2743.45 | Project Management and Supervision - punchlist and closeout labor
2026-03-03 | AP-0005378 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2220 |  | 53.43 | 9616.63 | Major HVAC Equipment - fabricated material delivery
2026-03-06 | AP-0005375 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2529 |  | 63.56 | 11440.05 | Plumbing Fixtures and Piping - ductwork release
2026-03-07 | PRJ-PAY-ARM-2514-20260307 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 41.06 | 2915.56 | Engineering, BIM and Coordination - field installation time
2026-03-07 | PRJ-PAY-ARM-2514-20260307 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1026 | 42.44 | 3289.01 | Field Installation Labor - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2514-20260307 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 42.61 | 3578.86 | Startup, Testing and Commissioning - supervision and planning
2026-03-07 | PRJ-PAY-ARM-2514-20260307 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 43.71 | 3956.2 | Sheet Metal Fabrication Labor - startup and checkout
2026-03-07 | PRJ-PAY-ARM-2514-20260307 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1047 | 36.77 | 3567.11 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-07 | PRJ-PAY-ARM-2514-20260307 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1080 | 28.94 | 2995.02 | Warranty and Punchlist - field installation time
2026-03-09 | AP-0005372 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2488 |  | 58.13 | 10463.29 | Major HVAC Equipment - released equipment package
2026-03-09 | AP-0005382 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2274 |  | 22955.37 | 22955.37 | Testing and Balancing Subcontract - trade partner progress billing
2026-03-09 | AP-0005385 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2310 |  | 8850 | 8850 | Small Tools and Consumables - freight and expediting
2026-03-10 | AP-0005379 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2241 |  | 63.68 | 11462.15 | Plumbing Fixtures and Piping - valves and piping lot
2026-03-13 | AP-0005376 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2021 |  | 74.97 | 13495.48 | Major HVAC Equipment - jobsite material replenishment
2026-03-14 | PRJ-PAY-ARM-2514-20260314 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1024 | 67.24 | 4774.13 | Field Installation Labor - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2514-20260314 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 45.84 | 3552.7 | Startup, Testing and Commissioning - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2514-20260314 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 34.59 | 2905.28 | Sheet Metal Fabrication Labor - startup and checkout
2026-03-14 | PRJ-PAY-ARM-2514-20260314 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1045 | 39.43 | 3568.13 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-14 | PRJ-PAY-ARM-2514-20260314 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1052 | 44.46 | 4313.1 | Warranty and Punchlist - field installation time
2026-03-16 | AP-0005373 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2502 |  | 60.66 | 10917.9 | Plumbing Fixtures and Piping - fabricated material delivery
2026-03-16 | AP-0005383 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2288 |  | 16884.39 | 16884.39 | Electrical and Controls Subcontract - insulation progress invoice
2026-03-16 | AP-0005386 | AP | ARM-2514 | 05-200 | Permits, Fees and Bonds | V-2324 |  | 7863.46 | 7863.46 | Permits, Fees and Bonds - small tools and field consumables
2026-03-17 | AP-0005380 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2258 |  | 76.28 | 13730.94 | Major HVAC Equipment - ductwork release
2026-03-20 | AP-0005377 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2094 |  | 59 | 10619.93 | Plumbing Fixtures and Piping - released equipment package
2026-03-21 | PRJ-PAY-ARM-2514-20260321 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 46.73 | 3317.86 | Startup, Testing and Commissioning - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2514-20260321 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 43.82 | 3396.15 | Sheet Metal Fabrication Labor - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2514-20260321 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1043 | 45.7 | 3838.87 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-21 | PRJ-PAY-ARM-2514-20260321 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1050 | 31.13 | 2817.02 | Warranty and Punchlist - field installation time
2026-03-21 | PRJ-PAY-ARM-2514-20260321 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1083 | 42.41 | 4113.42 | Closeout and O&M Documentation - coordination and layout
2026-03-21 | PRJ-PAY-ARM-2514-20260321 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1090 | 27.42 | 2837.86 | Rework and Quality Correction - supervision and planning
2026-03-23 | AP-0005374 | AP | ARM-2514 | 02-110 | Major HVAC Equipment | V-2515 |  | 68.5 | 12330.17 | Major HVAC Equipment - valves and piping lot
2026-03-23 | AP-0005384 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2301 |  | 32442.9 | 32442.9 | Insulation Subcontract - testing and balancing services
2026-03-23 | AP-0005387 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2338 |  | 5285.61 | 5285.61 | Temporary Facilities and Protection - rental and logistics
2026-03-24 | AP-0005381 | AP | ARM-2514 | 02-410 | Plumbing Fixtures and Piping | V-2277 |  | 85.26 | 15346.98 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-03-28 | PRJ-PAY-ARM-2514-20260328 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 57.37 | 4073.16 | Sheet Metal Fabrication Labor - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2514-20260328 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1041 | 39.98 | 3098.52 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2514-20260328 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1048 | 36.28 | 3047.3 | Warranty and Punchlist - field installation time
2026-03-28 | PRJ-PAY-ARM-2514-20260328 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1081 | 49.46 | 4476.09 | Closeout and O&M Documentation - coordination and layout
2026-03-28 | PRJ-PAY-ARM-2514-20260328 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1088 | 36.8 | 3569.62 | Rework and Quality Correction - supervision and planning
2026-03-28 | PRJ-PAY-ARM-2514-20260328 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1095 | 40.81 | 4550.1 | Project Management and Supervision - startup and checkout
2026-03-31 | PRJ-PAY-ARM-2514-20260331 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1039 | 62.28 | 4421.81 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2514-20260331 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1046 | 33.8 | 2619.43 | Warranty and Punchlist - field installation time
2026-03-31 | PRJ-PAY-ARM-2514-20260331 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 43.52 | 3655.3 | Closeout and O&M Documentation - coordination and layout
2026-03-31 | PRJ-PAY-ARM-2514-20260331 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1086 | 43.35 | 3923.05 | Rework and Quality Correction - supervision and planning
2026-03-31 | PRJ-PAY-ARM-2514-20260331 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1093 | 30.97 | 3251.93 | Project Management and Supervision - startup and checkout
2026-03-31 | PRJ-PAY-ARM-2514-20260331 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1100 | 33.84 | 3502.57 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2514-20260331 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1014 | 41.23 | 2927.47 | Field Installation Labor - field installation time
2026-04-03 | AP-0005397 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2471 |  | 98.91 | 17804.68 | Controls Panels and Devices - released equipment package
2026-04-06 | AP-0005394 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2431 |  | 59.13 | 10643.01 | Sheet Metal and Ductwork - valves and piping lot
2026-04-07 | PRJ-PAY-ARM-2514-20260407 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1020 | 50.18 | 3562.66 | Field Installation Labor - field installation time
2026-04-07 | PRJ-PAY-ARM-2514-20260407 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1027 | 42.15 | 3266.32 | Startup, Testing and Commissioning - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2514-20260407 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 36.56 | 3071.24 | Sheet Metal Fabrication Labor - supervision and planning
2026-04-07 | PRJ-PAY-ARM-2514-20260407 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1041 | 50.25 | 4547.49 | Controls Programming and Checkout - startup and checkout
2026-04-07 | PRJ-PAY-ARM-2514-20260407 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1048 | 29.51 | 2862.05 | Warranty and Punchlist - punchlist and closeout labor
2026-04-07 | PRJ-PAY-ARM-2514-20260407 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1081 | 42.29 | 4376.68 | Closeout and O&M Documentation - field installation time
2026-04-09 | AP-0005391 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2389 |  | 84.71 | 15248.4 | Controls Panels and Devices - jobsite material replenishment
2026-04-09 | AP-0005404 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2025 |  | 5375.71 | 5375.71 | Small Tools and Consumables - freight and expediting
2026-04-12 | AP-0005388 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2348 |  | 50.22 | 9039.11 | Sheet Metal and Ductwork - fabricated material delivery
2026-04-12 | AP-0005398 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2467 |  | 27898.23 | 27898.23 | Crane, Rigging and Specialty Trade - insulation progress invoice
2026-04-12 | AP-0005401 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2503 |  | 5840.82 | 5840.82 | Temporary Facilities and Protection - small tools and field consumables
2026-04-13 | AP-0005395 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2443 |  | 106.39 | 19150.5 | Controls Panels and Devices - ductwork release
2026-04-14 | PRJ-PAY-ARM-2514-20260414 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1025 | 43.85 | 3113.07 | Startup, Testing and Commissioning - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2514-20260414 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1032 | 56.16 | 4352.65 | Sheet Metal Fabrication Labor - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2514-20260414 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1039 | 39.69 | 3333.89 | Controls Programming and Checkout - startup and checkout
2026-04-14 | PRJ-PAY-ARM-2514-20260414 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1046 | 53.3 | 4823.7 | Warranty and Punchlist - punchlist and closeout labor
2026-04-14 | PRJ-PAY-ARM-2514-20260414 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 41.98 | 4071.96 | Closeout and O&M Documentation - field installation time
2026-04-14 | PRJ-PAY-ARM-2514-20260414 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1086 | 32.48 | 3361.61 | Rework and Quality Correction - coordination and layout
2026-04-16 | AP-0005392 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2403 |  | 73.98 | 13317.07 | Sheet Metal and Ductwork - released equipment package
2026-04-16 | AP-0005405 | AP | ARM-2514 | 05-200 | Permits, Fees and Bonds | V-2098 |  | 8292.08 | 8292.08 | Permits, Fees and Bonds - small tools and field consumables
2026-04-19 | AP-0005389 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2362 |  | 64.98 | 11695.61 | Controls Panels and Devices - valves and piping lot
2026-04-19 | AP-0005399 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2481 |  | 25987.51 | 25987.51 | Testing and Balancing Subcontract - testing and balancing services
2026-04-19 | AP-0005402 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2517 |  | 6266.19 | 6266.19 | Freight and Expediting - rental and logistics
2026-04-20 | AP-0005396 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2457 |  | 46.73 | 8410.86 | Sheet Metal and Ductwork - jobsite material replenishment
2026-04-21 | PRJ-PAY-ARM-2514-20260421 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1030 | 49.1 | 3486.22 | Sheet Metal Fabrication Labor - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2514-20260421 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1037 | 57.77 | 4476.84 | Controls Programming and Checkout - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2514-20260421 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1044 | 40.51 | 3402.64 | Warranty and Punchlist - punchlist and closeout labor
2026-04-21 | PRJ-PAY-ARM-2514-20260421 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1051 | 42.7 | 3864.42 | Closeout and O&M Documentation - field installation time
2026-04-21 | PRJ-PAY-ARM-2514-20260421 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1084 | 33.86 | 3284.21 | Rework and Quality Correction - coordination and layout
2026-04-21 | PRJ-PAY-ARM-2514-20260421 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1091 | 27.94 | 3115.46 | Project Management and Supervision - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2514-20260421 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1098 | 59.95 | 4256.4 | Engineering, BIM and Coordination - startup and checkout
2026-04-23 | AP-0005393 | AP | ARM-2514 | 02-510 | Controls Panels and Devices | V-2417 |  | 53.28 | 9590.43 | Controls Panels and Devices - fabricated material delivery
2026-04-25 | AP-0005390 | AP | ARM-2514 | 02-210 | Sheet Metal and Ductwork | V-2376 |  | 54.83 | 9869.66 | Sheet Metal and Ductwork - ductwork release
2026-04-25 | AP-0005400 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2495 |  | 26847.36 | 26847.36 | Electrical and Controls Subcontract - electrical coordination scope
2026-04-25 | AP-0005403 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2531 |  | 7252.37 | 7252.37 | Equipment Rental and Rigging - permit and inspection fees
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1035 | 56.21 | 3990.78 | Controls Programming and Checkout - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1042 | 40.42 | 3132.6 | Warranty and Punchlist - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 41.61 | 3495.59 | Closeout and O&M Documentation - field installation time
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1082 | 35.9 | 3248.96 | Rework and Quality Correction - coordination and layout
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1089 | 41.25 | 4331.32 | Project Management and Supervision - supervision and planning
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1096 | 26.49 | 2741.56 | Engineering, BIM and Coordination - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1009 | 40.73 | 2891.99 | Field Installation Labor - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2514-20260428 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 48.26 | 3740.31 | Startup, Testing and Commissioning - field installation time
2026-04-30 | PRJ-PAY-ARM-2514-20260430 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1040 | 43.58 | 3093.84 | Warranty and Punchlist - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2514-20260430 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 58.33 | 4520.72 | Closeout and O&M Documentation - field installation time
2026-04-30 | PRJ-PAY-ARM-2514-20260430 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1080 | 44.44 | 3733.16 | Rework and Quality Correction - coordination and layout
2026-04-30 | PRJ-PAY-ARM-2514-20260430 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1087 | 28.67 | 2823.78 | Project Management and Supervision - supervision and planning
2026-04-30 | PRJ-PAY-ARM-2514-20260430 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1094 | 39.03 | 3785.47 | Engineering, BIM and Coordination - startup and checkout
2026-04-30 | PRJ-PAY-ARM-2514-20260430 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1007 | 46.3 | 4792.28 | Field Installation Labor - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2514-20260430 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 53.77 | 3817.46 | Startup, Testing and Commissioning - field installation time
2026-05-05 | AP-0005408 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2253 |  | 98.11 | 17659.72 | Hydronic Piping and Valves - jobsite material replenishment
2026-05-05 | AP-0005420 | AP | ARM-2514 | 04-300 | Testing and Balancing Subcontract | V-2403 |  | 30391.83 | 30391.83 | Testing and Balancing Subcontract - rigging and specialty support
2026-05-05 | AP-0005424 | AP | ARM-2514 | 05-200 | Permits, Fees and Bonds | V-2450 |  | 4824.17 | 4824.17 | Permits, Fees and Bonds - freight and expediting
2026-05-06 | AP-0005415 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2355 |  | 72.81 | 13105.7 | Insulation and Specialty Material - fabricated material delivery
2026-05-07 | PRJ-PAY-ARM-2514-20260507 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1021 | 50.59 | 3591.78 | Startup, Testing and Commissioning - field installation time
2026-05-07 | PRJ-PAY-ARM-2514-20260507 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1028 | 46.63 | 3613.96 | Sheet Metal Fabrication Labor - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2514-20260507 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1035 | 40.92 | 3436.96 | Controls Programming and Checkout - supervision and planning
2026-05-07 | PRJ-PAY-ARM-2514-20260507 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1042 | 37.47 | 3390.72 | Warranty and Punchlist - startup and checkout
2026-05-07 | PRJ-PAY-ARM-2514-20260507 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1049 | 37 | 3589.04 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-07 | PRJ-PAY-ARM-2514-20260507 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1082 | 34.83 | 3605.16 | Rework and Quality Correction - field installation time
2026-05-07 | PRJ-PAY-ARM-2514-20260507 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1089 | 45.73 | 3612.31 | Project Management and Supervision - coordination and layout
2026-05-09 | AP-0005412 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2313 |  | 73.63 | 13252.93 | Hydronic Piping and Valves - ductwork release
2026-05-12 | AP-0005409 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2272 |  | 57.8 | 10403.87 | Insulation and Specialty Material - released equipment package
2026-05-12 | AP-0005421 | AP | ARM-2514 | 04-200 | Electrical and Controls Subcontract | V-2417 |  | 18990.64 | 18990.64 | Electrical and Controls Subcontract - trade partner progress billing
2026-05-12 | AP-0005425 | AP | ARM-2514 | 06-400 | Temporary Facilities and Protection | V-2464 |  | 7746.98 | 7746.98 | Temporary Facilities and Protection - small tools and field consumables
2026-05-13 | AP-0005416 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2369 |  | 42.72 | 7688.77 | Hydronic Piping and Valves - valves and piping lot
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1026 | 41.33 | 2934.76 | Sheet Metal Fabrication Labor - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1033 | 46.14 | 3576.16 | Controls Programming and Checkout - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1040 | 44.46 | 3734.34 | Warranty and Punchlist - startup and checkout
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1047 | 37.93 | 3432.98 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1080 | 39.26 | 3808.17 | Rework and Quality Correction - field installation time
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1087 | 33.46 | 3730.33 | Project Management and Supervision - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1094 | 47.24 | 3353.69 | Engineering, BIM and Coordination - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2514-20260514 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1007 | 42.81 | 3317.6 | Field Installation Labor - startup and checkout
2026-05-15 | AP-0005406 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2210 |  | 80.22 | 14440.19 | Hydronic Piping and Valves - valves and piping lot
2026-05-15 | AP-0005418 | AP | ARM-2514 | 04-100 | Insulation Subcontract | V-2376 |  | 23585.14 | 23585.14 | Insulation Subcontract - testing and balancing services
2026-05-15 | AP-0005422 | AP | ARM-2514 | 05-100 | Equipment Rental and Rigging | V-2424 |  | 3952.84 | 3952.84 | Equipment Rental and Rigging - rental and logistics
2026-05-16 | AP-0005413 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2327 |  | 72.13 | 12982.85 | Insulation and Specialty Material - jobsite material replenishment
2026-05-19 | AP-0005410 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2286 |  | 69.4 | 12492.22 | Hydronic Piping and Valves - fabricated material delivery
2026-05-19 | AP-0005426 | AP | ARM-2514 | 05-300 | Freight and Expediting | V-2477 |  | 8215.51 | 8215.51 | Freight and Expediting - rental and logistics
2026-05-20 | AP-0005417 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2383 |  | 62.65 | 11276.82 | Insulation and Specialty Material - ductwork release
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 03-400 | Controls Programming and Checkout |  | E-1031 | 42.57 | 3022.41 | Controls Programming and Checkout - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1038 | 55.94 | 4335.18 | Warranty and Punchlist - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1045 | 37.52 | 3151.56 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1052 | 39.22 | 3549.19 | Rework and Quality Correction - field installation time
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1085 | 40.74 | 4277.65 | Project Management and Supervision - coordination and layout
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1092 | 41.54 | 4299.8 | Engineering, BIM and Coordination - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1099 | 51.05 | 3624.27 | Field Installation Labor - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2514-20260521 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1013 | 44.46 | 3445.36 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-05-22 | AP-0005407 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2232 |  | 56.91 | 10244.44 | Insulation and Specialty Material - ductwork release
2026-05-22 | AP-0005419 | AP | ARM-2514 | 04-400 | Crane, Rigging and Specialty Trade | V-2389 |  | 19496.94 | 19496.94 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-05-22 | AP-0005423 | AP | ARM-2514 | 05-400 | Small Tools and Consumables | V-2438 |  | 7422.08 | 7422.08 | Small Tools and Consumables - permit and inspection fees
2026-05-23 | AP-0005414 | AP | ARM-2514 | 02-310 | Hydronic Piping and Valves | V-2341 |  | 46.78 | 8420.55 | Hydronic Piping and Valves - released equipment package
2026-05-25 | AP-0005411 | AP | ARM-2514 | 02-610 | Insulation and Specialty Material | V-2300 |  | 70.88 | 12759.06 | Insulation and Specialty Material - valves and piping lot
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 06-100 | Warranty and Punchlist |  | E-1036 | 44.21 | 3139.01 | Warranty and Punchlist - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1043 | 37.5 | 2906.1 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1050 | 39.29 | 3299.95 | Rework and Quality Correction - field installation time
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1083 | 30.45 | 2999.62 | Project Management and Supervision - coordination and layout
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1090 | 50.95 | 4941.75 | Engineering, BIM and Coordination - supervision and planning
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1097 | 29.43 | 3046.18 | Field Installation Labor - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 62.69 | 4451.21 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2514-20260528 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 49.51 | 3837.36 | Sheet Metal Fabrication Labor - field installation time
2026-05-31 | PRJ-PAY-ARM-2514-20260531 | PAY | ARM-2514 | 06-200 | Closeout and O&M Documentation |  | E-1041 | 50.2 | 3564.23 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2514-20260531 | PAY | ARM-2514 | 06-300 | Rework and Quality Correction |  | E-1048 | 53.53 | 4148.9 | Rework and Quality Correction - field installation time
2026-05-31 | PRJ-PAY-ARM-2514-20260531 | PAY | ARM-2514 | 01-100 | Project Management and Supervision |  | E-1081 | 43.96 | 4044.07 | Project Management and Supervision - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2514-20260531 | PAY | ARM-2514 | 01-200 | Engineering, BIM and Coordination |  | E-1088 | 42.71 | 3865.69 | Engineering, BIM and Coordination - supervision and planning
2026-05-31 | PRJ-PAY-ARM-2514-20260531 | PAY | ARM-2514 | 03-100 | Field Installation Labor |  | E-1095 | 31.24 | 3030.73 | Field Installation Labor - startup and checkout
2026-05-31 | PRJ-PAY-ARM-2514-20260531 | PAY | ARM-2514 | 03-200 | Startup, Testing and Commissioning |  | E-1008 | 39.21 | 4058.72 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2514-20260531 | PAY | ARM-2514 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 41.12 | 2919.83 | Sheet Metal Fabrication Labor - field installation time
2025-07-03 | AP-0005450 | AP | ARM-2518 | 02-310 | Hydronic Piping and Valves | V-2405 |  | 37.79 | 6802.67 | Hydronic Piping and Valves - released equipment package
2025-07-03 | AP-0005451 | AP | ARM-2518 | 04-100 | Insulation Subcontract | V-2417 |  | 4346.15 | 4346.15 | Insulation Subcontract - trade partner progress billing
2025-07-03 | AP-0005452 | AP | ARM-2518 | 05-400 | Small Tools and Consumables | V-2429 |  | 1511.71 | 1511.71 | Small Tools and Consumables - rental and logistics
2025-07-07 | PRJ-PAY-ARM-2518-20250707 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1007 | 5.54 | 437.66 | Project Management and Supervision - field installation time
2025-07-07 | PRJ-PAY-ARM-2518-20250707 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 4.89 | 379.21 | Engineering, BIM and Coordination - coordination and layout
2025-07-07 | PRJ-PAY-ARM-2518-20250707 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1023 | 5.17 | 434 | Field Installation Labor - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2518-20250714 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 5.2 | 368.87 | Engineering, BIM and Coordination - coordination and layout
2025-07-14 | PRJ-PAY-ARM-2518-20250714 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1021 | 7.02 | 543.82 | Field Installation Labor - supervision and planning
2025-07-14 | PRJ-PAY-ARM-2518-20250714 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 5.53 | 464.49 | Startup, Testing and Commissioning - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2518-20250721 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1019 | 7.35 | 521.5 | Field Installation Labor - supervision and planning
2025-07-21 | PRJ-PAY-ARM-2518-20250721 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 6.44 | 499 | Startup, Testing and Commissioning - startup and checkout
2025-07-21 | PRJ-PAY-ARM-2518-20250721 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 4.37 | 366.86 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2518-20250728 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 6.59 | 467.69 | Startup, Testing and Commissioning - startup and checkout
2025-07-28 | PRJ-PAY-ARM-2518-20250728 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 5.03 | 390.16 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-07-28 | PRJ-PAY-ARM-2518-20250728 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1038 | 4.93 | 414.21 | Controls Programming and Checkout - field installation time
2025-07-31 | PRJ-PAY-ARM-2518-20250731 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 5.87 | 417.04 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-07-31 | PRJ-PAY-ARM-2518-20250731 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1036 | 5.32 | 411.99 | Controls Programming and Checkout - field installation time
2025-07-31 | PRJ-PAY-ARM-2518-20250731 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1043 | 3.67 | 308.25 | Warranty and Punchlist - coordination and layout
2025-08-06 | AP-0005453 | AP | ARM-2518 | 02-410 | Plumbing Fixtures and Piping | V-2441 |  | 94.27 | 16969.35 | Plumbing Fixtures and Piping - fabricated material delivery
2025-08-06 | AP-0005454 | AP | ARM-2518 | 04-200 | Electrical and Controls Subcontract | V-2453 |  | 9824.36 | 9824.36 | Electrical and Controls Subcontract - insulation progress invoice
2025-08-06 | AP-0005455 | AP | ARM-2518 | 06-400 | Temporary Facilities and Protection | V-2465 |  | 3125.93 | 3125.93 | Temporary Facilities and Protection - permit and inspection fees
2025-08-07 | PRJ-PAY-ARM-2518-20250807 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 17.1 | 1214.25 | Engineering, BIM and Coordination - field installation time
2025-08-07 | PRJ-PAY-ARM-2518-20250807 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1016 | 12.35 | 956.88 | Field Installation Labor - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2518-20250807 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 13.79 | 1158.04 | Startup, Testing and Commissioning - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2518-20250814 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1014 | 15.68 | 1112.96 | Field Installation Labor - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2518-20250814 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 17.92 | 1389.1 | Startup, Testing and Commissioning - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2518-20250814 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 10.14 | 851.72 | Sheet Metal Fabrication Labor - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2518-20250821 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 10.54 | 748.19 | Startup, Testing and Commissioning - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2518-20250821 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 15.17 | 1175.83 | Sheet Metal Fabrication Labor - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2518-20250821 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1034 | 13.7 | 1151.02 | Controls Programming and Checkout - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2518-20250828 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 13.67 | 970.54 | Sheet Metal Fabrication Labor - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2518-20250828 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1032 | 10 | 775.36 | Controls Programming and Checkout - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2518-20250828 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1039 | 11.94 | 1003.32 | Warranty and Punchlist - field installation time
2025-08-31 | PRJ-PAY-ARM-2518-20250831 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1030 | 14.64 | 1039.53 | Controls Programming and Checkout - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2518-20250831 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1037 | 10.97 | 850.49 | Warranty and Punchlist - field installation time
2025-08-31 | PRJ-PAY-ARM-2518-20250831 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 9.36 | 785.87 | Closeout and O&M Documentation - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2518-20250907 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1009 | 32.76 | 2325.8 | Field Installation Labor - field installation time
2025-09-07 | PRJ-PAY-ARM-2518-20250907 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 25.27 | 1958.62 | Startup, Testing and Commissioning - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2518-20250907 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 17.42 | 1463.67 | Sheet Metal Fabrication Labor - supervision and planning
2025-09-09 | AP-0005456 | AP | ARM-2518 | 02-510 | Controls Panels and Devices | V-2479 |  | 61.89 | 11139.61 | Controls Panels and Devices - valves and piping lot
2025-09-09 | AP-0005458 | AP | ARM-2518 | 04-300 | Testing and Balancing Subcontract | V-2503 |  | 17131.88 | 17131.88 | Testing and Balancing Subcontract - testing and balancing services
2025-09-09 | AP-0005459 | AP | ARM-2518 | 05-100 | Equipment Rental and Rigging | V-2515 |  | 6703.79 | 6703.79 | Equipment Rental and Rigging - freight and expediting
2025-09-14 | PRJ-PAY-ARM-2518-20250914 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 20.13 | 1429.08 | Startup, Testing and Commissioning - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2518-20250914 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 22.47 | 1741.16 | Sheet Metal Fabrication Labor - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2518-20250914 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1030 | 25 | 2100.11 | Controls Programming and Checkout - startup and checkout
2025-09-16 | AP-0005457 | AP | ARM-2518 | 02-210 | Sheet Metal and Ductwork | V-2493 |  | 78.81 | 14185.78 | Sheet Metal and Ductwork - ductwork release
2025-09-21 | PRJ-PAY-ARM-2518-20250921 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 20.35 | 1445.04 | Sheet Metal Fabrication Labor - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2518-20250921 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1028 | 16.69 | 1293.55 | Controls Programming and Checkout - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2518-20250921 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1035 | 23.49 | 1973.33 | Warranty and Punchlist - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2518-20250928 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1026 | 22.59 | 1604.07 | Controls Programming and Checkout - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2518-20250928 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1033 | 19.08 | 1478.77 | Warranty and Punchlist - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2518-20250928 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 17.9 | 1503.38 | Closeout and O&M Documentation - field installation time
2025-09-30 | PRJ-PAY-ARM-2518-20250930 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1031 | 23.28 | 1652.87 | Warranty and Punchlist - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2518-20250930 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 21.72 | 1683.34 | Closeout and O&M Documentation - field installation time
2025-09-30 | PRJ-PAY-ARM-2518-20250930 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1045 | 19.91 | 1672.6 | Rework and Quality Correction - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2518-20251007 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 29.79 | 2114.84 | Startup, Testing and Commissioning - field installation time
2025-10-07 | PRJ-PAY-ARM-2518-20251007 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 28.69 | 2223.48 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2518-20251007 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1026 | 22.87 | 1921.39 | Controls Programming and Checkout - supervision and planning
2025-10-12 | AP-0005460 | AP | ARM-2518 | 02-610 | Insulation and Specialty Material | V-2529 |  | 52.16 | 9388.44 | Insulation and Specialty Material - ductwork release
2025-10-12 | AP-0005463 | AP | ARM-2518 | 04-400 | Crane, Rigging and Specialty Trade | V-2210 |  | 19342.63 | 19342.63 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-10-12 | AP-0005464 | AP | ARM-2518 | 05-200 | Permits, Fees and Bonds | V-2231 |  | 7033.68 | 7033.68 | Permits, Fees and Bonds - small tools and field consumables
2025-10-14 | PRJ-PAY-ARM-2518-20251014 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 28.4 | 2016.14 | Sheet Metal Fabrication Labor - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2518-20251014 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1024 | 22.36 | 1733.22 | Controls Programming and Checkout - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2518-20251014 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1031 | 21.99 | 1847.09 | Warranty and Punchlist - startup and checkout
2025-10-19 | AP-0005461 | AP | ARM-2518 | 02-310 | Hydronic Piping and Valves | V-2021 |  | 51.83 | 9329.43 | Hydronic Piping and Valves - jobsite material replenishment
2025-10-21 | PRJ-PAY-ARM-2518-20251021 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1022 | 32.51 | 2308.18 | Controls Programming and Checkout - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2518-20251021 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1029 | 20.46 | 1585.68 | Warranty and Punchlist - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2518-20251021 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 18.49 | 1553.3 | Closeout and O&M Documentation - punchlist and closeout labor
2025-10-25 | AP-0005462 | AP | ARM-2518 | 02-610 | Insulation and Specialty Material | V-2094 |  | 71.85 | 12933.71 | Insulation and Specialty Material - released equipment package
2025-10-28 | PRJ-PAY-ARM-2518-20251028 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1027 | 33.65 | 2389.5 | Warranty and Punchlist - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2518-20251028 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 25.39 | 1967.48 | Closeout and O&M Documentation - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2518-20251028 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1041 | 18.95 | 1592.1 | Rework and Quality Correction - field installation time
2025-10-31 | PRJ-PAY-ARM-2518-20251031 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 28.63 | 2032.84 | Closeout and O&M Documentation - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2518-20251031 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1039 | 34.6 | 2681.69 | Rework and Quality Correction - field installation time
2025-10-31 | PRJ-PAY-ARM-2518-20251031 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1046 | 20.94 | 1926.23 | Project Management and Supervision - coordination and layout
2025-11-05 | AP-0005467 | AP | ARM-2518 | 02-110 | Major HVAC Equipment | V-2284 |  | 99.81 | 17965.02 | Major HVAC Equipment - fabricated material delivery
2025-11-07 | PRJ-PAY-ARM-2518-20251107 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 26.77 | 1900.39 | Sheet Metal Fabrication Labor - field installation time
2025-11-07 | PRJ-PAY-ARM-2518-20251107 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1020 | 30.45 | 2359.74 | Controls Programming and Checkout - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2518-20251107 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1027 | 28.28 | 2375.52 | Warranty and Punchlist - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2518-20251114 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1018 | 34.33 | 2437.19 | Controls Programming and Checkout - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2518-20251114 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1025 | 23.27 | 1803.67 | Warranty and Punchlist - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2518-20251114 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 26.4 | 2217.77 | Closeout and O&M Documentation - startup and checkout
2025-11-15 | AP-0005465 | AP | ARM-2518 | 02-110 | Major HVAC Equipment | V-2250 |  | 52.82 | 9506.83 | Major HVAC Equipment - jobsite material replenishment
2025-11-15 | AP-0005468 | AP | ARM-2518 | 04-100 | Insulation Subcontract | V-2293 |  | 24479.34 | 24479.34 | Insulation Subcontract - rigging and specialty support
2025-11-15 | AP-0005469 | AP | ARM-2518 | 05-300 | Freight and Expediting | V-2305 |  | 7450.24 | 7450.24 | Freight and Expediting - rental and logistics
2025-11-21 | PRJ-PAY-ARM-2518-20251121 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1023 | 33.74 | 2395.85 | Warranty and Punchlist - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2518-20251121 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 25.47 | 1974.3 | Closeout and O&M Documentation - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2518-20251121 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1037 | 31.95 | 2683.6 | Rework and Quality Correction - punchlist and closeout labor
2025-11-22 | AP-0005466 | AP | ARM-2518 | 02-410 | Plumbing Fixtures and Piping | V-2270 |  | 72.07 | 12972.28 | Plumbing Fixtures and Piping - released equipment package
2025-11-28 | PRJ-PAY-ARM-2518-20251128 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 40.46 | 2872.68 | Closeout and O&M Documentation - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2518-20251128 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1035 | 29.36 | 2275.68 | Rework and Quality Correction - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2518-20251128 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1042 | 29.63 | 2725.51 | Project Management and Supervision - field installation time
2025-11-30 | PRJ-PAY-ARM-2518-20251130 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1033 | 42.13 | 2991.22 | Rework and Quality Correction - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2518-20251130 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1040 | 24.82 | 2122 | Project Management and Supervision - field installation time
2025-11-30 | PRJ-PAY-ARM-2518-20251130 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 36.33 | 3051.74 | Engineering, BIM and Coordination - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2518-20251207 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1013 | 22.54 | 1600.12 | Controls Programming and Checkout - field installation time
2025-12-07 | PRJ-PAY-ARM-2518-20251207 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1021 | 27.69 | 2146.05 | Warranty and Punchlist - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2518-20251207 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 30.37 | 2550.99 | Closeout and O&M Documentation - supervision and planning
2025-12-08 | AP-0005472 | AP | ARM-2518 | 02-210 | Sheet Metal and Ductwork | V-2346 |  | 66.26 | 11926.7 | Sheet Metal and Ductwork - valves and piping lot
2025-12-14 | PRJ-PAY-ARM-2518-20251214 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1019 | 33.49 | 2377.86 | Warranty and Punchlist - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2518-20251214 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 23.98 | 1858.81 | Closeout and O&M Documentation - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2518-20251214 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1033 | 31.44 | 2640.74 | Rework and Quality Correction - startup and checkout
2025-12-18 | AP-0005470 | AP | ARM-2518 | 02-210 | Sheet Metal and Ductwork | V-2319 |  | 56.7 | 10205.78 | Sheet Metal and Ductwork - released equipment package
2025-12-18 | AP-0005473 | AP | ARM-2518 | 04-200 | Electrical and Controls Subcontract | V-2355 |  | 23475.51 | 23475.51 | Electrical and Controls Subcontract - trade partner progress billing
2025-12-18 | AP-0005474 | AP | ARM-2518 | 05-400 | Small Tools and Consumables | V-2367 |  | 9603.61 | 9603.61 | Small Tools and Consumables - permit and inspection fees
2025-12-21 | PRJ-PAY-ARM-2518-20251221 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 35.38 | 2512.18 | Closeout and O&M Documentation - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2518-20251221 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1031 | 31.91 | 2472.92 | Rework and Quality Correction - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2518-20251221 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1038 | 29.26 | 2691.92 | Project Management and Supervision - punchlist and closeout labor
2025-12-25 | AP-0005471 | AP | ARM-2518 | 02-510 | Controls Panels and Devices | V-2332 |  | 78.6 | 14147.86 | Controls Panels and Devices - fabricated material delivery
2025-12-28 | PRJ-PAY-ARM-2518-20251228 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1029 | 37.69 | 2676.11 | Rework and Quality Correction - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2518-20251228 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1036 | 23.48 | 2007.28 | Project Management and Supervision - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2518-20251228 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 39.02 | 3277.45 | Engineering, BIM and Coordination - field installation time
2025-12-31 | PRJ-PAY-ARM-2518-20251231 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1034 | 28.12 | 2221.53 | Project Management and Supervision - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2518-20251231 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 28.23 | 2187.62 | Engineering, BIM and Coordination - field installation time
2025-12-31 | PRJ-PAY-ARM-2518-20251231 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1048 | 36.41 | 3058.76 | Field Installation Labor - coordination and layout
2026-01-04 | AP-0005476 | AP | ARM-2518 | 02-610 | Insulation and Specialty Material | V-2395 |  | 80.43 | 14477.78 | Insulation and Specialty Material - valves and piping lot
2026-01-07 | PRJ-PAY-ARM-2518-20260107 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1014 | 32.42 | 2301.71 | Warranty and Punchlist - field installation time
2026-01-07 | PRJ-PAY-ARM-2518-20260107 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 31.57 | 2446.75 | Closeout and O&M Documentation - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2518-20260107 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1029 | 26.38 | 2215.85 | Rework and Quality Correction - supervision and planning
2026-01-11 | AP-0005477 | AP | ARM-2518 | 02-310 | Hydronic Piping and Valves | V-2408 |  | 79.35 | 14283.37 | Hydronic Piping and Valves - ductwork release
2026-01-14 | PRJ-PAY-ARM-2518-20260114 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 43.03 | 3055.36 | Closeout and O&M Documentation - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2518-20260114 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1027 | 23.6 | 1829 | Rework and Quality Correction - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2518-20260114 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1034 | 31.41 | 2889.67 | Project Management and Supervision - startup and checkout
2026-01-21 | AP-0005475 | AP | ARM-2518 | 02-310 | Hydronic Piping and Valves | V-2381 |  | 58.44 | 10518.61 | Hydronic Piping and Valves - fabricated material delivery
2026-01-21 | AP-0005478 | AP | ARM-2518 | 04-300 | Testing and Balancing Subcontract | V-2417 |  | 25095.4 | 25095.4 | Testing and Balancing Subcontract - insulation progress invoice
2026-01-21 | AP-0005479 | AP | ARM-2518 | 06-400 | Temporary Facilities and Protection | V-2429 |  | 8728.83 | 8728.83 | Temporary Facilities and Protection - freight and expediting
2026-01-21 | PRJ-PAY-ARM-2518-20260121 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1025 | 41.87 | 2972.93 | Rework and Quality Correction - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2518-20260121 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1032 | 24.78 | 2118.53 | Project Management and Supervision - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2518-20260121 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 35.36 | 2969.97 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2518-20260128 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1030 | 34.3 | 2709.97 | Project Management and Supervision - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2518-20260128 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 36.52 | 2830.22 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2518-20260128 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1044 | 24.07 | 2022.1 | Field Installation Labor - field installation time
2026-01-31 | PRJ-PAY-ARM-2518-20260131 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 25.53 | 1812.76 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2518-20260131 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1042 | 35.47 | 2748.87 | Field Installation Labor - field installation time
2026-01-31 | PRJ-PAY-ARM-2518-20260131 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 25.88 | 2173.86 | Startup, Testing and Commissioning - coordination and layout
2026-02-07 | AP-0005481 | AP | ARM-2518 | 02-110 | Major HVAC Equipment | V-2455 |  | 60.59 | 10906.43 | Major HVAC Equipment - ductwork release
2026-02-07 | PRJ-PAY-ARM-2518-20260207 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 46.8 | 3323.1 | Closeout and O&M Documentation - field installation time
2026-02-07 | PRJ-PAY-ARM-2518-20260207 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1023 | 42 | 3255.24 | Rework and Quality Correction - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2518-20260207 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1030 | 40.53 | 3728.61 | Project Management and Supervision - supervision and planning
2026-02-14 | AP-0005482 | AP | ARM-2518 | 02-410 | Plumbing Fixtures and Piping | V-2469 |  | 57.65 | 10377.65 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-02-14 | PRJ-PAY-ARM-2518-20260214 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1021 | 52.11 | 3699.59 | Rework and Quality Correction - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2518-20260214 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1028 | 34.56 | 2954.79 | Project Management and Supervision - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2518-20260214 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 48.02 | 4033.61 | Engineering, BIM and Coordination - startup and checkout
2026-02-21 | AP-0005483 | AP | ARM-2518 | 02-110 | Major HVAC Equipment | V-2483 |  | 46.34 | 8341.52 | Major HVAC Equipment - released equipment package
2026-02-21 | PRJ-PAY-ARM-2518-20260221 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1026 | 40.9 | 3230.91 | Project Management and Supervision - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2518-20260221 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 37.92 | 2938.8 | Engineering, BIM and Coordination - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2518-20260221 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1040 | 45.91 | 3856.51 | Field Installation Labor - punchlist and closeout labor
2026-02-24 | AP-0005480 | AP | ARM-2518 | 02-410 | Plumbing Fixtures and Piping | V-2441 |  | 83.48 | 15025.75 | Plumbing Fixtures and Piping - valves and piping lot
2026-02-24 | AP-0005484 | AP | ARM-2518 | 04-400 | Crane, Rigging and Specialty Trade | V-2490 |  | 25850.78 | 25850.78 | Crane, Rigging and Specialty Trade - testing and balancing services
2026-02-24 | AP-0005485 | AP | ARM-2518 | 05-100 | Equipment Rental and Rigging | V-2502 |  | 8225.24 | 8225.24 | Equipment Rental and Rigging - small tools and field consumables
2026-02-28 | PRJ-PAY-ARM-2518-20260228 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 36.65 | 2602.34 | Engineering, BIM and Coordination - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2518-20260228 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1038 | 38.28 | 2966.38 | Field Installation Labor - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2518-20260228 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 40.02 | 3361.33 | Startup, Testing and Commissioning - field installation time
2026-03-03 | AP-0005486 | AP | ARM-2518 | 02-510 | Controls Panels and Devices | V-2515 |  | 60.89 | 10960.42 | Controls Panels and Devices - ductwork release
2026-03-03 | AP-0005489 | AP | ARM-2518 | 04-100 | Insulation Subcontract | V-2047 |  | 29245.79 | 29245.79 | Insulation Subcontract - electrical coordination scope
2026-03-03 | AP-0005490 | AP | ARM-2518 | 05-200 | Permits, Fees and Bonds | V-2208 |  | 5560.22 | 5560.22 | Permits, Fees and Bonds - rental and logistics
2026-03-07 | PRJ-PAY-ARM-2518-20260307 | PAY | ARM-2518 | 06-300 | Rework and Quality Correction |  | E-1016 | 47.6 | 3379.7 | Rework and Quality Correction - field installation time
2026-03-07 | PRJ-PAY-ARM-2518-20260307 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1024 | 39.92 | 3413.1 | Project Management and Supervision - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2518-20260307 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 36.2 | 3040.6 | Engineering, BIM and Coordination - supervision and planning
2026-03-10 | AP-0005487 | AP | ARM-2518 | 02-210 | Sheet Metal and Ductwork | V-2529 |  | 73.67 | 13259.86 | Sheet Metal and Ductwork - jobsite material replenishment
2026-03-10 | AP-0005491 | AP | ARM-2518 | 06-400 | Temporary Facilities and Protection | V-2231 |  | 5883.79 | 5883.79 | Temporary Facilities and Protection - permit and inspection fees
2026-03-14 | PRJ-PAY-ARM-2518-20260314 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1022 | 33.24 | 2626.08 | Project Management and Supervision - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2518-20260314 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 40.75 | 3158.23 | Engineering, BIM and Coordination - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2518-20260314 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1036 | 40.96 | 3440.23 | Field Installation Labor - startup and checkout
2026-03-17 | AP-0005488 | AP | ARM-2518 | 02-510 | Controls Panels and Devices | V-2021 |  | 105.63 | 19012.63 | Controls Panels and Devices - released equipment package
2026-03-21 | PRJ-PAY-ARM-2518-20260321 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 36.21 | 2571.15 | Engineering, BIM and Coordination - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2518-20260321 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1034 | 35.9 | 2782.39 | Field Installation Labor - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2518-20260321 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 34.08 | 2862.48 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2518-20260328 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1032 | 36.15 | 2566.83 | Field Installation Labor - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2518-20260328 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 32.33 | 2505.76 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2518-20260328 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 31.7 | 2662.48 | Sheet Metal Fabrication Labor - field installation time
2026-03-31 | PRJ-PAY-ARM-2518-20260331 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 36.66 | 2602.85 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2518-20260331 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 35.64 | 2762.28 | Sheet Metal Fabrication Labor - field installation time
2026-03-31 | PRJ-PAY-ARM-2518-20260331 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1051 | 34.03 | 2858.75 | Controls Programming and Checkout - coordination and layout
2026-04-03 | AP-0005495 | AP | ARM-2518 | 02-310 | Hydronic Piping and Valves | V-2296 |  | 60.78 | 10940.93 | Hydronic Piping and Valves - valves and piping lot
2026-04-06 | AP-0005492 | AP | ARM-2518 | 02-610 | Insulation and Specialty Material | V-2246 |  | 74.44 | 13399.96 | Insulation and Specialty Material - jobsite material replenishment
2026-04-06 | AP-0005496 | AP | ARM-2518 | 04-200 | Electrical and Controls Subcontract | V-2303 |  | 31704.13 | 31704.13 | Electrical and Controls Subcontract - rigging and specialty support
2026-04-06 | AP-0005497 | AP | ARM-2518 | 05-300 | Freight and Expediting | V-2315 |  | 6096.39 | 6096.39 | Freight and Expediting - permit and inspection fees
2026-04-07 | PRJ-PAY-ARM-2518-20260407 | PAY | ARM-2518 | 01-100 | Project Management and Supervision |  | E-1018 | 40.11 | 3169.01 | Project Management and Supervision - field installation time
2026-04-07 | PRJ-PAY-ARM-2518-20260407 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 53.12 | 4116.89 | Engineering, BIM and Coordination - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2518-20260407 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1032 | 39.47 | 3315.8 | Field Installation Labor - supervision and planning
2026-04-13 | AP-0005493 | AP | ARM-2518 | 02-310 | Hydronic Piping and Valves | V-2267 |  | 93.11 | 16760.59 | Hydronic Piping and Valves - released equipment package
2026-04-13 | AP-0005498 | AP | ARM-2518 | 05-100 | Equipment Rental and Rigging | V-2329 |  | 5432.39 | 5432.39 | Equipment Rental and Rigging - freight and expediting
2026-04-14 | PRJ-PAY-ARM-2518-20260414 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 42.29 | 3002.73 | Engineering, BIM and Coordination - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2518-20260414 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1030 | 47.6 | 3689.35 | Field Installation Labor - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2518-20260414 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 32.74 | 2750.54 | Startup, Testing and Commissioning - startup and checkout
2026-04-20 | AP-0005494 | AP | ARM-2518 | 02-610 | Insulation and Specialty Material | V-2282 |  | 59.88 | 10778.01 | Insulation and Specialty Material - fabricated material delivery
2026-04-21 | PRJ-PAY-ARM-2518-20260421 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1028 | 40.96 | 2908.49 | Field Installation Labor - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2518-20260421 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 43.15 | 3344.04 | Startup, Testing and Commissioning - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2518-20260421 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 31.4 | 2637.34 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2518-20260428 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 52.32 | 3715.06 | Startup, Testing and Commissioning - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2518-20260428 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 34.95 | 2708.86 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2518-20260428 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1047 | 36.04 | 3027.73 | Controls Programming and Checkout - field installation time
2026-04-30 | PRJ-PAY-ARM-2518-20260430 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 50.14 | 3559.67 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2518-20260430 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1045 | 46.83 | 3629.17 | Controls Programming and Checkout - field installation time
2026-04-30 | PRJ-PAY-ARM-2518-20260430 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1052 | 40.75 | 3422.62 | Warranty and Punchlist - coordination and layout
2026-05-06 | AP-0005502 | AP | ARM-2518 | 02-410 | Plumbing Fixtures and Piping | V-2383 |  | 82.56 | 14860.7 | Plumbing Fixtures and Piping - ductwork release
2026-05-07 | PRJ-PAY-ARM-2518-20260507 | PAY | ARM-2518 | 01-200 | Engineering, BIM and Coordination |  | E-1019 | 49.07 | 3483.8 | Engineering, BIM and Coordination - field installation time
2026-05-07 | PRJ-PAY-ARM-2518-20260507 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1026 | 42 | 3255.03 | Field Installation Labor - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2518-20260507 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 41.21 | 3461.76 | Startup, Testing and Commissioning - supervision and planning
2026-05-09 | AP-0005499 | AP | ARM-2518 | 02-110 | Major HVAC Equipment | V-2341 |  | 42.41 | 7633.86 | Major HVAC Equipment - released equipment package
2026-05-09 | AP-0005504 | AP | ARM-2518 | 04-300 | Testing and Balancing Subcontract | V-2402 |  | 24425.93 | 24425.93 | Testing and Balancing Subcontract - trade partner progress billing
2026-05-09 | AP-0005506 | AP | ARM-2518 | 05-400 | Small Tools and Consumables | V-2426 |  | 5160.89 | 5160.89 | Small Tools and Consumables - freight and expediting
2026-05-13 | AP-0005503 | AP | ARM-2518 | 02-110 | Major HVAC Equipment | V-2396 |  | 68.72 | 12370.26 | Major HVAC Equipment - jobsite material replenishment
2026-05-14 | PRJ-PAY-ARM-2518-20260514 | PAY | ARM-2518 | 03-100 | Field Installation Labor |  | E-1024 | 39.61 | 2812.19 | Field Installation Labor - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2518-20260514 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1031 | 40.32 | 3125.16 | Startup, Testing and Commissioning - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2518-20260514 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 43.64 | 3666.12 | Sheet Metal Fabrication Labor - startup and checkout
2026-05-16 | AP-0005500 | AP | ARM-2518 | 02-410 | Plumbing Fixtures and Piping | V-2355 |  | 60.48 | 10885.74 | Plumbing Fixtures and Piping - fabricated material delivery
2026-05-16 | AP-0005505 | AP | ARM-2518 | 04-200 | Electrical and Controls Subcontract | V-2415 |  | 11892.37 | 11892.37 | Electrical and Controls Subcontract - insulation progress invoice
2026-05-16 | AP-0005507 | AP | ARM-2518 | 05-200 | Permits, Fees and Bonds | V-2439 |  | 5892.51 | 5892.51 | Permits, Fees and Bonds - small tools and field consumables
2026-05-21 | PRJ-PAY-ARM-2518-20260521 | PAY | ARM-2518 | 03-200 | Startup, Testing and Commissioning |  | E-1029 | 55.55 | 3944.35 | Startup, Testing and Commissioning - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2518-20260521 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1036 | 33.66 | 2608.73 | Sheet Metal Fabrication Labor - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2518-20260521 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1043 | 43.54 | 3657.26 | Controls Programming and Checkout - punchlist and closeout labor
2026-05-23 | AP-0005501 | AP | ARM-2518 | 02-110 | Major HVAC Equipment | V-2369 |  | 79.19 | 14253.59 | Major HVAC Equipment - valves and piping lot
2026-05-28 | PRJ-PAY-ARM-2518-20260528 | PAY | ARM-2518 | 03-300 | Sheet Metal Fabrication Labor |  | E-1034 | 46.04 | 3268.64 | Sheet Metal Fabrication Labor - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2518-20260528 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1041 | 50.65 | 3925.28 | Controls Programming and Checkout - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2518-20260528 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1048 | 50.83 | 4269.33 | Warranty and Punchlist - field installation time
2026-05-31 | PRJ-PAY-ARM-2518-20260531 | PAY | ARM-2518 | 03-400 | Controls Programming and Checkout |  | E-1039 | 47.61 | 3380.38 | Controls Programming and Checkout - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2518-20260531 | PAY | ARM-2518 | 06-100 | Warranty and Punchlist |  | E-1046 | 57.56 | 4460.7 | Warranty and Punchlist - field installation time
2026-05-31 | PRJ-PAY-ARM-2518-20260531 | PAY | ARM-2518 | 06-200 | Closeout and O&M Documentation |  | E-1053 | 52.01 | 4369.2 | Closeout and O&M Documentation - coordination and layout
2025-08-03 | AP-0005517 | AP | ARM-2522 | 02-310 | Hydronic Piping and Valves | V-2014 |  | 48.87 | 8796.04 | Hydronic Piping and Valves - released equipment package
2025-08-03 | AP-0005518 | AP | ARM-2522 | 04-100 | Insulation Subcontract | V-2047 |  | 5619.69 | 5619.69 | Insulation Subcontract - trade partner progress billing
2025-08-03 | AP-0005519 | AP | ARM-2522 | 05-400 | Small Tools and Consumables | V-2208 |  | 1954.69 | 1954.69 | Small Tools and Consumables - rental and logistics
2025-08-07 | PRJ-PAY-ARM-2522-20250807 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1007 | 7.35 | 580.84 | Project Management and Supervision - field installation time
2025-08-07 | PRJ-PAY-ARM-2522-20250807 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 5.43 | 421.03 | Engineering, BIM and Coordination - coordination and layout
2025-08-07 | PRJ-PAY-ARM-2522-20250807 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1023 | 7.33 | 615.54 | Field Installation Labor - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2522-20250814 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 6.72 | 476.99 | Engineering, BIM and Coordination - coordination and layout
2025-08-14 | PRJ-PAY-ARM-2522-20250814 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1021 | 8.37 | 648.3 | Field Installation Labor - supervision and planning
2025-08-14 | PRJ-PAY-ARM-2522-20250814 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 7.8 | 655.44 | Startup, Testing and Commissioning - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2522-20250821 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1019 | 6.98 | 495.25 | Field Installation Labor - supervision and planning
2025-08-21 | PRJ-PAY-ARM-2522-20250821 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 7.45 | 577.26 | Startup, Testing and Commissioning - startup and checkout
2025-08-21 | PRJ-PAY-ARM-2522-20250821 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 8.59 | 721.39 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2522-20250828 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 7.91 | 561.8 | Startup, Testing and Commissioning - startup and checkout
2025-08-28 | PRJ-PAY-ARM-2522-20250828 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 7.84 | 607.39 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-08-28 | PRJ-PAY-ARM-2522-20250828 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1038 | 5.66 | 475.61 | Controls Programming and Checkout - field installation time
2025-08-31 | PRJ-PAY-ARM-2522-20250831 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 6.65 | 471.81 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-08-31 | PRJ-PAY-ARM-2522-20250831 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1036 | 5.74 | 445.19 | Controls Programming and Checkout - field installation time
2025-08-31 | PRJ-PAY-ARM-2522-20250831 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1043 | 6.59 | 553.53 | Warranty and Punchlist - coordination and layout
2025-09-06 | AP-0005520 | AP | ARM-2522 | 02-410 | Plumbing Fixtures and Piping | V-2231 |  | 56.29 | 10132.05 | Plumbing Fixtures and Piping - fabricated material delivery
2025-09-06 | AP-0005522 | AP | ARM-2522 | 04-200 | Electrical and Controls Subcontract | V-2265 |  | 12846.61 | 12846.61 | Electrical and Controls Subcontract - insulation progress invoice
2025-09-06 | AP-0005523 | AP | ARM-2522 | 06-400 | Temporary Facilities and Protection | V-2279 |  | 4087.55 | 4087.55 | Temporary Facilities and Protection - permit and inspection fees
2025-09-07 | PRJ-PAY-ARM-2522-20250907 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 22.43 | 1592.48 | Engineering, BIM and Coordination - field installation time
2025-09-07 | PRJ-PAY-ARM-2522-20250907 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1016 | 14.95 | 1158.78 | Field Installation Labor - coordination and layout
2025-09-07 | PRJ-PAY-ARM-2522-20250907 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 19.07 | 1602.06 | Startup, Testing and Commissioning - supervision and planning
2025-09-13 | AP-0005521 | AP | ARM-2522 | 02-110 | Major HVAC Equipment | V-2250 |  | 66.99 | 12057.54 | Major HVAC Equipment - valves and piping lot
2025-09-14 | PRJ-PAY-ARM-2522-20250914 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1014 | 24.29 | 1724.63 | Field Installation Labor - coordination and layout
2025-09-14 | PRJ-PAY-ARM-2522-20250914 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 13.81 | 1070.19 | Startup, Testing and Commissioning - supervision and planning
2025-09-14 | PRJ-PAY-ARM-2522-20250914 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 18.94 | 1590.68 | Sheet Metal Fabrication Labor - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2522-20250921 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 18.38 | 1304.74 | Startup, Testing and Commissioning - supervision and planning
2025-09-21 | PRJ-PAY-ARM-2522-20250921 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 16.2 | 1255.7 | Sheet Metal Fabrication Labor - startup and checkout
2025-09-21 | PRJ-PAY-ARM-2522-20250921 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1034 | 17.39 | 1460.57 | Controls Programming and Checkout - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2522-20250928 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 15.66 | 1112.06 | Sheet Metal Fabrication Labor - startup and checkout
2025-09-28 | PRJ-PAY-ARM-2522-20250928 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1032 | 12.3 | 953.52 | Controls Programming and Checkout - punchlist and closeout labor
2025-09-28 | PRJ-PAY-ARM-2522-20250928 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1039 | 18.21 | 1529.38 | Warranty and Punchlist - field installation time
2025-09-30 | PRJ-PAY-ARM-2522-20250930 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1030 | 14.7 | 1043.36 | Controls Programming and Checkout - punchlist and closeout labor
2025-09-30 | PRJ-PAY-ARM-2522-20250930 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1037 | 17.23 | 1335.38 | Warranty and Punchlist - field installation time
2025-09-30 | PRJ-PAY-ARM-2522-20250930 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 13.34 | 1120.32 | Closeout and O&M Documentation - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2522-20251007 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1009 | 40.1 | 2846.85 | Field Installation Labor - field installation time
2025-10-07 | PRJ-PAY-ARM-2522-20251007 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 24.35 | 1887.36 | Startup, Testing and Commissioning - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2522-20251007 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 32.38 | 2720.18 | Sheet Metal Fabrication Labor - supervision and planning
2025-10-09 | AP-0005524 | AP | ARM-2522 | 02-510 | Controls Panels and Devices | V-2293 |  | 49.47 | 8905.35 | Controls Panels and Devices - valves and piping lot
2025-10-09 | AP-0005527 | AP | ARM-2522 | 04-300 | Testing and Balancing Subcontract | V-2329 |  | 22217.44 | 22217.44 | Testing and Balancing Subcontract - testing and balancing services
2025-10-09 | AP-0005528 | AP | ARM-2522 | 05-100 | Equipment Rental and Rigging | V-2341 |  | 8693.78 | 8693.78 | Equipment Rental and Rigging - freight and expediting
2025-10-14 | PRJ-PAY-ARM-2522-20251014 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 34.14 | 2423.96 | Startup, Testing and Commissioning - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2522-20251014 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 30.79 | 2386.02 | Sheet Metal Fabrication Labor - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2522-20251014 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1030 | 24.11 | 2024.86 | Controls Programming and Checkout - startup and checkout
2025-10-16 | AP-0005525 | AP | ARM-2522 | 02-210 | Sheet Metal and Ductwork | V-2307 |  | 62.55 | 11259.73 | Sheet Metal and Ductwork - ductwork release
2025-10-21 | PRJ-PAY-ARM-2522-20251021 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 27.71 | 1967.76 | Sheet Metal Fabrication Labor - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2522-20251021 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1028 | 24.33 | 1885.81 | Controls Programming and Checkout - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2522-20251021 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1035 | 26.87 | 2257.08 | Warranty and Punchlist - punchlist and closeout labor
2025-10-23 | AP-0005526 | AP | ARM-2522 | 02-510 | Controls Panels and Devices | V-2320 |  | 70.43 | 12678.1 | Controls Panels and Devices - jobsite material replenishment
2025-10-28 | PRJ-PAY-ARM-2522-20251028 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1026 | 27.75 | 1970.58 | Controls Programming and Checkout - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2522-20251028 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1033 | 25.14 | 1948.54 | Warranty and Punchlist - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2522-20251028 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 24.15 | 2028.51 | Closeout and O&M Documentation - field installation time
2025-10-31 | PRJ-PAY-ARM-2522-20251031 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1031 | 28.43 | 2018.18 | Warranty and Punchlist - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2522-20251031 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 26.41 | 2046.65 | Closeout and O&M Documentation - field installation time
2025-10-31 | PRJ-PAY-ARM-2522-20251031 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1045 | 28.94 | 2430.84 | Rework and Quality Correction - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2522-20251107 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 41.33 | 2934.33 | Startup, Testing and Commissioning - field installation time
2025-11-07 | PRJ-PAY-ARM-2522-20251107 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 39.54 | 3064.09 | Sheet Metal Fabrication Labor - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2522-20251107 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1026 | 24.18 | 2031.1 | Controls Programming and Checkout - supervision and planning
2025-11-12 | AP-0005529 | AP | ARM-2522 | 02-610 | Insulation and Specialty Material | V-2355 |  | 74.89 | 13480.75 | Insulation and Specialty Material - ductwork release
2025-11-12 | AP-0005532 | AP | ARM-2522 | 04-400 | Crane, Rigging and Specialty Trade | V-2391 |  | 24811.37 | 24811.37 | Crane, Rigging and Specialty Trade - electrical coordination scope
2025-11-12 | AP-0005533 | AP | ARM-2522 | 05-200 | Permits, Fees and Bonds | V-2403 |  | 9022.31 | 9022.31 | Permits, Fees and Bonds - small tools and field consumables
2025-11-14 | PRJ-PAY-ARM-2522-20251114 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 27.25 | 1934.58 | Sheet Metal Fabrication Labor - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2522-20251114 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1024 | 35.56 | 2755.66 | Controls Programming and Checkout - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2522-20251114 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1031 | 29.62 | 2488.5 | Warranty and Punchlist - startup and checkout
2025-11-19 | AP-0005530 | AP | ARM-2522 | 02-310 | Hydronic Piping and Valves | V-2369 |  | 70.58 | 12703.89 | Hydronic Piping and Valves - jobsite material replenishment
2025-11-21 | PRJ-PAY-ARM-2522-20251121 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1022 | 30.52 | 2167.05 | Controls Programming and Checkout - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2522-20251121 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1029 | 26.4 | 2045.83 | Warranty and Punchlist - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2522-20251121 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 33.03 | 2774.35 | Closeout and O&M Documentation - punchlist and closeout labor
2025-11-25 | AP-0005531 | AP | ARM-2522 | 02-610 | Insulation and Specialty Material | V-2383 |  | 80.09 | 14415.78 | Insulation and Specialty Material - released equipment package
2025-11-28 | PRJ-PAY-ARM-2522-20251128 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1027 | 42.75 | 3035.24 | Warranty and Punchlist - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2522-20251128 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 27.18 | 2106.76 | Closeout and O&M Documentation - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2522-20251128 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1041 | 29.63 | 2489.06 | Rework and Quality Correction - field installation time
2025-11-30 | PRJ-PAY-ARM-2522-20251130 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 39.58 | 2810.02 | Closeout and O&M Documentation - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2522-20251130 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1039 | 44.3 | 3432.94 | Rework and Quality Correction - field installation time
2025-11-30 | PRJ-PAY-ARM-2522-20251130 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1046 | 24.73 | 2275.33 | Project Management and Supervision - coordination and layout
2025-12-05 | AP-0005536 | AP | ARM-2522 | 02-110 | Major HVAC Equipment | V-2443 |  | 62.54 | 11257.67 | Major HVAC Equipment - fabricated material delivery
2025-12-07 | PRJ-PAY-ARM-2522-20251207 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 40.97 | 2909.06 | Sheet Metal Fabrication Labor - field installation time
2025-12-07 | PRJ-PAY-ARM-2522-20251207 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1020 | 32.86 | 2546.72 | Controls Programming and Checkout - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2522-20251207 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1027 | 32.72 | 2748.75 | Warranty and Punchlist - supervision and planning
2025-12-12 | AP-0005537 | AP | ARM-2522 | 02-410 | Plumbing Fixtures and Piping | V-2457 |  | 53.76 | 9677.51 | Plumbing Fixtures and Piping - valves and piping lot
2025-12-14 | PRJ-PAY-ARM-2522-20251214 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1018 | 39.21 | 2783.65 | Controls Programming and Checkout - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2522-20251214 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1025 | 29.93 | 2319.35 | Warranty and Punchlist - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2522-20251214 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 34.32 | 2882.66 | Closeout and O&M Documentation - startup and checkout
2025-12-15 | AP-0005534 | AP | ARM-2522 | 02-110 | Major HVAC Equipment | V-2417 |  | 101.44 | 18258.72 | Major HVAC Equipment - jobsite material replenishment
2025-12-15 | AP-0005538 | AP | ARM-2522 | 04-100 | Insulation Subcontract | V-2464 |  | 30267.07 | 30267.07 | Insulation Subcontract - rigging and specialty support
2025-12-15 | AP-0005539 | AP | ARM-2522 | 05-300 | Freight and Expediting | V-2476 |  | 9211.72 | 9211.72 | Freight and Expediting - rental and logistics
2025-12-21 | PRJ-PAY-ARM-2522-20251221 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1023 | 46.52 | 3302.59 | Warranty and Punchlist - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2522-20251221 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 36.49 | 2827.74 | Closeout and O&M Documentation - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2522-20251221 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1037 | 30.85 | 2591.16 | Rework and Quality Correction - punchlist and closeout labor
2025-12-22 | AP-0005535 | AP | ARM-2522 | 02-410 | Plumbing Fixtures and Piping | V-2431 |  | 60.07 | 10812.56 | Plumbing Fixtures and Piping - released equipment package
2025-12-28 | PRJ-PAY-ARM-2522-20251228 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 52.43 | 3722.61 | Closeout and O&M Documentation - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2522-20251228 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1035 | 39.34 | 3048.97 | Rework and Quality Correction - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2522-20251228 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1042 | 32.22 | 2963.93 | Project Management and Supervision - field installation time
2025-12-31 | PRJ-PAY-ARM-2522-20251231 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1033 | 55.87 | 3966.81 | Rework and Quality Correction - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2522-20251231 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1040 | 39.81 | 3403.97 | Project Management and Supervision - field installation time
2025-12-31 | PRJ-PAY-ARM-2522-20251231 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 32.44 | 2724.65 | Engineering, BIM and Coordination - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2522-20260107 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1013 | 42.57 | 3022.25 | Controls Programming and Checkout - field installation time
2026-01-07 | PRJ-PAY-ARM-2522-20260107 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1021 | 28.52 | 2210.63 | Warranty and Punchlist - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2522-20260107 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 35.66 | 2995.6 | Closeout and O&M Documentation - supervision and planning
2026-01-08 | AP-0005542 | AP | ARM-2522 | 02-210 | Sheet Metal and Ductwork | V-2517 |  | 67.2 | 12095.2 | Sheet Metal and Ductwork - valves and piping lot
2026-01-14 | PRJ-PAY-ARM-2522-20260114 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1019 | 43.32 | 3075.6 | Warranty and Punchlist - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2522-20260114 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 39.42 | 3055.16 | Closeout and O&M Documentation - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2522-20260114 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1033 | 34 | 2855.92 | Rework and Quality Correction - startup and checkout
2026-01-15 | AP-0005543 | AP | ARM-2522 | 02-510 | Controls Panels and Devices | V-2531 |  | 63.13 | 11363.65 | Controls Panels and Devices - ductwork release
2026-01-18 | AP-0005540 | AP | ARM-2522 | 02-210 | Sheet Metal and Ductwork | V-2490 |  | 53.11 | 9558.93 | Sheet Metal and Ductwork - released equipment package
2026-01-18 | AP-0005544 | AP | ARM-2522 | 04-200 | Electrical and Controls Subcontract | V-2010 |  | 30675.38 | 30675.38 | Electrical and Controls Subcontract - trade partner progress billing
2026-01-18 | AP-0005545 | AP | ARM-2522 | 05-400 | Small Tools and Consumables | V-2037 |  | 7502.43 | 7502.43 | Small Tools and Consumables - permit and inspection fees
2026-01-21 | PRJ-PAY-ARM-2522-20260121 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 51.56 | 3660.9 | Closeout and O&M Documentation - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2522-20260121 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1031 | 41.21 | 3194.03 | Rework and Quality Correction - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2522-20260121 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1038 | 34.53 | 3176.61 | Project Management and Supervision - punchlist and closeout labor
2026-01-25 | AP-0005541 | AP | ARM-2522 | 02-510 | Controls Panels and Devices | V-2503 |  | 79.94 | 14389.63 | Controls Panels and Devices - fabricated material delivery
2026-01-25 | AP-0005546 | AP | ARM-2522 | 05-200 | Permits, Fees and Bonds | V-2208 |  | 5046.6 | 5046.6 | Permits, Fees and Bonds - freight and expediting
2026-01-28 | PRJ-PAY-ARM-2522-20260128 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1029 | 62.55 | 4440.86 | Rework and Quality Correction - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2522-20260128 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1036 | 39.65 | 3389.92 | Project Management and Supervision - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2522-20260128 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 30.61 | 2571.62 | Engineering, BIM and Coordination - field installation time
2026-01-31 | PRJ-PAY-ARM-2522-20260131 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1034 | 46.71 | 3690.08 | Project Management and Supervision - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2522-20260131 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 45.87 | 3554.84 | Engineering, BIM and Coordination - field installation time
2026-01-31 | PRJ-PAY-ARM-2522-20260131 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1048 | 29.92 | 2513.39 | Field Installation Labor - coordination and layout
2026-02-04 | AP-0005548 | AP | ARM-2522 | 02-610 | Insulation and Specialty Material | V-2246 |  | 52.79 | 9502.1 | Insulation and Specialty Material - valves and piping lot
2026-02-04 | AP-0005553 | AP | ARM-2522 | 05-300 | Freight and Expediting | V-2315 |  | 6831.28 | 6831.28 | Freight and Expediting - small tools and field consumables
2026-02-07 | PRJ-PAY-ARM-2522-20260207 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1014 | 61.03 | 4333.27 | Warranty and Punchlist - field installation time
2026-02-07 | PRJ-PAY-ARM-2522-20260207 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 47.33 | 3667.9 | Closeout and O&M Documentation - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2522-20260207 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1029 | 41.4 | 3477.5 | Rework and Quality Correction - supervision and planning
2026-02-11 | AP-0005549 | AP | ARM-2522 | 02-310 | Hydronic Piping and Valves | V-2267 |  | 78.91 | 14203.81 | Hydronic Piping and Valves - ductwork release
2026-02-14 | PRJ-PAY-ARM-2522-20260214 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 53.2 | 3777.24 | Closeout and O&M Documentation - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2522-20260214 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1027 | 35.32 | 2737.01 | Rework and Quality Correction - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2522-20260214 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1034 | 33.98 | 3126.11 | Project Management and Supervision - startup and checkout
2026-02-14 | PRJ-PAY-ARM-2522-20260214 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 35.06 | 3172.9 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-02-18 | AP-0005550 | AP | ARM-2522 | 02-610 | Insulation and Specialty Material | V-2282 |  | 108.44 | 19519.53 | Insulation and Specialty Material - jobsite material replenishment
2026-02-21 | AP-0005547 | AP | ARM-2522 | 02-310 | Hydronic Piping and Valves | V-2229 |  | 54.23 | 9761.44 | Hydronic Piping and Valves - fabricated material delivery
2026-02-21 | AP-0005551 | AP | ARM-2522 | 04-300 | Testing and Balancing Subcontract | V-2289 |  | 33852.73 | 33852.73 | Testing and Balancing Subcontract - insulation progress invoice
2026-02-21 | AP-0005552 | AP | ARM-2522 | 06-400 | Temporary Facilities and Protection | V-2301 |  | 4943.58 | 4943.58 | Temporary Facilities and Protection - freight and expediting
2026-02-21 | PRJ-PAY-ARM-2522-20260221 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1025 | 44.84 | 3183.95 | Rework and Quality Correction - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2522-20260221 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1032 | 31.79 | 2718.18 | Project Management and Supervision - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2522-20260221 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 36.05 | 3028.35 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-02-21 | PRJ-PAY-ARM-2522-20260221 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1046 | 48.14 | 4356.48 | Field Installation Labor - field installation time
2026-02-28 | PRJ-PAY-ARM-2522-20260228 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1030 | 54.81 | 4329.74 | Project Management and Supervision - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2522-20260228 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 56.87 | 4407.23 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2522-20260228 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1044 | 44.37 | 3727.3 | Field Installation Labor - field installation time
2026-03-04 | AP-0005558 | AP | ARM-2522 | 02-410 | Plumbing Fixtures and Piping | V-2383 |  | 50.83 | 9150.05 | Plumbing Fixtures and Piping - fabricated material delivery
2026-03-07 | AP-0005555 | AP | ARM-2522 | 02-110 | Major HVAC Equipment | V-2341 |  | 76.66 | 13798.25 | Major HVAC Equipment - ductwork release
2026-03-07 | AP-0005561 | AP | ARM-2522 | 05-400 | Small Tools and Consumables | V-2414 |  | 4383.97 | 4383.97 | Small Tools and Consumables - rental and logistics
2026-03-07 | PRJ-PAY-ARM-2522-20260307 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 59.2 | 4203.17 | Closeout and O&M Documentation - field installation time
2026-03-07 | PRJ-PAY-ARM-2522-20260307 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1023 | 45.17 | 3500.75 | Rework and Quality Correction - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2522-20260307 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1030 | 40.48 | 3723.94 | Project Management and Supervision - supervision and planning
2026-03-14 | AP-0005556 | AP | ARM-2522 | 02-410 | Plumbing Fixtures and Piping | V-2355 |  | 66.23 | 11921.4 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-03-14 | PRJ-PAY-ARM-2522-20260314 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1021 | 57.86 | 4107.97 | Rework and Quality Correction - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2522-20260314 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1028 | 36.56 | 3126.19 | Project Management and Supervision - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2522-20260314 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 54.95 | 4616.19 | Engineering, BIM and Coordination - startup and checkout
2026-03-21 | AP-0005557 | AP | ARM-2522 | 02-110 | Major HVAC Equipment | V-2369 |  | 79.54 | 14316.7 | Major HVAC Equipment - released equipment package
2026-03-21 | PRJ-PAY-ARM-2522-20260321 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1026 | 54.21 | 4282.52 | Project Management and Supervision - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2522-20260321 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 48.18 | 3734.01 | Engineering, BIM and Coordination - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2522-20260321 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1040 | 36.91 | 3100.07 | Field Installation Labor - punchlist and closeout labor
2026-03-24 | AP-0005554 | AP | ARM-2522 | 02-410 | Plumbing Fixtures and Piping | V-2327 |  | 59.66 | 10739.24 | Plumbing Fixtures and Piping - valves and piping lot
2026-03-24 | AP-0005559 | AP | ARM-2522 | 04-400 | Crane, Rigging and Specialty Trade | V-2388 |  | 34693.79 | 34693.79 | Crane, Rigging and Specialty Trade - testing and balancing services
2026-03-24 | AP-0005560 | AP | ARM-2522 | 05-100 | Equipment Rental and Rigging | V-2400 |  | 6654.96 | 6654.96 | Equipment Rental and Rigging - small tools and field consumables
2026-03-28 | PRJ-PAY-ARM-2522-20260328 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 48.79 | 3464.06 | Engineering, BIM and Coordination - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2522-20260328 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1038 | 43.32 | 3357.06 | Field Installation Labor - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2522-20260328 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 36.67 | 3080.11 | Startup, Testing and Commissioning - field installation time
2026-03-31 | PRJ-PAY-ARM-2522-20260331 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1036 | 40.68 | 2888.5 | Field Installation Labor - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2522-20260331 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 34.81 | 2698.01 | Startup, Testing and Commissioning - field installation time
2026-03-31 | PRJ-PAY-ARM-2522-20260331 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 44.47 | 3735.12 | Sheet Metal Fabrication Labor - coordination and layout
2026-04-03 | AP-0005562 | AP | ARM-2522 | 02-510 | Controls Panels and Devices | V-2426 |  | 74.5 | 13410.4 | Controls Panels and Devices - ductwork release
2026-04-03 | AP-0005567 | AP | ARM-2522 | 04-100 | Insulation Subcontract | V-2484 |  | 20417.48 | 20417.48 | Insulation Subcontract - electrical coordination scope
2026-04-03 | AP-0005569 | AP | ARM-2522 | 05-200 | Permits, Fees and Bonds | V-2509 |  | 9371.32 | 9371.32 | Permits, Fees and Bonds - rental and logistics
2026-04-07 | AP-0005566 | AP | ARM-2522 | 02-510 | Controls Panels and Devices | V-2479 |  | 55.9 | 10062.36 | Controls Panels and Devices - valves and piping lot
2026-04-07 | PRJ-PAY-ARM-2522-20260407 | PAY | ARM-2522 | 06-300 | Rework and Quality Correction |  | E-1016 | 51.22 | 3636.51 | Rework and Quality Correction - field installation time
2026-04-07 | PRJ-PAY-ARM-2522-20260407 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1024 | 32.07 | 2741.99 | Project Management and Supervision - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2522-20260407 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 51.24 | 4303.96 | Engineering, BIM and Coordination - supervision and planning
2026-04-07 | PRJ-PAY-ARM-2522-20260407 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1038 | 36.21 | 3277.25 | Field Installation Labor - startup and checkout
2026-04-10 | AP-0005563 | AP | ARM-2522 | 02-210 | Sheet Metal and Ductwork | V-2439 |  | 67.55 | 12159.13 | Sheet Metal and Ductwork - jobsite material replenishment
2026-04-10 | AP-0005568 | AP | ARM-2522 | 04-400 | Crane, Rigging and Specialty Trade | V-2498 |  | 21100.47 | 21100.47 | Crane, Rigging and Specialty Trade - rigging and specialty support
2026-04-10 | AP-0005570 | AP | ARM-2522 | 06-400 | Temporary Facilities and Protection | V-2522 |  | 6874.83 | 6874.83 | Temporary Facilities and Protection - permit and inspection fees
2026-04-14 | PRJ-PAY-ARM-2522-20260414 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1022 | 42.18 | 3331.93 | Project Management and Supervision - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2522-20260414 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1029 | 46.91 | 3635.47 | Engineering, BIM and Coordination - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2522-20260414 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1036 | 32.99 | 2770.94 | Field Installation Labor - startup and checkout
2026-04-14 | PRJ-PAY-ARM-2522-20260414 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 37.09 | 3357.01 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-04-17 | AP-0005564 | AP | ARM-2522 | 02-510 | Controls Panels and Devices | V-2452 |  | 73.8 | 13283.99 | Controls Panels and Devices - released equipment package
2026-04-21 | PRJ-PAY-ARM-2522-20260421 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1027 | 54.44 | 3865.02 | Engineering, BIM and Coordination - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2522-20260421 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1034 | 44.26 | 3429.95 | Field Installation Labor - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2522-20260421 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1041 | 52.01 | 4368.67 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-04-24 | AP-0005565 | AP | ARM-2522 | 02-210 | Sheet Metal and Ductwork | V-2465 |  | 69.21 | 12458.49 | Sheet Metal and Ductwork - fabricated material delivery
2026-04-28 | PRJ-PAY-ARM-2522-20260428 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1032 | 52.53 | 3729.87 | Field Installation Labor - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2522-20260428 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 54.76 | 4243.76 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2522-20260428 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1046 | 35.8 | 3007.25 | Sheet Metal Fabrication Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2522-20260430 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 55.02 | 3906.69 | Startup, Testing and Commissioning - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2522-20260430 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 51.13 | 3962.35 | Sheet Metal Fabrication Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2522-20260430 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1051 | 45.31 | 3805.75 | Controls Programming and Checkout - coordination and layout
2026-05-03 | AP-0005574 | AP | ARM-2522 | 02-310 | Hydronic Piping and Valves | V-2229 |  | 42.73 | 7690.62 | Hydronic Piping and Valves - valves and piping lot
2026-05-06 | AP-0005571 | AP | ARM-2522 | 02-610 | Insulation and Specialty Material | V-2534 |  | 83.76 | 15076.69 | Insulation and Specialty Material - jobsite material replenishment
2026-05-06 | AP-0005577 | AP | ARM-2522 | 04-200 | Electrical and Controls Subcontract | V-2272 |  | 22383.56 | 22383.56 | Electrical and Controls Subcontract - rigging and specialty support
2026-05-06 | AP-0005579 | AP | ARM-2522 | 05-300 | Freight and Expediting | V-2296 |  | 9972.39 | 9972.39 | Freight and Expediting - permit and inspection fees
2026-05-07 | PRJ-PAY-ARM-2522-20260507 | PAY | ARM-2522 | 01-100 | Project Management and Supervision |  | E-1018 | 37.81 | 2986.83 | Project Management and Supervision - field installation time
2026-05-07 | PRJ-PAY-ARM-2522-20260507 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1025 | 53.78 | 4167.8 | Engineering, BIM and Coordination - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2522-20260507 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1032 | 45.17 | 3793.99 | Field Installation Labor - supervision and planning
2026-05-07 | PRJ-PAY-ARM-2522-20260507 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1039 | 43.02 | 3893.47 | Startup, Testing and Commissioning - startup and checkout
2026-05-10 | AP-0005575 | AP | ARM-2522 | 02-610 | Insulation and Specialty Material | V-2246 |  | 68.36 | 12304.45 | Insulation and Specialty Material - ductwork release
2026-05-13 | AP-0005572 | AP | ARM-2522 | 02-310 | Hydronic Piping and Valves | V-2033 |  | 54.78 | 9859.83 | Hydronic Piping and Valves - released equipment package
2026-05-13 | AP-0005578 | AP | ARM-2522 | 04-100 | Insulation Subcontract | V-2286 |  | 22001.36 | 22001.36 | Insulation Subcontract - trade partner progress billing
2026-05-13 | AP-0005580 | AP | ARM-2522 | 05-100 | Equipment Rental and Rigging | V-2310 |  | 6167.58 | 6167.58 | Equipment Rental and Rigging - freight and expediting
2026-05-14 | PRJ-PAY-ARM-2522-20260514 | PAY | ARM-2522 | 01-200 | Engineering, BIM and Coordination |  | E-1023 | 47.87 | 3398.98 | Engineering, BIM and Coordination - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2522-20260514 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1030 | 38.66 | 2996.43 | Field Installation Labor - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2522-20260514 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1037 | 44.73 | 3757.74 | Startup, Testing and Commissioning - startup and checkout
2026-05-14 | PRJ-PAY-ARM-2522-20260514 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1044 | 33.88 | 3066.26 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-05-17 | AP-0005576 | AP | ARM-2522 | 02-310 | Hydronic Piping and Valves | V-2267 |  | 78.97 | 14214.2 | Hydronic Piping and Valves - jobsite material replenishment
2026-05-20 | AP-0005573 | AP | ARM-2522 | 02-610 | Insulation and Specialty Material | V-2205 |  | 74.91 | 13484.08 | Insulation and Specialty Material - fabricated material delivery
2026-05-21 | PRJ-PAY-ARM-2522-20260521 | PAY | ARM-2522 | 03-100 | Field Installation Labor |  | E-1028 | 55.51 | 3941.5 | Field Installation Labor - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2522-20260521 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1035 | 43.75 | 3390.34 | Startup, Testing and Commissioning - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2522-20260521 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1042 | 60.88 | 5113.73 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2522-20260528 | PAY | ARM-2522 | 03-200 | Startup, Testing and Commissioning |  | E-1033 | 46.69 | 3315.05 | Startup, Testing and Commissioning - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2522-20260528 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1040 | 51.58 | 3997.78 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2522-20260528 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1047 | 36.32 | 3051.29 | Controls Programming and Checkout - field installation time
2026-05-28 | PRJ-PAY-ARM-2522-20260528 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1080 | 31.69 | 2867.93 | Warranty and Punchlist - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2522-20260531 | PAY | ARM-2522 | 03-300 | Sheet Metal Fabrication Labor |  | E-1038 | 38.66 | 2744.81 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2522-20260531 | PAY | ARM-2522 | 03-400 | Controls Programming and Checkout |  | E-1045 | 42.69 | 3308.46 | Controls Programming and Checkout - field installation time
2026-05-31 | PRJ-PAY-ARM-2522-20260531 | PAY | ARM-2522 | 06-100 | Warranty and Punchlist |  | E-1052 | 51.45 | 4321.84 | Warranty and Punchlist - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2522-20260531 | PAY | ARM-2522 | 06-200 | Closeout and O&M Documentation |  | E-1085 | 49.51 | 4480.65 | Closeout and O&M Documentation - supervision and planning
2025-10-03 | AP-0005592 | AP | ARM-2526 | 02-310 | Hydronic Piping and Valves | V-2438 |  | 44.63 | 8032.74 | Hydronic Piping and Valves - released equipment package
2025-10-03 | AP-0005593 | AP | ARM-2526 | 04-100 | Insulation Subcontract | V-2448 |  | 5132.03 | 5132.03 | Insulation Subcontract - trade partner progress billing
2025-10-03 | AP-0005594 | AP | ARM-2526 | 05-400 | Small Tools and Consumables | V-2460 |  | 1785.05 | 1785.05 | Small Tools and Consumables - rental and logistics
2025-10-07 | PRJ-PAY-ARM-2526-20251007 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1007 | 7.98 | 630.04 | Project Management and Supervision - field installation time
2025-10-07 | PRJ-PAY-ARM-2526-20251007 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 4.92 | 381.57 | Engineering, BIM and Coordination - coordination and layout
2025-10-07 | PRJ-PAY-ARM-2526-20251007 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1023 | 5.54 | 465.45 | Field Installation Labor - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2526-20251014 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 7.63 | 541.5 | Engineering, BIM and Coordination - coordination and layout
2025-10-14 | PRJ-PAY-ARM-2526-20251014 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1021 | 5.87 | 454.92 | Field Installation Labor - supervision and planning
2025-10-14 | PRJ-PAY-ARM-2526-20251014 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 7.5 | 629.79 | Startup, Testing and Commissioning - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2526-20251021 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1019 | 8.61 | 611.62 | Field Installation Labor - supervision and planning
2025-10-21 | PRJ-PAY-ARM-2526-20251021 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 6.84 | 530.26 | Startup, Testing and Commissioning - startup and checkout
2025-10-21 | PRJ-PAY-ARM-2526-20251021 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 5.91 | 496.35 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2526-20251028 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 8 | 567.84 | Startup, Testing and Commissioning - startup and checkout
2025-10-28 | PRJ-PAY-ARM-2526-20251028 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 4.94 | 383.18 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-10-28 | PRJ-PAY-ARM-2526-20251028 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1038 | 6.56 | 551.05 | Controls Programming and Checkout - field installation time
2025-10-31 | PRJ-PAY-ARM-2526-20251031 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 5.18 | 367.76 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2025-10-31 | PRJ-PAY-ARM-2526-20251031 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1036 | 5.15 | 399.37 | Controls Programming and Checkout - field installation time
2025-10-31 | PRJ-PAY-ARM-2526-20251031 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1043 | 6.85 | 575.78 | Warranty and Punchlist - coordination and layout
2025-11-06 | AP-0005595 | AP | ARM-2526 | 02-410 | Plumbing Fixtures and Piping | V-2474 |  | 59.03 | 10625.26 | Plumbing Fixtures and Piping - fabricated material delivery
2025-11-06 | AP-0005597 | AP | ARM-2526 | 04-200 | Electrical and Controls Subcontract | V-2498 |  | 11889.98 | 11889.98 | Electrical and Controls Subcontract - insulation progress invoice
2025-11-06 | AP-0005598 | AP | ARM-2526 | 06-400 | Temporary Facilities and Protection | V-2510 |  | 3783.17 | 3783.17 | Temporary Facilities and Protection - permit and inspection fees
2025-11-07 | PRJ-PAY-ARM-2526-20251107 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 25.97 | 1844.05 | Engineering, BIM and Coordination - field installation time
2025-11-07 | PRJ-PAY-ARM-2526-20251107 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1016 | 14.12 | 1094.05 | Field Installation Labor - coordination and layout
2025-11-07 | PRJ-PAY-ARM-2526-20251107 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 12.99 | 1091.05 | Startup, Testing and Commissioning - supervision and planning
2025-11-13 | AP-0005596 | AP | ARM-2526 | 02-110 | Major HVAC Equipment | V-2488 |  | 55.07 | 9911.98 | Major HVAC Equipment - valves and piping lot
2025-11-14 | PRJ-PAY-ARM-2526-20251114 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1014 | 18.43 | 1308.41 | Field Installation Labor - coordination and layout
2025-11-14 | PRJ-PAY-ARM-2526-20251114 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 17.77 | 1377 | Startup, Testing and Commissioning - supervision and planning
2025-11-14 | PRJ-PAY-ARM-2526-20251114 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 16.35 | 1373.52 | Sheet Metal Fabrication Labor - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2526-20251121 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 16.45 | 1167.6 | Startup, Testing and Commissioning - supervision and planning
2025-11-21 | PRJ-PAY-ARM-2526-20251121 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 20.38 | 1579.15 | Sheet Metal Fabrication Labor - startup and checkout
2025-11-21 | PRJ-PAY-ARM-2526-20251121 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1034 | 11.61 | 974.83 | Controls Programming and Checkout - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2526-20251128 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 13.5 | 958.82 | Sheet Metal Fabrication Labor - startup and checkout
2025-11-28 | PRJ-PAY-ARM-2526-20251128 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1032 | 15.22 | 1179.82 | Controls Programming and Checkout - punchlist and closeout labor
2025-11-28 | PRJ-PAY-ARM-2526-20251128 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1039 | 14.15 | 1188.62 | Warranty and Punchlist - field installation time
2025-11-30 | PRJ-PAY-ARM-2526-20251130 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1030 | 12.83 | 910.94 | Controls Programming and Checkout - punchlist and closeout labor
2025-11-30 | PRJ-PAY-ARM-2526-20251130 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1037 | 15.41 | 1194.52 | Warranty and Punchlist - field installation time
2025-11-30 | PRJ-PAY-ARM-2526-20251130 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 13.49 | 1133.04 | Closeout and O&M Documentation - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2526-20251207 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1009 | 24.53 | 1741.48 | Field Installation Labor - field installation time
2025-12-07 | PRJ-PAY-ARM-2526-20251207 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 36.06 | 2794.77 | Startup, Testing and Commissioning - coordination and layout
2025-12-07 | PRJ-PAY-ARM-2526-20251207 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 25.14 | 2112.02 | Sheet Metal Fabrication Labor - supervision and planning
2025-12-09 | AP-0005599 | AP | ARM-2526 | 02-510 | Controls Panels and Devices | V-2524 |  | 112.94 | 20328.33 | Controls Panels and Devices - valves and piping lot
2025-12-09 | AP-0005601 | AP | ARM-2526 | 04-300 | Testing and Balancing Subcontract | V-2033 |  | 19814.83 | 19814.83 | Testing and Balancing Subcontract - testing and balancing services
2025-12-09 | AP-0005602 | AP | ARM-2526 | 05-100 | Equipment Rental and Rigging | V-2201 |  | 7753.63 | 7753.63 | Equipment Rental and Rigging - freight and expediting
2025-12-14 | PRJ-PAY-ARM-2526-20251214 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 25.78 | 1830.48 | Startup, Testing and Commissioning - coordination and layout
2025-12-14 | PRJ-PAY-ARM-2526-20251214 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 28.19 | 2184.35 | Sheet Metal Fabrication Labor - supervision and planning
2025-12-14 | PRJ-PAY-ARM-2526-20251214 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1030 | 24.77 | 2080.88 | Controls Programming and Checkout - startup and checkout
2025-12-16 | AP-0005600 | AP | ARM-2526 | 02-210 | Sheet Metal and Ductwork | V-2010 |  | 49.8 | 8963.15 | Sheet Metal and Ductwork - ductwork release
2025-12-21 | PRJ-PAY-ARM-2526-20251221 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 25.06 | 1778.93 | Sheet Metal Fabrication Labor - supervision and planning
2025-12-21 | PRJ-PAY-ARM-2526-20251221 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1028 | 19.59 | 1517.99 | Controls Programming and Checkout - startup and checkout
2025-12-21 | PRJ-PAY-ARM-2526-20251221 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1035 | 25.63 | 2152.91 | Warranty and Punchlist - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2526-20251228 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1026 | 24.11 | 1711.6 | Controls Programming and Checkout - startup and checkout
2025-12-28 | PRJ-PAY-ARM-2526-20251228 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1033 | 26.7 | 2069.08 | Warranty and Punchlist - punchlist and closeout labor
2025-12-28 | PRJ-PAY-ARM-2526-20251228 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 18.14 | 1523.77 | Closeout and O&M Documentation - field installation time
2025-12-31 | PRJ-PAY-ARM-2526-20251231 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1031 | 23.32 | 1655.65 | Warranty and Punchlist - punchlist and closeout labor
2025-12-31 | PRJ-PAY-ARM-2526-20251231 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 26.38 | 2044.26 | Closeout and O&M Documentation - field installation time
2025-12-31 | PRJ-PAY-ARM-2526-20251231 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1045 | 24.92 | 2093.31 | Rework and Quality Correction - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2526-20260107 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 39.06 | 2772.92 | Startup, Testing and Commissioning - field installation time
2026-01-07 | PRJ-PAY-ARM-2526-20260107 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 30.3 | 2348.03 | Sheet Metal Fabrication Labor - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2526-20260107 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1026 | 37.49 | 3149.18 | Controls Programming and Checkout - supervision and planning
2026-01-12 | AP-0005603 | AP | ARM-2526 | 02-610 | Insulation and Specialty Material | V-2225 |  | 100.03 | 18005.87 | Insulation and Specialty Material - ductwork release
2026-01-12 | AP-0005606 | AP | ARM-2526 | 04-400 | Crane, Rigging and Specialty Trade | V-2275 |  | 25554.86 | 25554.86 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-01-12 | AP-0005607 | AP | ARM-2526 | 05-200 | Permits, Fees and Bonds | V-2288 |  | 9292.67 | 9292.67 | Permits, Fees and Bonds - small tools and field consumables
2026-01-14 | PRJ-PAY-ARM-2526-20260114 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 37.5 | 2662.66 | Sheet Metal Fabrication Labor - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2526-20260114 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1024 | 27.74 | 2149.52 | Controls Programming and Checkout - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2526-20260114 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1031 | 30.73 | 2581.67 | Warranty and Punchlist - startup and checkout
2026-01-19 | AP-0005604 | AP | ARM-2526 | 02-310 | Hydronic Piping and Valves | V-2244 |  | 71.6 | 12888.72 | Hydronic Piping and Valves - jobsite material replenishment
2026-01-21 | PRJ-PAY-ARM-2526-20260121 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1022 | 34.98 | 2483.71 | Controls Programming and Checkout - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2526-20260121 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1029 | 27.76 | 2151.64 | Warranty and Punchlist - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2526-20260121 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 30.49 | 2561.26 | Closeout and O&M Documentation - punchlist and closeout labor
2026-01-25 | AP-0005605 | AP | ARM-2526 | 02-610 | Insulation and Specialty Material | V-2265 |  | 60.68 | 10922.45 | Insulation and Specialty Material - released equipment package
2026-01-28 | PRJ-PAY-ARM-2526-20260128 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1027 | 38.4 | 2726.47 | Warranty and Punchlist - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2526-20260128 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 25.77 | 1997.33 | Closeout and O&M Documentation - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2526-20260128 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1041 | 37.33 | 3135.93 | Rework and Quality Correction - field installation time
2026-01-31 | PRJ-PAY-ARM-2526-20260131 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 32.1 | 2279.35 | Closeout and O&M Documentation - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2526-20260131 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1039 | 43.23 | 3350.71 | Rework and Quality Correction - field installation time
2026-01-31 | PRJ-PAY-ARM-2526-20260131 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1046 | 34.17 | 3143.49 | Project Management and Supervision - coordination and layout
2026-02-05 | AP-0005610 | AP | ARM-2526 | 02-110 | Major HVAC Equipment | V-2329 |  | 68.48 | 12325.51 | Major HVAC Equipment - fabricated material delivery
2026-02-07 | PRJ-PAY-ARM-2526-20260207 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 46.14 | 3275.82 | Sheet Metal Fabrication Labor - field installation time
2026-02-07 | PRJ-PAY-ARM-2526-20260207 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1020 | 38.89 | 3014.18 | Controls Programming and Checkout - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2526-20260207 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1027 | 42.67 | 3584.16 | Warranty and Punchlist - supervision and planning
2026-02-12 | AP-0005611 | AP | ARM-2526 | 02-410 | Plumbing Fixtures and Piping | V-2343 |  | 79.42 | 14295.52 | Plumbing Fixtures and Piping - valves and piping lot
2026-02-14 | PRJ-PAY-ARM-2526-20260214 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1018 | 41.13 | 2920.24 | Controls Programming and Checkout - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2526-20260214 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1025 | 44.9 | 3479.9 | Warranty and Punchlist - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2526-20260214 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 38.22 | 3210.6 | Closeout and O&M Documentation - startup and checkout
2026-02-15 | AP-0005608 | AP | ARM-2526 | 02-110 | Major HVAC Equipment | V-2301 |  | 43.61 | 7849.94 | Major HVAC Equipment - jobsite material replenishment
2026-02-15 | AP-0005612 | AP | ARM-2526 | 04-100 | Insulation Subcontract | V-2350 |  | 28207.41 | 28207.41 | Insulation Subcontract - rigging and specialty support
2026-02-15 | AP-0005613 | AP | ARM-2526 | 05-300 | Freight and Expediting | V-2362 |  | 8584.86 | 8584.86 | Freight and Expediting - rental and logistics
2026-02-21 | PRJ-PAY-ARM-2526-20260221 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1023 | 51.52 | 3657.88 | Warranty and Punchlist - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2526-20260221 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 43.58 | 3377.43 | Closeout and O&M Documentation - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2526-20260221 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1037 | 41.2 | 3461 | Rework and Quality Correction - punchlist and closeout labor
2026-02-22 | AP-0005609 | AP | ARM-2526 | 02-410 | Plumbing Fixtures and Piping | V-2315 |  | 67.4 | 12132.57 | Plumbing Fixtures and Piping - released equipment package
2026-02-28 | PRJ-PAY-ARM-2526-20260228 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 63.92 | 4538.28 | Closeout and O&M Documentation - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2526-20260228 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1035 | 50.04 | 3878 | Rework and Quality Correction - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2526-20260228 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1042 | 35.87 | 3300.41 | Project Management and Supervision - field installation time
2026-03-07 | PRJ-PAY-ARM-2526-20260307 | PAY | ARM-2526 | 03-400 | Controls Programming and Checkout |  | E-1013 | 32.16 | 2283.56 | Controls Programming and Checkout - field installation time
2026-03-07 | PRJ-PAY-ARM-2526-20260307 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1021 | 32.83 | 2544.24 | Warranty and Punchlist - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2526-20260307 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 37.64 | 3161.63 | Closeout and O&M Documentation - supervision and planning
2026-03-08 | AP-0005616 | AP | ARM-2526 | 02-210 | Sheet Metal and Ductwork | V-2403 |  | 71.93 | 12947.14 | Sheet Metal and Ductwork - valves and piping lot
2026-03-14 | PRJ-PAY-ARM-2526-20260314 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1019 | 41.15 | 2921.48 | Warranty and Punchlist - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2526-20260314 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1026 | 35.51 | 2751.96 | Closeout and O&M Documentation - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2526-20260314 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1033 | 36.34 | 3052.17 | Rework and Quality Correction - startup and checkout
2026-03-15 | AP-0005617 | AP | ARM-2526 | 02-510 | Controls Panels and Devices | V-2417 |  | 79.41 | 14292.94 | Controls Panels and Devices - ductwork release
2026-03-18 | AP-0005614 | AP | ARM-2526 | 02-210 | Sheet Metal and Ductwork | V-2376 |  | 49.04 | 8826.61 | Sheet Metal and Ductwork - released equipment package
2026-03-18 | AP-0005618 | AP | ARM-2526 | 04-200 | Electrical and Controls Subcontract | V-2424 |  | 29784.22 | 29784.22 | Electrical and Controls Subcontract - trade partner progress billing
2026-03-18 | AP-0005619 | AP | ARM-2526 | 05-400 | Small Tools and Consumables | V-2436 |  | 7164.29 | 7164.29 | Small Tools and Consumables - permit and inspection fees
2026-03-21 | PRJ-PAY-ARM-2526-20260321 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1024 | 36.65 | 2602.37 | Closeout and O&M Documentation - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2526-20260321 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1031 | 37.59 | 2913.41 | Rework and Quality Correction - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2526-20260321 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1038 | 45.92 | 4224.32 | Project Management and Supervision - punchlist and closeout labor
2026-03-25 | AP-0005615 | AP | ARM-2526 | 02-510 | Controls Panels and Devices | V-2389 |  | 55.35 | 9963.46 | Controls Panels and Devices - fabricated material delivery
2026-03-25 | AP-0005620 | AP | ARM-2526 | 05-200 | Permits, Fees and Bonds | V-2448 |  | 5020.16 | 5020.16 | Permits, Fees and Bonds - freight and expediting
2026-03-28 | PRJ-PAY-ARM-2526-20260328 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1029 | 55.82 | 3963.13 | Rework and Quality Correction - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2526-20260328 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1036 | 39.86 | 3408.19 | Project Management and Supervision - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2526-20260328 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1043 | 32.49 | 2728.88 | Engineering, BIM and Coordination - field installation time
2026-03-31 | PRJ-PAY-ARM-2526-20260331 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1034 | 47.33 | 3739.43 | Project Management and Supervision - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2526-20260331 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1041 | 35.58 | 2757.8 | Engineering, BIM and Coordination - field installation time
2026-03-31 | PRJ-PAY-ARM-2526-20260331 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1048 | 35.45 | 2977.58 | Field Installation Labor - coordination and layout
2026-04-04 | AP-0005622 | AP | ARM-2526 | 02-610 | Insulation and Specialty Material | V-2474 |  | 59.62 | 10732.14 | Insulation and Specialty Material - valves and piping lot
2026-04-04 | AP-0005627 | AP | ARM-2526 | 05-300 | Freight and Expediting | V-2534 |  | 4496.42 | 4496.42 | Freight and Expediting - small tools and field consumables
2026-04-07 | PRJ-PAY-ARM-2526-20260407 | PAY | ARM-2526 | 06-100 | Warranty and Punchlist |  | E-1014 | 35.34 | 2509.13 | Warranty and Punchlist - field installation time
2026-04-07 | PRJ-PAY-ARM-2526-20260407 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1022 | 40.07 | 3105.33 | Closeout and O&M Documentation - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2526-20260407 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1029 | 47.44 | 3985 | Rework and Quality Correction - supervision and planning
2026-04-11 | AP-0005623 | AP | ARM-2526 | 02-310 | Hydronic Piping and Valves | V-2488 |  | 107.53 | 19356.14 | Hydronic Piping and Valves - ductwork release
2026-04-14 | PRJ-PAY-ARM-2526-20260414 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1020 | 57.19 | 4060.74 | Closeout and O&M Documentation - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2526-20260414 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1027 | 44.77 | 3469.65 | Rework and Quality Correction - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2526-20260414 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1034 | 34.62 | 3185.16 | Project Management and Supervision - startup and checkout
2026-04-18 | AP-0005624 | AP | ARM-2526 | 02-610 | Insulation and Specialty Material | V-2502 |  | 59.02 | 10624.35 | Insulation and Specialty Material - jobsite material replenishment
2026-04-21 | AP-0005621 | AP | ARM-2526 | 02-310 | Hydronic Piping and Valves | V-2460 |  | 74.61 | 13429.77 | Hydronic Piping and Valves - fabricated material delivery
2026-04-21 | AP-0005625 | AP | ARM-2526 | 04-300 | Testing and Balancing Subcontract | V-2509 |  | 34590.98 | 34590.98 | Testing and Balancing Subcontract - insulation progress invoice
2026-04-21 | AP-0005626 | AP | ARM-2526 | 06-400 | Temporary Facilities and Protection | V-2521 |  | 7535.21 | 7535.21 | Temporary Facilities and Protection - freight and expediting
2026-04-21 | PRJ-PAY-ARM-2526-20260421 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1025 | 47.08 | 3342.48 | Rework and Quality Correction - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2526-20260421 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1032 | 46.82 | 4003.18 | Project Management and Supervision - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2526-20260421 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1039 | 44.83 | 3766.05 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2526-20260428 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1030 | 41.68 | 3293.09 | Project Management and Supervision - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2526-20260428 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1037 | 51.45 | 3987.11 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2526-20260428 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1044 | 37.42 | 3143.5 | Field Installation Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2526-20260430 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 43.39 | 3080.55 | Engineering, BIM and Coordination - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2526-20260430 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1042 | 42.56 | 3298.41 | Field Installation Labor - field installation time
2026-04-30 | PRJ-PAY-ARM-2526-20260430 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1049 | 34.58 | 2905.11 | Startup, Testing and Commissioning - coordination and layout
2026-05-04 | AP-0005632 | AP | ARM-2526 | 02-410 | Plumbing Fixtures and Piping | V-2265 |  | 61.79 | 11122.87 | Plumbing Fixtures and Piping - fabricated material delivery
2026-05-07 | AP-0005629 | AP | ARM-2526 | 02-110 | Major HVAC Equipment | V-2201 |  | 50.6 | 9108.21 | Major HVAC Equipment - ductwork release
2026-05-07 | AP-0005634 | AP | ARM-2526 | 04-300 | Testing and Balancing Subcontract | V-2286 |  | 13502.52 | 13502.52 | Testing and Balancing Subcontract - electrical coordination scope
2026-05-07 | AP-0005636 | AP | ARM-2526 | 05-400 | Small Tools and Consumables | V-2310 |  | 5641.32 | 5641.32 | Small Tools and Consumables - rental and logistics
2026-05-07 | PRJ-PAY-ARM-2526-20260507 | PAY | ARM-2526 | 06-200 | Closeout and O&M Documentation |  | E-1015 | 70.97 | 5038.71 | Closeout and O&M Documentation - field installation time
2026-05-07 | PRJ-PAY-ARM-2526-20260507 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1023 | 44.57 | 3454.08 | Rework and Quality Correction - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2526-20260507 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1030 | 40.09 | 3688.01 | Project Management and Supervision - supervision and planning
2026-05-14 | AP-0005630 | AP | ARM-2526 | 02-410 | Plumbing Fixtures and Piping | V-2225 |  | 56.65 | 10196.1 | Plumbing Fixtures and Piping - jobsite material replenishment
2026-05-14 | PRJ-PAY-ARM-2526-20260514 | PAY | ARM-2526 | 06-300 | Rework and Quality Correction |  | E-1021 | 49.22 | 3494.35 | Rework and Quality Correction - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2526-20260514 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1028 | 28.15 | 2407.07 | Project Management and Supervision - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2526-20260514 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1035 | 40.01 | 3361.23 | Engineering, BIM and Coordination - startup and checkout
2026-05-14 | PRJ-PAY-ARM-2526-20260514 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1042 | 37.22 | 3368.47 | Field Installation Labor - punchlist and closeout labor
2026-05-21 | AP-0005631 | AP | ARM-2526 | 02-110 | Major HVAC Equipment | V-2244 |  | 87.46 | 15743.37 | Major HVAC Equipment - released equipment package
2026-05-21 | PRJ-PAY-ARM-2526-20260521 | PAY | ARM-2526 | 01-100 | Project Management and Supervision |  | E-1026 | 44.09 | 3482.77 | Project Management and Supervision - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2526-20260521 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1033 | 55.97 | 4337.29 | Engineering, BIM and Coordination - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2526-20260521 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1040 | 47.96 | 4028.97 | Field Installation Labor - punchlist and closeout labor
2026-05-24 | AP-0005628 | AP | ARM-2526 | 02-410 | Plumbing Fixtures and Piping | V-2029 |  | 98.35 | 17703.32 | Plumbing Fixtures and Piping - valves and piping lot
2026-05-24 | AP-0005633 | AP | ARM-2526 | 04-400 | Crane, Rigging and Specialty Trade | V-2272 |  | 23477.09 | 23477.09 | Crane, Rigging and Specialty Trade - testing and balancing services
2026-05-24 | AP-0005635 | AP | ARM-2526 | 05-100 | Equipment Rental and Rigging | V-2296 |  | 6124.92 | 6124.92 | Equipment Rental and Rigging - small tools and field consumables
2026-05-28 | PRJ-PAY-ARM-2526-20260528 | PAY | ARM-2526 | 01-200 | Engineering, BIM and Coordination |  | E-1031 | 53.82 | 3821.16 | Engineering, BIM and Coordination - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2526-20260528 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1038 | 52.93 | 4101.72 | Field Installation Labor - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2526-20260528 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1045 | 31.32 | 2630.7 | Startup, Testing and Commissioning - field installation time
2026-05-31 | PRJ-PAY-ARM-2526-20260531 | PAY | ARM-2526 | 03-100 | Field Installation Labor |  | E-1036 | 50.92 | 3615.05 | Field Installation Labor - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2526-20260531 | PAY | ARM-2526 | 03-200 | Startup, Testing and Commissioning |  | E-1043 | 50.03 | 3877.57 | Startup, Testing and Commissioning - field installation time
2026-05-31 | PRJ-PAY-ARM-2526-20260531 | PAY | ARM-2526 | 03-300 | Sheet Metal Fabrication Labor |  | E-1050 | 29.09 | 2443.16 | Sheet Metal Fabrication Labor - coordination and layout
2026-01-03 | AP-0005647 | AP | ARM-2602 | 02-310 | Hydronic Piping and Valves | V-2429 |  | 75.44 | 13579 | Hydronic Piping and Valves - released equipment package
2026-01-03 | AP-0005650 | AP | ARM-2602 | 04-100 | Insulation Subcontract | V-2464 |  | 27194.2 | 27194.2 | Insulation Subcontract - trade partner progress billing
2026-01-03 | AP-0005651 | AP | ARM-2602 | 05-400 | Small Tools and Consumables | V-2476 |  | 9458.85 | 9458.85 | Small Tools and Consumables - rental and logistics
2026-01-07 | PRJ-PAY-ARM-2602-20260107 | PAY | ARM-2602 | 01-100 | Project Management and Supervision |  | E-1007 | 35.61 | 2813.17 | Project Management and Supervision - field installation time
2026-01-07 | PRJ-PAY-ARM-2602-20260107 | PAY | ARM-2602 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 38.82 | 3008.45 | Engineering, BIM and Coordination - coordination and layout
2026-01-07 | PRJ-PAY-ARM-2602-20260107 | PAY | ARM-2602 | 03-100 | Field Installation Labor |  | E-1023 | 23.87 | 2005.19 | Field Installation Labor - supervision and planning
2026-01-10 | AP-0005648 | AP | ARM-2602 | 02-610 | Insulation and Specialty Material | V-2441 |  | 76.31 | 13736.41 | Insulation and Specialty Material - fabricated material delivery
2026-01-14 | PRJ-PAY-ARM-2602-20260114 | PAY | ARM-2602 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 44.82 | 3182.35 | Engineering, BIM and Coordination - coordination and layout
2026-01-14 | PRJ-PAY-ARM-2602-20260114 | PAY | ARM-2602 | 03-100 | Field Installation Labor |  | E-1021 | 29.37 | 2276.02 | Field Installation Labor - supervision and planning
2026-01-14 | PRJ-PAY-ARM-2602-20260114 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 37.6 | 3158.76 | Startup, Testing and Commissioning - startup and checkout
2026-01-17 | AP-0005649 | AP | ARM-2602 | 02-310 | Hydronic Piping and Valves | V-2455 |  | 84.72 | 15249.42 | Hydronic Piping and Valves - valves and piping lot
2026-01-21 | PRJ-PAY-ARM-2602-20260121 | PAY | ARM-2602 | 03-100 | Field Installation Labor |  | E-1019 | 46.55 | 3305.32 | Field Installation Labor - supervision and planning
2026-01-21 | PRJ-PAY-ARM-2602-20260121 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 30.67 | 2377.17 | Startup, Testing and Commissioning - startup and checkout
2026-01-21 | PRJ-PAY-ARM-2602-20260121 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 35.69 | 2998.34 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2602-20260128 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 37.42 | 2656.68 | Startup, Testing and Commissioning - startup and checkout
2026-01-28 | PRJ-PAY-ARM-2602-20260128 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 30.9 | 2394.52 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-01-28 | PRJ-PAY-ARM-2602-20260128 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1038 | 34.62 | 2908.15 | Controls Programming and Checkout - field installation time
2026-01-31 | PRJ-PAY-ARM-2602-20260131 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 35.75 | 2538.02 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-01-31 | PRJ-PAY-ARM-2602-20260131 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1036 | 32.51 | 2519.5 | Controls Programming and Checkout - field installation time
2026-01-31 | PRJ-PAY-ARM-2602-20260131 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1043 | 24.51 | 2058.48 | Warranty and Punchlist - coordination and layout
2026-02-03 | AP-0005655 | AP | ARM-2602 | 02-110 | Major HVAC Equipment | V-2531 |  | 51.15 | 9207.46 | Major HVAC Equipment - jobsite material replenishment
2026-02-06 | AP-0005652 | AP | ARM-2602 | 02-410 | Plumbing Fixtures and Piping | V-2490 |  | 82.27 | 14808.55 | Plumbing Fixtures and Piping - fabricated material delivery
2026-02-06 | AP-0005656 | AP | ARM-2602 | 04-200 | Electrical and Controls Subcontract | V-2010 |  | 28012.75 | 28012.75 | Electrical and Controls Subcontract - insulation progress invoice
2026-02-06 | AP-0005657 | AP | ARM-2602 | 06-400 | Temporary Facilities and Protection | V-2037 |  | 8913.15 | 8913.15 | Temporary Facilities and Protection - permit and inspection fees
2026-02-07 | PRJ-PAY-ARM-2602-20260207 | PAY | ARM-2602 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 48.41 | 3436.82 | Engineering, BIM and Coordination - field installation time
2026-02-07 | PRJ-PAY-ARM-2602-20260207 | PAY | ARM-2602 | 03-100 | Field Installation Labor |  | E-1016 | 49.58 | 3842.08 | Field Installation Labor - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2602-20260207 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 50.53 | 4244.68 | Startup, Testing and Commissioning - supervision and planning
2026-02-13 | AP-0005653 | AP | ARM-2602 | 02-110 | Major HVAC Equipment | V-2503 |  | 54.34 | 9780.62 | Major HVAC Equipment - valves and piping lot
2026-02-14 | PRJ-PAY-ARM-2602-20260214 | PAY | ARM-2602 | 03-100 | Field Installation Labor |  | E-1014 | 55.46 | 3937.31 | Field Installation Labor - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2602-20260214 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 51.78 | 4012.99 | Startup, Testing and Commissioning - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2602-20260214 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 43.55 | 3658.47 | Sheet Metal Fabrication Labor - startup and checkout
2026-02-20 | AP-0005654 | AP | ARM-2602 | 02-410 | Plumbing Fixtures and Piping | V-2517 |  | 81.05 | 14589.03 | Plumbing Fixtures and Piping - ductwork release
2026-02-21 | PRJ-PAY-ARM-2602-20260221 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 39.6 | 2811.57 | Startup, Testing and Commissioning - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2602-20260221 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 51.22 | 3969.82 | Sheet Metal Fabrication Labor - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2602-20260221 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1034 | 45.98 | 3862.55 | Controls Programming and Checkout - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2602-20260228 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 44 | 3123.89 | Sheet Metal Fabrication Labor - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2602-20260228 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1032 | 38.89 | 3014.27 | Controls Programming and Checkout - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2602-20260228 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1039 | 40.21 | 3377.99 | Warranty and Punchlist - field installation time
2026-03-06 | AP-0005661 | AP | ARM-2602 | 02-210 | Sheet Metal and Ductwork | V-2270 |  | 39.76 | 7155.97 | Sheet Metal and Ductwork - released equipment package
2026-03-07 | PRJ-PAY-ARM-2602-20260307 | PAY | ARM-2602 | 03-100 | Field Installation Labor |  | E-1009 | 57.56 | 4086.42 | Field Installation Labor - field installation time
2026-03-07 | PRJ-PAY-ARM-2602-20260307 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 38.71 | 2999.73 | Startup, Testing and Commissioning - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2602-20260307 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 42.23 | 3547.04 | Sheet Metal Fabrication Labor - supervision and planning
2026-03-09 | AP-0005658 | AP | ARM-2602 | 02-510 | Controls Panels and Devices | V-2208 |  | 81.81 | 14726.1 | Controls Panels and Devices - valves and piping lot
2026-03-09 | AP-0005662 | AP | ARM-2602 | 04-300 | Testing and Balancing Subcontract | V-2277 |  | 31691.7 | 31691.7 | Testing and Balancing Subcontract - testing and balancing services
2026-03-09 | AP-0005663 | AP | ARM-2602 | 05-100 | Equipment Rental and Rigging | V-2289 |  | 8236.26 | 8236.26 | Equipment Rental and Rigging - freight and expediting
2026-03-14 | PRJ-PAY-ARM-2602-20260314 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 41.08 | 2916.59 | Startup, Testing and Commissioning - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2602-20260314 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 54.91 | 4255.64 | Sheet Metal Fabrication Labor - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2602-20260314 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1030 | 30.68 | 2577.21 | Controls Programming and Checkout - startup and checkout
2026-03-16 | AP-0005659 | AP | ARM-2602 | 02-210 | Sheet Metal and Ductwork | V-2231 |  | 67.84 | 12211.92 | Sheet Metal and Ductwork - ductwork release
2026-03-16 | AP-0005664 | AP | ARM-2602 | 05-400 | Small Tools and Consumables | V-2303 |  | 4164.84 | 4164.84 | Small Tools and Consumables - small tools and field consumables
2026-03-21 | PRJ-PAY-ARM-2602-20260321 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 43.71 | 3103.27 | Sheet Metal Fabrication Labor - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2602-20260321 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1028 | 40.34 | 3126.25 | Controls Programming and Checkout - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2602-20260321 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1035 | 29.61 | 2486.91 | Warranty and Punchlist - punchlist and closeout labor
2026-03-23 | AP-0005660 | AP | ARM-2602 | 02-510 | Controls Panels and Devices | V-2250 |  | 70.86 | 12754.61 | Controls Panels and Devices - jobsite material replenishment
2026-03-28 | PRJ-PAY-ARM-2602-20260328 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1026 | 35.74 | 2537.4 | Controls Programming and Checkout - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2602-20260328 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1033 | 36.95 | 2863.96 | Warranty and Punchlist - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2602-20260328 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 36.7 | 3082.54 | Closeout and O&M Documentation - field installation time
2026-03-31 | PRJ-PAY-ARM-2602-20260331 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1031 | 45 | 3195.1 | Warranty and Punchlist - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2602-20260331 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 43.07 | 3338.06 | Closeout and O&M Documentation - field installation time
2026-03-31 | PRJ-PAY-ARM-2602-20260331 | PAY | ARM-2602 | 06-300 | Rework and Quality Correction |  | E-1045 | 32.53 | 2732.48 | Rework and Quality Correction - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2602-20260407 | PAY | ARM-2602 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 52.94 | 3758.54 | Startup, Testing and Commissioning - field installation time
2026-04-07 | PRJ-PAY-ARM-2602-20260407 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 41.1 | 3185.28 | Sheet Metal Fabrication Labor - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2602-20260407 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1026 | 49.7 | 4174.44 | Controls Programming and Checkout - supervision and planning
2026-04-09 | AP-0005668 | AP | ARM-2602 | 02-310 | Hydronic Piping and Valves | V-2357 |  | 85.19 | 15334.62 | Hydronic Piping and Valves - fabricated material delivery
2026-04-12 | AP-0005665 | AP | ARM-2602 | 02-610 | Insulation and Specialty Material | V-2315 |  | 55.51 | 9991.41 | Insulation and Specialty Material - ductwork release
2026-04-12 | AP-0005669 | AP | ARM-2602 | 04-400 | Crane, Rigging and Specialty Trade | V-2364 |  | 34355.64 | 34355.64 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-04-12 | AP-0005670 | AP | ARM-2602 | 05-200 | Permits, Fees and Bonds | V-2376 |  | 6214.03 | 6214.03 | Permits, Fees and Bonds - small tools and field consumables
2026-04-14 | PRJ-PAY-ARM-2602-20260414 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 39.4 | 2797.42 | Sheet Metal Fabrication Labor - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2602-20260414 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1024 | 38.79 | 3005.9 | Controls Programming and Checkout - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2602-20260414 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1031 | 49.25 | 4136.89 | Warranty and Punchlist - startup and checkout
2026-04-19 | AP-0005666 | AP | ARM-2602 | 02-310 | Hydronic Piping and Valves | V-2329 |  | 107.94 | 19429.33 | Hydronic Piping and Valves - jobsite material replenishment
2026-04-19 | AP-0005671 | AP | ARM-2602 | 06-400 | Temporary Facilities and Protection | V-2389 |  | 6278.93 | 6278.93 | Temporary Facilities and Protection - rental and logistics
2026-04-21 | PRJ-PAY-ARM-2602-20260421 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1022 | 43.05 | 3056.34 | Controls Programming and Checkout - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2602-20260421 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1029 | 46.64 | 3614.74 | Warranty and Punchlist - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2602-20260421 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 35.76 | 3003.95 | Closeout and O&M Documentation - punchlist and closeout labor
2026-04-25 | AP-0005667 | AP | ARM-2602 | 02-610 | Insulation and Specialty Material | V-2343 |  | 63.68 | 11462.96 | Insulation and Specialty Material - released equipment package
2026-04-28 | PRJ-PAY-ARM-2602-20260428 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1027 | 48.73 | 3459.67 | Warranty and Punchlist - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2602-20260428 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 36.47 | 2826.19 | Closeout and O&M Documentation - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2602-20260428 | PAY | ARM-2602 | 06-300 | Rework and Quality Correction |  | E-1041 | 50.96 | 4280.67 | Rework and Quality Correction - field installation time
2026-04-30 | PRJ-PAY-ARM-2602-20260430 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 68.99 | 4898 | Closeout and O&M Documentation - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2602-20260430 | PAY | ARM-2602 | 06-300 | Rework and Quality Correction |  | E-1039 | 39.6 | 3068.64 | Rework and Quality Correction - field installation time
2026-04-30 | PRJ-PAY-ARM-2602-20260430 | PAY | ARM-2602 | 01-100 | Project Management and Supervision |  | E-1046 | 41.61 | 3828.41 | Project Management and Supervision - coordination and layout
2026-05-05 | AP-0005674 | AP | ARM-2602 | 02-110 | Major HVAC Equipment | V-2429 |  | 54.44 | 9799.5 | Major HVAC Equipment - fabricated material delivery
2026-05-07 | PRJ-PAY-ARM-2602-20260507 | PAY | ARM-2602 | 03-300 | Sheet Metal Fabrication Labor |  | E-1012 | 46.42 | 3295.74 | Sheet Metal Fabrication Labor - field installation time
2026-05-07 | PRJ-PAY-ARM-2602-20260507 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1020 | 49 | 3797.72 | Controls Programming and Checkout - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2602-20260507 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1027 | 42.56 | 3574.74 | Warranty and Punchlist - supervision and planning
2026-05-12 | AP-0005675 | AP | ARM-2602 | 02-410 | Plumbing Fixtures and Piping | V-2441 |  | 96.21 | 17317.25 | Plumbing Fixtures and Piping - valves and piping lot
2026-05-14 | PRJ-PAY-ARM-2602-20260514 | PAY | ARM-2602 | 03-400 | Controls Programming and Checkout |  | E-1018 | 44.29 | 3144.88 | Controls Programming and Checkout - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2602-20260514 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1025 | 50.69 | 3928.67 | Warranty and Punchlist - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2602-20260514 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 39.41 | 3310.05 | Closeout and O&M Documentation - startup and checkout
2026-05-15 | AP-0005672 | AP | ARM-2602 | 02-110 | Major HVAC Equipment | V-2402 |  | 64.73 | 11651.87 | Major HVAC Equipment - jobsite material replenishment
2026-05-15 | AP-0005677 | AP | ARM-2602 | 04-100 | Insulation Subcontract | V-2460 |  | 24874.1 | 24874.1 | Insulation Subcontract - rigging and specialty support
2026-05-15 | AP-0005679 | AP | ARM-2602 | 05-300 | Freight and Expediting | V-2484 |  | 5839.33 | 5839.33 | Freight and Expediting - rental and logistics
2026-05-19 | AP-0005676 | AP | ARM-2602 | 02-110 | Major HVAC Equipment | V-2455 |  | 94.63 | 17033.38 | Major HVAC Equipment - ductwork release
2026-05-21 | PRJ-PAY-ARM-2602-20260521 | PAY | ARM-2602 | 06-100 | Warranty and Punchlist |  | E-1023 | 51.05 | 3624.43 | Warranty and Punchlist - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2602-20260521 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1030 | 48.48 | 3757.15 | Closeout and O&M Documentation - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2602-20260521 | PAY | ARM-2602 | 06-300 | Rework and Quality Correction |  | E-1037 | 47.13 | 3958.81 | Rework and Quality Correction - punchlist and closeout labor
2026-05-22 | AP-0005673 | AP | ARM-2602 | 02-410 | Plumbing Fixtures and Piping | V-2415 |  | 51.22 | 9220.47 | Plumbing Fixtures and Piping - released equipment package
2026-05-22 | AP-0005678 | AP | ARM-2602 | 04-400 | Crane, Rigging and Specialty Trade | V-2474 |  | 14481.61 | 14481.61 | Crane, Rigging and Specialty Trade - trade partner progress billing
2026-05-22 | AP-0005680 | AP | ARM-2602 | 05-100 | Equipment Rental and Rigging | V-2498 |  | 6138.49 | 6138.49 | Equipment Rental and Rigging - permit and inspection fees
2026-05-28 | PRJ-PAY-ARM-2602-20260528 | PAY | ARM-2602 | 06-200 | Closeout and O&M Documentation |  | E-1028 | 45.98 | 3264.55 | Closeout and O&M Documentation - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2602-20260528 | PAY | ARM-2602 | 06-300 | Rework and Quality Correction |  | E-1035 | 44.44 | 3443.74 | Rework and Quality Correction - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2602-20260528 | PAY | ARM-2602 | 01-100 | Project Management and Supervision |  | E-1042 | 29.64 | 2726.44 | Project Management and Supervision - field installation time
2026-05-28 | PRJ-PAY-ARM-2602-20260528 | PAY | ARM-2602 | 01-200 | Engineering, BIM and Coordination |  | E-1049 | 35.63 | 3224.17 | Engineering, BIM and Coordination - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2602-20260531 | PAY | ARM-2602 | 06-300 | Rework and Quality Correction |  | E-1033 | 52.87 | 3754.08 | Rework and Quality Correction - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2602-20260531 | PAY | ARM-2602 | 01-100 | Project Management and Supervision |  | E-1040 | 35.04 | 2996.31 | Project Management and Supervision - field installation time
2026-05-31 | PRJ-PAY-ARM-2602-20260531 | PAY | ARM-2602 | 01-200 | Engineering, BIM and Coordination |  | E-1047 | 35.26 | 2962.21 | Engineering, BIM and Coordination - coordination and layout
2026-05-31 | PRJ-PAY-ARM-2602-20260531 | PAY | ARM-2602 | 03-100 | Field Installation Labor |  | E-1080 | 37.73 | 3414.31 | Field Installation Labor - supervision and planning
2026-02-03 | AP-0005692 | AP | ARM-2605 | 02-310 | Hydronic Piping and Valves | V-2300 |  | 62.89 | 11319.48 | Hydronic Piping and Valves - released equipment package
2026-02-03 | AP-0005695 | AP | ARM-2605 | 04-100 | Insulation Subcontract | V-2336 |  | 25805.44 | 25805.44 | Insulation Subcontract - trade partner progress billing
2026-02-03 | AP-0005696 | AP | ARM-2605 | 05-400 | Small Tools and Consumables | V-2348 |  | 8975.81 | 8975.81 | Small Tools and Consumables - rental and logistics
2026-02-07 | PRJ-PAY-ARM-2605-20260207 | PAY | ARM-2605 | 01-100 | Project Management and Supervision |  | E-1007 | 40.03 | 3162.1 | Project Management and Supervision - field installation time
2026-02-07 | PRJ-PAY-ARM-2605-20260207 | PAY | ARM-2605 | 01-200 | Engineering, BIM and Coordination |  | E-1015 | 36.8 | 2852.28 | Engineering, BIM and Coordination - coordination and layout
2026-02-07 | PRJ-PAY-ARM-2605-20260207 | PAY | ARM-2605 | 03-100 | Field Installation Labor |  | E-1023 | 35.84 | 3010.21 | Field Installation Labor - supervision and planning
2026-02-10 | AP-0005693 | AP | ARM-2605 | 02-610 | Insulation and Specialty Material | V-2313 |  | 78.67 | 14159.76 | Insulation and Specialty Material - fabricated material delivery
2026-02-14 | PRJ-PAY-ARM-2605-20260214 | PAY | ARM-2605 | 01-200 | Engineering, BIM and Coordination |  | E-1013 | 44.19 | 3137.71 | Engineering, BIM and Coordination - coordination and layout
2026-02-14 | PRJ-PAY-ARM-2605-20260214 | PAY | ARM-2605 | 03-100 | Field Installation Labor |  | E-1021 | 45.65 | 3537.56 | Field Installation Labor - supervision and planning
2026-02-14 | PRJ-PAY-ARM-2605-20260214 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1028 | 38.82 | 3260.59 | Startup, Testing and Commissioning - startup and checkout
2026-02-17 | AP-0005694 | AP | ARM-2605 | 02-310 | Hydronic Piping and Valves | V-2327 |  | 82.84 | 14911.88 | Hydronic Piping and Valves - valves and piping lot
2026-02-21 | PRJ-PAY-ARM-2605-20260221 | PAY | ARM-2605 | 03-100 | Field Installation Labor |  | E-1019 | 55.12 | 3913.39 | Field Installation Labor - supervision and planning
2026-02-21 | PRJ-PAY-ARM-2605-20260221 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 34.06 | 2639.37 | Startup, Testing and Commissioning - startup and checkout
2026-02-21 | PRJ-PAY-ARM-2605-20260221 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1033 | 41.15 | 3456.55 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2605-20260228 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 45.72 | 3246.13 | Startup, Testing and Commissioning - startup and checkout
2026-02-28 | PRJ-PAY-ARM-2605-20260228 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 31.48 | 2439.87 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-02-28 | PRJ-PAY-ARM-2605-20260228 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1038 | 41.56 | 3491.41 | Controls Programming and Checkout - field installation time
2026-03-03 | AP-0005700 | AP | ARM-2605 | 02-110 | Major HVAC Equipment | V-2403 |  | 52.14 | 9385.45 | Major HVAC Equipment - jobsite material replenishment
2026-03-06 | AP-0005697 | AP | ARM-2605 | 02-410 | Plumbing Fixtures and Piping | V-2362 |  | 71.22 | 12820.26 | Plumbing Fixtures and Piping - fabricated material delivery
2026-03-06 | AP-0005701 | AP | ARM-2605 | 04-200 | Electrical and Controls Subcontract | V-2410 |  | 26446.57 | 26446.57 | Electrical and Controls Subcontract - insulation progress invoice
2026-03-06 | AP-0005702 | AP | ARM-2605 | 06-400 | Temporary Facilities and Protection | V-2422 |  | 8414.81 | 8414.81 | Temporary Facilities and Protection - permit and inspection fees
2026-03-07 | PRJ-PAY-ARM-2605-20260307 | PAY | ARM-2605 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 42.23 | 2998.48 | Engineering, BIM and Coordination - field installation time
2026-03-07 | PRJ-PAY-ARM-2605-20260307 | PAY | ARM-2605 | 03-100 | Field Installation Labor |  | E-1016 | 34.88 | 2702.99 | Field Installation Labor - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2605-20260307 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 38.81 | 3260.46 | Startup, Testing and Commissioning - supervision and planning
2026-03-13 | AP-0005698 | AP | ARM-2605 | 02-110 | Major HVAC Equipment | V-2376 |  | 54.62 | 9832.5 | Major HVAC Equipment - valves and piping lot
2026-03-14 | PRJ-PAY-ARM-2605-20260314 | PAY | ARM-2605 | 03-100 | Field Installation Labor |  | E-1014 | 39.61 | 2812.65 | Field Installation Labor - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2605-20260314 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 46.92 | 3636.15 | Startup, Testing and Commissioning - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2605-20260314 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 30.71 | 2579.38 | Sheet Metal Fabrication Labor - startup and checkout
2026-03-20 | AP-0005699 | AP | ARM-2605 | 02-410 | Plumbing Fixtures and Piping | V-2389 |  | 75.79 | 13642.23 | Plumbing Fixtures and Piping - ductwork release
2026-03-21 | PRJ-PAY-ARM-2605-20260321 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 43.54 | 3091.67 | Startup, Testing and Commissioning - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2605-20260321 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 39.21 | 3038.53 | Sheet Metal Fabrication Labor - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2605-20260321 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1034 | 25.57 | 2147.62 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2605-20260328 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 30.14 | 2139.91 | Sheet Metal Fabrication Labor - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2605-20260328 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1032 | 33.21 | 2573.79 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2605-20260328 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1039 | 31.99 | 2687.04 | Warranty and Punchlist - field installation time
2026-03-31 | PRJ-PAY-ARM-2605-20260331 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1030 | 31.84 | 2260.99 | Controls Programming and Checkout - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2605-20260331 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1037 | 36.12 | 2799.64 | Warranty and Punchlist - field installation time
2026-03-31 | PRJ-PAY-ARM-2605-20260331 | PAY | ARM-2605 | 06-200 | Closeout and O&M Documentation |  | E-1044 | 25.51 | 2142.67 | Closeout and O&M Documentation - coordination and layout
2026-04-06 | AP-0005706 | AP | ARM-2605 | 02-210 | Sheet Metal and Ductwork | V-2476 |  | 59.88 | 10778.24 | Sheet Metal and Ductwork - released equipment package
2026-04-07 | PRJ-PAY-ARM-2605-20260407 | PAY | ARM-2605 | 03-100 | Field Installation Labor |  | E-1009 | 53.2 | 3777.04 | Field Installation Labor - field installation time
2026-04-07 | PRJ-PAY-ARM-2605-20260407 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 47.59 | 3687.98 | Startup, Testing and Commissioning - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2605-20260407 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 37.54 | 3153.69 | Sheet Metal Fabrication Labor - supervision and planning
2026-04-09 | AP-0005703 | AP | ARM-2605 | 02-510 | Controls Panels and Devices | V-2436 |  | 68.24 | 12284.05 | Controls Panels and Devices - valves and piping lot
2026-04-09 | AP-0005707 | AP | ARM-2605 | 04-300 | Testing and Balancing Subcontract | V-2483 |  | 31648.53 | 31648.53 | Testing and Balancing Subcontract - testing and balancing services
2026-04-09 | AP-0005708 | AP | ARM-2605 | 05-100 | Equipment Rental and Rigging | V-2495 |  | 8409.06 | 8409.06 | Equipment Rental and Rigging - freight and expediting
2026-04-14 | PRJ-PAY-ARM-2605-20260414 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1015 | 53.82 | 3821.22 | Startup, Testing and Commissioning - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2605-20260414 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 42.61 | 3302.07 | Sheet Metal Fabrication Labor - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2605-20260414 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1030 | 31.11 | 2612.87 | Controls Programming and Checkout - startup and checkout
2026-04-16 | AP-0005704 | AP | ARM-2605 | 02-210 | Sheet Metal and Ductwork | V-2448 |  | 61.92 | 11145.5 | Sheet Metal and Ductwork - ductwork release
2026-04-16 | AP-0005709 | AP | ARM-2605 | 05-400 | Small Tools and Consumables | V-2509 |  | 3975.15 | 3975.15 | Small Tools and Consumables - small tools and field consumables
2026-04-21 | PRJ-PAY-ARM-2605-20260421 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 38.6 | 2740.85 | Sheet Metal Fabrication Labor - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2605-20260421 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1028 | 41.84 | 3242.36 | Controls Programming and Checkout - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2605-20260421 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1035 | 32.4 | 2721.34 | Warranty and Punchlist - punchlist and closeout labor
2026-04-23 | AP-0005705 | AP | ARM-2605 | 02-510 | Controls Panels and Devices | V-2462 |  | 69.87 | 12576.99 | Controls Panels and Devices - jobsite material replenishment
2026-04-28 | PRJ-PAY-ARM-2605-20260428 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1026 | 33.75 | 2396.27 | Controls Programming and Checkout - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2605-20260428 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1033 | 35.49 | 2750.27 | Warranty and Punchlist - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2605-20260428 | PAY | ARM-2605 | 06-200 | Closeout and O&M Documentation |  | E-1040 | 39.59 | 3325.8 | Closeout and O&M Documentation - field installation time
2026-04-30 | PRJ-PAY-ARM-2605-20260430 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1031 | 48.04 | 3410.88 | Warranty and Punchlist - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2605-20260430 | PAY | ARM-2605 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 36.84 | 2855.46 | Closeout and O&M Documentation - field installation time
2026-04-30 | PRJ-PAY-ARM-2605-20260430 | PAY | ARM-2605 | 06-300 | Rework and Quality Correction |  | E-1045 | 35.56 | 2986.68 | Rework and Quality Correction - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2605-20260507 | PAY | ARM-2605 | 03-200 | Startup, Testing and Commissioning |  | E-1010 | 52.72 | 3743.22 | Startup, Testing and Commissioning - field installation time
2026-05-07 | PRJ-PAY-ARM-2605-20260507 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 53.72 | 4163.36 | Sheet Metal Fabrication Labor - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2605-20260507 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1026 | 36.22 | 3042.85 | Controls Programming and Checkout - supervision and planning
2026-05-09 | AP-0005713 | AP | ARM-2605 | 02-310 | Hydronic Piping and Valves | V-2205 |  | 67.69 | 12185.03 | Hydronic Piping and Valves - fabricated material delivery
2026-05-12 | AP-0005710 | AP | ARM-2605 | 02-610 | Insulation and Specialty Material | V-2521 |  | 66.51 | 11971.54 | Insulation and Specialty Material - ductwork release
2026-05-12 | AP-0005714 | AP | ARM-2605 | 04-400 | Crane, Rigging and Specialty Trade | V-2217 |  | 33833.98 | 33833.98 | Crane, Rigging and Specialty Trade - electrical coordination scope
2026-05-12 | AP-0005715 | AP | ARM-2605 | 05-200 | Permits, Fees and Bonds | V-2234 |  | 8559.36 | 8559.36 | Permits, Fees and Bonds - small tools and field consumables
2026-05-14 | PRJ-PAY-ARM-2605-20260514 | PAY | ARM-2605 | 03-300 | Sheet Metal Fabrication Labor |  | E-1016 | 36.57 | 2596.39 | Sheet Metal Fabrication Labor - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2605-20260514 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1024 | 39.9 | 3092.25 | Controls Programming and Checkout - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2605-20260514 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1031 | 48.82 | 4100.63 | Warranty and Punchlist - startup and checkout
2026-05-19 | AP-0005711 | AP | ARM-2605 | 02-310 | Hydronic Piping and Valves | V-2534 |  | 79.29 | 14271.61 | Hydronic Piping and Valves - jobsite material replenishment
2026-05-19 | AP-0005716 | AP | ARM-2605 | 06-400 | Temporary Facilities and Protection | V-2255 |  | 3743.9 | 3743.9 | Temporary Facilities and Protection - rental and logistics
2026-05-21 | PRJ-PAY-ARM-2605-20260521 | PAY | ARM-2605 | 03-400 | Controls Programming and Checkout |  | E-1022 | 37.86 | 2687.73 | Controls Programming and Checkout - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2605-20260521 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1029 | 49.79 | 3858.96 | Warranty and Punchlist - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2605-20260521 | PAY | ARM-2605 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 35.49 | 2981.43 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-25 | AP-0005712 | AP | ARM-2605 | 02-610 | Insulation and Specialty Material | V-2033 |  | 94.09 | 16936.51 | Insulation and Specialty Material - released equipment package
2026-05-28 | PRJ-PAY-ARM-2605-20260528 | PAY | ARM-2605 | 06-100 | Warranty and Punchlist |  | E-1027 | 46.52 | 3303.17 | Warranty and Punchlist - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2605-20260528 | PAY | ARM-2605 | 06-200 | Closeout and O&M Documentation |  | E-1034 | 55.44 | 4296.31 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2605-20260528 | PAY | ARM-2605 | 06-300 | Rework and Quality Correction |  | E-1041 | 33.41 | 2806.6 | Rework and Quality Correction - field installation time
2026-05-31 | PRJ-PAY-ARM-2605-20260531 | PAY | ARM-2605 | 06-200 | Closeout and O&M Documentation |  | E-1032 | 46.87 | 3327.84 | Closeout and O&M Documentation - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2605-20260531 | PAY | ARM-2605 | 06-300 | Rework and Quality Correction |  | E-1039 | 52.47 | 4066.3 | Rework and Quality Correction - field installation time
2026-05-31 | PRJ-PAY-ARM-2605-20260531 | PAY | ARM-2605 | 01-100 | Project Management and Supervision |  | E-1046 | 45.89 | 4221.83 | Project Management and Supervision - coordination and layout
2026-03-03 | AP-0005726 | AP | ARM-2608 | 02-310 | Hydronic Piping and Valves | V-2374 |  | 76.09 | 13695.89 | Hydronic Piping and Valves - released equipment package
2026-03-03 | AP-0005729 | AP | ARM-2608 | 04-100 | Insulation Subcontract | V-2410 |  | 24930.96 | 24930.96 | Insulation Subcontract - trade partner progress billing
2026-03-03 | AP-0005730 | AP | ARM-2608 | 05-400 | Small Tools and Consumables | V-2422 |  | 8671.64 | 8671.64 | Small Tools and Consumables - rental and logistics
2026-03-07 | PRJ-PAY-ARM-2608-20260307 | PAY | ARM-2608 | 01-100 | Project Management and Supervision |  | E-1007 | 31.43 | 2482.76 | Project Management and Supervision - field installation time
2026-03-07 | PRJ-PAY-ARM-2608-20260307 | PAY | ARM-2608 | 01-200 | Engineering, BIM and Coordination |  | E-1014 | 30.78 | 2385.13 | Engineering, BIM and Coordination - coordination and layout
2026-03-07 | PRJ-PAY-ARM-2608-20260307 | PAY | ARM-2608 | 03-100 | Field Installation Labor |  | E-1021 | 27.47 | 2307.53 | Field Installation Labor - supervision and planning
2026-03-10 | AP-0005727 | AP | ARM-2608 | 02-610 | Insulation and Specialty Material | V-2388 |  | 76.38 | 13748.36 | Insulation and Specialty Material - fabricated material delivery
2026-03-14 | PRJ-PAY-ARM-2608-20260314 | PAY | ARM-2608 | 01-200 | Engineering, BIM and Coordination |  | E-1012 | 39.53 | 2806.65 | Engineering, BIM and Coordination - coordination and layout
2026-03-14 | PRJ-PAY-ARM-2608-20260314 | PAY | ARM-2608 | 03-100 | Field Installation Labor |  | E-1019 | 39.24 | 3040.89 | Field Installation Labor - supervision and planning
2026-03-14 | PRJ-PAY-ARM-2608-20260314 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1026 | 24.43 | 2052.43 | Startup, Testing and Commissioning - startup and checkout
2026-03-17 | AP-0005728 | AP | ARM-2608 | 02-310 | Hydronic Piping and Valves | V-2402 |  | 64.32 | 11578.13 | Hydronic Piping and Valves - valves and piping lot
2026-03-21 | PRJ-PAY-ARM-2608-20260321 | PAY | ARM-2608 | 03-100 | Field Installation Labor |  | E-1017 | 38.64 | 2743.69 | Field Installation Labor - supervision and planning
2026-03-21 | PRJ-PAY-ARM-2608-20260321 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1024 | 35.9 | 2781.94 | Startup, Testing and Commissioning - startup and checkout
2026-03-21 | PRJ-PAY-ARM-2608-20260321 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1031 | 28.96 | 2432.74 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2608-20260328 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 37.12 | 2635.82 | Startup, Testing and Commissioning - startup and checkout
2026-03-28 | PRJ-PAY-ARM-2608-20260328 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1029 | 26.96 | 2089.26 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-03-28 | PRJ-PAY-ARM-2608-20260328 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1036 | 30.62 | 2571.85 | Controls Programming and Checkout - field installation time
2026-03-31 | PRJ-PAY-ARM-2608-20260331 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 33.06 | 2347.41 | Sheet Metal Fabrication Labor - punchlist and closeout labor
2026-03-31 | PRJ-PAY-ARM-2608-20260331 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1034 | 27.01 | 2093.11 | Controls Programming and Checkout - field installation time
2026-03-31 | PRJ-PAY-ARM-2608-20260331 | PAY | ARM-2608 | 06-100 | Warranty and Punchlist |  | E-1041 | 24.8 | 2083.26 | Warranty and Punchlist - coordination and layout
2026-04-03 | AP-0005734 | AP | ARM-2608 | 02-110 | Major HVAC Equipment | V-2476 |  | 57.12 | 10281.3 | Major HVAC Equipment - jobsite material replenishment
2026-04-06 | AP-0005731 | AP | ARM-2608 | 02-410 | Plumbing Fixtures and Piping | V-2436 |  | 70.62 | 12710.8 | Plumbing Fixtures and Piping - fabricated material delivery
2026-04-06 | AP-0005735 | AP | ARM-2608 | 04-200 | Electrical and Controls Subcontract | V-2483 |  | 27026.61 | 27026.61 | Electrical and Controls Subcontract - insulation progress invoice
2026-04-06 | AP-0005736 | AP | ARM-2608 | 06-400 | Temporary Facilities and Protection | V-2495 |  | 8599.37 | 8599.37 | Temporary Facilities and Protection - permit and inspection fees
2026-04-07 | PRJ-PAY-ARM-2608-20260407 | PAY | ARM-2608 | 01-200 | Engineering, BIM and Coordination |  | E-1008 | 31.59 | 2243.18 | Engineering, BIM and Coordination - field installation time
2026-04-07 | PRJ-PAY-ARM-2608-20260407 | PAY | ARM-2608 | 03-100 | Field Installation Labor |  | E-1015 | 48.97 | 3795.4 | Field Installation Labor - coordination and layout
2026-04-07 | PRJ-PAY-ARM-2608-20260407 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1022 | 37.14 | 3119.9 | Startup, Testing and Commissioning - supervision and planning
2026-04-13 | AP-0005732 | AP | ARM-2608 | 02-110 | Major HVAC Equipment | V-2448 |  | 55.99 | 10078.28 | Major HVAC Equipment - valves and piping lot
2026-04-14 | PRJ-PAY-ARM-2608-20260414 | PAY | ARM-2608 | 03-100 | Field Installation Labor |  | E-1013 | 45.19 | 3208.65 | Field Installation Labor - coordination and layout
2026-04-14 | PRJ-PAY-ARM-2608-20260414 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1020 | 33.78 | 2617.85 | Startup, Testing and Commissioning - supervision and planning
2026-04-14 | PRJ-PAY-ARM-2608-20260414 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1027 | 40.47 | 3399.69 | Sheet Metal Fabrication Labor - startup and checkout
2026-04-20 | AP-0005733 | AP | ARM-2608 | 02-410 | Plumbing Fixtures and Piping | V-2462 |  | 75.62 | 13611.95 | Plumbing Fixtures and Piping - ductwork release
2026-04-21 | PRJ-PAY-ARM-2608-20260421 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1018 | 37.25 | 2645.1 | Startup, Testing and Commissioning - supervision and planning
2026-04-21 | PRJ-PAY-ARM-2608-20260421 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1025 | 39.1 | 3030.42 | Sheet Metal Fabrication Labor - startup and checkout
2026-04-21 | PRJ-PAY-ARM-2608-20260421 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1032 | 33.14 | 2783.86 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2608-20260428 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 44.87 | 3185.76 | Sheet Metal Fabrication Labor - startup and checkout
2026-04-28 | PRJ-PAY-ARM-2608-20260428 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1030 | 29.25 | 2266.91 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-28 | PRJ-PAY-ARM-2608-20260428 | PAY | ARM-2608 | 06-100 | Warranty and Punchlist |  | E-1037 | 25.12 | 2110.38 | Warranty and Punchlist - field installation time
2026-04-30 | PRJ-PAY-ARM-2608-20260430 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1028 | 32.54 | 2310.5 | Controls Programming and Checkout - punchlist and closeout labor
2026-04-30 | PRJ-PAY-ARM-2608-20260430 | PAY | ARM-2608 | 06-100 | Warranty and Punchlist |  | E-1035 | 34.93 | 2707.21 | Warranty and Punchlist - field installation time
2026-04-30 | PRJ-PAY-ARM-2608-20260430 | PAY | ARM-2608 | 06-200 | Closeout and O&M Documentation |  | E-1042 | 27.9 | 2343.59 | Closeout and O&M Documentation - coordination and layout
2026-05-06 | AP-0005740 | AP | ARM-2608 | 02-210 | Sheet Metal and Ductwork | V-2037 |  | 57.14 | 10285.88 | Sheet Metal and Ductwork - released equipment package
2026-05-07 | PRJ-PAY-ARM-2608-20260507 | PAY | ARM-2608 | 03-100 | Field Installation Labor |  | E-1009 | 45.76 | 3248.79 | Field Installation Labor - field installation time
2026-05-07 | PRJ-PAY-ARM-2608-20260507 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1016 | 46.69 | 3618.33 | Startup, Testing and Commissioning - coordination and layout
2026-05-07 | PRJ-PAY-ARM-2608-20260507 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1023 | 45.65 | 3834.29 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-09 | AP-0005737 | AP | ARM-2608 | 02-510 | Controls Panels and Devices | V-2509 |  | 65.89 | 11860.62 | Controls Panels and Devices - valves and piping lot
2026-05-09 | AP-0005741 | AP | ARM-2608 | 04-300 | Testing and Balancing Subcontract | V-2094 |  | 31895.01 | 31895.01 | Testing and Balancing Subcontract - testing and balancing services
2026-05-09 | AP-0005742 | AP | ARM-2608 | 05-100 | Equipment Rental and Rigging | V-2217 |  | 7358.94 | 7358.94 | Equipment Rental and Rigging - freight and expediting
2026-05-14 | PRJ-PAY-ARM-2608-20260514 | PAY | ARM-2608 | 03-200 | Startup, Testing and Commissioning |  | E-1014 | 51.23 | 3637.3 | Startup, Testing and Commissioning - coordination and layout
2026-05-14 | PRJ-PAY-ARM-2608-20260514 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1021 | 43.56 | 3375.93 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-14 | PRJ-PAY-ARM-2608-20260514 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1028 | 33.32 | 2798.76 | Controls Programming and Checkout - startup and checkout
2026-05-16 | AP-0005738 | AP | ARM-2608 | 02-210 | Sheet Metal and Ductwork | V-2522 |  | 60.59 | 10905.39 | Sheet Metal and Ductwork - ductwork release
2026-05-16 | AP-0005743 | AP | ARM-2608 | 05-400 | Small Tools and Consumables | V-2237 |  | 5121.72 | 5121.72 | Small Tools and Consumables - small tools and field consumables
2026-05-21 | PRJ-PAY-ARM-2608-20260521 | PAY | ARM-2608 | 03-300 | Sheet Metal Fabrication Labor |  | E-1019 | 42.91 | 3046.94 | Sheet Metal Fabrication Labor - supervision and planning
2026-05-21 | PRJ-PAY-ARM-2608-20260521 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1026 | 29.51 | 2286.97 | Controls Programming and Checkout - startup and checkout
2026-05-21 | PRJ-PAY-ARM-2608-20260521 | PAY | ARM-2608 | 06-100 | Warranty and Punchlist |  | E-1033 | 40.93 | 3438.44 | Warranty and Punchlist - punchlist and closeout labor
2026-05-23 | AP-0005739 | AP | ARM-2608 | 02-510 | Controls Panels and Devices | V-2001 |  | 78.32 | 14097.26 | Controls Panels and Devices - jobsite material replenishment
2026-05-28 | PRJ-PAY-ARM-2608-20260528 | PAY | ARM-2608 | 03-400 | Controls Programming and Checkout |  | E-1024 | 37.56 | 2666.41 | Controls Programming and Checkout - startup and checkout
2026-05-28 | PRJ-PAY-ARM-2608-20260528 | PAY | ARM-2608 | 06-100 | Warranty and Punchlist |  | E-1031 | 37.72 | 2923.68 | Warranty and Punchlist - punchlist and closeout labor
2026-05-28 | PRJ-PAY-ARM-2608-20260528 | PAY | ARM-2608 | 06-200 | Closeout and O&M Documentation |  | E-1038 | 35.1 | 2948.23 | Closeout and O&M Documentation - field installation time
2026-05-31 | PRJ-PAY-ARM-2608-20260531 | PAY | ARM-2608 | 06-100 | Warranty and Punchlist |  | E-1029 | 41.48 | 2945.33 | Warranty and Punchlist - punchlist and closeout labor
2026-05-31 | PRJ-PAY-ARM-2608-20260531 | PAY | ARM-2608 | 06-200 | Closeout and O&M Documentation |  | E-1036 | 32 | 2480.34 | Closeout and O&M Documentation - field installation time
2026-05-31 | PRJ-PAY-ARM-2608-20260531 | PAY | ARM-2608 | 06-300 | Rework and Quality Correction |  | E-1043 | 46.42 | 3899.41 | Rework and Quality Correction - coordination and layout

## billing dump 5.31
AR-415 export run 6/1/26 06:49 by KS - includes paid invoices because the WIP tie uses cumulative billings
Invoice | Job | Customer ID | Invoice date | Due date | Gross bill | Applied cash | Retainage | Status
PAYAPP-ARM-2318-202308 | ARM-2318 | C-1039 | 2023-08-31 | 2023-09-30 | 48155.18 | 43339.66 | 4815.52 | Partially Paid
PAYAPP-ARM-2318-202309 | ARM-2318 | C-1039 | 2023-09-30 | 2023-10-30 | 83179.71 | 74861.74 | 8317.97 | Partially Paid
PAYAPP-ARM-2318-202310 | ARM-2318 | C-1039 | 2023-10-31 | 2023-11-30 | 129786.82 | 116808.14 | 12978.68 | Partially Paid
PAYAPP-ARM-2318-202311 | ARM-2318 | C-1039 | 2023-11-30 | 2023-12-30 | 131145.12 | 118030.61 | 13114.51 | Partially Paid
PAYAPP-ARM-2318-202312 | ARM-2318 | C-1039 | 2023-12-31 | 2024-01-30 | 164545.05 | 148090.54 | 16454.51 | Partially Paid
PAYAPP-ARM-2318-202401 | ARM-2318 | C-1039 | 2024-01-31 | 2024-03-01 | 188986.52 | 170087.87 | 18898.65 | Partially Paid
PAYAPP-ARM-2318-202402 | ARM-2318 | C-1039 | 2024-02-29 | 2024-03-30 | 226311.19 | 203680.07 | 22631.12 | Partially Paid
PAYAPP-ARM-2318-202403 | ARM-2318 | C-1039 | 2024-03-31 | 2024-04-30 | 292499.93 | 263249.94 | 29249.99 | Partially Paid
PAYAPP-ARM-2318-202404 | ARM-2318 | C-1039 | 2024-04-30 | 2024-05-30 | 309384.83 | 278446.35 | 30938.48 | Partially Paid
PAYAPP-ARM-2318-202405 | ARM-2318 | C-1039 | 2024-05-31 | 2024-06-30 | 324808.2 | 292327.38 | 32480.82 | Partially Paid
PAYAPP-ARM-2318-202406 | ARM-2318 | C-1039 | 2024-06-30 | 2024-07-30 | 374090 | 336681 | 37409 | Partially Paid
PAYAPP-ARM-2318-202407 | ARM-2318 | C-1039 | 2024-07-31 | 2024-08-30 | 381464.06 | 343317.65 | 38146.41 | Partially Paid
PAYAPP-ARM-2318-202408 | ARM-2318 | C-1039 | 2024-08-31 | 2024-09-30 | 450666.42 | 405599.78 | 45066.64 | Partially Paid
PAYAPP-ARM-2318-202409 | ARM-2318 | C-1039 | 2024-09-30 | 2024-10-30 | 453153.59 | 407838.23 | 45315.36 | Partially Paid
PAYAPP-ARM-2318-202410 | ARM-2318 | C-1039 | 2024-10-31 | 2024-11-30 | 439489.83 | 395540.85 | 43948.98 | Partially Paid
PAYAPP-ARM-2318-202411 | ARM-2318 | C-1039 | 2024-11-30 | 2024-12-30 | 484750.27 | 436275.24 | 48475.03 | Partially Paid
PAYAPP-ARM-2318-202412 | ARM-2318 | C-1039 | 2024-12-31 | 2025-01-30 | 452321.35 | 407089.21 | 45232.14 | Partially Paid
PAYAPP-ARM-2318-202501 | ARM-2318 | C-1039 | 2025-01-31 | 2025-03-02 | 235613.32 | 212051.99 | 23561.33 | Partially Paid
PAYAPP-ARM-2318-202502 | ARM-2318 | C-1039 | 2025-02-28 | 2025-03-30 | 220570.29 | 198513.26 | 22057.03 | Partially Paid
PAYAPP-ARM-2318-202503 | ARM-2318 | C-1039 | 2025-03-31 | 2025-04-30 | 204276.63 | 183848.97 | 20427.66 | Partially Paid
PAYAPP-ARM-2318-202504 | ARM-2318 | C-1039 | 2025-04-30 | 2025-05-30 | 210954.83 | 189859.35 | 21095.48 | Partially Paid
PAYAPP-ARM-2318-202505 | ARM-2318 | C-1039 | 2025-05-31 | 2025-06-30 | 184427.79 | 165985.01 | 18442.78 | Partially Paid
PAYAPP-ARM-2318-202506 | ARM-2318 | C-1039 | 2025-06-30 | 2025-07-30 | 200876.89 | 180789.2 | 20087.69 | Partially Paid
PAYAPP-ARM-2318-202507 | ARM-2318 | C-1039 | 2025-07-31 | 2025-08-30 | 170299.32 | 153269.39 | 17029.93 | Partially Paid
PAYAPP-ARM-2318-202508 | ARM-2318 | C-1039 | 2025-08-31 | 2025-09-30 | 152528.75 | 137275.87 | 15252.88 | Partially Paid
PAYAPP-ARM-2318-202509 | ARM-2318 | C-1039 | 2025-09-30 | 2025-10-30 | 140922.44 | 126830.2 | 14092.24 | Partially Paid
PAYAPP-ARM-2318-202510 | ARM-2318 | C-1039 | 2025-10-31 | 2025-11-30 | 116667.38 | 105000.64 | 11666.74 | Partially Paid
PAYAPP-ARM-2318-202511 | ARM-2318 | C-1039 | 2025-11-30 | 2025-12-30 | 123919.15 | 111527.23 | 12391.92 | Partially Paid
PAYAPP-ARM-2318-202512 | ARM-2318 | C-1039 | 2025-12-31 | 2026-01-30 | 88252.32 | 79427.09 | 8825.23 | Partially Paid
PAYAPP-ARM-2318-202601 | ARM-2318 | C-1039 | 2026-01-31 | 2026-03-02 | 459481.94 | 413533.75 | 45948.19 | Partially Paid
PAYAPP-ARM-2318-202602 | ARM-2318 | C-1039 | 2026-02-28 | 2026-03-30 | 328373.4 | 295536.06 | 32837.34 | Partially Paid
PAYAPP-ARM-2318-202603 | ARM-2318 | C-1039 | 2026-03-31 | 2026-04-30 | 273214.47 | 245893.02 | 27321.45 | Partially Paid
PAYAPP-ARM-2318-202604 | ARM-2318 | C-1039 | 2026-04-30 | 2026-05-30 | 311080.3 | 279972.27 | 31108.03 | Partially Paid
PAYAPP-ARM-2318-202605 | ARM-2318 | C-1039 | 2026-05-31 | 2026-06-30 | 155955.47 | 0 | 15595.55 | Open
PAYAPP-ARM-2403-202402 | ARM-2403 | C-1007 | 2024-02-29 | 2024-04-14 | 43614.9 | 41434.15 | 2180.75 | Partially Paid
PAYAPP-ARM-2403-202403 | ARM-2403 | C-1007 | 2024-03-31 | 2024-05-15 | 78119.81 | 74213.82 | 3905.99 | Partially Paid
PAYAPP-ARM-2403-202404 | ARM-2403 | C-1007 | 2024-04-30 | 2024-06-14 | 124444.39 | 118222.17 | 6222.22 | Partially Paid
PAYAPP-ARM-2403-202405 | ARM-2403 | C-1007 | 2024-05-31 | 2024-07-15 | 134746.71 | 128009.37 | 6737.34 | Partially Paid
PAYAPP-ARM-2403-202406 | ARM-2403 | C-1007 | 2024-06-30 | 2024-08-14 | 167483.73 | 159109.54 | 8374.19 | Partially Paid
PAYAPP-ARM-2403-202407 | ARM-2403 | C-1007 | 2024-07-31 | 2024-09-14 | 200909.39 | 190863.92 | 10045.47 | Partially Paid
PAYAPP-ARM-2403-202408 | ARM-2403 | C-1007 | 2024-08-31 | 2024-10-15 | 235057.21 | 223304.35 | 11752.86 | Partially Paid
PAYAPP-ARM-2403-202409 | ARM-2403 | C-1007 | 2024-09-30 | 2024-11-14 | 297961.88 | 283063.79 | 14898.09 | Partially Paid
PAYAPP-ARM-2403-202410 | ARM-2403 | C-1007 | 2024-10-31 | 2024-12-15 | 318665.89 | 302732.6 | 15933.29 | Partially Paid
PAYAPP-ARM-2403-202411 | ARM-2403 | C-1007 | 2024-11-30 | 2025-01-14 | 325821.74 | 309530.65 | 16291.09 | Partially Paid
PAYAPP-ARM-2403-202412 | ARM-2403 | C-1007 | 2024-12-31 | 2025-02-14 | 373858.67 | 355165.74 | 18692.93 | Partially Paid
PAYAPP-ARM-2403-202501 | ARM-2403 | C-1007 | 2025-01-31 | 2025-03-17 | 170718.09 | 162182.19 | 8535.9 | Partially Paid
PAYAPP-ARM-2403-202502 | ARM-2403 | C-1007 | 2025-02-28 | 2025-04-14 | 195391.32 | 185621.75 | 9769.57 | Partially Paid
PAYAPP-ARM-2403-202503 | ARM-2403 | C-1007 | 2025-03-31 | 2025-05-15 | 191828.59 | 182237.16 | 9591.43 | Partially Paid
PAYAPP-ARM-2403-202504 | ARM-2403 | C-1007 | 2025-04-30 | 2025-06-14 | 179091.25 | 170136.69 | 8954.56 | Partially Paid
PAYAPP-ARM-2403-202505 | ARM-2403 | C-1007 | 2025-05-31 | 2025-07-15 | 189829.24 | 180337.78 | 9491.46 | Partially Paid
PAYAPP-ARM-2403-202506 | ARM-2403 | C-1007 | 2025-06-30 | 2025-08-14 | 169255.87 | 160793.08 | 8462.79 | Partially Paid
PAYAPP-ARM-2403-202507 | ARM-2403 | C-1007 | 2025-07-31 | 2025-09-14 | 181955.77 | 172857.98 | 9097.79 | Partially Paid
PAYAPP-ARM-2403-202508 | ARM-2403 | C-1007 | 2025-08-31 | 2025-10-15 | 159018.04 | 151067.14 | 7950.9 | Partially Paid
PAYAPP-ARM-2403-202509 | ARM-2403 | C-1007 | 2025-09-30 | 2025-11-14 | 139240.75 | 132278.71 | 6962.04 | Partially Paid
PAYAPP-ARM-2403-202510 | ARM-2403 | C-1007 | 2025-10-31 | 2025-12-15 | 129629.89 | 123148.4 | 6481.49 | Partially Paid
PAYAPP-ARM-2403-202511 | ARM-2403 | C-1007 | 2025-11-30 | 2026-01-14 | 105940.21 | 100643.2 | 5297.01 | Partially Paid
PAYAPP-ARM-2403-202512 | ARM-2403 | C-1007 | 2025-12-31 | 2026-02-14 | 108052.35 | 102649.73 | 5402.62 | Partially Paid
PAYAPP-ARM-2403-202601 | ARM-2403 | C-1007 | 2026-01-31 | 2026-03-17 | 450201.11 | 427691.05 | 22510.06 | Partially Paid
PAYAPP-ARM-2403-202602 | ARM-2403 | C-1007 | 2026-02-28 | 2026-04-14 | 376541.71 | 357714.62 | 18827.09 | Partially Paid
PAYAPP-ARM-2403-202603 | ARM-2403 | C-1007 | 2026-03-31 | 2026-05-15 | 252958.55 | 240310.62 | 12647.93 | Partially Paid
PAYAPP-ARM-2403-202604 | ARM-2403 | C-1007 | 2026-04-30 | 2026-06-14 | 203907 | 193711.65 | 10195.35 | Partially Paid
PAYAPP-ARM-2403-202605 | ARM-2403 | C-1007 | 2026-05-31 | 2026-07-15 | 229820.19 | 126630.92 | 11491.01 | Partially Paid
PAYAPP-ARM-2409-202405 | ARM-2409 | C-1021 | 2024-05-31 | 2024-06-30 | 38669.38 | 36735.91 | 1933.47 | Partially Paid
PAYAPP-ARM-2409-202406 | ARM-2409 | C-1021 | 2024-06-30 | 2024-07-30 | 70877.25 | 67333.39 | 3543.86 | Partially Paid
PAYAPP-ARM-2409-202407 | ARM-2409 | C-1021 | 2024-07-31 | 2024-08-30 | 114262.19 | 108549.08 | 5713.11 | Partially Paid
PAYAPP-ARM-2409-202408 | ARM-2409 | C-1021 | 2024-08-31 | 2024-09-30 | 128444.39 | 122022.17 | 6422.22 | Partially Paid
PAYAPP-ARM-2409-202409 | ARM-2409 | C-1021 | 2024-09-30 | 2024-10-30 | 158512.4 | 150586.78 | 7925.62 | Partially Paid
PAYAPP-ARM-2409-202410 | ARM-2409 | C-1021 | 2024-10-31 | 2024-11-30 | 193764.08 | 184075.88 | 9688.2 | Partially Paid
PAYAPP-ARM-2409-202411 | ARM-2409 | C-1021 | 2024-11-30 | 2024-12-30 | 223261.93 | 212098.83 | 11163.1 | Partially Paid
PAYAPP-ARM-2409-202412 | ARM-2409 | C-1021 | 2024-12-31 | 2025-01-30 | 279064.31 | 265111.09 | 13953.22 | Partially Paid
PAYAPP-ARM-2409-202501 | ARM-2409 | C-1021 | 2025-01-31 | 2025-03-02 | 137880.58 | 130986.55 | 6894.03 | Partially Paid
PAYAPP-ARM-2409-202502 | ARM-2409 | C-1021 | 2025-02-28 | 2025-03-30 | 138321.82 | 131405.73 | 6916.09 | Partially Paid
PAYAPP-ARM-2409-202503 | ARM-2409 | C-1021 | 2025-03-31 | 2025-04-30 | 156955.75 | 149107.96 | 7847.79 | Partially Paid
PAYAPP-ARM-2409-202504 | ARM-2409 | C-1021 | 2025-04-30 | 2025-05-30 | 151364.04 | 143795.84 | 7568.2 | Partially Paid
PAYAPP-ARM-2409-202505 | ARM-2409 | C-1021 | 2025-05-31 | 2025-06-30 | 169037.41 | 160585.54 | 8451.87 | Partially Paid
PAYAPP-ARM-2409-202506 | ARM-2409 | C-1021 | 2025-06-30 | 2025-07-30 | 161570.82 | 153492.28 | 8078.54 | Partially Paid
PAYAPP-ARM-2409-202507 | ARM-2409 | C-1021 | 2025-07-31 | 2025-08-30 | 146301.26 | 138986.2 | 7315.06 | Partially Paid
PAYAPP-ARM-2409-202508 | ARM-2409 | C-1021 | 2025-08-31 | 2025-09-30 | 148689.81 | 141255.32 | 7434.49 | Partially Paid
PAYAPP-ARM-2409-202509 | ARM-2409 | C-1021 | 2025-09-30 | 2025-10-30 | 127597.39 | 121217.52 | 6379.87 | Partially Paid
PAYAPP-ARM-2409-202510 | ARM-2409 | C-1021 | 2025-10-31 | 2025-11-30 | 131810.78 | 125220.24 | 6590.54 | Partially Paid
PAYAPP-ARM-2409-202511 | ARM-2409 | C-1021 | 2025-11-30 | 2025-12-30 | 106843.63 | 101501.45 | 5342.18 | Partially Paid
PAYAPP-ARM-2409-202512 | ARM-2409 | C-1021 | 2025-12-31 | 2026-01-30 | 89048.6 | 84596.17 | 4452.43 | Partially Paid
PAYAPP-ARM-2409-202601 | ARM-2409 | C-1021 | 2026-01-31 | 2026-03-02 | 429792.63 | 408303 | 21489.63 | Partially Paid
PAYAPP-ARM-2409-202602 | ARM-2409 | C-1021 | 2026-02-28 | 2026-03-30 | 331466.44 | 314893.12 | 16573.32 | Partially Paid
PAYAPP-ARM-2409-202603 | ARM-2409 | C-1021 | 2026-03-31 | 2026-04-30 | 324464.17 | 308240.96 | 16223.21 | Partially Paid
PAYAPP-ARM-2409-202604 | ARM-2409 | C-1021 | 2026-04-30 | 2026-05-30 | 179266.06 | 170302.76 | 8963.3 | Partially Paid
PAYAPP-ARM-2409-202605 | ARM-2409 | C-1021 | 2026-05-31 | 2026-06-30 | 158812.46 | 87505.67 | 7940.62 | Partially Paid
PAYAPP-ARM-2412-202407 | ARM-2412 | C-1051 | 2024-07-31 | 2024-09-14 | 39398.32 | 37428.4 | 1969.92 | Partially Paid
PAYAPP-ARM-2412-202408 | ARM-2412 | C-1051 | 2024-08-31 | 2024-10-15 | 73496.09 | 69821.29 | 3674.8 | Partially Paid
PAYAPP-ARM-2412-202409 | ARM-2412 | C-1051 | 2024-09-30 | 2024-11-14 | 119484.01 | 113509.81 | 5974.2 | Partially Paid
PAYAPP-ARM-2412-202410 | ARM-2412 | C-1051 | 2024-10-31 | 2024-12-15 | 137791.31 | 130901.74 | 6889.57 | Partially Paid
PAYAPP-ARM-2412-202411 | ARM-2412 | C-1051 | 2024-11-30 | 2025-01-14 | 168981.84 | 160532.75 | 8449.09 | Partially Paid
PAYAPP-ARM-2412-202412 | ARM-2412 | C-1051 | 2024-12-31 | 2025-02-14 | 208728.63 | 198292.2 | 10436.43 | Partially Paid
PAYAPP-ARM-2412-202501 | ARM-2412 | C-1051 | 2025-01-31 | 2025-03-17 | 109832.84 | 104341.2 | 5491.64 | Partially Paid
PAYAPP-ARM-2412-202502 | ARM-2412 | C-1051 | 2025-02-28 | 2025-04-14 | 135634.94 | 128853.19 | 6781.75 | Partially Paid
PAYAPP-ARM-2412-202503 | ARM-2412 | C-1051 | 2025-03-31 | 2025-05-15 | 144242.68 | 137030.55 | 7212.13 | Partially Paid
PAYAPP-ARM-2412-202504 | ARM-2412 | C-1051 | 2025-04-30 | 2025-06-14 | 142343.55 | 135226.37 | 7117.18 | Partially Paid
PAYAPP-ARM-2412-202505 | ARM-2412 | C-1051 | 2025-05-31 | 2025-07-15 | 159351.69 | 151384.11 | 7967.58 | Partially Paid
PAYAPP-ARM-2412-202506 | ARM-2412 | C-1051 | 2025-06-30 | 2025-08-14 | 150474.06 | 142950.36 | 7523.7 | Partially Paid
PAYAPP-ARM-2412-202507 | ARM-2412 | C-1051 | 2025-07-31 | 2025-09-14 | 164339.48 | 156122.51 | 8216.97 | Partially Paid
PAYAPP-ARM-2412-202508 | ARM-2412 | C-1051 | 2025-08-31 | 2025-10-15 | 152673.55 | 145039.87 | 7633.68 | Partially Paid
PAYAPP-ARM-2412-202509 | ARM-2412 | C-1051 | 2025-09-30 | 2025-11-14 | 134348.86 | 127631.42 | 6717.44 | Partially Paid
PAYAPP-ARM-2412-202510 | ARM-2412 | C-1051 | 2025-10-31 | 2025-12-15 | 130467.46 | 123944.09 | 6523.37 | Partially Paid
PAYAPP-ARM-2412-202511 | ARM-2412 | C-1051 | 2025-11-30 | 2026-01-14 | 107872.37 | 102478.75 | 5393.62 | Partially Paid
PAYAPP-ARM-2412-202512 | ARM-2412 | C-1051 | 2025-12-31 | 2026-02-14 | 107238.45 | 101876.53 | 5361.92 | Partially Paid
PAYAPP-ARM-2412-202601 | ARM-2412 | C-1051 | 2026-01-31 | 2026-03-17 | 468583.08 | 445153.93 | 23429.15 | Partially Paid
PAYAPP-ARM-2412-202602 | ARM-2412 | C-1051 | 2026-02-28 | 2026-04-14 | 372914.5 | 354268.77 | 18645.73 | Partially Paid
PAYAPP-ARM-2412-202603 | ARM-2412 | C-1051 | 2026-03-31 | 2026-05-15 | 257779.25 | 244890.29 | 12888.96 | Partially Paid
PAYAPP-ARM-2412-202604 | ARM-2412 | C-1051 | 2026-04-30 | 2026-06-14 | 193084.26 | 183430.05 | 9654.21 | Partially Paid
PAYAPP-ARM-2412-202605 | ARM-2412 | C-1051 | 2026-05-31 | 2026-07-15 | 197922.7 | 109055.4 | 9896.14 | Partially Paid
PAYAPP-ARM-2417-202409 | ARM-2417 | C-1013 | 2024-09-30 | 2024-11-14 | 68084.14 | 61275.73 | 6808.41 | Partially Paid
PAYAPP-ARM-2417-202410 | ARM-2417 | C-1013 | 2024-10-31 | 2024-12-15 | 129522.66 | 116570.39 | 12952.27 | Partially Paid
PAYAPP-ARM-2417-202411 | ARM-2417 | C-1013 | 2024-11-30 | 2025-01-14 | 212378.66 | 191140.79 | 21237.87 | Partially Paid
PAYAPP-ARM-2417-202412 | ARM-2417 | C-1013 | 2024-12-31 | 2025-02-14 | 251245.98 | 226121.38 | 25124.6 | Partially Paid
PAYAPP-ARM-2417-202501 | ARM-2417 | C-1013 | 2025-01-31 | 2025-03-17 | 141329.76 | 127196.78 | 14132.98 | Partially Paid
PAYAPP-ARM-2417-202502 | ARM-2417 | C-1013 | 2025-02-28 | 2025-04-14 | 175939.66 | 158345.69 | 17593.97 | Partially Paid
PAYAPP-ARM-2417-202503 | ARM-2417 | C-1013 | 2025-03-31 | 2025-05-15 | 197202.01 | 177481.81 | 19720.2 | Partially Paid
PAYAPP-ARM-2417-202504 | ARM-2417 | C-1013 | 2025-04-30 | 2025-06-14 | 239818.37 | 215836.53 | 23981.84 | Partially Paid
PAYAPP-ARM-2417-202505 | ARM-2417 | C-1013 | 2025-05-31 | 2025-07-15 | 252566.73 | 227310.06 | 25256.67 | Partially Paid
PAYAPP-ARM-2417-202506 | ARM-2417 | C-1013 | 2025-06-30 | 2025-08-14 | 244038.77 | 219634.89 | 24403.88 | Partially Paid
PAYAPP-ARM-2417-202507 | ARM-2417 | C-1013 | 2025-07-31 | 2025-09-14 | 267489.38 | 240740.44 | 26748.94 | Partially Paid
PAYAPP-ARM-2417-202508 | ARM-2417 | C-1013 | 2025-08-31 | 2025-10-15 | 245682.79 | 221114.51 | 24568.28 | Partially Paid
PAYAPP-ARM-2417-202509 | ARM-2417 | C-1013 | 2025-09-30 | 2025-11-14 | 260421.69 | 234379.52 | 26042.17 | Partially Paid
PAYAPP-ARM-2417-202510 | ARM-2417 | C-1013 | 2025-10-31 | 2025-12-15 | 231753.19 | 208577.87 | 23175.32 | Partially Paid
PAYAPP-ARM-2417-202511 | ARM-2417 | C-1013 | 2025-11-30 | 2026-01-14 | 196022.37 | 176420.13 | 19602.24 | Partially Paid
PAYAPP-ARM-2417-202512 | ARM-2417 | C-1013 | 2025-12-31 | 2026-02-14 | 177088.34 | 159379.51 | 17708.83 | Partially Paid
PAYAPP-ARM-2417-202601 | ARM-2417 | C-1013 | 2026-01-31 | 2026-03-17 | 817247.78 | 735523 | 81724.78 | Partially Paid
PAYAPP-ARM-2417-202602 | ARM-2417 | C-1013 | 2026-02-28 | 2026-04-14 | 771038.09 | 693934.28 | 77103.81 | Partially Paid
PAYAPP-ARM-2417-202603 | ARM-2417 | C-1013 | 2026-03-31 | 2026-05-15 | 489873.79 | 440886.41 | 48987.38 | Partially Paid
PAYAPP-ARM-2417-202604 | ARM-2417 | C-1013 | 2026-04-30 | 2026-06-14 | 373832.96 | 336449.66 | 37383.3 | Partially Paid
PAYAPP-ARM-2417-202605 | ARM-2417 | C-1013 | 2026-05-31 | 2026-07-15 | 187770.12 | 98016 | 18777.01 | Partially Paid
PAYAPP-ARM-2421-202410 | ARM-2421 | C-1044 | 2024-10-31 | 2024-11-30 | 38603.42 | 36673.25 | 1930.17 | Partially Paid
PAYAPP-ARM-2421-202411 | ARM-2421 | C-1044 | 2024-11-30 | 2024-12-30 | 75932.24 | 72135.63 | 3796.61 | Partially Paid
PAYAPP-ARM-2421-202412 | ARM-2421 | C-1044 | 2024-12-31 | 2025-01-30 | 126052.8 | 119750.16 | 6302.64 | Partially Paid
PAYAPP-ARM-2421-202501 | ARM-2421 | C-1044 | 2025-01-31 | 2025-03-02 | 71510.6 | 67935.07 | 3575.53 | Partially Paid
PAYAPP-ARM-2421-202502 | ARM-2421 | C-1044 | 2025-02-28 | 2025-03-30 | 85504.14 | 81228.93 | 4275.21 | Partially Paid
PAYAPP-ARM-2421-202503 | ARM-2421 | C-1044 | 2025-03-31 | 2025-04-30 | 106847.68 | 101505.3 | 5342.38 | Partially Paid
PAYAPP-ARM-2421-202504 | ARM-2421 | C-1044 | 2025-04-30 | 2025-05-30 | 116124.06 | 110317.86 | 5806.2 | Partially Paid
PAYAPP-ARM-2421-202505 | ARM-2421 | C-1044 | 2025-05-31 | 2025-06-30 | 136654.08 | 129821.38 | 6832.7 | Partially Paid
PAYAPP-ARM-2421-202506 | ARM-2421 | C-1044 | 2025-06-30 | 2025-07-30 | 139680.27 | 132696.26 | 6984.01 | Partially Paid
PAYAPP-ARM-2421-202507 | ARM-2421 | C-1044 | 2025-07-31 | 2025-08-30 | 128868.31 | 122424.89 | 6443.42 | Partially Paid
PAYAPP-ARM-2421-202508 | ARM-2421 | C-1044 | 2025-08-31 | 2025-09-30 | 133489.54 | 126815.06 | 6674.48 | Partially Paid
PAYAPP-ARM-2421-202509 | ARM-2421 | C-1044 | 2025-09-30 | 2025-10-30 | 115036.59 | 109284.76 | 5751.83 | Partially Paid
PAYAPP-ARM-2421-202510 | ARM-2421 | C-1044 | 2025-10-31 | 2025-11-30 | 113676.71 | 107992.87 | 5683.84 | Partially Paid
PAYAPP-ARM-2421-202511 | ARM-2421 | C-1044 | 2025-11-30 | 2025-12-30 | 89748.22 | 85260.81 | 4487.41 | Partially Paid
PAYAPP-ARM-2421-202512 | ARM-2421 | C-1044 | 2025-12-31 | 2026-01-30 | 68854.19 | 65411.48 | 3442.71 | Partially Paid
PAYAPP-ARM-2421-202601 | ARM-2421 | C-1044 | 2026-01-31 | 2026-03-02 | 290422.34 | 275901.22 | 14521.12 | Partially Paid
PAYAPP-ARM-2421-202602 | ARM-2421 | C-1044 | 2026-02-28 | 2026-03-30 | 201009.88 | 190959.39 | 10050.49 | Partially Paid
PAYAPP-ARM-2421-202603 | ARM-2421 | C-1044 | 2026-03-31 | 2026-04-30 | 181327.72 | 172261.33 | 9066.39 | Partially Paid
PAYAPP-ARM-2421-202604 | ARM-2421 | C-1044 | 2026-04-30 | 2026-05-30 | 85657.21 | 81374.35 | 4282.86 | Partially Paid
PAYAPP-ARM-2501-202501 | ARM-2501 | C-1032 | 2025-01-31 | 2025-03-17 | 14782.77 | 14043.63 | 739.14 | Partially Paid
PAYAPP-ARM-2501-202502 | ARM-2501 | C-1032 | 2025-02-28 | 2025-04-14 | 29433.85 | 27962.16 | 1471.69 | Partially Paid
PAYAPP-ARM-2501-202503 | ARM-2501 | C-1032 | 2025-03-31 | 2025-05-15 | 49041.14 | 46589.08 | 2452.06 | Partially Paid
PAYAPP-ARM-2501-202504 | ARM-2501 | C-1032 | 2025-04-30 | 2025-06-14 | 60832.89 | 57791.25 | 3041.64 | Partially Paid
PAYAPP-ARM-2501-202505 | ARM-2501 | C-1032 | 2025-05-31 | 2025-07-15 | 72170.23 | 68561.72 | 3608.51 | Partially Paid
PAYAPP-ARM-2501-202506 | ARM-2501 | C-1032 | 2025-06-30 | 2025-08-14 | 90011.11 | 85510.55 | 4500.56 | Partially Paid
PAYAPP-ARM-2501-202507 | ARM-2501 | C-1032 | 2025-07-31 | 2025-09-14 | 96504.86 | 91679.62 | 4825.24 | Partially Paid
PAYAPP-ARM-2501-202508 | ARM-2501 | C-1032 | 2025-08-31 | 2025-10-15 | 111873.48 | 106279.81 | 5593.67 | Partially Paid
PAYAPP-ARM-2501-202509 | ARM-2501 | C-1032 | 2025-09-30 | 2025-11-14 | 112487.75 | 106863.36 | 5624.39 | Partially Paid
PAYAPP-ARM-2501-202510 | ARM-2501 | C-1032 | 2025-10-31 | 2025-12-15 | 101552.55 | 96474.92 | 5077.63 | Partially Paid
PAYAPP-ARM-2501-202511 | ARM-2501 | C-1032 | 2025-11-30 | 2026-01-14 | 102066.45 | 96963.13 | 5103.32 | Partially Paid
PAYAPP-ARM-2501-202512 | ARM-2501 | C-1032 | 2025-12-31 | 2026-02-14 | 85234.94 | 80973.19 | 4261.75 | Partially Paid
PAYAPP-ARM-2501-202601 | ARM-2501 | C-1032 | 2026-01-31 | 2026-03-17 | 478880.41 | 454936.39 | 23944.02 | Partially Paid
PAYAPP-ARM-2501-202602 | ARM-2501 | C-1032 | 2026-02-28 | 2026-04-14 | 352665.89 | 335032.6 | 17633.29 | Partially Paid
PAYAPP-ARM-2501-202603 | ARM-2501 | C-1032 | 2026-03-31 | 2026-05-15 | 257618.69 | 244737.76 | 12880.93 | Partially Paid
PAYAPP-ARM-2501-202604 | ARM-2501 | C-1032 | 2026-04-30 | 2026-06-14 | 157700.9 | 149815.85 | 7885.05 | Partially Paid
PAYAPP-ARM-2501-202605 | ARM-2501 | C-1032 | 2026-05-31 | 2026-07-15 | 107514.43 | 59240.45 | 5375.72 | Partially Paid
PAYAPP-ARM-2506-202502 | ARM-2506 | C-1048 | 2025-02-28 | 2025-03-30 | 33655.19 | 30289.67 | 3365.52 | Partially Paid
PAYAPP-ARM-2506-202503 | ARM-2506 | C-1048 | 2025-03-31 | 2025-04-30 | 67864.23 | 61077.81 | 6786.42 | Partially Paid
PAYAPP-ARM-2506-202504 | ARM-2506 | C-1048 | 2025-04-30 | 2025-05-30 | 113434.39 | 102090.95 | 11343.44 | Partially Paid
PAYAPP-ARM-2506-202505 | ARM-2506 | C-1048 | 2025-05-31 | 2025-06-30 | 142126.51 | 127913.86 | 14212.65 | Partially Paid
PAYAPP-ARM-2506-202506 | ARM-2506 | C-1048 | 2025-06-30 | 2025-07-30 | 167052.49 | 150347.24 | 16705.25 | Partially Paid
PAYAPP-ARM-2506-202507 | ARM-2506 | C-1048 | 2025-07-31 | 2025-08-30 | 207465.25 | 186718.72 | 20746.53 | Partially Paid
PAYAPP-ARM-2506-202508 | ARM-2506 | C-1048 | 2025-08-31 | 2025-09-30 | 218892.02 | 197002.82 | 21889.2 | Partially Paid
PAYAPP-ARM-2506-202509 | ARM-2506 | C-1048 | 2025-09-30 | 2025-10-30 | 249211.26 | 224290.13 | 24921.13 | Partially Paid
PAYAPP-ARM-2506-202510 | ARM-2506 | C-1048 | 2025-10-31 | 2025-11-30 | 245275.99 | 220748.39 | 24527.6 | Partially Paid
PAYAPP-ARM-2506-202511 | ARM-2506 | C-1048 | 2025-11-30 | 2025-12-30 | 215613.92 | 194052.53 | 21561.39 | Partially Paid
PAYAPP-ARM-2506-202512 | ARM-2506 | C-1048 | 2025-12-31 | 2026-01-30 | 208272.97 | 187445.67 | 20827.3 | Partially Paid
PAYAPP-ARM-2506-202601 | ARM-2506 | C-1048 | 2026-01-31 | 2026-03-02 | 983935.56 | 885542 | 98393.56 | Partially Paid
PAYAPP-ARM-2506-202602 | ARM-2506 | C-1048 | 2026-02-28 | 2026-03-30 | 898279.72 | 808451.75 | 89827.97 | Partially Paid
PAYAPP-ARM-2506-202603 | ARM-2506 | C-1048 | 2026-03-31 | 2026-04-30 | 599275.38 | 539347.84 | 59927.54 | Partially Paid
PAYAPP-ARM-2506-202604 | ARM-2506 | C-1048 | 2026-04-30 | 2026-05-30 | 413812.14 | 372430.93 | 41381.21 | Partially Paid
PAYAPP-ARM-2506-202605 | ARM-2506 | C-1048 | 2026-05-31 | 2026-06-30 | 200466.04 | 104643.28 | 20046.6 | Partially Paid
PAYAPP-ARM-2510-202503 | ARM-2510 | C-1062 | 2025-03-31 | 2025-04-30 | 23570.24 | 21213.22 | 2357.02 | Partially Paid
PAYAPP-ARM-2510-202504 | ARM-2510 | C-1062 | 2025-04-30 | 2025-05-30 | 48153.18 | 43337.86 | 4815.32 | Partially Paid
PAYAPP-ARM-2510-202505 | ARM-2510 | C-1062 | 2025-05-31 | 2025-06-30 | 80692.38 | 72623.14 | 8069.24 | Partially Paid
PAYAPP-ARM-2510-202506 | ARM-2510 | C-1062 | 2025-06-30 | 2025-07-30 | 101983.7 | 91785.33 | 10198.37 | Partially Paid
PAYAPP-ARM-2510-202507 | ARM-2510 | C-1062 | 2025-07-31 | 2025-08-30 | 118533.73 | 106680.36 | 11853.37 | Partially Paid
PAYAPP-ARM-2510-202508 | ARM-2510 | C-1062 | 2025-08-31 | 2025-09-30 | 146148.79 | 131533.91 | 14614.88 | Partially Paid
PAYAPP-ARM-2510-202509 | ARM-2510 | C-1062 | 2025-09-30 | 2025-10-30 | 151257.83 | 136132.05 | 15125.78 | Partially Paid
PAYAPP-ARM-2510-202510 | ARM-2510 | C-1062 | 2025-10-31 | 2025-11-30 | 168451.28 | 151606.15 | 16845.13 | Partially Paid
PAYAPP-ARM-2510-202511 | ARM-2510 | C-1062 | 2025-11-30 | 2025-12-30 | 161191.2 | 145072.08 | 16119.12 | Partially Paid
PAYAPP-ARM-2510-202512 | ARM-2510 | C-1062 | 2025-12-31 | 2026-01-30 | 137044.29 | 123339.86 | 13704.43 | Partially Paid
PAYAPP-ARM-2510-202601 | ARM-2510 | C-1062 | 2026-01-31 | 2026-03-02 | 738695.13 | 664825.62 | 73869.51 | Partially Paid
PAYAPP-ARM-2510-202602 | ARM-2510 | C-1062 | 2026-02-28 | 2026-03-30 | 562538.26 | 506284.43 | 56253.83 | Partially Paid
PAYAPP-ARM-2510-202603 | ARM-2510 | C-1062 | 2026-03-31 | 2026-04-30 | 485364.54 | 436828.09 | 48536.45 | Partially Paid
PAYAPP-ARM-2510-202604 | ARM-2510 | C-1062 | 2026-04-30 | 2026-05-30 | 279719.21 | 251747.29 | 27971.92 | Partially Paid
PAYAPP-ARM-2510-202605 | ARM-2510 | C-1062 | 2026-05-31 | 2026-06-30 | 186558.63 | 97383.61 | 18655.86 | Partially Paid
PAYAPP-ARM-2514-202505 | ARM-2514 | C-1028 | 2025-05-31 | 2025-07-15 | 41683.04 | 39598.89 | 2084.15 | Partially Paid
PAYAPP-ARM-2514-202506 | ARM-2514 | C-1028 | 2025-06-30 | 2025-08-14 | 87467.78 | 83094.39 | 4373.39 | Partially Paid
PAYAPP-ARM-2514-202507 | ARM-2514 | C-1028 | 2025-07-31 | 2025-09-14 | 146846.06 | 139503.76 | 7342.3 | Partially Paid
PAYAPP-ARM-2514-202508 | ARM-2514 | C-1028 | 2025-08-31 | 2025-10-15 | 187675.33 | 178291.56 | 9383.77 | Partially Paid
PAYAPP-ARM-2514-202509 | ARM-2514 | C-1028 | 2025-09-30 | 2025-11-14 | 211548.77 | 200971.33 | 10577.44 | Partially Paid
PAYAPP-ARM-2514-202510 | ARM-2514 | C-1028 | 2025-10-31 | 2025-12-15 | 253756.54 | 241068.71 | 12687.83 | Partially Paid
PAYAPP-ARM-2514-202511 | ARM-2514 | C-1028 | 2025-11-30 | 2026-01-14 | 249070.32 | 236616.8 | 12453.52 | Partially Paid
PAYAPP-ARM-2514-202512 | ARM-2514 | C-1028 | 2025-12-31 | 2026-02-14 | 260562.81 | 247534.67 | 13028.14 | Partially Paid
PAYAPP-ARM-2514-202601 | ARM-2514 | C-1028 | 2026-01-31 | 2026-03-17 | 1342745.37 | 1275608.1 | 67137.27 | Partially Paid
PAYAPP-ARM-2514-202602 | ARM-2514 | C-1028 | 2026-02-28 | 2026-04-14 | 1032762.08 | 981123.98 | 51638.1 | Partially Paid
PAYAPP-ARM-2514-202603 | ARM-2514 | C-1028 | 2026-03-31 | 2026-05-15 | 783983.13 | 744783.97 | 39199.16 | Partially Paid
PAYAPP-ARM-2514-202604 | ARM-2514 | C-1028 | 2026-04-30 | 2026-06-14 | 505076.63 | 479822.8 | 25253.83 | Partially Paid
PAYAPP-ARM-2514-202605 | ARM-2514 | C-1028 | 2026-05-31 | 2026-07-15 | 383286.23 | 0 | 19164.31 | Open
PAYAPP-ARM-2518-202507 | ARM-2518 | C-1067 | 2025-07-31 | 2025-09-14 | 13103.31 | 12448.14 | 655.17 | Partially Paid
PAYAPP-ARM-2518-202508 | ARM-2518 | C-1067 | 2025-08-31 | 2025-10-15 | 28214.8 | 26804.06 | 1410.74 | Partially Paid
PAYAPP-ARM-2518-202509 | ARM-2518 | C-1067 | 2025-09-30 | 2025-11-14 | 47085.78 | 44731.49 | 2354.29 | Partially Paid
PAYAPP-ARM-2518-202510 | ARM-2518 | C-1067 | 2025-10-31 | 2025-12-15 | 59988.71 | 56989.27 | 2999.44 | Partially Paid
PAYAPP-ARM-2518-202511 | ARM-2518 | C-1067 | 2025-11-30 | 2026-01-14 | 64378.37 | 61159.45 | 3218.92 | Partially Paid
PAYAPP-ARM-2518-202512 | ARM-2518 | C-1067 | 2025-12-31 | 2026-02-14 | 72899.13 | 69254.17 | 3644.96 | Partially Paid
PAYAPP-ARM-2518-202601 | ARM-2518 | C-1067 | 2026-01-31 | 2026-03-17 | 385756.1 | 366468.29 | 19287.81 | Partially Paid
PAYAPP-ARM-2518-202602 | ARM-2518 | C-1067 | 2026-02-28 | 2026-04-14 | 362014.47 | 343913.75 | 18100.72 | Partially Paid
PAYAPP-ARM-2518-202603 | ARM-2518 | C-1067 | 2026-03-31 | 2026-05-15 | 263908.62 | 250713.19 | 13195.43 | Partially Paid
PAYAPP-ARM-2518-202604 | ARM-2518 | C-1067 | 2026-04-30 | 2026-06-14 | 167539.13 | 159162.17 | 8376.96 | Partially Paid
PAYAPP-ARM-2518-202605 | ARM-2518 | C-1067 | 2026-05-31 | 2026-07-15 | 77845.05 | 42892.62 | 3892.25 | Partially Paid
PAYAPP-ARM-2522-202508 | ARM-2522 | C-1071 | 2025-08-31 | 2025-09-30 | 16333.91 | 14700.52 | 1633.39 | Partially Paid
PAYAPP-ARM-2522-202509 | ARM-2522 | C-1071 | 2025-09-30 | 2025-10-30 | 35568.28 | 32011.45 | 3556.83 | Partially Paid
PAYAPP-ARM-2522-202510 | ARM-2522 | C-1071 | 2025-10-31 | 2025-11-30 | 58868.14 | 52981.33 | 5886.81 | Partially Paid
PAYAPP-ARM-2522-202511 | ARM-2522 | C-1071 | 2025-11-30 | 2025-12-30 | 74183.32 | 66764.99 | 7418.33 | Partially Paid
PAYAPP-ARM-2522-202512 | ARM-2522 | C-1071 | 2025-12-31 | 2026-01-30 | 76738.3 | 69064.47 | 7673.83 | Partially Paid
PAYAPP-ARM-2522-202601 | ARM-2522 | C-1071 | 2026-01-31 | 2026-03-02 | 486854.23 | 438168.81 | 48685.42 | Partially Paid
PAYAPP-ARM-2522-202602 | ARM-2522 | C-1071 | 2026-02-28 | 2026-03-30 | 408099.37 | 367289.43 | 40809.94 | Partially Paid
PAYAPP-ARM-2522-202603 | ARM-2522 | C-1071 | 2026-03-31 | 2026-04-30 | 350321.39 | 315289.25 | 35032.14 | Partially Paid
PAYAPP-ARM-2522-202604 | ARM-2522 | C-1071 | 2026-04-30 | 2026-05-30 | 214024.34 | 192621.91 | 21402.43 | Partially Paid
PAYAPP-ARM-2522-202605 | ARM-2522 | C-1071 | 2026-05-31 | 2026-06-30 | 116771.2 | 60954.57 | 11677.12 | Partially Paid
PAYAPP-ARM-2526-202510 | ARM-2526 | C-1058 | 2025-10-31 | 2025-11-30 | 15004.43 | 14254.21 | 750.22 | Partially Paid
PAYAPP-ARM-2526-202511 | ARM-2526 | C-1058 | 2025-11-30 | 2025-12-30 | 33113.76 | 31458.07 | 1655.69 | Partially Paid
PAYAPP-ARM-2526-202512 | ARM-2526 | C-1058 | 2025-12-31 | 2026-01-30 | 52811.63 | 50171.05 | 2640.58 | Partially Paid
PAYAPP-ARM-2526-202601 | ARM-2526 | C-1058 | 2026-01-31 | 2026-03-02 | 369648.01 | 351165.61 | 18482.4 | Partially Paid
PAYAPP-ARM-2526-202602 | ARM-2526 | C-1058 | 2026-02-28 | 2026-03-30 | 338074.9 | 321171.15 | 16903.75 | Partially Paid
PAYAPP-ARM-2526-202603 | ARM-2526 | C-1058 | 2026-03-31 | 2026-04-30 | 300344.94 | 285327.69 | 15017.25 | Partially Paid
PAYAPP-ARM-2526-202604 | ARM-2526 | C-1058 | 2026-04-30 | 2026-05-30 | 193020.68 | 183369.65 | 9651.03 | Partially Paid
PAYAPP-ARM-2526-202605 | ARM-2526 | C-1058 | 2026-05-31 | 2026-06-30 | 118408.64 | 65243.16 | 5920.43 | Partially Paid
PAYAPP-ARM-2602-202601 | ARM-2602 | C-1076 | 2026-01-31 | 2026-03-02 | 122667.22 | 110400.5 | 12266.72 | Partially Paid
PAYAPP-ARM-2602-202602 | ARM-2602 | C-1076 | 2026-02-28 | 2026-03-30 | 256225.28 | 230602.75 | 25622.53 | Partially Paid
PAYAPP-ARM-2602-202603 | ARM-2602 | C-1076 | 2026-03-31 | 2026-04-30 | 333234.02 | 299910.62 | 33323.4 | Partially Paid
PAYAPP-ARM-2602-202604 | ARM-2602 | C-1076 | 2026-04-30 | 2026-05-30 | 270924.78 | 243832.3 | 27092.48 | Partially Paid
PAYAPP-ARM-2602-202605 | ARM-2602 | C-1076 | 2026-05-31 | 2026-06-30 | 128216.33 | 66928.93 | 12821.63 | Partially Paid
PAYAPP-ARM-2605-202602 | ARM-2605 | C-1080 | 2026-02-28 | 2026-03-30 | 140158.65 | 126142.79 | 14015.86 | Partially Paid
PAYAPP-ARM-2605-202603 | ARM-2605 | C-1080 | 2026-03-31 | 2026-04-30 | 269604.82 | 242644.34 | 26960.48 | Partially Paid
PAYAPP-ARM-2605-202604 | ARM-2605 | C-1080 | 2026-04-30 | 2026-05-30 | 287027.73 | 258324.96 | 28702.77 | Partially Paid
PAYAPP-ARM-2605-202605 | ARM-2605 | C-1080 | 2026-05-31 | 2026-06-30 | 147162.48 | 76818.81 | 14716.25 | Partially Paid
PAYAPP-ARM-2608-202603 | ARM-2608 | C-1013 | 2026-03-31 | 2026-05-15 | 184864.21 | 175621 | 9243.21 | Partially Paid
PAYAPP-ARM-2608-202604 | ARM-2608 | C-1013 | 2026-04-30 | 2026-06-14 | 295371.13 | 280602.57 | 14768.56 | Partially Paid
PAYAPP-ARM-2608-202605 | ARM-2608 | C-1013 | 2026-05-31 | 2026-07-15 | 199963.61 | 110179.95 | 9998.18 | Partially Paid

## x_map old
Legacy mapping carried from FY24 conversion. Columns F-H are no longer used, but deleting them broke the April file.
Job | Old phase | Current cost code | Revenue bucket | Branch override | FY24 PM | Do not use | last touched
ARM-2318 | P01 | 02-110 | Construction | manual-Bend | MC | old formula anchor | 2025-01-28
ARM-2403 | P02 | 03-100 | Construction |  | EM |  | 2025-02-28
ARM-2409 | P03 | 04-100 | Construction |  | PR |  | 2025-03-28
ARM-2412 | P04 | 05-100 | Construction |  | LB |  | 2025-04-28
ARM-2417 | P05 | 02-110 | Construction |  | MC |  | 2025-05-28
ARM-2421 | P06 | 03-100 | Construction |  | EM | old formula anchor | 2025-06-28
ARM-2501 | P07 | 04-100 | Controls |  | PR |  | 2025-07-28
ARM-2506 | P08 | 05-100 | Construction | manual-Bend | LB |  | 2025-08-28
ARM-2510 | P09 | 02-110 | Construction |  | MC |  | 2025-09-28
ARM-2514 | P01 | 03-100 | Construction |  | EM |  | 2025-01-28
ARM-2518 | P02 | 04-100 | Construction |  | PR | old formula anchor | 2025-02-28
ARM-2522 | P03 | 05-100 | Construction |  | LB |  | 2025-03-28
ARM-2526 | P04 | 02-110 | Construction |  | MC |  | 2025-04-28
ARM-2602 | P05 | 03-100 | Construction |  | EM |  | 2025-05-28
ARM-2605 | P06 | 04-100 | Construction | manual-Bend | PR |  | 2025-06-28
ARM-2608 | P07 | 05-100 | Controls |  | LB | old formula anchor | 2025-07-28

## notes - NB KS
Working notes copied forward. Some items are resolved; initials/date are more reliable than the status column.
When | Initials | Note | status?
5/31 7:14p | KS | 2409 ETC includes the backcharge recovery - ask PR before rolling | open
6/1 8:03a | NB | Do not net claim until accepted. Reclass in June forecast if still disputed. | OPEN
6/2 10:44a | KS | 2417 night work PCO not signed; cost likely real | open
6/3 4:22p | NB | May JE posted and set to auto reverse | done
6/4 11:10a | KS | Final file saved after NB margin review | done
6/4 11:13a | KS | Didn't remove old x_map because April links still point there | leave
6/5 | DC | Use May deck numbers from operating review, not this cover--deck was refreshed after close | FYI

## Source Log
May WIP Source Log
Recurring workpaper metadata and refresh lineage
Item | Period / As-of | Source Type | Source Name | Reference | Owner | Refresh Date | Status | Notes
Posted job cost | Through 2026-05-31 | Accounting report | Job Cost Detail by Project | System report JC-220 | Project Accounting | 2026-06-01 | Current | Imported values in WIP Detail column H
Posted contract billings | Through 2026-05-31 | Accounting report | Project Billing Register | System report AR-415 | Project Accounting | 2026-06-01 | Current | Imported values in WIP Detail column M
Project ETC | May 2026 | Department submission | PM EAC Submission Register | Operations/Project Forecasts/2026-05 | Project Managers | 2026-06-02 | Current | Controller-reviewed remaining cost estimate
Contract value | As of 2026-05-31 | Accounting report | Project Contract Status | System report JC-105 | Commercial Manager | 2026-06-01 | Current | Executed change orders only