## READ ME first
June WIP — risk-case review copy
Controller working file created 7/1/26 8:47am ¦ not a posted close schedule
Purpose | Refresh the four judgment-heavy jobs after reconciling posted actuals to Vista ERP.
Current contract | Executed base contract plus approved bilateral change orders only.
Cost / billings | Accounting-system actuals through 2026-06-30 control.
PM ETC | Latest PM submission before finance policy overlays.
Finance overlay | Probable unavoidable cost is added even when related recovery remains unapproved.
Do not use | Pending revenue, disputed recoveries, or unsupported netting to improve margin.
Required formulas | Close ETC, EAC, percent complete, earned revenue, WIP position and margin must remain formula-driven.
Status | WORKING / REVIEW — blank calculation columns are intentional.
Sign-off | Controller review required before values are copied into the close schedule.
Control — project rows
Control — named evidence rows
Control — blank formula cells

## Risk Review
June project estimate risk review
Blue cells require a current-source refresh or a referenced finance formula
Project ID | Project | Current contract | Posted cost to date | PM ETC | Documented ETC overlay | Close ETC | EAC | % complete | Earned revenue | Billings to date | Contract asset | Contract liability | Estimated margin | Margin %
ARM-2318 | Columbia Biologics Clean Utilities
ARM-2409 | Northline Cold Storage Expansion
ARM-2417 | Cascade Health Ambulatory Pavilion
ARM-2506 | Eastbank Data Hall Cooling Expansion
TOTAL / CONTROL

## Evidence Map
Risk-case evidence map
Paths are intentionally messy because they mirror the active shared-drive close folder
Project | Forecast evidence role | Commercial evidence role | Support clue | Accounting population | Policy question | Reviewer note
ARM-2318 | Latest consolidated June PM submission | Current commercial master / retest item | PM comment and commercial backup; no standalone packet retained | Current project summary through 6/30 | Can a recovery be recognized, and what unavoidable retest cost remains? | Closeout evidence incomplete
ARM-2409 | Latest consolidated June PM submission | Current commercial master / concrete backcharge | Draft project-numbered backcharge packet in commercial support | Current project summary through 6/30 | Can a disputed recovery be netted against ETC? | Concrete trade has not accepted
ARM-2417 | Latest consolidated June PM submission | Current commercial master / night-shift directive | Owner correspondence and field-direction packet | Current project summary through 6/30 | How should unexecuted revenue and probable after-hours cost be treated? | Owner directive not executed
ARM-2506 | Latest consolidated June PM submission | Current commercial master / design bulletin | Project-numbered design-bulletin cost estimate | Current project summary through 6/30 | How should technical direction without executed price be treated? | Technical direction only