## Slide 1
ALDER RIDGE MECHANICAL
May 2026
Operating Review
Performance, project outlook, working capital and June close priorities
Leadership review | June 5, 2026
FINAL_v4

## Slide 2
MAY 2026 OPERATING REVIEW
May revenue outpaced plan, while project mix compressed margin
ARM | 6/5/26 leadership room | internal
FINAL_v4 • NB / DC
Metric | May actual | May plan | Variance
Revenue | $3.9m | $4.2m | -5.0%
Gross profit | $0.5m | $1.0m | -54.5%
Operating expense | $0.8m | $0.6m | +36.0%
Operating income | ($0.3m) | $0.5m | ($0.8m)
What changed
Construction revenue conversion remained on schedule. Gross margin finished below plan as the mix shifted toward Eastbank procurement and Cascade Health night-work exposure. Service utilization partially offset the pressure.
June focus
Hold pending change-order revenue out of the close, refresh low-confidence EACs, and convert large underbillings where the contract permits.

## Slide 3
MAY 2026 OPERATING REVIEW
Revenue is ahead of plan; margin quality is the constraint
ARM | 6/5/26 leadership room | internal
FINAL_v4 • NB / DC
Chart: 
| Jan | Feb | Mar | Apr | May
Actual revenue | 4.3498 | 4.1804 | 4.1436 | 4.4719 | 3.9452
Plan revenue | 3.4343 | 3.5141 | 3.7537 | 3.9135 | 4.1531
YTD revenue
$21.1m
YTD gross margin
24.1%
The June close must distinguish real margin erosion from timing: pending commercial recoveries cannot mask probable cost exposure.

## Slide 4
MAY 2026 OPERATING REVIEW
Four projects concentrate WIP and commercial follow-through
ARM | 6/5/26 leadership room | internal
FINAL_v4 • NB / DC
Chart: 
| ARM-2514 | ARM-2318 | ARM-2526 | ARM-2417 | ARM-2409 | ARM-2403
Contract asset | 0 | 0.4204 | 0 | 0.28135 | 0.27481 | 0
Contract liability | -0.842 | 0 | -0.28525 | 0 | 0 | -0.23812
Contract assets
$1.1m
Contract liabilities
$2.3m
Eastbank, Cascade Health, Northline and Columbia Biologics account for most estimate uncertainty. June review must update ETC before evaluating billing actions.

## Slide 5
MAY 2026 OPERATING REVIEW
Three timing dates drive the liquidity low point
ARM | 6/5/26 leadership room | internal
FINAL_v4 • NB / DC
Chart: 
| 07-03 | 07-10 | 07-17 | 07-24 | 07-31 | 08-07 | 08-14 | 08-21 | 08-28 | 09-04
Ending cash | 3.941 | 4.2589 | 4.4484 | 5.4681 | 5.1071 | 5.8136 | 5.3637 | 5.4931 | 4.9348 | 5.0913
Liquidity floor | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
Timing drivers
1 Eastbank funding draw
Expected mid-July; lien-waiver completion is the near-term dependency.
2 Trane factory release
The remaining chiller commitment is the largest single equipment outflow.
3 Columbia close-out
Keep disputed validation and retainage receipts outside the July base case.

## Slide 6
MAY 2026 OPERATING REVIEW
June close priorities: protect estimates and preserve cash options
ARM | 6/5/26 leadership room | internal
FINAL_v4 • NB / DC
Workstream | Decision / action | Owner | Due
WIP estimates | Resolve low-confidence ETCs and record probable cost without pending revenue. | Controller + Ops | July 2
Commercial | Advance executed documentation on Cascade Health, Eastbank and Northline positions. | Commercial Mgr | July 2
Billing | Identify contract-compliant billing actions for large, supportable underbillings. | Project Acctg | July 3
Collections | Escalate Eastbank and public-owner dates; keep Columbia close-out outside July base. | Controller | Weekly
Liquidity | Prepare revolver draw mechanics before headroom reaches the policy floor. | CFO / Treasury | July 3
Outcome for the June review
A reconciled WIP close, a 13-week cash view grounded in invoice-level timing, and explicit decisions on commercial risk and liquidity.

## Slide 7
MAY 2026 | APPENDIX / WORKING REFERENCES
Source reconciliation — what was used and what was not
ARM | 6/5/26 leadership room | internal
FINAL_v4 • NB / DC
Page / metric | Controlling source | Cross-check | Open item / note
P&L actual | Accounting system GL through 5/31 | FY26 plan tab | June not closed
Revenue plan | BoardApproved AOP FINAL2 | Monthly Plan | v3 deck used old phasing
WIP | 5.31 WIP v7 revised NB | JC + billing dumps | manual EAC overrides
Commercial | CO log PR copy | support PDFs | status labels inconsistent
Collections | system AR aging | NB call notes | dates are judgmental
Liquidity | 13wk cash v9 | AP dump / bank rec | May page is directional
Retained note: do not reuse May deck numbers for June. Preserve page geometry and decision rhythm only; rebuild every metric from current sources.

## Slide 8
MAY 2026 | APPENDIX / FOLLOW-THROUGH
Items carried forward from the room
ARM | 6/5/26 leadership room | internal
FINAL_v4 • NB / DC
Numbers / controls
• Reconcile plan version before next deck
• Show YTD dollars and margin rate
• Separate executed revenue from cost exposure
• Keep invoice-level cash mapping once only
Decisions / owners
• NB — WIP estimate quality page
• PR — change support and status cleanup
• KS — evidence-based receipt dates
• DC — liquidity trigger and lender wording
DC handwritten follow-up (transcribed): June pack = 9 pages max; decision page before appendix; send PPT + PDF + source/notes file together.