## detail - working
Major-project cash curves and funding needs — supporting detail
Scenario B uses PM milestone dates and treasury collection lags; it is not a posted forecast. Source amounts reflect the current 6/30 company records.
record | date | category | dimension | description | source amount | documented adjustment | working amount | status | source / cutoff
ARM-2318-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 58425 | -15147.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 63736.37 | -16830.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 42490.91 | -18513.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 47802.27 | -20196.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 53113.64 | -13464.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 58425 | -15147.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 63736.37 | -16830.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 42490.91 | -18513.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 47802.27 | -20196.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 53113.64 | -13464.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 58425 | -15147.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 63736.37 | -16830.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2318-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2318 | Planned billings less planned project cost | 42490.91 | -18513.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 86138.46 | -61753.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 93969.23 | -68615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 62646.15 | -75476.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 70476.92 | -82338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 78307.69 | -54892.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 86138.46 | -61753.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 93969.23 | -68615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 62646.15 | -75476.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 70476.92 | -82338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 78307.69 | -54892.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 86138.46 | -61753.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 93969.23 | -68615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2403-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2403 | Planned billings less planned project cost | 62646.15 | -75476.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 97342.12 | -53238.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 106191.4 | -59153.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 70794.27 | -65069.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 79643.55 | -70984.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 88492.84 | -47323.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 97342.12 | -53238.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 106191.4 | -59153.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 70794.27 | -65069.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 79643.55 | -70984.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 88492.84 | -47323.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 97342.12 | -53238.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 106191.4 | -59153.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2409-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2409 | Planned billings less planned project cost | 70794.27 | -65069.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 121518.84 | -65561.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 132566.01 | -72846.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 88377.34 | -80130.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 99424.51 | -87415.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 110471.68 | -58276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 121518.84 | -65561.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 132566.01 | -72846.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 88377.34 | -80130.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 99424.51 | -87415.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 110471.68 | -58276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 121518.84 | -65561.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 132566.01 | -72846.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2412-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2412 | Planned billings less planned project cost | 88377.34 | -80130.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 369953.16 | -230053.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 403585.26 | -255615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 269056.84 | -281176.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 302688.95 | -306738.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 336321.05 | -204492.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 369953.16 | -230053.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 403585.26 | -255615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 269056.84 | -281176.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 302688.95 | -306738.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 336321.05 | -204492.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 369953.16 | -230053.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 403585.26 | -255615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2417-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2417 | Planned billings less planned project cost | 269056.84 | -281176.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 338.46 | -2146.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 369.23 | -2384.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 246.15 | -2623.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 276.92 | -2861.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 307.69 | -1907.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 338.46 | -2146.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 369.23 | -2384.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 246.15 | -2623.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 276.92 | -2861.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 307.69 | -1907.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 338.46 | -2146.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 369.23 | -2384.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2421-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2421 | Planned billings less planned project cost | 246.15 | -2623.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 109273.74 | -63276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 119207.72 | -70307.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 79471.81 | -77338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 89405.79 | -84369.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 99339.77 | -56246.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 109273.74 | -63276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 119207.72 | -70307.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 79471.81 | -77338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 89405.79 | -84369.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 99339.77 | -56246.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 109273.74 | -63276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 119207.72 | -70307.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2501-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2501 | Planned billings less planned project cost | 79471.81 | -77338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 545296.99 | -342069.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 594869.44 | -380076.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 396579.63 | -418084.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 446152.08 | -456092.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 495724.53 | -304061.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 545296.99 | -342069.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 594869.44 | -380076.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 396579.63 | -418084.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 446152.08 | -456092.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 495724.53 | -304061.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 545296.99 | -342069.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 594869.44 | -380076.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2506-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2506 | Planned billings less planned project cost | 396579.63 | -418084.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 369440.32 | -227353.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 403025.81 | -252615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 268683.87 | -277876.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 302269.36 | -303138.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 335854.84 | -202092.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 369440.32 | -227353.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 403025.81 | -252615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 268683.87 | -277876.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 302269.36 | -303138.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 335854.84 | -202092.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 369440.32 | -227353.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 403025.81 | -252615.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2510-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2510 | Planned billings less planned project cost | 268683.87 | -277876.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 138261.54 | -103292.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 150830.77 | -114769.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 100553.85 | -126246.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 113123.08 | -137723.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 125692.31 | -91815.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 138261.54 | -103292.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 150830.77 | -114769.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 100553.85 | -126246.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 113123.08 | -137723.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 125692.31 | -91815.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 138261.54 | -103292.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 150830.77 | -114769.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2514-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2514 | Planned billings less planned project cost | 100553.85 | -126246.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 148412.78 | -89723.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 161904.85 | -99692.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 107936.57 | -109661.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 121428.64 | -119630.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 134920.71 | -79753.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 148412.78 | -89723.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 161904.85 | -99692.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 107936.57 | -109661.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 121428.64 | -119630.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 134920.71 | -79753.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 148412.78 | -89723.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 161904.85 | -99692.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2518-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2518 | Planned billings less planned project cost | 107936.57 | -109661.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 229015.84 | -137215.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 249835.46 | -152461.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 166556.97 | -167707.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 187376.6 | -182953.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 208196.22 | -121969.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 229015.84 | -137215.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 249835.46 | -152461.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 166556.97 | -167707.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 187376.6 | -182953.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 208196.22 | -121969.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 229015.84 | -137215.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 249835.46 | -152461.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2522-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2522 | Planned billings less planned project cost | 166556.97 | -167707.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 33211.54 | -24023.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 36230.77 | -26692.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 24153.85 | -29361.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 27173.08 | -32030.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 30192.31 | -21353.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 33211.54 | -24023.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 36230.77 | -26692.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 24153.85 | -29361.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 27173.08 | -32030.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 30192.31 | -21353.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 33211.54 | -24023.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 36230.77 | -26692.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2526-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2526 | Planned billings less planned project cost | 24153.85 | -29361.54 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 404609.29 | -252276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 441391.95 | -280307.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 294261.3 | -308338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 331043.96 | -336369.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 367826.63 | -224246.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 404609.29 | -252276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 441391.95 | -280307.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 294261.3 | -308338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 331043.96 | -336369.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 367826.63 | -224246.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 404609.29 | -252276.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 441391.95 | -280307.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2602-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2602 | Planned billings less planned project cost | 294261.3 | -308338.46 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 463195.4 | -285507.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 505304.07 | -317230.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 336869.38 | -348953.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 378978.05 | -380676.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 421086.73 | -253784.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 463195.4 | -285507.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 505304.07 | -317230.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 336869.38 | -348953.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 378978.05 | -380676.92 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 421086.73 | -253784.62 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 463195.4 | -285507.69 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 505304.07 | -317230.77 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2605-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2605 | Planned billings less planned project cost | 336869.38 | -348953.85 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-07-03 | 2026-07-03 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 107350 | -60992.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-07-10 | 2026-07-10 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 117109.1 | -67769.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-07-17 | 2026-07-17 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 78072.73 | -74546.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-07-24 | 2026-07-24 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 87831.82 | -81323.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-07-31 | 2026-07-31 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 97590.91 | -54215.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-08-07 | 2026-08-07 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 107350 | -60992.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-08-14 | 2026-08-14 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 117109.1 | -67769.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-08-21 | 2026-08-21 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 78072.73 | -74546.15 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-08-28 | 2026-08-28 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 87831.82 | -81323.08 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-09-04 | 2026-09-04 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 97590.91 | -54215.38 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-09-11 | 2026-09-11 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 107350 | -60992.31 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-09-18 | 2026-09-18 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 117109.1 | -67769.23 |  | scenario B | PM milestones + treasury lag assumptions
ARM-2608-2026-09-25 | 2026-09-25 | weekly project cash | ARM-2608 | Planned billings less planned project cost | 78072.73 | -74546.15 |  | scenario B | PM milestones + treasury lag assumptions

## working summary
Major-project cash curves and funding needs
Owner-maintained finance workpaper ¦ rev 4 ¦ formula summary from detail
category | record count | source total | documented adj | working total | owner | status | interpretation
weekly project cash |  |  |  |  | NB | review | Documented timing/classification item; not an arbitrary plug

## links + lineage
Workbook links and lineage
External links are convenience references; imported source tabs and the 6/30 ERP cutoff remain the auditable basis.
upstream source | role | cutoff/version | link behavior | current imported total | control note
WIP 5.31.26_FINAL_v7_revised NB.xlsx | primary upstream workbook/import | 6/30/26 or named version | Owner refreshes the imported source tab or scheduled query before close |  | Imported detail is retained so the workbook remains auditable without a live connection
Vista ERP | posted actuals | 2026-06-30 | scheduled report export |  | Authoritative for posted balances and transactions
FY26 Op Plan_BoardApproved_12.18.25_FINAL2.xlsx | plan | approved 12/18/25 | external workbook |  | Authoritative approved plan, not actuals
WIP 5.31.26_FINAL_v7_revised NB.xlsx | prior close | 2026-05-31 | external workbook |  | Prior-period baseline only
manual owner evidence | judgment / classification | noted per row | documented adjustment column |  | No silent plugs permitted

## checks + signoff
Major-project cash curves and funding needs — checks / sign-off
Formula-driven arithmetic, population and lineage controls
check | expected | actual / delta | result | explanation | reviewer
Detail arithmetic | 0 |  |  | Working amount equals source plus documented adjustment
Population count | 208 |  |  | Full source population used for this workpaper
Source lineage present | 208 |  |  | Every row names a source/cutoff
Silent adjustment check | 0 |  |  | All adjustments are visible in column G
Reviewer sign-off | required | pending |  | Working file; sign-off remains open