## Contract Backlog
Complete the backlog burn and capacity model ¦ Contract Backlog
LOCKED INPUT SCHEDULE • refreshed from current management workbooks and Vista ERP • Do not edit
Source Ref | Schedule | Entity | Period | Scenario | Measure | Numeric Value | Text Value | Unit | Source Document | Source Date | System Tie
035-SRC0001 | Signed contract backlog | P-3101 | 2026-06-30 | Approved case | Remaining transaction price | 8400000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0002 | Signed contract backlog | P-3101 | FY27 | Approved case | Contract start month |  | 2026-07 | classification | Finance operating schedule | 2026-06-30
035-SRC0003 | Signed contract backlog | P-3101 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0004 | Signed contract backlog | P-3101 | FY27 | Approved case | Revenue per productive hour | 118 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0008 | Project burn curve | P-3101 | 2026-07 | Approved case | Monthly burn share | 0.012821 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0009 | Project burn curve | P-3101 | 2026-08 | Approved case | Monthly burn share | 0.025641 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0010 | Project burn curve | P-3101 | 2026-09 | Approved case | Monthly burn share | 0.038462 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0011 | Project burn curve | P-3101 | 2026-10 | Approved case | Monthly burn share | 0.051282 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0012 | Project burn curve | P-3101 | 2026-11 | Approved case | Monthly burn share | 0.064103 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0013 | Project burn curve | P-3101 | 2026-12 | Approved case | Monthly burn share | 0.076923 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0014 | Project burn curve | P-3101 | 2027-01 | Approved case | Monthly burn share | 0.089744 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0015 | Project burn curve | P-3101 | 2027-02 | Approved case | Monthly burn share | 0.10256 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0016 | Project burn curve | P-3101 | 2027-03 | Approved case | Monthly burn share | 0.11538 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0017 | Project burn curve | P-3101 | 2027-04 | Approved case | Monthly burn share | 0.12821 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0018 | Project burn curve | P-3101 | 2027-05 | Approved case | Monthly burn share | 0.14103 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0019 | Project burn curve | P-3101 | 2027-06 | Approved case | Monthly burn share | 0.15385 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0020 | Signed contract backlog | P-3107 | 2026-06-30 | Approved case | Remaining transaction price | 6900 |  | USD thousands | Finance operating schedule | 2026-06-30
035-SRC0021 | Signed contract backlog | P-3107 | FY27 | Approved case | Contract start month |  | 2026-08 | classification | Finance operating schedule | 2026-06-30
035-SRC0022 | Signed contract backlog | P-3107 | FY27 | Approved case | Execution probability | 0.95 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0023 | Signed contract backlog | P-3107 | FY27 | Approved case | Revenue per productive hour | 126 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0027 | Project burn curve | P-3107 | 2026-08 | Approved case | Monthly burn share | 0.015152 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0028 | Project burn curve | P-3107 | 2026-09 | Approved case | Monthly burn share | 0.030303 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0029 | Project burn curve | P-3107 | 2026-10 | Approved case | Monthly burn share | 0.045455 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0030 | Project burn curve | P-3107 | 2026-11 | Approved case | Monthly burn share | 0.060606 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0031 | Project burn curve | P-3107 | 2026-12 | Approved case | Monthly burn share | 0.075758 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0032 | Project burn curve | P-3107 | 2027-01 | Approved case | Monthly burn share | 0.090909 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0033 | Project burn curve | P-3107 | 2027-02 | Approved case | Monthly burn share | 0.10606 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0034 | Project burn curve | P-3107 | 2027-03 | Approved case | Monthly burn share | 0.12121 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0035 | Project burn curve | P-3107 | 2027-04 | Approved case | Monthly burn share | 0.13636 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0036 | Project burn curve | P-3107 | 2027-05 | Approved case | Monthly burn share | 0.15152 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0037 | Project burn curve | P-3107 | 2027-06 | Approved case | Monthly burn share | 0.16667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0038 | Signed contract backlog | P-3114 | 2026-06-30 | Approved case | Remaining transaction price | 5600000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0039 | Signed contract backlog | P-3114 | FY27 | Approved case | Contract start month |  | 2026-10 | classification | Finance operating schedule | 2026-06-30
035-SRC0040 | Signed contract backlog | P-3114 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0041 | Signed contract backlog | P-3114 | FY27 | Approved case | Revenue per productive hour | 132 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0045 | Project burn curve | P-3114 | 2026-10 | Approved case | Monthly burn share | 0.022222 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0046 | Project burn curve | P-3114 | 2026-11 | Approved case | Monthly burn share | 0.044444 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0047 | Project burn curve | P-3114 | 2026-12 | Approved case | Monthly burn share | 0.066667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0048 | Project burn curve | P-3114 | 2027-01 | Approved case | Monthly burn share | 0.088889 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0049 | Project burn curve | P-3114 | 2027-02 | Approved case | Monthly burn share | 0.11111 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0050 | Project burn curve | P-3114 | 2027-03 | Approved case | Monthly burn share | 0.13333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0051 | Project burn curve | P-3114 | 2027-04 | Approved case | Monthly burn share | 0.15556 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0052 | Project burn curve | P-3114 | 2027-05 | Approved case | Monthly burn share | 0.17778 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0053 | Project burn curve | P-3114 | 2027-06 | Approved case | Monthly burn share | 0.2 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0054 | Signed contract backlog | P-3122 | 2026-06-30 | Approved case | Remaining transaction price | 4750000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0055 | Signed contract backlog | P-3122 | FY27 | Approved case | Contract start month |  | 2026-12 | classification | Finance operating schedule | 2026-06-30
035-SRC0056 | Signed contract backlog | P-3122 | FY27 | Approved case | Execution probability | 0.85 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0057 | Signed contract backlog | P-3122 | FY27 | Approved case | Revenue per productive hour | 120 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0061 | Project burn curve | P-3122 | 2026-12 | Approved case | Monthly burn share | 0.035714 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0062 | Project burn curve | P-3122 | 2027-01 | Approved case | Monthly burn share | 0.071429 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0063 | Project burn curve | P-3122 | 2027-02 | Approved case | Monthly burn share | 0.10714 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0064 | Project burn curve | P-3122 | 2027-03 | Approved case | Monthly burn share | 0.14286 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0065 | Project burn curve | P-3122 | 2027-04 | Approved case | Monthly burn share | 0.17857 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0066 | Project burn curve | P-3122 | 2027-05 | Approved case | Monthly burn share | 0.21429 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0067 | Project burn curve | P-3122 | 2027-06 | Approved case | Monthly burn share | 0.25 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0068 | Signed contract backlog | P-3130 | 2026-06-30 | Approved case | Remaining transaction price | 7200 |  | USD thousands | Finance operating schedule | 2026-06-30
035-SRC0069 | Signed contract backlog | P-3130 | FY27 | Approved case | Contract start month |  | 2027-01 | classification | Finance operating schedule | 2026-06-30
035-SRC0070 | Signed contract backlog | P-3130 | FY27 | Approved case | Execution probability | 0.9 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0071 | Signed contract backlog | P-3130 | FY27 | Approved case | Revenue per productive hour | 138 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0075 | Project burn curve | P-3130 | 2027-01 | Approved case | Monthly burn share | 0.047619 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0076 | Project burn curve | P-3130 | 2027-02 | Approved case | Monthly burn share | 0.095238 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0077 | Project burn curve | P-3130 | 2027-03 | Approved case | Monthly burn share | 0.14286 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0078 | Project burn curve | P-3130 | 2027-04 | Approved case | Monthly burn share | 0.19048 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0079 | Project burn curve | P-3130 | 2027-05 | Approved case | Monthly burn share | 0.2381 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0080 | Project burn curve | P-3130 | 2027-06 | Approved case | Monthly burn share | 0.28571 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0081 | Signed contract backlog | P-3138 | 2026-06-30 | Approved case | Remaining transaction price | 3900000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0082 | Signed contract backlog | P-3138 | FY27 | Approved case | Contract start month |  | 2027-02 | classification | Finance operating schedule | 2026-06-30
035-SRC0083 | Signed contract backlog | P-3138 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0084 | Signed contract backlog | P-3138 | FY27 | Approved case | Revenue per productive hour | 125 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0088 | Project burn curve | P-3138 | 2027-02 | Approved case | Monthly burn share | 0.066667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0089 | Project burn curve | P-3138 | 2027-03 | Approved case | Monthly burn share | 0.13333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0090 | Project burn curve | P-3138 | 2027-04 | Approved case | Monthly burn share | 0.2 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0091 | Project burn curve | P-3138 | 2027-05 | Approved case | Monthly burn share | 0.26667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0092 | Project burn curve | P-3138 | 2027-06 | Approved case | Monthly burn share | 0.33333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0093 | Signed contract backlog | P-3145 | 2026-06-30 | Approved case | Remaining transaction price | 5100000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0094 | Signed contract backlog | P-3145 | FY27 | Approved case | Contract start month |  | 2027-03 | classification | Finance operating schedule | 2026-06-30
035-SRC0095 | Signed contract backlog | P-3145 | FY27 | Approved case | Execution probability | 0.8 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0096 | Signed contract backlog | P-3145 | FY27 | Approved case | Revenue per productive hour | 145 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0100 | Project burn curve | P-3145 | 2027-03 | Approved case | Monthly burn share | 0.1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0101 | Project burn curve | P-3145 | 2027-04 | Approved case | Monthly burn share | 0.2 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0102 | Project burn curve | P-3145 | 2027-05 | Approved case | Monthly burn share | 0.3 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0103 | Project burn curve | P-3145 | 2027-06 | Approved case | Monthly burn share | 0.4 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0104 | Signed contract backlog | P-3152 | 2026-06-30 | Approved case | Remaining transaction price | 2850 |  | USD thousands | Finance operating schedule | 2026-06-30
035-SRC0105 | Signed contract backlog | P-3152 | FY27 | Approved case | Contract start month |  | 2027-04 | classification | Finance operating schedule | 2026-06-30
035-SRC0106 | Signed contract backlog | P-3152 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0107 | Signed contract backlog | P-3152 | FY27 | Approved case | Revenue per productive hour | 130 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0111 | Project burn curve | P-3152 | 2027-04 | Approved case | Monthly burn share | 0.16667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0112 | Project burn curve | P-3152 | 2027-05 | Approved case | Monthly burn share | 0.33333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0113 | Project burn curve | P-3152 | 2027-06 | Approved case | Monthly burn share | 0.5 |  | decimal ratio | Finance operating schedule | 2026-06-30

## Capacity Inputs
Complete the backlog burn and capacity model ¦ Capacity Inputs
LOCKED INPUT SCHEDULE • refreshed from current management workbooks and Vista ERP • Do not edit
Source Ref | Schedule | Entity | Period | Scenario | Measure | Numeric Value | Text Value | Unit | Source Document | Source Date | System Tie
035-SRC0114 | Monthly capacity | All field labor | 2026-07 | Approved case | Productive internal hours | 31500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0115 | Monthly capacity | All field labor | 2026-07 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0116 | Monthly capacity | All field labor | 2026-07 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0117 | Capacity remediation | All field labor | 2026-07 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0118 | Capacity remediation | All field labor | 2026-07 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0119 | Capacity remediation | All field labor | 2026-07 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0120 | Capacity remediation | All field labor | 2026-07 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0121 | Monthly capacity | All field labor | 2026-08 | Approved case | Productive internal hours | 31780 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0122 | Monthly capacity | All field labor | 2026-08 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0123 | Monthly capacity | All field labor | 2026-08 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0124 | Capacity remediation | All field labor | 2026-08 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0125 | Capacity remediation | All field labor | 2026-08 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0126 | Capacity remediation | All field labor | 2026-08 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0127 | Capacity remediation | All field labor | 2026-08 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0128 | Monthly capacity | All field labor | 2026-09 | Approved case | Productive internal hours | 32060 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0129 | Monthly capacity | All field labor | 2026-09 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0130 | Monthly capacity | All field labor | 2026-09 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0131 | Capacity remediation | All field labor | 2026-09 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0132 | Capacity remediation | All field labor | 2026-09 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0133 | Capacity remediation | All field labor | 2026-09 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0134 | Capacity remediation | All field labor | 2026-09 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0135 | Monthly capacity | All field labor | 2026-10 | Approved case | Productive internal hours | 32340 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0136 | Monthly capacity | All field labor | 2026-10 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0137 | Monthly capacity | All field labor | 2026-10 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0138 | Capacity remediation | All field labor | 2026-10 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0139 | Capacity remediation | All field labor | 2026-10 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0140 | Capacity remediation | All field labor | 2026-10 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0141 | Capacity remediation | All field labor | 2026-10 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0142 | Monthly capacity | All field labor | 2026-11 | Approved case | Productive internal hours | 32620 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0143 | Monthly capacity | All field labor | 2026-11 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0144 | Monthly capacity | All field labor | 2026-11 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0145 | Capacity remediation | All field labor | 2026-11 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0146 | Capacity remediation | All field labor | 2026-11 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0147 | Capacity remediation | All field labor | 2026-11 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0148 | Capacity remediation | All field labor | 2026-11 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0149 | Monthly capacity | All field labor | 2026-12 | Approved case | Productive internal hours | 30100 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0150 | Monthly capacity | All field labor | 2026-12 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0151 | Monthly capacity | All field labor | 2026-12 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0152 | Capacity remediation | All field labor | 2026-12 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0153 | Capacity remediation | All field labor | 2026-12 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0154 | Capacity remediation | All field labor | 2026-12 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0155 | Capacity remediation | All field labor | 2026-12 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0156 | Monthly capacity | All field labor | 2027-01 | Approved case | Productive internal hours | 30380 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0157 | Monthly capacity | All field labor | 2027-01 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0158 | Monthly capacity | All field labor | 2027-01 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0159 | Capacity remediation | All field labor | 2027-01 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0160 | Capacity remediation | All field labor | 2027-01 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0161 | Capacity remediation | All field labor | 2027-01 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0162 | Capacity remediation | All field labor | 2027-01 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0163 | Monthly capacity | All field labor | 2027-02 | Approved case | Productive internal hours | 33460 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0164 | Monthly capacity | All field labor | 2027-02 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0165 | Monthly capacity | All field labor | 2027-02 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0166 | Capacity remediation | All field labor | 2027-02 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0167 | Capacity remediation | All field labor | 2027-02 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0168 | Capacity remediation | All field labor | 2027-02 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0169 | Capacity remediation | All field labor | 2027-02 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0170 | Monthly capacity | All field labor | 2027-03 | Approved case | Productive internal hours | 33740 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0171 | Monthly capacity | All field labor | 2027-03 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0172 | Monthly capacity | All field labor | 2027-03 | Approved case | Overtime limit on internal hours | 0.05 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0173 | Capacity remediation | All field labor | 2027-03 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0174 | Capacity remediation | All field labor | 2027-03 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0175 | Capacity remediation | All field labor | 2027-03 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0176 | Capacity remediation | All field labor | 2027-03 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0177 | Monthly capacity | All field labor | 2027-04 | Approved case | Productive internal hours | 34020 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0178 | Monthly capacity | All field labor | 2027-04 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0179 | Monthly capacity | All field labor | 2027-04 | Approved case | Overtime limit on internal hours | 0.05 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0180 | Capacity remediation | All field labor | 2027-04 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0181 | Capacity remediation | All field labor | 2027-04 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0182 | Capacity remediation | All field labor | 2027-04 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0183 | Capacity remediation | All field labor | 2027-04 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0184 | Monthly capacity | All field labor | 2027-05 | Approved case | Productive internal hours | 34300 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0185 | Monthly capacity | All field labor | 2027-05 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0186 | Monthly capacity | All field labor | 2027-05 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0187 | Capacity remediation | All field labor | 2027-05 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0188 | Capacity remediation | All field labor | 2027-05 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0189 | Capacity remediation | All field labor | 2027-05 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0190 | Capacity remediation | All field labor | 2027-05 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0191 | Monthly capacity | All field labor | 2027-06 | Approved case | Productive internal hours | 34580 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0192 | Monthly capacity | All field labor | 2027-06 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0193 | Monthly capacity | All field labor | 2027-06 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0194 | Capacity remediation | All field labor | 2027-06 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0195 | Capacity remediation | All field labor | 2027-06 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0196 | Capacity remediation | All field labor | 2027-06 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0197 | Capacity remediation | All field labor | 2027-06 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30

## Execution Authority
Complete the backlog burn and capacity model ¦ Execution Authority
LOCKED INPUT SCHEDULE • refreshed from current management workbooks and Vista ERP • Do not edit
Source Ref | Schedule | Entity | Period | Scenario | Measure | Numeric Value | Text Value | Unit | Source Document | Source Date | System Tie
035-SRC0005 | Execution authority | P-3101 | FY27 | Approved case | Customer delivery priority | 1 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0006 | Execution authority | P-3101 | FY27 | Approved case | Contract gross margin | 0.24 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0007 | Execution authority | P-3101 | FY27 | Approved case | Monthly liquidated damages rate | 0.006 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0024 | Execution authority | P-3107 | FY27 | Approved case | Customer delivery priority | 2 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0025 | Execution authority | P-3107 | FY27 | Approved case | Contract gross margin | 0.22 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0026 | Execution authority | P-3107 | FY27 | Approved case | Monthly liquidated damages rate | 0.008 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0042 | Execution authority | P-3114 | FY27 | Approved case | Customer delivery priority | 1 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0043 | Execution authority | P-3114 | FY27 | Approved case | Contract gross margin | 0.27 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0044 | Execution authority | P-3114 | FY27 | Approved case | Monthly liquidated damages rate | 0.007 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0058 | Execution authority | P-3122 | FY27 | Approved case | Customer delivery priority | 3 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0059 | Execution authority | P-3122 | FY27 | Approved case | Contract gross margin | 0.2 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0060 | Execution authority | P-3122 | FY27 | Approved case | Monthly liquidated damages rate | 0.01 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0072 | Execution authority | P-3130 | FY27 | Approved case | Customer delivery priority | 2 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0073 | Execution authority | P-3130 | FY27 | Approved case | Contract gross margin | 0.25 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0074 | Execution authority | P-3130 | FY27 | Approved case | Monthly liquidated damages rate | 0.009 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0085 | Execution authority | P-3138 | FY27 | Approved case | Customer delivery priority | 4 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0086 | Execution authority | P-3138 | FY27 | Approved case | Contract gross margin | 0.18 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0087 | Execution authority | P-3138 | FY27 | Approved case | Monthly liquidated damages rate | 0.012 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0097 | Execution authority | P-3145 | FY27 | Approved case | Customer delivery priority | 3 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0098 | Execution authority | P-3145 | FY27 | Approved case | Contract gross margin | 0.29 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0099 | Execution authority | P-3145 | FY27 | Approved case | Monthly liquidated damages rate | 0.011 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0108 | Execution authority | P-3152 | FY27 | Approved case | Customer delivery priority | 4 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0109 | Execution authority | P-3152 | FY27 | Approved case | Contract gross margin | 0.17 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0110 | Execution authority | P-3152 | FY27 | Approved case | Monthly liquidated damages rate | 0.014 |  | decimal ratio | Executed contract terms | 2026-06-30

## Revenue Burn
FY27 backlog burn ¦ planning cases
Build from the controlled source schedules; keep probability plan, signed commitment, and pipeline distinct
Case | Signed backlog | FY27 revenue | Required hours | First constrained month | Unresolved hours | Remediation cost | Release conclusion
Approved probability plan
Full signed commitment
Month | Probability-plan revenue | Gross-commitment revenue | Revenue variance | Probability-plan hours | Gross-commitment hours | Source / version | Control
2026-07
2026-08
2026-09
2026-10
2026-11
2026-12
2027-01
2027-02
2027-03
2027-04
2027-05
2027-06

## Labor Capacity
FY27 labor capacity ¦ approved availability
Reconcile recurring capacity and keep ordinary availability separate from emergency response
Month | Productive internal hours | Permitted overtime | Planned subcontractable | Base available hours | Emergency OT capacity | Contingent surge capacity | Remediated available hours | Source / authority
2026-07
2026-08
2026-09
2026-10
2026-11
2026-12
2027-01
2027-02
2027-03
2027-04
2027-05
2027-06

## Gap Analysis
FY27 capacity response ¦ case comparison
Capacity gap = required hours less available hours; positive is a shortfall and negative is spare capacity
Case | Month | Revenue | Required hours | Available hours | Capacity gap | Emergency OT used | Surge used | Unresolved shortfall | Remediation cost | Decision
Approved probability plan | 2026-07
Approved probability plan | 2026-08
Approved probability plan | 2026-09
Approved probability plan | 2026-10
Approved probability plan | 2026-11
Approved probability plan | 2026-12
Approved probability plan | 2027-01
Approved probability plan | 2027-02
Approved probability plan | 2027-03
Approved probability plan | 2027-04
Approved probability plan | 2027-05
Approved probability plan | 2027-06
Full signed commitment | 2026-07
Full signed commitment | 2026-08
Full signed commitment | 2026-09
Full signed commitment | 2026-10
Full signed commitment | 2026-11
Full signed commitment | 2026-12
Full signed commitment | 2027-01
Full signed commitment | 2027-02
Full signed commitment | 2027-03
Full signed commitment | 2027-04
Full signed commitment | 2027-05
Full signed commitment | 2027-06

## Project Execution
FY27 signed-backlog execution ¦ priority and earnings
Use approved customer priority and contract terms; roll unfinished work rather than manufacturing capacity
Project | Priority | Signed backlog | Required hours | Completed hours | Deferred hours | Completed revenue | Deferred revenue | Completed gross profit | Liquidated damages | Release decision
P-3101
P-3107
P-3114
P-3122
P-3130
P-3138
P-3145
P-3152
MONTHLY EARNINGS RELEASE BRIDGE
Month | Probability-plan GP after response | Gross-commitment GP after response | Executable GP after damages | Deferred revenue at risk | Management decision
2026-07
2026-08
2026-09
2026-10
2026-11
2026-12
2027-01
2027-02
2027-03
2027-04
2027-05
2027-06

## Checks
FY27 backlog and capacity ¦ controls and executive decision
One assertion per control; the model is releasable only when the calculations and decision conditions agree
Check | Actual | Expected | Difference | Tolerance | Status | Where to fix / source
Source population tie
Backlog roll-forward
Probability-plan burn
Gross-commitment burn
Capacity sign convention
Remediation sequence
Project-to-month roll-forward
Revenue and gross-profit bridge
MODEL STATUS
EXECUTIVE RECOVERY DECISION
Recommendation | Probability-plan GP | Gross-commitment GP | Executable GP after damages | Deferred revenue | Deferred gross profit | Damages | Recovery required | Priority item | Release condition / owner action