## Commercial Log
Change Order and Claims Log
Commercial status through 2026-06-30 17:00 PT ¦ Executed changes are reflected in Vista ERP
Project ID | Reference | Description | Revenue Amount | Estimated Cost | Estimated Margin | Status | Last Updated | Contract Included? | Finance Review Status | Support / Notes
ARM-2417 | PCO-017 | OR congestion and after-hours premium | 382000 | 275000 |  | Submitted | 2026-06-17 | No | Pending controller assessment under signed WIP policy | Owner review; no executed directive
ARM-2409 | PCO-011 | Freezer slab rework backcharge to concrete trade | 185000 | -185000 |  | Draft | 2026-06-24 | No | Pending controller assessment under signed WIP policy | Recovery disputed; no subcontractor acceptance
ARM-2506 | PCO-006 | Chiller electrical service redesign | 296000 | 210000 |  | Pricing | 2026-06-21 | No | Pending controller assessment under signed WIP policy | Engineer-directed pricing only
ARM-2514 | CO-008 | Gym ventilation scope revision | 214000 | 147000 |  | Approved | 2026-06-12 | Yes | Executed before cutoff | Executed bilateral change order
ARM-2318 | PCO-029 | Final validation retest and extended support | 68000 | 45000 |  | Submitted | 2026-06-27 | No | Pending controller assessment under signed WIP policy | Customer disputes responsibility
ARM-2605 | PCO-002 | Temporary ventilation for summer events | 174000 | 121000 |  | Under Review | 2026-06-28 | No | Pending controller assessment under signed WIP policy | Work not authorized at cutoff
ARM-2403 | CO-014 | AHU-4 controls sequence revision | 96000 | 62000 |  | Approved | 2026-05-19 | Yes | Executed before cutoff | Executed
ARM-2412 | CO-009 | Lab exhaust fan VFD replacements | 133000 | 88000 |  | Approved | 2026-06-03 | Yes | Executed before cutoff | Executed

## Status Summary
Commercial Pipeline Summary
Unapproved amounts are pipeline only and do not alter WIP contract value
Status | Item Count | Revenue Amount | Estimated Cost
Approved
Submitted
Under Review
Pricing
Draft

## Data Dictionary
Commercial Log Data Dictionary
Definitions used by Commercial, Project Accounting and WIP review
Field | Definition | Owner | Accounting Treatment
Approved | Executed bilateral change order or written directive meeting contract authorization requirements. | Commercial Manager | May be included in current contract value when recorded in Vista ERP.
Submitted | Formal pricing submitted; owner has not executed the change. | Project Manager | Do not recognize revenue solely from this status.
Under Review | Scope and commercial terms remain under owner/GC review. | Commercial Manager | Revenue excluded; evaluate unavoidable costs separately.
Pricing | Scope is being estimated or negotiated and is not yet a complete submission. | Estimator / PM | Revenue excluded; probable cost may require EAC treatment.
Draft | Internal position or claim theory not yet formally transmitted. | Commercial Manager | No revenue; recovery cannot reduce cost without persuasive support.
Contract Included? | Whether Vista ERP current contract value reflects the item at cutoff. | Project Accounting | Must reconcile to project contract report.
Close Treatment | Controller guidance for June estimate and recognition judgment. | Controller | Apply with source evidence and document any override.

## PR working notes
Priya's running commercial notes. Status values are informal; the Commercial Log and executed documents control.
date typed | job | ref | person | note copied from call/e-mail | next chase | resolved?
2026-06-17 | ARM-2417 | PCO-017 | PR | Owner review; no executed directive | 7/2 | NO
6/12 | ARM-2417 | PCO-017 | PR | GC says pricing is with owner | see above
2026-06-24 | ARM-2409 | PCO-011 | MC | Recovery disputed; no subcontractor acceptance | 7/3 | NO
6/13 | ARM-2409 | PCO-011 | PR | need executed page not meeting minutes | see above
2026-06-21 | ARM-2506 | PCO-006 | EM | Engineer-directed pricing only | 7/4 | NO
6/14 | ARM-2506 | PCO-006 | PR | cost is moving before price | see above
2026-06-12 | ARM-2514 | CO-008 | LB | Executed bilateral change order | 7/5 | maybe
6/15 | ARM-2514 | CO-008 | PR | PM assumed recovery - not accepted | see above
2026-06-27 | ARM-2318 | PCO-029 | PR | Customer disputes responsibility | 7/6 | NO
6/16 | ARM-2318 | PCO-029 | PR | GC says pricing is with owner | see above
2026-06-28 | ARM-2605 | PCO-002 | MC | Work not authorized at cutoff | 7/7 | NO
6/17 | ARM-2605 | PCO-002 | PR | need executed page not meeting minutes | see above
2026-05-19 | ARM-2403 | CO-014 | EM | Executed | 7/2 | NO
6/18 | ARM-2403 | CO-014 | PR | cost is moving before price | see above
2026-06-03 | ARM-2412 | CO-009 | LB | Executed | 7/3 | maybe
6/19 | ARM-2412 | CO-009 | PR | PM assumed recovery - not accepted | see above

## status xwalk old
Old Procore-to-accounting status crosswalk. 'Directed' was removed from the current policy but is still present in historical exports.
Ops status | Commercial log status | system contract? | WIP revenue? | cost treatment | last policy review
Potential | Draft | No | No | Assess probable cost | 2024-11
Pricing | Pricing | No | No | Assess probable cost | 2024-11
Submitted | Submitted | No | No | Include unavoidable cost | 2024-11
Directed | Under Review | Maybe | NO - see policy | Include probable cost | 2023-06
Approved | Approved | Yes after posting | Yes after system update | Include | 2024-11
Rejected | Closed | No | No | Recognize incurred cost | 2024-11