## Submission Register
June 2026 Project Forecast Submissions
Snapshot exported 2026-06-29 17:30 PT ¦ Operations Finance working file
Project ID | Project | Project Manager | Submitted At | Confidence | Forecast ETC | Current Cost Budget | PM Comment | Controller Follow-up
ARM-2318 | Columbia Biologics Clean Utilities | Maya Chen | 2026-06-27 15:15 | Medium | 173800 | 7271000 | Disputed validation retest support is not included. | Standard review
ARM-2403 | Riverton Civic Center HVAC Renewal | Elliot Marks | 2026-06-27 18:15 | High | 892000 | 5109000 | Current field plan and committed buyout reflected. | Standard review
ARM-2409 | Northline Cold Storage Expansion | Priya Raman | 2026-06-28 16:15 | Low | 584000 | 4321000 | Forecast assumes $185k backcharge recovery from concrete trade. | Required before WIP posting
ARM-2412 | OSU Kelley Engineering Lab Ventilation | Elliot Marks | 2026-06-26 17:15 | High | 947000 | 4083000 | Current field plan and committed buyout reflected. | Standard review
ARM-2417 | Cascade Health Ambulatory Pavilion | Maya Chen | 2026-06-26 18:15 | Low | 3048000 | 7970000 | Night-shift premium is not included pending owner direction. | Required before WIP posting
ARM-2421 | Juniper Hotel Boiler Plant Replacement | Lucas Bennett | 2026-06-25 16:15 | High | 31000 | 1755000 | Current field plan and committed buyout reflected. | Standard review
ARM-2501 | PDX Concourse E Controls Retrofit | Sofia Alvarez | 2026-06-25 16:15 | High | 914000 | 2624000 | Current field plan and committed buyout reflected. | Standard review
ARM-2506 | Eastbank Data Hall Cooling Expansion | Priya Raman | 2026-06-25 17:15 | Low | 4731000 | 8722000 | Electrical redesign exposure excluded pending approved PCO. | Required before WIP posting
ARM-2510 | Hawthorne Yard Mixed-Use Mechanical | Maya Chen | 2026-06-24 15:15 | High | 3284000 | 5968000 | Current field plan and committed buyout reflected. | Standard review
ARM-2514 | Redmond Unified Schools Phase 2 | Lucas Bennett | 2026-06-28 15:15 | High | 1492000 | 5529000 | Current field plan and committed buyout reflected. | Standard review
ARM-2518 | Deschutes Fleet Services Maintenance Facility | Lucas Bennett | 2026-06-27 15:15 | High | 1296000 | 2523000 | Current field plan and committed buyout reflected. | Standard review
ARM-2522 | Summit Surgical Center Central Plant | Elliot Marks | 2026-06-26 17:15 | High | 1982000 | 3424000 | Current field plan and committed buyout reflected. | Standard review
ARM-2526 | Willamette Food Co-op Refrigeration Upgrade | Sofia Alvarez | 2026-06-25 17:15 | High | 347000 | 1370000 | Current field plan and committed buyout reflected. | Standard review
ARM-2602 | Pacific NW Distribution Center Heat Recovery | Priya Raman | 2026-06-26 17:15 | High | 3644000 | 4455000 | Current field plan and committed buyout reflected. | Standard review
ARM-2605 | Rose Quarter Event Level Ventilation | Elliot Marks | 2026-06-24 16:15 | Medium | 4124000 | 4782000 | Current field plan and committed buyout reflected. | Standard review
ARM-2608 | Cascade Health Imaging Suite Controls | Sofia Alvarez | 2026-06-27 15:15 | High | 881000 | 1396000 | Current field plan and committed buyout reflected. | Standard review

## Project Forecasts
PM Forecast Detail
Forecast ETC excludes accounting-system cost posted after each PM's field review unless noted
Project ID | Remaining Field Labor | Material / Equipment | Subcontract | Commissioning & Close-out | Contingency | Forecast ETC | Included Exposure | Excluded / Pending Exposure | Confidence | Narrative
ARM-2318 | 62568 | 53878 | 31284 | 15642 | 10428 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | Disputed validation retest support is not included. | Medium | Buyout and production forecast updated from weekly look-ahead.
ARM-2403 | 321120 | 276520 | 160560 | 80280 | 53520 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Labor forecast aligned to current crew plan and schedule logic.
ARM-2409 | 210240 | 181040 | 105120 | 52560 | 35040 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | Forecast assumes $185k backcharge recovery from concrete trade. | Low | Remaining procurement tied to released packages and ordinary allowance.
ARM-2412 | 340920 | 293570 | 170460 | 85230 | 56820 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Buyout and production forecast updated from weekly look-ahead.
ARM-2417 | 1097280 | 944880 | 548640 | 274320 | 182880 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | Night-shift premium is not included pending owner direction. | Low | Labor forecast aligned to current crew plan and schedule logic.
ARM-2421 | 11160 | 9610 | 5580 | 2790 | 1860 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Remaining procurement tied to released packages and ordinary allowance.
ARM-2501 | 329040 | 283340 | 164520 | 82260 | 54840 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Buyout and production forecast updated from weekly look-ahead.
ARM-2506 | 1703160 | 1466610 | 851580 | 425790 | 283860 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | Electrical redesign exposure excluded pending approved PCO. | Low | Labor forecast aligned to current crew plan and schedule logic.
ARM-2510 | 1182240 | 1018040 | 591120 | 295560 | 197040 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Remaining procurement tied to released packages and ordinary allowance.
ARM-2514 | 537120 | 462520 | 268560 | 134280 | 89520 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Buyout and production forecast updated from weekly look-ahead.
ARM-2518 | 466560 | 401760 | 233280 | 116640 | 77760 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Labor forecast aligned to current crew plan and schedule logic.
ARM-2522 | 713520 | 614420 | 356760 | 178380 | 118920 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Remaining procurement tied to released packages and ordinary allowance.
ARM-2526 | 124920 | 107570 | 62460 | 31230 | 20820 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Buyout and production forecast updated from weekly look-ahead.
ARM-2602 | 1311840 | 1129640 | 655920 | 327960 | 218640 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Labor forecast aligned to current crew plan and schedule logic.
ARM-2605 | 1484640 | 1278440 | 742320 | 371160 | 247440 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | Medium | Remaining procurement tied to released packages and ordinary allowance.
ARM-2608 | 317160 | 273110 | 158580 | 79290 | 52860 |  | Remaining buyout, field labor, commissioning, punchlist and documented schedule effects | None reported | High | Buyout and production forecast updated from weekly look-ahead.

## Risks & Opportunities
Risks, Opportunities and Unpriced Exposure
This register informs EAC judgment; it is not authorization to recognize pending change-order revenue
Project ID | Reference | Description | Revenue Opportunity | Cost Exposure / (Recovery) | Commercial Status | Probability | PM Forecast Treatment | Finance Review Status | Evidence / Owner
ARM-2417 | PCO-017 | OR congestion and after-hours premium | 382000 | 275000 | Submitted | 75% | Cost exposure excluded | Pending controller assessment under signed WIP policy | Owner review; no executed directive ¦ Owner: Maya Chen
ARM-2409 | PCO-011 | Freezer slab rework backcharge to concrete trade | 185000 | -185000 | Draft | 40% | Disputed recovery netted | Pending controller assessment under signed WIP policy | Recovery disputed; no subcontractor acceptance ¦ Owner: Priya Raman
ARM-2506 | PCO-006 | Chiller electrical service redesign | 296000 | 210000 | Pricing | 80% | Cost exposure excluded | Pending controller assessment under signed WIP policy | Engineer-directed pricing only ¦ Owner: Priya Raman
ARM-2514 | CO-008 | Gym ventilation scope revision | 214000 | 147000 | Approved | 100% | Reflected in approved forecast | Executed before cutoff | Executed bilateral change order ¦ Owner: Lucas Bennett
ARM-2318 | PCO-029 | Final validation retest and extended support | 68000 | 45000 | Submitted | 65% | Cost exposure excluded | Pending controller assessment under signed WIP policy | Customer disputes responsibility ¦ Owner: Maya Chen
ARM-2605 | PCO-002 | Temporary ventilation for summer events | 174000 | 121000 | Under Review | 25% | Cost exposure excluded | Pending controller assessment under signed WIP policy | Work not authorized at cutoff ¦ Owner: Elliot Marks
ARM-2403 | CO-014 | AHU-4 controls sequence revision | 96000 | 62000 | Approved | 100% | Reflected in approved forecast | Executed before cutoff | Executed ¦ Owner: Elliot Marks
ARM-2412 | CO-009 | Lab exhaust fan VFD replacements | 133000 | 88000 | Approved | 100% | Reflected in approved forecast | Executed before cutoff | Executed ¦ Owner: Elliot Marks

## Instructions & Sign-off
Forecast Submission Protocol
Operations Finance ¦ Rev. 2026-03
Required close sequence
1 | Reconcile posted job cost through the close cutoff to the accounting-system project summary.
2 | Carry the PM's remaining-cost forecast, not the submitted EAC total, when actual cost has moved after submission.
3 | Add probable cost exposures not included in PM ETC when supported by the risk register or contract evidence.
4 | Do not net disputed recoveries or unapproved backcharges against cost until enforceable and accepted.
5 | Include only executed change-order revenue in current contract value.
6 | Escalate any forecast loss, margin movement greater than 100 bps, or material estimate uncertainty.
7 | Document preparer and reviewer timestamps; this workbook is an input, not the final WIP schedule.

## PM inputs - raw
Combined from individual PM files and two e-mail replies at 5:30pm 6/29. Timestamps differ because some files were resaved by Ops Finance.
job_no | pm | submitted | etc_from_pm | confidence typed | comment copied | source filename | Ops Fin note
ARM-2318 | Maya Chen | 2026-06-27 15:15 | 173800 | medium | Disputed validation retest support is not included. | ARM-2318_Maya_ETC_final.xlsx | manual copy - formulas removed
ARM-2403 | Elliot Marks | 2026-06-27 18:15 | 892000 | High | Current field plan and committed buyout reflected. | ARM-2403_Elliot_ETC_v2.xlsx | linked then pasted values
ARM-2409 | Priya Raman | 2026-06-28 16:15 | 584000 | Low | Forecast assumes $185k backcharge recovery from concrete trade. | ARM-2409_Priya_ETC_6.29.xlsx | linked then pasted values
ARM-2412 | Elliot Marks | 2026-06-26 17:15 | 947000 | High | Current field plan and committed buyout reflected. | ARM-2412_Elliot_ETC_USE THIS.xlsx | linked then pasted values
ARM-2417 | Maya Chen | 2026-06-26 18:15 | 3048000 | low | Night-shift premium is not included pending owner direction. | ARM-2417_Maya_ETC_final.xlsx | linked then pasted values
ARM-2421 | Lucas Bennett | 2026-06-25 16:15 | 31000 | High | Current field plan and committed buyout reflected. | ARM-2421_Lucas_ETC_v2.xlsx | manual copy - formulas removed
ARM-2501 | Sofia Alvarez | 2026-06-25 16:15 | 914000 | High | Current field plan and committed buyout reflected. | ARM-2501_Sofia_ETC_6.29.xlsx | linked then pasted values
ARM-2506 | Priya Raman | 2026-06-25 17:15 | 4731000 | Low | Electrical redesign exposure excluded pending approved PCO. | ARM-2506_Priya_ETC_USE THIS.xlsx | linked then pasted values
ARM-2510 | Maya Chen | 2026-06-24 15:15 | 3284000 | high | Current field plan and committed buyout reflected. | ARM-2510_Maya_ETC_final.xlsx | linked then pasted values
ARM-2514 | Lucas Bennett | 2026-06-28 15:15 | 1492000 | High | Current field plan and committed buyout reflected. | ARM-2514_Lucas_ETC_v2.xlsx | linked then pasted values
ARM-2518 | Lucas Bennett | 2026-06-27 15:15 | 1296000 | High | Current field plan and committed buyout reflected. | ARM-2518_Lucas_ETC_6.29.xlsx | manual copy - formulas removed
ARM-2522 | Elliot Marks | 2026-06-26 17:15 | 1982000 | High | Current field plan and committed buyout reflected. | ARM-2522_Elliot_ETC_USE THIS.xlsx | linked then pasted values
ARM-2526 | Sofia Alvarez | 2026-06-25 17:15 | 347000 | high | Current field plan and committed buyout reflected. | ARM-2526_Sofia_ETC_final.xlsx | linked then pasted values
ARM-2602 | Priya Raman | 2026-06-26 17:15 | 3644000 | High | Current field plan and committed buyout reflected. | ARM-2602_Priya_ETC_v2.xlsx | linked then pasted values
ARM-2605 | Elliot Marks | 2026-06-24 16:15 | 4124000 | Medium | Current field plan and committed buyout reflected. | ARM-2605_Elliot_ETC_6.29.xlsx | linked then pasted values
ARM-2608 | Sofia Alvarez | 2026-06-27 15:15 | 881000 | High | Current field plan and committed buyout reflected. | ARM-2608_Sofia_ETC_USE THIS.xlsx | manual copy - formulas removed

## old roll fwd
Copied from May combined file. Kept because Submission Register formulas used to reference columns C/F; no longer authoritative.
Job | May ETC | June placeholder | delta | old flag | May reviewer note
ARM-2318 | 167543 | 173800 |  | FOLLOW UP | waiting on quote
ARM-2403 | 875944 | 892000 |  |  | crew plan updated
ARM-2409 | 584000 | 584000 |  |  | closeout only
ARM-2412 | 964046 | 947000 |  |  | carry prior until PM reply
ARM-2417 | 3157728 | 3048000 |  |  | waiting on quote
ARM-2421 | 29884 | 31000 |  |  | crew plan updated
ARM-2501 | 897548 | 914000 |  | FOLLOW UP | closeout only
ARM-2506 | 4731000 | 4731000 |  |  | carry prior until PM reply
ARM-2510 | 3343112 | 3284000 |  |  | waiting on quote
ARM-2514 | 1545712 | 1492000 |  |  | crew plan updated
ARM-2518 | 1249344 | 1296000 |  |  | closeout only
ARM-2522 | 1946324 | 1982000 |  |  | carry prior until PM reply
ARM-2526 | 347000 | 347000 |  | FOLLOW UP | waiting on quote
ARM-2602 | 3709592 | 3644000 |  |  | crew plan updated
ARM-2605 | 4272464 | 4124000 |  |  | closeout only
ARM-2608 | 849284 | 881000 |  |  | carry prior until PM reply